## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-217-CIV-HOP-Subgrade Preparation - Road | itp |  |  |  |  | ITP-217-CIV-HOP-Subgrade Preparation - Road Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-217-CIV-HOP-Subgrade Preparation - Road
label | ITP Description: Subgrade Preparation - Road
label | Discipline (e.g. CIV/STR/RAIL): 217-CIV-HOP
label | Revision Number: 0
label | Revision Date: 27/11/2024
label | ITP created by: Cedric Guico
label | ITP approved for use by: Pradeep Tisala
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 204
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 173
section | 2. Preliminaries-Materials
checkpoint-no-value | 2.1 - Non Dependent
label | Reference - N/A
section | 3. Preliminaries-Documentations
checkpoint-no-value | 3.1 - Non Dependent
label | Reference - N/A
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set-Out
label | Reference - IFC Drawings
label | Acceptance Criteria - Area has been set out in accordance with the drawings
label | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC Drawing/Propellel/GIS Mapping (LOT MAP):
label | Method - Verify
label | Frequency - Prior to commencement of excavation
label | Category - IP
label | Responsibility - SE/Surveyor
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
label | Reference - Section 204.06 (c), Section 204.06 (e) IFC Drawings
label | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | ○ Assigned CBR ≥ 2.5%
label | ○ If parameters are met, rip and re compact to a depth of 150mm.
label | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type B fill.
label | ○ If existing material needs to be removed and replaced with Type B Fill, ITP-CIV Type B Fill - Road is to be utilised.
label | ○ Attach: Laboratory testing Verification:
textbox | Enter: Type B fill Lot Number:
label | Method - Verify-Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - PE/Nominated Authority
label | Verifying Documents - This ITP/Test Report/Referenced Lot number
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Material classified as silt
label | Reference - Section 204.04 b)
label | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type B material without stablisation to the satisfaction of the Nominated Authority
label | Method - Document Review
label | Frequency - Prior to commencing
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/records
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
label | Reference - Section 204.06 f)
label | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | Method - Site Inspection/ Document Review
label | Frequency - Prior construction of the regulating layer
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Unsuitable Material
label | Reference - Section 204.07 d)
label | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Groundwater
label | Reference - Section 204.06 h)
label | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Cut to Fill Zones
label | Reference - Section 204.06 g)
label | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type B material.
label | Method - Site Inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.7 - Proof Roll
label | Reference - Section 173
label | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Site Engineer/Superintendent
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 - Compaction Testing
label | Reference - Table 204.131
label | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
label | ○ Ripped and re-compacted material below Cut Floor Level
label | ○ Scale B: Standard Compaction 98%.
label | ○ Attach: Compaction Test Result:
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Test Records, Lot Register
date | Date Completed:
checkpoint | 5.9 - Post Compaction Material Property Testing
label | Reference - Vic Roada 204.04 Table 204.141, Section 204.14 a) or b)
label | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | • CBR ≥ 3% and Swell ≤ 1.5%
label | • Max Permeability = 5X10-9 m/s
label | ○ Grading:
label | • 75.0mm 100%
label | • 4.75mm 40-80%
label | • 0.075mm 10-40%
label | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | ○ Scale B:
label | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | ○ Attach: Post compaction test results:
label | Method - Review Document
label | Frequency - Refer to Section 204
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Sign ITP, Attach Material Property Test Report
date | Date Completed:
section | 6. Post Construction Activities
checkpoint | 6.1 - Survey Conformance
label | Reference - VicRoads 204.03f,g and h
label | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Level tolerances (Scale A):
label | • Range x = +5, -15mm
label | • Max S = 12 mm
label | • 80 measurements per lot
label | ○ Level tolerances (Scale B):
label | • Range x = +5, -25mm
label | • Max S = 15 mm
label | • 40 measurements per lot
label | ○ Level tolerances (Scale C):
label | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | Method - Review Document
label | Frequency - Each lot
label | Category - SCP
label | Responsibility - SE/Surveyor
label | Verifying Documents - Sign ITP, Attach Survey Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP