## ITP Cover Page
Landscaping & Urban Design Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 010 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 010
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status:
ITP Description: |  |  | Landscaping and Urban Design |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-UDL
Customer: |  |  | NZTA |  |  |  |  | Specification: |  |  | Project Specification, NZTA P39:2013 Section F, Section 3.9
Quality Specified: |  |  | Project Specification
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-11-19 |  | Joshua Fraser |  | For approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Issued for construction | 2024-12-05 |  | Rex Humpherson |  | NTC-0352 - (Added in Table 21.13: testing requirements for Rip rap) |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | CHRIS BENSON | [5 empty] | Downer PM
Downer QM |  | Cordelia Girdler-Brown | [5 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Landscaping & Urban Design Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 010 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
1.1 | MATERIAL TESTING PRE APPROVALS
1.1.1 | Wetland & Landscaping Methodology | The Contractor shall submit the construction and QA methodology, for each element of Wetland & Landscaping including, testing, inspection and hold points for review and approval prior to works. | Engineers Approval | Appendix V | Approved Methodology | Prior to Earthworks | HP | ENG
1.1.2 | Wetland impermeable clay liner | Liner permeability limit and material approval | Permeability limit of ≥10-7 m/s | PS 21.5.15 | Engineers Approval | Once per source - prior to commencement of works | HP | ENG
1.1.3 | Geotextile Fabric | Geotextile fabric approval | Class D geotextile fabric | PS 21.5.15 | Engineers Approval | Once prior to commencement of works | HP | ENG
1.1.4 | Topsoil Analysis | Testing of on-site and imported topsoil for quality. | Topsoil must meet the criteria specified in the project standards. | NZTA P39: 2013, Section F | Soil Testing Report | Once per source | HP | SE
1.1.5 | Mulch Material Verification | Verify that the mulch used meets the specified criteria (e.g., pallet mulch, arborist mulch). | Mulch material should be free of contaminants, sufficiently aged, and appropriate to site and slope conditions | NZTA P39: 2013 Section 3.9 | Mulch Material Certification | 100% of mulch used | HP | ENG
1.1.6 | Biodegradeable Weed Mat | Biodegradeable weed mat approval | 450 GSM, 7mm thick, biodegradeable weed mat | PS 27.3.8 | Weed Mat Approval | Once prior to commencement of works | HP | ENG
1.1.7 | Rock Rip Rap Approval - Grading | D50=150mm Grading Approval D50=250mm Grading Approval | #VALUE! | PS 21.5.14 | Engineers Approval | Once prior to commencement of works | HP | ENG
1.1.8 | Rock Rip Rap Approval-Weathering | Weathering Index of Coarse Aggregate | AA to CA | PS 21.7.4 | Engineers Approval | 1 per 1000m3 | HP | ENG
1.1.9 | Rock Rip Rap Approval-Crushing resistance | Crushing Resistance of Course Aggregate | >150kN | PS 21.7.4 | Engineers Approval | 1 per 1000m3 | HP | ENG
1.1.10 | Rock Rip Rap Approval-Solid density | Solid Density of Aggregate | >2.65 tonnes per m3 | PS 21.7.4 | Engineers Approval | 1 per 1000m3 | HP | ENG
1.1.11 | Rock Rip Rap Approval - UCS | 1 per 1000m3 AS4133.4.2.1 >30 MPa | >30 MPa | PS 21.7.4 | Engineers Approval | 1 per 1000m3 | HP | NTC-0352 (Added in Table 21.13: testing requirements for Rip rap)
1.1.12 | Rock Rip Rap Approval-Point load | Point Load Strength | > 1.5 Mpa | PS 21.7.4 | Engineers Approval | 1 per 1000m3 | HP | ENG
1.1.13 | Hydro-seeding | Grass mix approved | Send seed mix to engineer for approval | NZTA P39: 2013, Section F | Seed Mix | Once prior to commencement of works | HP | ENG
SECTION 2 – CONSTRUCTION ACTIVITY - LANDSCAPING
2.1.1 | Wetland impermeable clay liner | Liner level | Ensure clay liner has been installed to RL 8.60m | PS 21.5.15 | Setting Out Notice Report | Before excavation | HP | ENG
2.1.2 | Forebay Rip Rap | Rip Rap thickness | D50=150mm placed 300mm thick over class D geotextile | PS 21.5.15 | Site Records / As Built Survey | 5 tests per 1000m2 | I | SE
2.1.3 | Setting out Notice | Confirm that the site has been marked out according to the project plans and specifications before construction begins. | The Contractor shall provide written notice to the Engineer, at least two days prior to Setting out. | PS 27.3.2 | Setting Out Notice Report | Before each stage | HP | ENG
2.1.4 | Site Grading | Grading for planting areas to ensure drainage. | Smooth, flowing contours with proper drainage. | NZTA P39: 2013, Section G PS 16.6.3 | Visual Inspection | 100% of areas | I | SE
2.1.5 | Tree Pit Excavation | Excavation of tree pits according to specified dimensions. | #VALUE! | 2-32735.02-WSP-DR-UDL 0402 Rev 1 | inspection report | Per tree pit | I | SE
2.2 | PLANTING
2.2.1 | Specimen and street trees | Correct staking and tree placement as per plan and specifications | Newly planted specimen trees shall be staked with two 50 x 50 x 1.8m rough sawn Pine H4 treated or hardwood stakes with at least one third of their length (600mm) in the ground and at least 1.0m exposed minimum, or as specified on the plan with the approval of the Overseeing Organisation. | NZTA P39: 2013, Section G | site records | Each Tree | I | SE
2.2.2 | Timber Stakes | Timber stakes used for landscaping must be of specified type, treated to prevent decay, and meet size and quality requirements. 50mmx50mmx1500mm H4 Treated Pine Stakes | #VALUE! | NZTA P39: 2013, Section I | Material Dockets | Per order | I | SE
2.2.3 | Fertilising | All plantings shall have two-year slow-release fertilizer tablets installed at the time of planting. | Fertiliser tablet placed in bottom of hole before planting. Fertiliser composition: 6:15:3 (N:P:K). Up to 14l is 1 tab, 45l is 4 tabs | NZTA P39: 2013, 3.13 | Site Records/photos | Each Area | I | SE
2.3 | MULCHING
2.3.1 | Mulch Spreading | Correct mulch application on flat sites | On sites flatter than a 1:3 grade (1.0m high by 3.0m metres long), mulch shall be spread evenly to a depth of 80-100mm after settlement, over the planted area, creating an inverted cone hollow around each plant stem with a maximum 25mm depth around plant stems. | NZTA P39: 2013, Section G | Site Records / As Built Survey | Each Area | I | SE
2.4 | WEED MAT
2.4.1 | Weed mat laps | Lap joints | On slopes steeper than 1:3 biodegradeable matting shall over lap 100mm between adjacent rolls and 500mm longitudinally | NZTA P39: 2013, Section G | Site Records/photos | Each Area | I | SE
2.4.2 | Weed mat keys | Key in edges | On slopes steeper than 1:3 edges shall be keyed in to topsoil 150mm x 150mm | NZTA P39: 2013, Section G | Site Records/photos | Each Area | I | SE
2.4.3 | Weed mat pins | Freqency of pins | On slopes steeper than 1:3 biodegradeable matting shall be pinned with frequency of 2 per m2 min. | NZTA P39: 2013, Section G | Site Records/photos | Each Area | I | SE
2.5 | GRASSING
2.5.1 | Establishment of sown areas | Apply grass seed as soon as practical after area is prepped. Protect newly established grass areas. | Newly established grass shall be protected from damage by pedestrian and vehicular traffic until grass has reached a self-sustaining state. Newly grassed areas shall be maintained with regular mowing (90mm-30mm) ensuring that all clippings are removed from adjacent hard surfaces. | NZTA P39: 2013, Section G | Site Records/Photos | Each Area | I | SE
SECTION 3 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
3.1 | AS-BUILTS
3.1.1 | As-Builts/ Red pen markup | As-Built records and drawings shall accurately record the layout and extents of all the work. | Record of work completed | PS 16.7.6 | Red pen markups | During Earthworks | D | SV