## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-010 ITP Landscaping & Urban Design | itp |  |  |  |  | DN1210-010 ITP Landscaping & Urban Design Rev 1
section | SECTION 1 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 1.1.1 - Wetland & Landscaping Methodology
label | Detail - The Contractor shall submit the construction and QA methodology, for each element of Wetland & Landscaping including, testing, inspection and hold points for review and approval prior to works.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Approved Methodology
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.2 - Wetland impermeable clay liner
label | Detail - Liner permeability limit and material approval
label | Acceptance / Conformance Criteria - Permeability limit of ≥10-7 m/s
label | Standard / Specification - PS 21.5.15
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - Once per source - prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.3 - Geotextile Fabric
label | Detail - Geotextile fabric approval
label | Acceptance / Conformance Criteria - Class D geotextile fabric
label | Standard / Specification - PS 21.5.15
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - Once prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.4 - Topsoil Analysis
label | Detail - Testing of on-site and imported topsoil for quality.
label | Acceptance / Conformance Criteria - Topsoil must meet the criteria specified in the project standards.
label | Standard / Specification - NZTA P39: 2013, Section F
label | Verifying Document - Soil Testing Report
label | Testing Quantity Required (based from schedule qtys) - Once per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.5 - Mulch Material Verification
label | Detail - Verify that the mulch used meets the specified criteria (e.g., pallet mulch, arborist mulch).
label | Acceptance / Conformance Criteria - Mulch material should be free of contaminants, sufficiently aged, and appropriate to site and slope conditions
label | Standard / Specification - NZTA P39: 2013 Section 3.9
label | Verifying Document - Mulch Material Certification
label | Testing Quantity Required (based from schedule qtys) - 100% of mulch used
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.6 - Biodegradeable Weed Mat
label | Detail - Biodegradeable weed mat approval
label | Acceptance / Conformance Criteria - 450 GSM, 7mm thick, biodegradeable weed mat
label | Standard / Specification - PS 27.3.8
label | Verifying Document - Weed Mat Approval
label | Testing Quantity Required (based from schedule qtys) - Once prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.7 - Rock Rip Rap Approval - Grading
label | Detail - D50=150mm Grading Approval
label | ○ D50=250mm Grading Approval
label | Acceptance / Conformance Criteria -
label | – – – – – – – – – – – – –
label | Table 21.3: D50 = 150mm Riprap Grading
label | Aperture Size (mm) ¦¦ Percentage Passing
label | – – – – – – – – – – – – –
label | 230 ¦¦ 85
label | 150 ¦¦ 50
label | 95 ¦¦ 15
label | – – – – – – – – – – – – –
label | – – – – – – – – – – – – –
label | Table 21.4: D50 = 250mm Riprap Grading
label | Aperture Size (mm) ¦¦ Percentage Passing
label | – – – – – – – – – – – – –
label | 380 ¦¦ 85
label | 250 ¦¦ 50
label | 160 ¦¦ 15
label | – – – – – – – – – – – – –
label | Standard / Specification - PS 21.5.14
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - Once prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.8 - Rock Rip Rap Approval-Weathering
label | Detail - Weathering Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA to CA
label | Standard / Specification - PS 21.7.4
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.9 - Rock Rip Rap Approval-Crushing resistance
label | Detail - Crushing Resistance of Course Aggregate
label | Acceptance / Conformance Criteria - >150kN
label | Standard / Specification - PS 21.7.4
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.10 - Rock Rip Rap Approval-Solid density
label | Detail - Solid Density of Aggregate
label | Acceptance / Conformance Criteria - >2.65 tonnes per m3
label | Standard / Specification - PS 21.7.4
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.11 - Rock Rip Rap Approval - UCS
label | Detail - 1 per 1000m3 AS4133.4.2.1 >30 MPa
label | Acceptance / Conformance Criteria - >30 MPa
label | Standard / Specification - PS 21.7.4
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - NTC-0352 (Added in Table 21.13: testing requirements for Rip rap)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.12 - Rock Rip Rap Approval-Point load
label | Detail - Point Load Strength
label | Acceptance / Conformance Criteria - > 1.5 Mpa
label | Standard / Specification - PS 21.7.4
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.13 - Hydro-seeding
label | Detail - Grass mix approved
label | Acceptance / Conformance Criteria - Send seed mix to engineer for approval
label | Standard / Specification - NZTA P39: 2013, Section F
label | Verifying Document - Seed Mix
label | Testing Quantity Required (based from schedule qtys) - Once prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – CONSTRUCTION ACTIVITY - LANDSCAPING
checkpoint | 2.1.1 - Wetland impermeable clay liner
label | Detail - Liner level
label | Acceptance / Conformance Criteria - Ensure clay liner has been installed to RL 8.60m
label | Standard / Specification - PS 21.5.15
label | Verifying Document - Setting Out Notice Report
label | Testing Quantity Required (based from schedule qtys) - Before excavation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.2 - Forebay Rip Rap
label | Detail - Rip Rap thickness
label | Acceptance / Conformance Criteria - D50=150mm placed 300mm thick over class D geotextile
label | Standard / Specification - PS 21.5.15
label | Verifying Document - Site Records / As Built Survey
label | Testing Quantity Required (based from schedule qtys) - 5 tests per 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.1.3 - Setting out Notice
label | Detail - Confirm that the site has been marked out according to the project plans and specifications before construction begins.
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Setting out.
label | Standard / Specification - PS 27.3.2
label | Verifying Document - Setting Out Notice Report
label | Testing Quantity Required (based from schedule qtys) - Before each stage
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.4 - Site Grading
label | Detail - Grading for planting areas to ensure drainage.
label | Acceptance / Conformance Criteria - Smooth, flowing contours with proper drainage.
label | Standard / Specification - NZTA P39: 2013, Section G, PS 16.6.3
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - 100% of areas
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.1.5 - Tree Pit Excavation
label | Detail - Excavation of tree pits according to specified dimensions.
label | Acceptance / Conformance Criteria -
label | – – – – – – – – – – – – –
label | TABLE 1
label | PLANT SIZE (LITRE / PB) ¦¦ NO. OF STAKES ¦¦ TREE PIT SIZE
label | – – – – – – – – – – – – –
label | LESS THAN 15LT / PB28 ¦¦ 1 ¦¦ 2X SIZE OF ROOT BALL
label | 45LT / PB95 ¦¦ 3 ¦¦ 1000x1000x1000 mm
label | – – – – – – – – – – – – –
label | Standard / Specification - 2-32735.02-WSP-DR-UDL 0402 Rev 1
label | Verifying Document - inspection report
label | Testing Quantity Required (based from schedule qtys) - Per tree pit
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.2.1 - Specimen and street trees
label | Detail - Correct staking and tree placement as per plan and specifications
label | Acceptance / Conformance Criteria - Newly planted specimen trees shall be staked with two 50 x 50 x 1.8m rough sawn Pine H4 treated or hardwood stakes with at least one third of their length (600mm) in the ground and at least 1.0m exposed minimum, or as specified on the plan with the approval of the Overseeing Organisation.
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - site records
label | Testing Quantity Required (based from schedule qtys) - Each Tree
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.2.2 - Timber Stakes
label | Detail - Timber stakes used for landscaping must be of specified type, treated to prevent decay, and meet size and quality requirements.
label | ○ 50mmx50mmx1500mm H4 Treated Pine Stakes
label | Acceptance / Conformance Criteria -
label | – – – – – – – – – – – – –
label | TABLE 1
label | PLANT SIZE (LITRE / PB) ¦¦ NO. OF STAKES ¦¦ TREE PIT SIZE
label | – – – – – – – – – – – – –
label | LESS THAN 15LT / PB28 ¦¦ 1 ¦¦ 2X SIZE OF ROOT BALL
label | 45LT / PB95 ¦¦ 3 ¦¦ 1000x1000x1000 mm
label | – – – – – – – – – – – – –
label | Standard / Specification - NZTA P39: 2013, Section I
label | Verifying Document - Material Dockets
label | Testing Quantity Required (based from schedule qtys) - Per order
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.2.3 - Fertilising
label | Detail - All plantings shall have two-year slow-release fertilizer tablets installed at the time of planting.
label | Acceptance / Conformance Criteria - Fertiliser tablet placed in bottom of hole before planting. Fertiliser composition: 6:15:3 (N:P:K). Up to 14l is 1 tab, 45l is 4 tabs
label | Standard / Specification - NZTA P39: 2013, 3.13
label | Verifying Document - Site Records/photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.3.1 - Mulch Spreading
label | Detail - Correct mulch application on flat sites
label | Acceptance / Conformance Criteria - On sites flatter than a 1:3 grade (1.0m high by 3.0m metres long), mulch shall be spread evenly to a depth of 80-100mm after settlement, over the planted area, creating an inverted cone hollow around each plant stem with a maximum 25mm depth around plant stems.
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Site Records / As Built Survey
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.4.1 - Weed mat laps
label | Detail - Lap joints
label | Acceptance / Conformance Criteria - On slopes steeper than 1:3 biodegradeable matting shall over lap 100mm between adjacent rolls and 500mm longitudinally
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Site Records/photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.4.2 - Weed mat keys
label | Detail - Key in edges
label | Acceptance / Conformance Criteria - On slopes steeper than 1:3 edges shall be keyed in to topsoil 150mm x 150mm
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Site Records/photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.4.3 - Weed mat pins
label | Detail - Freqency of pins
label | Acceptance / Conformance Criteria - On slopes steeper than 1:3 biodegradeable matting shall be pinned with frequency of 2 per m2 min.
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Site Records/photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.5.1 - Establishment of sown areas
label | Detail - Apply grass seed as soon as practical after area is prepped. Protect newly established grass areas.
label | Acceptance / Conformance Criteria - Newly established grass shall be protected from damage by pedestrian and vehicular traffic until grass has reached a self-sustaining state. Newly grassed areas shall be maintained with regular mowing (90mm-30mm) ensuring that all clippings are removed from adjacent hard surfaces.
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Site Records/Photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 3 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 3.1.1 - As-Builts/ Red pen markup
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work.
label | Acceptance / Conformance Criteria - Record of work completed
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red pen markups
label | Testing Quantity Required (based from schedule qtys) - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature