## Tunnel Pre Construction
Item | Titles | Description | Specifications and Standards | Acceptance criteria and testing |  |  | Verification Activity by |  |  |  | Verifying Records
|  |  |  | Method/ Description | Test frequency | Conformance Criteria | Constructor | CPS | Lab | IOM
1. Pre construction
1.1 | CWP for tunnel excavation & support work | Approved CWP | Technical Specification - C0651 - Tunnel Shotcrete Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 3.2 | Submission | Once prior to works commencing | Approval CWP has been transmitted via InEight | H | H |  |  | Approved CWP
1.2 | ITP for tunnel excavation & support work | Approved ITP | Technical Specification - C0651 - Tunnel Shotcrete Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 3.2 | Submission | Once prior to works commencing | Approval ITP has been transmitted via InEight | H | H |  |  | Approved ITP
1.3 | IFC Drawings | Approved IFC Drawings | N/A | Submission | Once prior to works commencing | Ensure all drawings are approved and transmitted Via InEight with IFC status | H | H |  |  | IFC Drawings transmitted into InEight with IFC status
1.4 | IFC Specification | Approved IFC Specification | N/A | Submission | Once prior to works commencing | Ensure all relevant Specifications have been approved and transmitted Via InEight with IFC status | H | H |  |  | IFC Specification transmitted into InEight with IFC status
1.5 | Permit to tunnel/excavate template | No work shall commence until a valid Permit to Tunnel has been signed off for the current section of excavation | NZ Legislation | Submission | Prior to the commencement of the excavation work | Valid permit to tunnel | H | H |  |  | Permit to tunnel signed off by all nominated personnel
1.6 | The groundwater control system Methodology | The Constructor shall propose a method for a preconstruction trial of the groundwater control system and submit it to the Designer’s Representative for review. | Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6 | Submission | Prior to the commencement of the excavation work | Designer’s Representative Approval | H | H |  |  | Groundwater control system methodology
1.7 | Post-installation Groundwater Control Methodology | Where the inflow into the tunnel exceeds 3L/m of length/day averaged over a 100m length of tunnel, appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative. | Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6 | Submission | Prior to the commencement of the remedial work | Designer’s Representative Approval | H | H |  |  | Post-installation groundwater control system methodology
1.8 | The groundwater control system Trial | A preconstruction trial shall be carried out by the Constructor to demonstrate the effectiveness of the connections of strip drains from the top heading to the bench, unless using approved manufacturer's recommended connections installed to the manufacturer's specification. | Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6 | Trial | Prior to the commencement of the excavation work | Designer’s Representative Witness | H | W |  |  | Groundwater control system Trial Results
1.9 | Cement Grout Encapsulation Test | A pre-construction trial shall be carried out by the constructure to demonstrate that the proposed grout used is able to fully encapsulate the bolt using the proposed installation method | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.2 | Trial | Prior to the commencement of the excavation work | Designer’s Representative Witness | H | W |  |  | The rock reinforcement Trial Results
1.10 | Investigation Tests | The Constructor shall conduct a Investigation test (pre-production) on sacrificial rock reinforcements and tested progressively to failure. Investigation load test rock reinforcements are to be installed at locations, agreed with the Designer’s Representative. The Constructor shall notify the Designer’s Representative with a minimum of 48 hour notice. | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6 | Trial | Prior to the commencement with A minimum of six investigation tests shall be carried out for each type of rock, grout mix, and rock bolt or dowel orientation, or as agreed upon with the Designer’s Representative. | At the end of the third Load Cycle the bolt shall be incrementally loaded at intervals of not greater than 33% of Proof Load | H | W |  |  | Investigation test results
1.11 | End Anchorage Tests | The Constructor shall conduct end anchorage test with a minimum of six rock bolts per proposed rock reinforcement system shall be tested in each ground type. For acceptance of end anchorage, all individual bolts shall achieve the pre-tension load shown on the Drawings. | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6 | Trial | Prior to the commencement with A minimum of six tests shall be carried out in each ground type. | All individual bolts shall achieve the pre-tension load shown on the Drawings. | H | W |  |  | End Anchorage test results
1.12 | Approval of shotcrete equipment | Details of all equipment to be approved by the designers representative | Technical Specification - C0651 - Tunnel Shotcrete Clause 3.2 | Review | Prior to the commencement of the excavation work | Designer’s Representative Approval | H | H |  |  | Equipment Technical Data Sheets
1.13 | Probing ahead trial | A trial shall be carried out in advance of tunnelling activities to identify optimum drill bit, drill diameter and flushing and percussion rates | Technical Specification - C0650 - Tunnel Sequential Excavation Section 5.5.g | Trial | Prior to start of tunnelling | Designer’s Representative Approval | H | H |  |  | Probe hole trial result

## Tunnel Material Compliance & Ap
Item | Titles | Description | Specifications and Standards | Acceptance criteria and testing |  |  | Verification Activity by |  |  |  | Verifying Records
|  |  |  | Method/ Description | Test frequency | Conformance Criteria | Constructor | CPS | Lab | IOM
2. Material Compliance and approvals
2.1. Shotcrete
2.1.1. | Shotcrete base mix design | Compliance with Technical Specification - C0651 - Tunnel Shotcrete Clause 4 | Technical Specification - C0651 - Tunnel Shotcrete Clause 4 | Material Review | Prior to the commencement of the excavation work | as per Technical Specification - C0651 - Tunnel Shotcrete Clause 4 | H | H |  |  | Material Approval Record
2.1.2. | Shotcrete Accelerator | Type and dosage of shotcrete accelerator shall conform to the requirements of the Specification | Technical Specification - C0651 - Tunnel Shotcrete Clause 4.7.1 | Material Review | Prior to the commencement of the excavation work | Material Approval Record | H | H |  |  | Material Approval Record
2.1.3. | Nozzelman Certification | Nozzelman shall hold a verification of competence (VOC) issued by the constructor | Technical Specification - C0651 - Tunnel Shotcrete Clause 5.2 | Document Review | Prior to trial | Ensure only personnel hodling VOC are operating the shotcrete robot on site. | H | R |  |  | Nozzelman Certificate/ VOC
2.2. Reinforcing Mesh
2.2.1. | Reinforcing Mesh | SE92 GR 500E mesh | AS/NZS 4671 | Material Review | Prior to the commencement of the excavation work | Material Approval Record | H | H |  |  | Material Approval Record
2.3. Rockbolts/Dowels Bar
2.3.1. | Tunnel rockbolts and plates | rockbolts material and corrosion protection | AS/NZS 4671, AS/NZS 3678, AS/NZ 4680 Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.1 and 4.2 | Material Review | Prior to the commencement of the excavation work | Grade 500N, galvanised HDG to AS/NZS 4680 Material Approval Record including mill certificate | H | H |  |  | Material Approval Record
2.3.2. | Face Dowels | glass fibre reinforced face dowels material | ASTM D3916 Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.2.2 | Material Review | Prior to the commencement of the excavation work | Material Approval Record | H | H |  |  | Material Approval Record
2.3.3. | Delivery acceptance | Inspect fabricated rock bolts and rock dowels prior to installation | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 3.2 | Visual Inspection | upon delivery | N/A | H | W |  |  | Delivery Docket/Mil Test cert
2.4. Spile bars
2.4.1. | Spile bars | spile bar material | AS/NZS 4671 Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.2.3 AS 1391 | Material Review | Prior to the commencement of the excavation work | Material Approval Record | H | H |  |  | Material Approval Record
2.4.2. | Delivery acceptance | Visual confirmation of delivered items | N/A | Visual Inspection | Upon delivery | N/A | H | R |  |  | Delivery Docket/Mil Test cert
2.5. Cement grout for rock bolts, dowels, spiles
2.5.1. | cement grout | grout material and properties | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.3.1 NZS3122 | Material Review | Prior to the commencement of the excavation work | Material Approval Record | H | H |  |  | Material Approval Record
2.5.2. | Delivery acceptance | Visual confirmation of delivered items | N/A | Visual Inspection | Upon delivery |  | H | R |  |  | Delivery Docket
2.6. Resin
2.6.1. | resin grout | grout material and properties | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.3.2 | Material Review | Prior to the commencement of the excavation work | Material Approval Record | H | H |  |  | Material Approval Record
2.6.2. | Delivery acceptance | Visual confirmation of delivered items | N/A | Visual Inspection | Upon delivery | As per accepted MAR | H | W |  |  | Delivery Docket
2.7. Monitoring Instruments
2.7.1. | Monitoring instrumets | Compliance with Technical Specification C0660 - Tunnel Convergence Monitoring | Technical Specification C0660 - Tunnel Convergence Monitoring | Review | Prior to installation | Designer’s Representative Approval | H | H |  |  | Material Approval Record

## Tunnel Construction
Item | Titles | Description | Specifications and Standards | Acceptance criteria and testing |  |  | Verification Activity by |  |  |  | Verifying Records
|  |  |  | Method/ Description | Test frequency | Conformance Criteria | Constructor | CPS | Lab | IOM
3.0 Construction
3.1. Excavation
3.1.1. | PTT | PTT shall define the planned excavation limits and support types (RESS) prior to each defined period of excavation in each heading or bench face. Tunnel excavation shall not commence on a shift until PTT has been signed off | Technical Specifications C0650 Tunnel Sequential Excavation Section 5.1 | PTT form | Every advance or as agreed in DRM | N/A | H | H |  |  | PTT
3.1.2. | Face Mapping | Recommend the required support type based on the Actual Ground Conditions. Determine any corrective measures required to ensure safety and stability of the excavation. Identify if the ground conditions depart from the expected range of conditions for which a support type has been designed and notify the Designer if new design is required. | Technical Specifications C0650 Tunnel Sequential Excavation Section 5.1 | Geological mapping record | Every advance or as agreed in DRM | N/A | H | H |  |  | Required Excavation and support sheet
3.1.3. | E-line control | Control the E-Line before, during and after excavation is finished | Drawing MMMA-DES-TUN-E1-DRG-8119 | Surveyor to set out and record as built. VMT system to provide e-line guidance | Every advance | Over excavation tolerance -0/+150mm | H | W |  |  | As-built Report
3.2. Shotcrete
3.2.1. | Delivery docket Check | Check delivery docket to ensure the mix used is the correct mix | N/A | Document Review | Prior to any shotcrete application | N/A | H | R |  |  | Delivery docket
3.2.2. | Rock Surface Preparation | Prepare all surfaces to be shotcreted prior to application of shotcrete | Technical Specification - C0650 - Tunnel Civil Works Section 5.4 | Visual Inspection | Prior to spraying | Surface clean and free of loose material, pre-wet surface immediately prior to spraying. Any residual flowing or seeping water shall be controlled using channels, chases, pipes, or other approved means. | H | W |  |  | Cut CheckSHeet
3.2.3. | Shotcrete Surface Preparation | Prepare all surfaces to be shotcreted prior to application of shotcrete | Technical Specification - C0650 - Tunnel Civil Works Section 5.4 | Visual Inspection | Prior to spraying | Surface clean and free of loose material, loose shotcrete rebound removed. Pre-wet surface immediately prior to spraying. Spalled, cracked, loose or contaminated shotcrete removed. | H | W |  |  | Cut CheckSHeet
3.2.4. | Temperature check | Check the temperature of the shotcrete is within acceptable range between 5°C and 35°C. The ambient temperature shoule be more than or equal 5ᴼC. | Technical Specification - C0651 - Tunnel Shotcrete Clause 5.4 NZS 3109: 1997 | thermometer | Each mixer truck prior to discharging | Between 5°C and 35°C | H | R |  |  | Shotcrete Installation Record refer to Item 3.2
3.2.5. | Slump check | Slump to be within the alocated tolerance | NZS 3112.1 Technical Specification - C0651 - Tunnel Shotcrete Clause Clause 5.4 | slump test | Each delivery truck prior to discharging | 220mm ± 20mm | H | R |  |  | Shotcrete Record
3.2.6. | Personnel Entry | Test prior to each personnel entry and/or face advance. Test results must be verified once a month during construction. | BS EN 14488-2 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 | Penetrometer test | Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction. | Min 1MPa for man entry (providing the shotcrete layer is 75mm thick, rockbolts have been installed and the rockbolt grout compressive strength is min 3MPa) | H | W |  |  | Penetrometer test results refer to Item 3.3
3.2.7. | Beam End Test (early age compressive strength) | Safe shotcrete strength before next advancement to max. advance length | Technical Specification - C0651 - Tunnel Shotcrete Table 6.1 and 6.4 ASTM C116 | field test | Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction. | Min. 1.00 MPa at 3 Hours Min. 5.00 MPa at 6 Hours Min. 7.00 MPa at 12 Hours Min. 12.00 MPa at 24-36 Hours | H | W |  |  | Beam End Test Results refer to Item 3.3
3.2.8. | compressive strength (cast sample) | To prove compressive strength compliance requirement | NZS3112 Technical Specification - C0651 - Tunnel Shotcrete Table 6.1 and 6.4 | certified lab test | 1 test (I test shall include 4 cored specimen, 3 tested and 1 spare) for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter | Min. 35 MPa at 28 days | W | R |  |  | IANZ lab test report
3.2.9. | compressive strength (cored sample) | To prove compressive strength compliance requirement | NZS3112 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 | certified lab test | 1 test for every 50m3 of sprayed shotcrete | Min. 20 MPa at 7 days Min. 35 MPa at 28 days Min. 35 MPa at 90 days | W | R |  |  | IANZ lab test report
3.2.10. | Residual Flexural Tensile Strength | To prove compliance with flexural strength requirements | BS EN 14651: 2005 + A1: 2007 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 and 6.1 | certified lab test | 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter | Min. FR,1 of 1.25MPa and FR,4 at 1MPa | W | R |  |  | IANZ lab test report
3.2.11. | Drying Shrinkage Testing | To prove compliance with shrinkage requirements | AS1012.13 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 and 6.1 | certified lab test | 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter | Max 850 micro strain | W | R |  |  | IANZ lab test report
3.2.12. | Permeability testing | to prove compliance with permeability requirements | BS EN 12390-8 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4. and 6.1 | certified lab test | 3 tests for the first 50m3 of shotcrete then 1 test every 1 month thereafter | Maximum allowable penetration 25mm | W | R |  |  | IANZ lab test report
3.2.13. | Steel fibre content | To prove compliance with fibre content test requirement | BS EN 14488-7 (fresh concrete) Technical Specification - C0651 - Tunnel Shotcrete Section 4.8 | certified lab test | 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter | Minimum 35kg/m3 | H | R |  |  | IANZ lab test report
3.2.14. | Relative density | To prove compliance with the relative density requirement | NZS 3112.1 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 and 6.1 | certified lab test | 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter | Minimum 98% of the density measured from base mix | H | R |  |  | IANZ lab test report
3.2.15. | Layer thickness, Tunnel Lining Intrados, C-Line | Provide control means to verify the thickness of final shotcrete layer | Technical Specification C0650 - Tunnel Sequential Excavation, section 5.7 Drawing MMA-DES-TUN-E1-DRG-8119 Drawing MMA-DES-TUN-E1-DRG-8130 | Survey scans, deep pins | As-builts shall be taken of EACH layer of shotcrete | Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8130 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8119 | H | R |  |  | As-built Report
3.2.16. | Construction joints | Construction joints in the shotcrete lining top heading/bench shall be inspected by the Designer’s Representative as required by the Drawings. | Technical Specification - C0651 - Tunnel Shotcrete Clause 3.2 Table 3.1 | Visual Inspection | Every Construction Joints | Hold point released by CPS | H | H |  |  | Site Inspection Report Shotcrete Checklist
3.2.17. | Curing | Curing to be carried out in accordance with the Specification | Technical Specification - C0651 - Tunnel Shotcrete Clause 5.5 |  | Each Spray |  | H | R |  |  | Shotcrete Checklist
3.2.18. | Defects and Repair | The final layer of shotcrete shall be inspected for any defects and repaired accordingly. At the completion of the lining, all core holes in the lining (resulting from testing or inspection) shall be backfilled with non-shrink mortar of an equivalent strength and fire resistance properties unless otherwise specified. The surface of the restored hole shall be similar to the surrounding surface in texture and colour. | Technical Specification C0650 - Tunnel Sequential Excavation, section 5.6 | Visual Inspection | Every defect on Every advance | Crack <0.5mm ,Crack >0.5mm -Non corformance report | H | W |  |  | Post spray inspection record
3.3. Reinforcing mesh
3.3.1. | Reinforcing mesh for primary lining | To prove position, cover and overlap are achieved | Drawing MMMA-DES-TUN-E1-DRG-8011 | Visual inspection and survey | Every advance | Longitudinal and transverse overlap of 250mm ( one mesh square plus 50mm) Min. cover 65mm at the extrados and 85mm at the intrados | H | W |  |  | Check sheet
3.4. Rockbolts
3.4.1. | Drilling | Bolts shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. | Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3 Drawing MMMA-DES-TUN-E1-DRG-8011 | Survey | Each bolt | Rockbolts shall be installed perpendicular to the excavation face unless stated otherwise. Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular. Position Tolerence +150,-150mm No overdrill tolerance -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. | H | W |  |  | Drilling log
3.4.2. | Installation | Record all information on installation (position, hole length and dianeterm length of the bolt…) | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3 | Review | Each bolt | Rockbolts to be clean and free from rust or any other physical damage at the time of installation -Type of bolts, diameter, length, location, spacing and orientation according to detailed design -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. | H | W |  |  | Drilling log
3.4.3. | Grouting mixing | To ensure correct practice | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.4.1 NZ 3109 | Review | Every batch prior to grouting | Target w/c ratio as per MAR | H | W |  |  | Grouting records
3.4.4. | Grout test | Testing specimen to measure UCS | Technical Specification C0652 - Tunnel Rock Reinforcement section 6.4 NZ 3112.4:1986 | Compressive strength test | Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days) | min 20MPa at 1 day min 40MPa at 28 days The average compressive strength determined from any group of cubes shall exceed the specified characterisitc strength by: 1MPa at 1 day 3MPa at 28 days | H | W |  |  | Test results
3.4.5. | Resin | To ensure correct practice and full encapsulation | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.4.2 | Review | Each bolt | Sufficient number of resin cartridges to be used with each rock reinforcement installation in accordance with the approved project specific procedure developed during the trials. daily records of all grouting works to be kept | H | W |  |  | Grouting records
3.4.6. | Pull test | Demonstrate that the installed rock reinforcements can provide at least the design working load capacity. . | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.5 | Test | 1. First three installations of both rock bolts and rock dowels in each ground type as present in production. 2. 5% of the next 100 installations of rock bolts and rock dowels, proportionately throughout the ground types presenting. 3. 2.5% of the remaining bolts and dowels proportionately throughout the ground types presenting Note: 3 neighbouring installations of rock reinforcement surrounding a failed rock bolt or dowel test (and test frequency to revert back to 5% for the next 100 and 2.5% for the remaining installations) | The bolt or dowel is deemed acceptable if, during the cycle, the displacement of the bolt or dowel head relative to the measuring datum (after allowing for any temperature changes) does not exceed the criteria for 100% of the working load, as set out in Table 6.4 of the specification. Failure criteria: 2% Maximum Permissible Displacement or failure to maintain specified loads or ongoing creep of the rock bolt or rock dowel | H | W |  |  | Testing records
3.5. Spile installation
3.5.1. | Drilling | Spiles shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. | Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3 | Survey | Each spile | Positional tolerance of portal spile bars not to exceed 25mm in any direction -Setout angle shall be as per drawing. Max. angular tolerance not to exceed 1 in 60. | H | W |  |  | Drilling record ,Survey Report
3.5.2. | Installation | Record information on installation. | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3 | Review | Each bolt | -Spiles shall be free of dirt, detrimental rust or any other deleterious substance. - Type of spile, diameter, length, location, spacing and orientation according to detailed design. | H | W |  |  | Rock Bolt Installation Record
3.5.3. | Grouting mixing | To ensure correct practice and w/c ratio check | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.4.1 NZ 3109 | Review | Every batch prior to grouting | Target w/c ratio as per MAR | H | W |  |  | Rock Bolt Installation Record
3.5.4. | Grout test | Testing specimen to measure UCS | Technical Specification C0652 - Tunnel Rock Reinforcement section 6.4 NZ 3112.4:1986 | Compressive strength test | Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days) | min 20MPa at 1 day min 40MPa at 28 days The average compressive strength determined from any group of cubes shall excess the specified characterisitc strength by: 1MPa at 1 day 3MPa at 28 days | H | W |  |  | IANZ lab test report
3.6. Face dowels
3.6.1. | Drilling | Dowels shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. | Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3 | Survey | Each dowel | Dowels shall be installed perpendicular to the excavation face unless stated otherwise. Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular. Position Tolerence +150,-150mm No overdrill tolerance -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. | H | W |  |  | Rock Bolt Installation Record/Check list /As built Survey
3.6.2. | Installation | Dowels shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3 | Review | Each dowel | dowels to be clean or any other physical damage at the time of installation -Type of bolts, diameter, length, location, spacing and orientation according to detailed design -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. | H | W |  |  | Rock Bolt Installation Record
3.6.3. | Grouting | To ensure correct practice and w/c ratio check | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.4.1 NZ 3109 | Review | Every batch prior to grouting | Target w/c ratio as per MAR | H | W |  |  | Rock Bolt Installation Record
|  | Testing specimen to measure UCS | Technical Specification C0652 - Tunnel Rock Reinforcement section 6.4 NZ 3112.4:1986 | Compressive strength test | Every batch prior to grouting (three cubes at 1 day, three cubes at 28 days) | min 20MPa at 1 day, and average to exceed specified strength by 1MPa min 40MPa at 28 days, and average to exceed specified strength | H | W |  |  | IANZ lab test report
3.7. Probe holes
3.7.1. | Drilling probe holes | Record information during drilling Check the water inflow during and after drilling | Technical specification C0650 - Tunnel Sequential Excavation, section 5.5 | Geological monitoring | Maintain minimum one probe at 20 m ahead of the face at all times | -Hole diameter minimum 50 mm - Not less than three probe holes shall be maintained a minimum of 6m ahead of the excavation face at all times and with at least 1 probe hole maintained a minimum 20m ahead of the excavation face at all times | H | W |  |  | Probe holes record ,Survey As built report
3.8. Monitoring
3.8.1. | Tunnel convergency (Extensometer) | Monitoring and reading records of the tunnel extensometer | Technical Specification C0660 - Tunnel Convergence Monitoring | Review | from excavation face >100m = Monthly 40m-100m = Weekly 15m - 40m = 2x weekly <15m = daily |  | H | R |  |  | Monitoring Report
3.8.2. | In-Tunnel Optical Survey Convergence | Monitoring and reading records on the tunnel optical survey targets | Technical Specification C0660 - Tunnel Convergence Monitoring | Review | from excavation face >100m = Monthly 40m-100m = Weekly 15m - 40m = 2x weekly <15m = daily |  | H | R |  |  | Monitoring Report
3.9. Ground water control
3.9.1 | Strip drain installations | Record location and ensure correct installation | Technical Specification C0653 - Tunnel Groundwater Control Systems Section 5 | Review |  | Location and quantity of the strip drains shall be as instructed on site by the Designer's representative | H | R |  |  | Excavation and shotcrete check sheet,Survey as built record
3.9.2 | Groundwater (rectification) | Where the inflow into the tunnel exceeds the design criteria,appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative. | Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6 | Visual Inspection | Ongoing | Shall not be exceed 3L/m of length/day averaged over a 100m length of tunnel. Where exceeded, the post-installation groundwater methodology is to be followed. | H | H |  |  | Installation Checksheet
Note on B24: Ramy Faragalla: Add the requirement of construction joints as Tunnel Shotcrete Spec. Clause 3.2 table 3.1
Note on B25: Ramy Faragalla: Add the requirement of Curing as Tunnel Shotcrete Spec. Clause 5.5
Note on I26: Ramy Faragalla: Please add The contractor will provide a proposal outlining the methodology for repairing any defects.
Note on N37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There is no “drilling record” sheet, please be consistent with wording
Note on I42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed text to reflect drg 8011
Note on I43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: They are GRP dowels, they don’t rust ☺️ please amend to suit don’t just copy paste without thinking
Note on I49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Ramy Faragalla can I say to refere to drawings MMA-DES-TUN-E1-DRG-8180? Or can I paste the table in? Reply: Both ways ok I prefer to copy the table.

## Tunnel Post Construction
Item | Titles | Description | Specifications and Standards | Acceptance criteria and testing |  |  | Verification Activity by |  |  |  | Verifying Records
|  |  |  | Method/ Description | Test frequency | Conformance Criteria | Constructor | CPS | Lab | IOM
4.0 Post construction
4.1. | Red Line Mark Up Drawings | As-built drawings to capture any deviation from the IFC drawings. |  | Submit | At Completion |  | H | R |  |  | Red Line Mark Up Drawings
4.2. | As-built Drawings | As-built drawings to capture any deviation from the IFC drawings. | Quality Management Plan | Submit | At Completion |  | H | R |  |  | As-built drawings, installation record, as built records, PTT, testing results, monitoring documentation, operation and maintenance report, Producer Statements
4.3. | Tunnel Operation and maintenance report | Tunnel Operation and maintenance report to detail the maintenance frequency and maintenance procedures. |  | Submit | At Completion |  | H | R |  | R | Tunnel operation and maintenance report
4.4 | Final Handover Package | Collation of all QA, as-built drawings,as-built records, installation records, PTT, testing and monitoring documentation. Provision of asset management operation and maintenance report to NZTA, including Producer Statements. | Quality Management Plan | Submit | At Completion |  | H | R |  | R | As-built drawings, installation record, as built records, PTT, testing results, monitoring documentation, operation and maintenance report, Producer Statements
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Katerina Howard @Teringa Horton do we need this in ITP? Can we discuss Reply: yes we do, happy to discuss, it should probably be called "Construction Final Report/Quality Pack" or whatever terminology is used in the Quality Management Plan Reply: We can chat on Monday about ITP vs ConQA reports, thanks