## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Tunnel Pre Construction | itp |  |  |  |  | ITP - Tunnel Pre Construction
section | 1. Pre construction
checkpoint | 1.1 - CWP for tunnel excavation & support work
label | Description - Approved CWP
label | Method/Description - Submission
label | Test frequency - Once prior to works commencing
label | Conformance Criteria - Approval CWP has been transmitted via InEight
label | Constructor - H
label | CPS - H
label | Verifying Records - Approved CWP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - ITP for tunnel excavation & support work
label | Description - Approved ITP
label | Method/Description - Submission
label | Test frequency - Once prior to works commencing
label | Conformance Criteria - Approval ITP has been transmitted via InEight
label | Constructor - H
label | CPS - H
label | Verifying Records - Approved ITP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - IFC Drawings
label | Description - Approved IFC Drawings
label | Method/Description - Submission
label | Test frequency - Once prior to works commencing
label | Conformance Criteria - Ensure all drawings are approved and transmitted Via InEight with IFC status
label | Constructor - H
label | CPS - H
label | Verifying Records - IFC Drawings transmitted into InEight with IFC status
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - IFC Specification
label | Description - Approved IFC Specification
label | Method/Description - Submission
label | Test frequency - Once prior to works commencing
label | Conformance Criteria - Ensure all relevant Specifications have been approved and transmitted Via InEight with IFC status
label | Constructor - H
label | CPS - H
label | Verifying Records - IFC Specification transmitted into InEight with IFC status
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Permit to tunnel/excavate template
label | Description - No work shall commence until a valid Permit to Tunnel has been signed off for the current section of excavation
label | Method/Description - Submission
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Valid permit to tunnel
label | Constructor - H
label | CPS - H
label | Verifying Records - Permit to tunnel signed off by all nominated personnel
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - The groundwater control system Methodology
label | Description - The Constructor shall propose a method for a preconstruction trial of the groundwater control system and submit it to the Designer’s Representative for review.
label | Method/Description - Submission
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Designer’s Representative Approval
label | Constructor - H
label | CPS - H
label | Verifying Records - Groundwater control system methodology
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Post-installation Groundwater Control Methodology
label | Description - Where the inflow into the tunnel exceeds 3L/m of length/day averaged over a 100m length of tunnel, appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative.
label | Method/Description - Submission
label | Test frequency - Prior to the commencement of the remedial work
label | Conformance Criteria - Designer’s Representative Approval
label | Constructor - H
label | CPS - H
label | Verifying Records - Post-installation groundwater control system methodology
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - The groundwater control system Trial
label | Description - A preconstruction trial shall be carried out by the Constructor to demonstrate the effectiveness of the connections of strip drains from the top heading to the bench, unless using approved manufacturer's recommended connections installed to the manufacturer's specification.
label | Method/Description - Trial
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Designer’s Representative Witness
label | Constructor - H
label | CPS - W
label | Verifying Records - Groundwater control system Trial Results
checkpoint | 1.9 - Cement Grout Encapsulation Test
label | Description - A pre-construction trial shall be carried out by the constructure to demonstrate that the proposed grout used is able to fully encapsulate the bolt using the proposed installation method
label | Method/Description - Trial
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Designer’s Representative Witness
label | Constructor - H
label | CPS - W
label | Verifying Records - The rock reinforcement Trial Results
checkpoint | 1.10 - Investigation Tests
label | Description - The Constructor shall conduct a Investigation test (pre-production) on sacrificial rock reinforcements and tested progressively to failure. Investigation load test rock reinforcements are to be installed at locations, agreed with the Designer’s Representative.
label | ○ The Constructor shall notify the Designer’s Representative with a minimum of 48 hour notice.
label | Method/Description - Trial
label | Test frequency - Prior to the commencement with A minimum of six investigation tests shall be carried out for each type of rock, grout mix, and rock bolt or dowel orientation, or as agreed upon with the Designer’s Representative.
label | Conformance Criteria - At the end of the third Load Cycle the bolt shall be incrementally loaded at intervals of not greater than 33% of Proof Load
label | Constructor - H
label | CPS - W
label | Verifying Records - Investigation test results
checkpoint | 1.11 - End Anchorage Tests
label | Description - The Constructor shall conduct end anchorage test with a minimum of six rock bolts per proposed rock reinforcement system shall be tested in each ground type. For acceptance of end anchorage, all individual bolts shall achieve the pre-tension load shown on the Drawings.
label | Method/Description - Trial
label | Test frequency - Prior to the commencement with A minimum of six tests shall be carried out in each ground type.
label | Conformance Criteria - All individual bolts shall achieve the pre-tension load shown on the Drawings.
label | Constructor - H
label | CPS - W
label | Verifying Records - End Anchorage test results
checkpoint | 1.12 - Approval of shotcrete equipment
label | Description - Details of all equipment to be approved by the designers representative
label | Method/Description - Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Designer’s Representative Approval
label | Constructor - H
label | CPS - H
label | Verifying Records - Equipment Technical Data Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.13 - Probing ahead trial
label | Description - A trial shall be carried out in advance of tunnelling activities to identify optimum drill bit, drill diameter and flushing and percussion rates
label | Method/Description - Trial
label | Test frequency - Prior to start of tunnelling
label | Conformance Criteria - Designer’s Representative Approval
label | Constructor - H
label | CPS - H
label | Verifying Records - Probe hole trial result
holdpoint | AUTHORITY HOLDPOINT
section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
note | Site Engineer/Project Engineer
note | Zone Manager Approval
note | Construction Manager Approval
note | Quality Manager Approval
date | Date:
signoff | SIGNATURE
checklist | ITP - Tunnel Material Compliance & Approvals | itp |  |  |  |  | ITP - Tunnel Material Compliance & Approvals
section | 2.1. Shotcrete
checkpoint | 2.1.1. - Shotcrete base mix design
label | Description - Compliance with Technical Specification - C0651 - Tunnel Shotcrete Clause 4
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - as per Technical Specification - C0651 - Tunnel Shotcrete Clause 4
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.2. - Shotcrete Accelerator
label | Description - Type and dosage of shotcrete accelerator shall conform to the requirements of the Specification
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Material Approval Record
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.3. - Nozzelman Certification
label | Description - Nozzelman shall hold a verification of competence (VOC) issued by the constructor
label | Method/Description - Document Review
label | Test frequency - Prior to trial
label | Conformance Criteria - Ensure only personnel hodling VOC are operating the shotcrete robot on site.
label | Constructor - H
label | CPS - R
label | Verifying Records - Nozzelman Certificate/ VOC
section | 2.2. Reinforcing Mesh
checkpoint | 2.2.1. - Reinforcing Mesh
label | Description - SE92 GR 500E mesh
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Material Approval Record
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
section | 2.3. Rockbolts/Dowels Bar
checkpoint | 2.3.1. - Tunnel rockbolts and plates
label | Description - rockbolts material and corrosion protection
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Grade 500N, galvanised HDG to AS/NZS 4680 Material Approval Record including mill certificate
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.2. - Face Dowels
label | Description - glass fibre reinforced face dowels material
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Material Approval Record
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.3. - Delivery acceptance
label | Description - Inspect fabricated rock bolts and rock dowels prior to installation
label | Method/Description - Visual Inspection
label | Test frequency - upon delivery
label | Conformance Criteria - N/A
label | Constructor - H
label | CPS - W
label | Verifying Records - Delivery Docket/Mil Test cert
section | 2.4. Spile bars
checkpoint | 2.4.1. - Spile bars
label | Description - spile bar material
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Material Approval Record
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4.2. - Delivery acceptance
label | Description - Visual confirmation of delivered items
label | Method/Description - Visual Inspection
label | Test frequency - Upon delivery
label | Conformance Criteria - N/A
label | Constructor - H
label | CPS - R
label | Verifying Records - Delivery Docket/Mil Test cert
section | 2.5. Cement grout for rock bolts, dowels, spiles
checkpoint | 2.5.1. - cement grout
label | Description - grout material and properties
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Material Approval Record
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5.2. - Delivery acceptance
label | Description - Visual confirmation of delivered items
label | Method/Description - Visual Inspection
label | Test frequency - Upon delivery
label | Constructor - H
label | CPS - R
label | Verifying Records - Delivery Docket
section | 2.6. Resin
checkpoint | 2.6.1. - resin grout
label | Description - grout material and properties
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Material Approval Record
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6.2. - Delivery acceptance
label | Description - Visual confirmation of delivered items
label | Method/Description - Visual Inspection
label | Test frequency - Upon delivery
label | Conformance Criteria - As per accepted MAR
label | Constructor - H
label | CPS - W
label | Verifying Records - Delivery Docket
section | 2.7. Monitoring Instruments
checkpoint | 2.7.1. - Monitoring instrumets
label | Description - Compliance with Technical Specification C0660 - Tunnel Convergence Monitoring
label | Method/Description - Review
label | Test frequency - Prior to installation
label | Conformance Criteria - Designer’s Representative Approval
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
note | Site Engineer/Project Engineer
note | Zone Manager Approval
note | Construction Manager Approval
note | Quality Manager Approval
date | Date:
signoff | SIGNATURE
checklist | ITP - Tunnel Construction | itp |  |  |  |  | ITP - Tunnel Construction
section | 3.1. Excavation
checkpoint | 3.1.1. - PTT
label | Description - PTT shall define the planned excavation limits and support types (RESS) prior to each defined period of excavation in each heading or bench face.
label | ○ Tunnel excavation shall not commence on a shift until PTT has been signed off
label | Method/Description - PTT form
label | Test frequency - Every advance or as agreed in DRM
label | Conformance Criteria - N/A
label | Constructor - H
label | CPS - H
label | Verifying Records - PTT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2. - Face Mapping
label | Description - Recommend the required support type based on the Actual Ground Conditions.
label | ○ Determine any corrective measures required to ensure safety and stability of the excavation.
label | ○ Identify if the ground conditions depart from the expected range of conditions for which a support type has been designed and notify the Designer if new design is required.
label | Method/Description - Geological mapping record
label | Test frequency - Every advance or as agreed in DRM
label | Conformance Criteria - N/A
label | Constructor - H
label | CPS - H
label | Verifying Records - Required Excavation and support sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3. - E-line control
label | Description - Control the E-Line before, during and after excavation is finished
label | Method/Description - Surveyor to set out and record as built. VMT system to provide e-line guidance
label | Test frequency - Every advance
label | Conformance Criteria - Over excavation tolerance -0/+150mm
label | Constructor - H
label | CPS - W
label | Verifying Records - As-built Report
section | 3.2. Shotcrete
checkpoint | 3.2.1. - Delivery docket Check
label | Description - Check delivery docket to ensure the mix used is the correct mix
label | Method/Description - Document Review
label | Test frequency - Prior to any shotcrete application
label | Conformance Criteria - N/A
label | Constructor - H
label | CPS - R
label | Verifying Records - Delivery docket
checkpoint | 3.2.2. - Rock Surface Preparation
label | Description - Prepare all surfaces to be shotcreted prior to application of shotcrete
label | Method/Description - Visual Inspection
label | Test frequency - Prior to spraying
label | Conformance Criteria - Surface clean and free of loose material, pre-wet surface immediately prior to spraying.
label | ○ Any residual flowing or seeping water shall be controlled using channels, chases, pipes, or other approved means.
label | Constructor - H
label | CPS - W
label | Verifying Records - Cut CheckSHeet
checkpoint | 3.2.3. - Shotcrete Surface Preparation
label | Description - Prepare all surfaces to be shotcreted prior to application of shotcrete
label | Method/Description - Visual Inspection
label | Test frequency - Prior to spraying
label | Conformance Criteria - Surface clean and free of loose material, loose shotcrete rebound removed. Pre-wet surface immediately prior to spraying. Spalled, cracked, loose or contaminated shotcrete removed.
label | Constructor - H
label | CPS - W
label | Verifying Records - Cut CheckSHeet
checkpoint | 3.2.4. - Temperature check
label | Description - Check the temperature of the shotcrete is within acceptable range between 5°C and 35°C.
label | ○ The ambient temperature shoule be more than or equal 5ᴼC.
label | Method/Description - thermometer
label | Test frequency - Each mixer truck prior to discharging
label | Conformance Criteria - Between 5°C and 35°C
label | Constructor - H
label | CPS - R
label | Verifying Records - Shotcrete Installation Record refer to Item 3.2
checkpoint | 3.2.5. - Slump check
label | Description - Slump to be within the alocated tolerance
label | Method/Description - slump test
label | Test frequency - Each delivery truck prior to discharging
label | Conformance Criteria - 220mm ± 20mm
label | Constructor - H
label | CPS - R
label | Verifying Records - Shotcrete Record
checkpoint | 3.2.6. - Personnel Entry
label | Description - Test prior to each personnel entry and/or face advance.
label | ○ Test results must be verified once a month during construction.
label | Method/Description - Penetrometer test
label | Test frequency - Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction.
label | Conformance Criteria - Min 1MPa for man entry (providing the shotcrete layer is 75mm thick, rockbolts have been installed and the rockbolt grout compressive strength is min 3MPa)
label | Constructor - H
label | CPS - W
label | Verifying Records - Penetrometer test results refer to Item 3.3
checkpoint | 3.2.7. - Beam End Test (early age compressive strength)
label | Description - Safe shotcrete strength before next advancement to max. advance length
label | Method/Description - field test
label | Test frequency - Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction.
label | Conformance Criteria - Min. 1.00 MPa at 3 Hours
label | ○ Min. 5.00 MPa at 6 Hours
label | ○ Min. 7.00 MPa at 12 Hours
label | ○ Min. 12.00 MPa at 24-36 Hours
label | Constructor - H
label | CPS - W
label | Verifying Records - Beam End Test Results refer to Item 3.3
checkpoint | 3.2.8. - compressive strength (cast sample)
label | Description - To prove compressive strength compliance requirement
label | Method/Description - certified lab test
label | Test frequency - 1 test (I test shall include 4 cored specimen, 3 tested and 1 spare) for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter
label | Conformance Criteria - Min. 35 MPa at 28 days
label | Constructor - W
label | CPS - R
label | Verifying Records - IANZ lab test report
checkpoint | 3.2.9. - compressive strength (cored sample)
label | Description - To prove compressive strength compliance requirement
label | Method/Description - certified lab test
label | Test frequency - 1 test for every 50m3 of sprayed shotcrete
label | Conformance Criteria - Min. 20 MPa at 7 days
label | ○ Min. 35 MPa at 28 days
label | ○ Min. 35 MPa at 90 days
label | Constructor - W
label | CPS - R
label | Verifying Records - IANZ lab test report
checkpoint | 3.2.10. - Residual Flexural Tensile Strength
label | Description - To prove compliance with flexural strength requirements
label | Method/Description - certified lab test
label | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter
label | Conformance Criteria - Min. FR,1 of 1.25MPa and FR,4 at 1MPa
label | Constructor - W
label | CPS - R
label | Verifying Records - IANZ lab test report
checkpoint | 3.2.11. - Drying Shrinkage Testing
label | Description - To prove compliance with shrinkage requirements
label | Method/Description - certified lab test
label | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter
label | Conformance Criteria - Max 850 micro strain
label | Constructor - W
label | CPS - R
label | Verifying Records - IANZ lab test report
checkpoint | 3.2.12. - Permeability testing
label | Description - to prove compliance with permeability requirements
label | Method/Description - certified lab test
label | Test frequency - 3 tests for the first 50m3 of shotcrete then 1 test every 1 month thereafter
label | Conformance Criteria - Maximum allowable penetration 25mm
label | Constructor - W
label | CPS - R
label | Verifying Records - IANZ lab test report
checkpoint | 3.2.13. - Steel fibre content
label | Description - To prove compliance with fibre content test requirement
label | Method/Description - certified lab test
label | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter
label | Conformance Criteria - Minimum 35kg/m3
label | Constructor - H
label | CPS - R
label | Verifying Records - IANZ lab test report
checkpoint | 3.2.14. - Relative density
label | Description - To prove compliance with the relative density requirement
label | Method/Description - certified lab test
label | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter
label | Conformance Criteria - Minimum 98% of the density measured from base mix
label | Constructor - H
label | CPS - R
label | Verifying Records - IANZ lab test report
checkpoint | 3.2.15. - Layer thickness, Tunnel Lining Intrados, C-Line
label | Description - Provide control means to verify the thickness of final shotcrete layer
label | Method/Description - Survey scans, deep pins
label | Test frequency - As-builts shall be taken of EACH layer of shotcrete
label | Conformance Criteria - Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8130 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8119
label | Constructor - H
label | CPS - R
label | Verifying Records - As-built Report
checkpoint | 3.2.16. - Construction joints
label | Description - Construction joints in the shotcrete lining top heading/bench shall be inspected by the Designer’s Representative as required by the Drawings.
label | Method/Description - Visual Inspection
label | Test frequency - Every Construction Joints
label | Conformance Criteria - Hold point released by CPS
label | Constructor - H
label | CPS - H
label | Verifying Records - Site Inspection Report, Shotcrete Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.17. - Curing
label | Description - Curing to be carried out in accordance with the Specification
label | Test frequency - Each Spray
label | Constructor - H
label | CPS - R
label | Verifying Records - Shotcrete Checklist
checkpoint | 3.2.18. - Defects and Repair
label | Description - The final layer of shotcrete shall be inspected for any defects and repaired accordingly.
label | ○ At the completion of the lining, all core holes in the lining (resulting from testing or inspection) shall be backfilled with non-shrink mortar of an equivalent strength and fire resistance properties unless otherwise specified. The surface of the restored hole shall be similar to the surrounding surface in texture and colour.
label | Method/Description - Visual Inspection
label | Test frequency - Every defect on Every advance
label | Conformance Criteria - Crack <0.5mm ,Crack >0.5mm -Non corformance report
label | Constructor - H
label | CPS - W
label | Verifying Records - Post spray inspection record
section | 3.3. Reinforcing mesh
checkpoint | 3.3.1. - Reinforcing mesh for primary lining
label | Description - To prove position, cover and overlap are achieved
label | Method/Description - Visual inspection and survey
label | Test frequency - Every advance
label | Conformance Criteria - Longitudinal and transverse overlap of 250mm (one mesh square plus 50mm)
label | ○ Min. cover 65mm at the extrados and 85mm at the intrados
label | Constructor - H
label | CPS - W
label | Verifying Records - Check sheet
section | 3.4. Rockbolts
checkpoint | 3.4.1. - Drilling
label | Description - Bolts shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
label | Method/Description - Survey
label | Test frequency - Each bolt
label | Conformance Criteria - Rockbolts shall be installed perpendicular to the excavation face unless stated otherwise.
label | ○ Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular.
label | ○ Position Tolerence +150,-150mm
label | ○ No overdrill tolerance
label | – The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
label | Constructor - H
label | CPS - W
label | Verifying Records - Drilling log
checkpoint | 3.4.2. - Installation
label | Description - Record all information on installation (position, hole length and dianeterm length of the bolt…)
label | Method/Description - Review
label | Test frequency - Each bolt
label | Conformance Criteria - Rockbolts to be clean and free from rust or any other physical damage at the time of installation
label | ○ Type of bolts, diameter, length, location, spacing and orientation according to detailed design
label | ○ The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
label | Constructor - H
label | CPS - W
label | Verifying Records - Drilling log
checkpoint | 3.4.3. - Grouting mixing
label | Description - To ensure correct practice
label | Method/Description - Review
label | Test frequency - Every batch prior to grouting
label | Conformance Criteria - Target w/c ratio as per MAR
label | Constructor - H
label | CPS - W
label | Verifying Records - Grouting records
checkpoint | 3.4.4. - Grout test
label | Description - Testing specimen to measure UCS
label | Method/Description - Compressive strength test
label | Test frequency - Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days)
label | Conformance Criteria - min 20MPa at 1 day
label | min 40MPa at 28 days
label | The average compressive strength determined from any group of cubes shall exceed the specified characterisitc strength by:
label | ○ 1MPa at 1 day
label | ○ 3MPa at 28 days
label | Constructor - H
label | CPS - W
label | Verifying Records - Test results
checkpoint | 3.4.5. - Resin
label | Description - To ensure correct practice and full encapsulation
label | Method/Description - Review
label | Test frequency - Each bolt
label | Conformance Criteria - Sufficient number of resin cartridges to be used with each rock reinforcement installation in accordance with the approved project specific procedure developed during the trials.
label | ○ daily records of all grouting works to be kept
label | Constructor - H
label | CPS - W
label | Verifying Records - Grouting records
checkpoint | 3.4.6. - Pull test
label | Description - Demonstrate that the installed rock reinforcements can provide at least the design working load capacity.
label | Method/Description - Test
label | Test frequency - 1. First three installations of both rock bolts and rock dowels in each ground type as present in production.
label | ○ 2. 5% of the next 100 installations of rock bolts and rock dowels, proportionately throughout the ground types presenting.
label | ○ 3. 2.5% of the remaining bolts and dowels proportionately throughout the ground types presenting
label | ○ Note: 3 neighbouring installations of rock reinforcement surrounding a failed rock bolt or dowel test (and test frequency to revert back to 5% for the next 100 and 2.5% for the remaining installations)
label | Conformance Criteria - The bolt or dowel is deemed acceptable if, during the cycle, the displacement of the bolt or dowel head relative to the measuring datum (after allowing for any temperature changes) does not exceed the criteria for 100% of the working load, as set out in Table 6.4 of the specification.
label | ○ Failure criteria: 2% Maximum Permissible Displacement or failure to maintain specified loads or ongoing creep of the rock bolt or rock dowel
label | Constructor - H
label | CPS - W
label | Verifying Records - Testing records
section | 3.5. Spile installation
checkpoint | 3.5.1. - Drilling
label | Description - Spiles shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
label | Method/Description - Survey
label | Test frequency - Each spile
label | Conformance Criteria - Positional tolerance of portal spile bars not to exceed 25mm in any direction
label | ○ Setout angle shall be as per drawing. Max. angular tolerance not to exceed 1 in 60.
label | Constructor - H
label | CPS - W
label | Verifying Records - Drilling record ,Survey Report
checkpoint | 3.5.2. - Installation
label | Description - Record information on installation.
label | Method/Description - Review
label | Test frequency - Each bolt
label | Conformance Criteria - Spiles shall be free of dirt, detrimental rust or any other deleterious substance.
label | ○ Type of spile, diameter, length, location, spacing and orientation according to detailed design.
label | Constructor - H
label | CPS - W
label | Verifying Records - Rock Bolt Installation Record
checkpoint | 3.5.3. - Grouting mixing
label | Description - To ensure correct practice and w/c ratio check
label | Method/Description - Review
label | Test frequency - Every batch prior to grouting
label | Conformance Criteria - Target w/c ratio as per MAR
label | Constructor - H
label | CPS - W
label | Verifying Records - Rock Bolt Installation Record
checkpoint | 3.5.4. - Grout test
label | Description - Testing specimen to measure UCS
label | Method/Description - Compressive strength test
label | Test frequency - Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days)
label | Conformance Criteria - min 20MPa at 1 day
label | ○ min 40MPa at 28 days
label | The average compressive strength determined from any group of cubes shall excess the specified characterisitc strength by:
label | ○ 1MPa at 1 day
label | ○ 3MPa at 28 days
label | Constructor - H
label | CPS - W
label | Verifying Records - IANZ lab test report
section | 3.6. Face dowels
checkpoint | 3.6.1. - Drilling
label | Description - Dowels shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
label | Method/Description - Survey
label | Test frequency - Each dowel
label | Conformance Criteria - Dowels shall be installed perpendicular to the excavation face unless stated otherwise.
label | ○ Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular.
label | ○ Position Tolerence +150,-150mm
label | ○ No overdrill tolerance
label | –The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
label | Constructor - H
label | CPS - W
label | Verifying Records - Rock Bolt Installation Record/Check list /As built Survey
checkpoint | 3.6.2. - Installation
label | Description - Dowels shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
label | Method/Description - Review
label | Test frequency - Each dowel
label | Conformance Criteria - dowels to be clean or any other physical damage at the time of installation
label | ○ Type of bolts, diameter, length, location, spacing and orientation according to detailed design
label | ○ The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
label | Constructor - H
label | CPS - W
label | Verifying Records - Rock Bolt Installation Record
checkpoint | 3.6.3. - Grouting (1)
label | Description - To ensure correct practice and w/c ratio check
label | Method/Description - Review
label | Test frequency - Every batch prior to grouting
label | Conformance Criteria - Target w/c ratio as per MAR
label | Constructor - H
label | CPS - W
label | Verifying Records - Rock Bolt Installation Record
checkpoint | 3.6.3. - Grouting (2)
label | Description - Testing specimen to measure UCS
label | Method/Description - Compressive strength test
label | Test frequency - Every batch prior to grouting (three cubes at 1 day, three cubes at 28 days)
label | Conformance Criteria - min 20MPa at 1 day, and average to exceed specified strength by 1MPa
label | ○ min 40MPa at 28 days, and average to exceed specified strength
label | Constructor - H
label | CPS - W
label | Verifying Records - IANZ lab test report
section | 3.7. Probe holes
checkpoint | 3.7.1. - Drilling probe holes
label | Description - Record information during drilling
label | ○ Check the water inflow during and after drilling
label | Method/Description - Geological monitoring
label | Test frequency - Maintain minimum one probe at 20 m ahead of the face at all times
label | Conformance Criteria - Hole diameter minimum 50 mm
label | ○ Not less than three probe holes shall be maintained a minimum of 6m ahead of the excavation face at all times and with at least 1 probe hole maintained a minimum 20m ahead of the excavation face at all times
label | Constructor - H
label | CPS - W
label | Verifying Records - Probe holes record ,Survey As built report
section | 3.8. Monitoring
checkpoint | 3.8.1. - Tunnel convergency (Extensometer)
label | Description - Monitoring and reading records of the tunnel extensometer
label | Method/Description - Review
label | Test frequency - from excavation face
label | ○ >100m = Monthly
label | ○ 40m-100m = Weekly
label | ○ 15m - 40m = 2x weekly
label | ○ <15m = daily
label | Conformance Criteria - Refer to drawings MMA-DES-TUN-E1-DRG-8180
label | Constructor - H
label | CPS - R
label | Verifying Records - Monitoring Report
checkpoint | 3.8.2. - In-Tunnel Optical Survey Convergence
label | Description - Monitoring and reading records on the tunnel optical survey targets
label | Method/Description - Review
label | Test frequency - from excavation face
label | ○ >100m = Monthly
label | ○ 40m-100m = Weekly
label | ○ 15m - 40m = 2x weekly
label | ○ <15m = daily
label | Constructor - H
label | CPS - R
label | Verifying Records - Monitoring Report
section | 3.9. Ground water control
checkpoint | 3.9.1 - Strip drain installations
label | Description - Record location and ensure correct installation
label | Method/Description - Review
label | Conformance Criteria - Location and quantity of the strip drains shall be as instructed on site by the Designer's representative
label | Constructor - H
label | CPS - R
label | Verifying Records - Excavation and shotcrete check sheet,Survey as built record
checkpoint | 3.9.2 - Groundwater (rectification)
label | Description - Where the inflow into the tunnel exceeds the design criteria,appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative.
label | Method/Description - Visual Inspection
label | Test frequency - Ongoing
label | Conformance Criteria - Shall not be exceed 3L/m of length/day averaged over a 100m length of tunnel. Where exceeded, the post-installation groundwater methodology is to be followed.
label | Constructor - H
label | CPS - H
label | Verifying Records - Installation Checksheet
holdpoint | AUTHORITY HOLDPOINT
section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
note | Site Engineer/Project Engineer
note | Zone Manager Approval
note | Construction Manager Approval
note | Quality Manager Approval
date | Date:
signoff | SIGNATURE
checklist | ITP - Tunnel Post Construction | itp |  |  |  |  | ITP - Tunnel Post Construction
section | 4.0 Post construction
checkpoint | 4.1. - Red Line Mark Up Drawings
label | Description - As-built drawings to capture any deviation from the IFC drawings.
label | Method/Description - Submit
label | Test frequency - At Completion
label | Constructor - H
label | CPS - R
label | Verifying Records - Red Line Mark Up Drawings
checkpoint | 4.2. - As-built Drawings
label | Description - As-built drawings to capture any deviation from the IFC drawings.
label | Method/Description - Submit
label | Test frequency - At Completion
label | Constructor - H
label | CPS - R
label | Verifying Records - As-built drawings, installation record, as built records, PTT, testing results, monitoring documentation, operation and maintenance report, Producer Statements
checkpoint | 4.3. - Tunnel Operation and maintenance report
label | Description - Tunnel Operation and maintenance report to detail the maintenance frequency and maintenance procedures.
label | Method/Description - Submit
label | Test frequency - At Completion
label | Constructor - H
label | CPS - R
label | IOM - R
label | Verifying Records - Tunnel operation and maintenance report
checkpoint | 4.4 - Final Handover Package
label | Description - Collation of all QA, as-built drawings,as-built records, installation records, PTT, testing and monitoring documentation. Provision of asset management operation and maintenance report to NZTA, including Producer Statements.
label | Method/Description - Submit
label | Test frequency - At Completion
label | Constructor - H
label | CPS - R
label | IOM - R
label | Verifying Records - As-built drawings, installation record, as built records, PTT, testing results, monitoring documentation, operation and maintenance report, Producer Statements
section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
note | Site Engineer/Project Engineer
note | Zone Manager Approval
note | Construction Manager Approval
note | Quality Manager Approval
date | Date:
signoff | SIGNATURE