## Master List Templates
Id | Type | Name | Values | Prompting Name | Resource Id
054ede44-8eb6-4e13-878e-4004cdbdc4e2 | checklist | ITP-002 - Cement Stabilisation | itp | ITP-002 - Cement Stabilisation | 4354f7a2-1952-4139-ab7c-55ff3c5624d1
857405fa-85ca-48bc-809a-9bd1da8daf36 | section | Cement Stabilisation
211533ca-5805-4d71-b0d7-6792fc45bd60 | checkpoint | 1 - Mix Design
384fb554-cf0d-59eb-90bf-b6fb71af28cc | note | FREQUENCY - Prior to start
3747d49e-3a7b-5282-91ac-8ad2be9c21f0 | note | ACCEPTANCE CRITERIA - Mix design to be selected based on pavement material investigation. Binder application rates to be confirmed with client prior to start.
00628e39-730f-58fa-a3e3-112bbd4a6faf | note | REFERENCE DOCUMENTS - VR 307.05
8a535256-11e1-58cb-b799-c5503eb2436f | note | INSPECTION / TEST METHOD - Record
ea5f15e2-3aa6-5193-81e4-c0a092f2624e | note | RECORD OF CONFORMITY - Record
8bd7767d-ebcc-52d4-82dc-2bed99e3cafc | note | HP*
3d743550-9f10-5b89-8973-62aa79108fbf | note | RESPONSIBILITY - Project Engineer
7a85e3f7-b11a-584e-bc50-4aa201f36a92 | date | Date Completed:
9f3911a5-4f47-4aed-9fe4-13bf8764d9be | checkpoint | 2 - Preliminary level confirmation
ff60f601-c148-5ad6-865e-6e15a6df273b | note | FREQUENCY - Prior to start
47dd3d87-6faa-545c-9b8b-1432adb632b8 | note | ACCEPTANCE CRITERIA - The surface level of the area to be stabilised shall be confirmed to be within level tolerances prior to commencement of stabilisation. Unless otherwise specified, +15/-25mm.
cfba47b5-42ce-5e3b-82c2-78bd0b60accd | note | REFERENCE DOCUMENTS - VR 307.03(a)
3e4c02e1-3bd5-5847-877c-63876c6ac8ce | note | INSPECTION / TEST METHOD - Visual
b854368f-d066-54cf-b68e-960c327abea5 | note | RECORD OF CONFORMITY - Visual
c8e50bac-7d05-55f8-93bf-7f413e73cf32 | note | IP
882145fe-1483-5a40-969b-ec6fd593a72d | note | RESPONSIBILITY - Project Engineer
291853e0-f4f3-5ccf-b09d-2c3a6d896633 | date | Date Completed:
00d54696-f99b-422e-a4e7-92b5ee393315 | checkpoint | 3 - Binder Supply
4314f9c8-937c-52d6-a4be-78395e9c0939 | note | FREQUENCY - Each production day
be703c3e-6bde-5d42-a367-a8614a91bc75 | note | ACCEPTANCE CRITERIA - Quicklime & Hydrated Lime to meet requirements of AS1672. Cement supply to comply with AS 3972. ALI shown on delivery dockets.
63431d19-7f04-5275-b328-01d6c2c0b9f3 | note | REFERENCE DOCUMENTS - VR 307.04
dd137de7-7213-5ce5-8cfb-e3f303cd1c42 | note | INSPECTION / TEST METHOD - Test Report
886b7eb6-0a20-5ff0-8a27-507197a0bd8a | note | RECORD OF CONFORMITY - Test Report
a2fae1e3-07d8-501a-8bdc-18289ddcc3ad | note | IP
1a362821-71ab-5f57-ac45-3d8851abce12 | note | RESPONSIBILITY - Project Engineer
42fe5711-fbc1-58cb-b688-783194f68df2 | date | Date Completed:
234b66b2-9e36-4b87-aecd-5314e6bc8ef9 | checkpoint | 4 - Spreading of stabilising agent
5eb8c8ba-94d6-565d-8e3b-c07d43f00aef | note | FREQUENCY - Each Lot
a7c83163-734a-5a43-bb11-cf27fa89866e | note | ACCEPTANCE CRITERIA - Binder shall be spread at the specified rate. In passes not exceeding 15kg/m2. No traffic to be allowed after spreading other than construction traffic. Matt test & load cell outputs recorded for QA purposes.
17ea66b5-9f67-55e7-a63d-982c391529b4 | note | REFERENCE DOCUMENTS - VR 307.14
1d069a39-16af-5c76-818d-80b31ca96351 | note | INSPECTION / TEST METHOD - QA Report
99502a6e-6287-5f68-b48a-fc88df335496 | note | RECORD OF CONFORMITY - QA Report
29d85bdf-96e1-5c51-bc9d-c2fb87284596 | note | IP
f4126577-e218-533c-b299-0da63d056a05 | note | RESPONSIBILITY - Project Engineer
0bfc193c-9866-5ae9-b9ff-cc00a05432e4 | date | Date Completed:
11df4343-a2f8-4fcf-8d99-f5ae3086c484 | checkpoint | 5 - Slaking of Lime
689de229-9953-50cd-a7fc-3719119a48d2 | note | FREQUENCY - Each Run
e64fd0ca-f44c-513a-bb3c-6997920552a0 | note | ACCEPTANCE CRITERIA - If quicklime is used it shall be slaked with sufficient water to allow full slaking to take place prior to mixing. Full slaking will be deemed to have been achieved when all quicklime that has been spread has changed from a cream coloured granulate to a fine white powder and there is a cessation of rising vapours.
69b5e4d2-e046-5510-bfb7-99431304bfa5 | note | REFERENCE DOCUMENTS - VR 307.08 (c)
d4e17935-f15a-5986-b205-fcb1ec7e945f | note | INSPECTION / TEST METHOD - Visual
63699f4c-9ba0-5483-a167-0fcd1324d384 | note | RECORD OF CONFORMITY - Visual
abc4eed3-8d04-5651-9024-c9660992cc11 | note | IP
c12d786b-5867-5b6e-80c8-a7dbd9d18e2c | note | RESPONSIBILITY - Project Engineer
a1b36ae5-a2e3-5339-8498-978042f82172 | date | Date Completed:
95799c10-a35f-420f-a9fb-b026e36c660c | checkpoint | 6 - Mixing of stabilising agent
132c0357-59f9-58c4-92cf-47893713d041 | note | FREQUENCY - Each Run
0c162f02-8828-53e7-9221-592547e43113 | note | ACCEPTANCE CRITERIA - Mixing shall commence as soon as practical after spreading of the cementitious binder. Water to be added as required to achieve and maintain close to optimum moisture content. Mixing depth to be physically checked.
1914ca6e-9fe8-5a02-bc2c-cef9d5d2513e | note | REFERENCE DOCUMENTS - VR 307.08(e)
76f30061-b855-590d-bd7f-2857f706424b | note | INSPECTION / TEST METHOD - Visual/ QA report
21a16b57-d02f-52b8-a29f-08128e924330 | note | RECORD OF CONFORMITY - Visual/ QA report
de5435da-fa9d-5c1b-b8d1-1f7653c60491 | note | IP
cb5c192c-b3b2-5edf-9322-121cf79db2cc | note | RESPONSIBILITY - Project Engineer
f81eb0ca-2dbe-5780-8f0f-e25d036ad971 | date | Date Completed:
0922a61f-0aa9-4d6e-91b8-8035ee7356c7 | checkpoint | 7 - Compaction
e2dd7b21-32aa-5576-88b7-8881d10616c5 | note | FREQUENCY - Each Run
c0dcd38b-59c3-5d9e-8133-b792dc851266 | note | ACCEPTANCE CRITERIA - Compaction of the stabilised layer shall commence immediately after mixing.
a58ad524-b1bf-593b-ab93-00fe9b72126b | note | ○ All compaction shall be completed within the times specified in Table VR 307.052 after addition of the cementitious binder.
3d01408b-dce5-590d-810b-9b9591e639d8 | note | REFERENCE DOCUMENTS - VR 307.08(f)
032625a9-5c46-5e9c-834d-93eeddc95e00 | note | INSPECTION / TEST METHOD - Visual
07ef0049-c5db-54a3-826b-13aa632ec3ea | note | RECORD OF CONFORMITY - Visual
a1967668-8f94-554a-8a9a-12ba6c0affa2 | note | TP
3a7b0ca6-9f2d-5792-972d-6a7ba9fe57d8 | note | RESPONSIBILITY - Project Engineer
2e4d3d6e-cbd6-5d69-a87a-fa03b7ecd377 | date | Date Completed:
7f1669fd-991e-452f-982e-da1036b3efda | checkpoint | 8 - Trimming
e72c0e36-f4f6-5b58-8ba4-c5a07fcd550c | note | FREQUENCY - Each Lot
7dd8ab88-306f-5b30-a5ff-d1c77ddc4576 | note | ACCEPTANCE CRITERIA - On completion of initial rolling, the stabilised material shall be trimmed to the specified surface tolerances. Water may be applied during this operation to replace evaporated moisture.
3e37b5e4-b0bc-56e0-85e3-55f3394fe361 | note | REFERENCE DOCUMENTS - VR 307.08(g)
620a1526-adf8-5246-993b-ad4f9d697efa | note | INSPECTION / TEST METHOD - Visual
185f82f3-d9ce-595d-a82e-8c5be90c776f | note | RECORD OF CONFORMITY - Visual
9b192d14-67ef-5c8f-bac4-9ca024e3295f | note | IP
220194bd-e879-5ab5-b423-4cab8a2fbd69 | note | RESPONSIBILITY - Project Engineer
ed38ae14-636d-511f-bd58-cfec4d8d60f5 | date | Date Completed:
b62aa8d4-d01f-4451-b0ed-4bc8c75e6852 | checkpoint | 9 - Test Rolling
0f07b646-7dd3-5604-b1d2-3eb4e2d8ae18 | note | FREQUENCY - Each Lot
31203af8-29f9-591b-8b9b-88389900d9f2 | note | ACCEPTANCE CRITERIA - Stabilised layers shall pass test rolling in accordance with Section 173, prior to acceptance of the layer.
4ac80e37-bd42-5cfd-a218-688e5a3756af | note | REFERENCE DOCUMENTS - VR 307.10
5337b595-e3a0-521a-9886-11137dc059f4 | note | INSPECTION / TEST METHOD - Visual
b34708e6-945c-57d7-9573-012a94832280 | note | RECORD OF CONFORMITY - Visual
3b876763-2a72-5ff5-a4c7-fbf2a807c7e1 | note | HP, WP
c8fe3744-2c66-5b38-aede-483b034e7271 | note | RESPONSIBILITY - Project Engineer / DTP
86b292d8-967f-5192-9037-7387c0f61331 | date | Date Completed:
446662e0-2cbd-4d6b-b6e9-87f42b382e8e | signoff | AUTHORITY HOLDPOINT
b8230bd9-3c25-4f4c-87c4-a626ec0f10e1 | checkpoint | 10 - Compaction Testing
fff40d79-c68d-5832-adf7-4bff052991ea | note | FREQUENCY - Each Lot
d6ceb9b0-4a8c-5d8e-ad51-a8775c03fcbb | note | ACCEPTANCE CRITERIA - If required, density testing to be undertaken as per table 307.151 or otherwise specified
c014796f-6467-5535-944f-a2119eee4f88 | note | REFERENCE DOCUMENTS - VR 307.15
f7dbd2ad-70c3-507b-bb08-ed3c2a8acd8c | note | INSPECTION / TEST METHOD - Test Report
71b0c00d-0aff-5a88-bac4-7db11c566d54 | note | RECORD OF CONFORMITY - Test Report
1e1fba40-14e4-5882-9046-3a5e4b681cd7 | note | TP
4e793f49-f7dd-592b-a4fd-9f5629a9ad98 | note | RESPONSIBILITY - Project Engineer
f9e824d4-ce33-50ad-9a8e-3430912d5675 | date | Date Completed:
719f67f7-a2bb-4b5d-bb6e-1287188872c6 | checkpoint | 11 - Maintenance of Stabilised layer
ce86cc5b-3214-5a74-adbd-2f4cdd42b925 | note | FREQUENCY - Each Lot
77afaea5-2ed6-515e-97b5-76e6d1988d00 | note | ACCEPTANCE CRITERIA - Surface shall be kept moist and protected from damage by traffic and construction activities until further pavement layer is applied.
d1710ddb-4225-5f91-8d11-34cea298b2cb | note | REFERENCE DOCUMENTS - VR 307.11
f2cababd-5598-527a-a464-5c1a0d5d50b9 | note | INSPECTION / TEST METHOD - Visual
a61bb987-a201-54e5-aa93-f16f924c339a | note | RECORD OF CONFORMITY - Visual
39525603-82ff-5729-8ef0-049b053a4e5d | note | IP
7f62279c-845f-5bf9-ba10-39c77cd0c4df | note | RESPONSIBILITY - Project Engineer
cdee3857-4918-5cd5-9266-93c210cf44b0 | date | Date Completed:
8d41508b-d7b7-445c-a62c-ef47bcc0b43f | checkpoint | Final Inspection
a90427b8-034d-55db-9b7c-9859e00c27d9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
a5e37654-341b-58fe-8d5c-c8794614a70a | textbox | Print Name:
d6770516-17fb-5f07-ba7e-09b5c3d48fca | textbox | Position:
c4b6b016-d4e2-5b46-b4a7-bcd5fb415363 | date | Date:
e174e8ac-105b-412c-96d1-2550f6fa80bf | signoff | Sign ITP
d475b86f-f799-5f15-9f50-f9ea507a9f6a | checklist | ITP-002 - Earthworks | itp | ITP-002 - Earthworks | a1c13c96-9540-4df8-af90-a6a42142b510
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
78f2eb97-4d27-5397-9616-d0974c63c400 | checkpoint | 1.1 - Check for correct documentation
63ef06e4-2920-5a35-b5b9-535fc9e300ba | note | FREQUENCY: Prior to commencing any activity
975a3e51-9557-5498-a0e6-f409be88ad10 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
613e7170-9728-5570-9c31-94beb88c7c44 | note | – using the correct and complete set of drawings
8feb9044-c864-5b37-9c61-519e64230102 | note | – all drawings are the latest revision
7ef1083c-e883-5714-9b92-dd73a27abd47 | note | REFERENCE DOCUMENTS: IFC Drawings
c62d4720-bd30-52d5-8674-bf431547ccff | note | METHOD: Visual Inspection
661abbd6-eca8-532e-a3ff-1a64e77beb1b | note | RECORD: Signed ITP
9a9af3b3-4708-566d-a616-369ced59562c | note | IHP
72fb4da4-635e-5a66-ab2f-552827b9e2ba | note | RESPONSIBILITY: SWA Project Manager
51e49a8c-5445-526e-984b-423795089fd5 | date | Date Completed:
457fc29c-5478-51c3-a60f-061f5ba4ad0d | checkpoint | 1.2 - Implementation of all measures and controls
07d8c898-2208-523a-80f7-1387c0f63df8 | note | FREQUENCY: Prior to commencing any activity
0751365c-1d20-5c53-b1bb-3b51d00d3665 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
a8f70dba-46e3-5a26-95d6-26e96fae383e | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
1352caef-d602-554b-a7da-1423cabffbbb | note | METHOD: Visual Inspection
a0b75b41-f0dd-5860-96b6-6da3307d8ce6 | note | RECORD: Signed ITP
b53b50a3-f195-5159-859f-bc717daeffdb | note | IHP
06ed450d-b079-5465-9db2-0846a76be876 | note | RESPONSIBILITY: SWA Project Manager
7c543fa3-0593-5ec2-863a-f310fc8ca8f9 | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
8ca7bcd9-51c2-5af5-a939-2cb980971168 | checkpoint | 2.1 - Survey Set-Out
046dd51c-0175-5459-a6c5-f55a289e5f9f | note | FREQUENCY: Prior to commencement of excavation.
59adf8ec-c302-58b0-9358-84cc178503e2 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
f4ef093d-e2c1-520a-bcb4-4f73075c4346 | note | REFERENCE DOCUMENTS: Work Procedure
6cb1adab-fa85-5394-b96a-55d7a6d14d84 | note | METHOD: Verify
f4f4540d-46e7-5141-aded-2d93b7455cf6 | note | RECORD: Signed ITP
8ef72872-7802-5f59-bf65-b457024a33ac | note | IP
4357050c-8bee-5b9c-851a-a546b7d3e05b | note | RESPONSIBILITY: SWA Project Manager
4f7fa3db-aedc-5e1b-aadc-9eee1d7a7f47 | date | Date Completed:
4fa02bcf-128c-52b5-bef2-2b0ba5d23d06 | checkpoint | 2.2 - Excavation Permit
b66700e3-f3fb-5637-82da-e55576bdf4b2 | note | FREQUENCY: Each Lot
19e84c8b-81ad-5fc9-9c1c-2cf7de12c162 | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
ce7a9b89-7a27-5c68-9149-9254a6ab0e3c | note | REFERENCE DOCUMENTS: Excavation Permit
1fcaa11d-5c25-529c-bc7a-fb66f002513e | note | METHOD: Verify
b940a2cc-622a-5268-b6d5-4174d5bfe926 | note | RECORD: Signed ITP
8d23f1bc-479e-5750-b0a8-4dc379f2e99d | note | IHP/IP
19cde785-dfd3-5089-a243-0103582f7314 | note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
329413a2-cceb-5639-8216-500c4af30ad1 | date | Date Completed:
696a0b9e-a6bb-510b-9f82-a68874efa52d | checkpoint | 2.3 - Sub grade Material Properties
5fd83012-c466-593d-9c1a-748bded75184 | note | FREQUENCY: Each Lot
afe4b2e2-ed25-5b1b-9af5-d1e138adac8a | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut ﬂoor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
a1ffa119-4d34-5673-9c44-9dc6ea662460 | note | ○ If parameter met, rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
ad5e0754-0df5-5c5e-abad-2aae1ada4c77 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
8ae13c3c-13ac-50c2-8189-e50b75a74f02 | note | METHOD: Site Inspection/Test Report
6d2aaaa3-68de-5559-b12a-b31c9741aade | note | RECORD: Signed ITP & Test Report
07fd6496-84d5-54b1-b081-eab94ff926ce | note | TP/AP
10ab7e0c-4532-54d5-a31a-e33a6cd96b1d | note | RESPONSIBILITY: SWA Project Manager/External testing Company representative/RRV Superintendent
3e8552c4-a105-5534-846a-e1af640e3f76 | date | Date Completed:
cf0f983f-dec6-5c5c-b317-8e537435bfb7 | checkpoint | 2.4 - Inspection of Subgrade Material
fc2ff622-f8b0-5225-9a20-3b3fb6fdc287 | note | FREQUENCY: Each Lot
13024377-9a3c-5b23-84e9-ad46c0eb0d37 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to veriﬁcation by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
d2cc98f5-f540-50ae-8a5e-e3e548ef5835 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
0db4cef1-508a-5807-bef9-04f66542a0d3 | note | METHOD: Visual Inspection
76a001cd-1c60-595d-81ea-30fe6d7c513e | note | RECORD: Signed ITP
5b5cb03e-be09-5c3e-ae18-32be5d6e95ec | note | IHP/AP
c06704ae-32fe-5fa2-9cb1-3c0294866db3 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
d3926330-b65c-5374-aab5-5164629eeec9 | date | Date Completed:
ed73382c-33d9-5bab-a623-7ebe94daf695 | checkpoint | 2.5 - Material Classiﬁed as Silt
43018c9f-362c-57f1-a789-d614010c526d | note | FREQUENCY: Prior to commencing
762a0a86-0d34-5b1d-abfa-fa16440eb526 | note | ACCEPTANCE CRITERIA: Material classiﬁed as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
56b42410-7b7a-50f6-b7d5-89d80bb5a441 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (e)
68b0c69e-dc73-5f91-a426-5d5e86656bb2 | note | METHOD: Visual Inspection
5e98c672-e09a-5ac8-982a-016dbe24374d | note | RECORD: Signed ITP
cf5098b9-e705-5cac-a813-266e60de3dc5 | note | IHP/AP
b907f15a-9cc7-564b-8b66-da57e9316eb3 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
a0191669-b753-5b5a-a7a3-8c73f82bad58 | date | Date Completed:
1a64b919-5767-579b-b78d-b80a73f9f71f | checkpoint | 2.6 - Acceptance of Rock Subgrade (when applicable)
cb481af3-2357-5cbf-ad97-bc04aed2500c | note | FREQUENCY: Prior construction of the regulating layer.
51f0b093-c186-5f27-a8c3-ccabdfbfd53c | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
8ad4bf0a-5290-51af-a3e5-ee684a223608 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
61cb11b6-7c28-56b9-8dc8-cf645c711174 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (f)
14a6497b-1d6f-5818-8481-9bf14cba7709 | note | METHOD: Site Inspection/ Document Review
d35e44fd-e587-5be6-a24f-718975f149ec | note | RECORD: Signed ITP
49338d4e-2a96-5325-800c-ad111c64dd75 | note | IHP/AP
12cb7c2b-36df-5553-ba6f-24e68e0207a8 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
2b1425cc-b454-5d77-98dd-96bd3b7aa072 | date | Date Completed:
6b5dbb08-09a3-59e4-9d78-56fe202c28ac | checkpoint | 2.7 - Unsuitable Material
db94795f-3834-5c1c-91f3-9fc4301600ab | note | FREQUENCY: Each lot as required
702af76c-3a00-56f1-9fd7-7ccc840360ca | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review
1b3e2ac5-48c1-5654-bd54-7761b3098b42 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (d)
36c5022f-b720-5452-8061-86025516a283 | note | METHOD: Visual Inspection
244ed7f3-e86b-5bac-9517-ea83524d8369 | note | RECORD: Signed ITP & Test Reports
f80bc235-fc80-596b-85fd-e33c182b9bd7 | note | IHP/AP/TP
f10559a8-06b7-5b31-8da5-5968ae7501a7 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
56094748-985f-5079-8f95-88fb28e47e3f | date | Date Completed:
85d203c2-ff88-5ee1-9095-c8f8c10eb8c6 | checkpoint | 2.8 - Groundwater
8e947778-8b84-5100-89f5-2f3fd0129bdf | note | FREQUENCY: Each lot as required
7673e185-bc79-53b7-bcb2-29c2e8a77f19 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
516134ef-d6bb-59c1-8b17-ab08d4c1f88c | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (h)
d1271fbf-7904-518b-b1e7-07dbd73a020f | note | METHOD: Visual Inspection
5ea962a4-e35d-5646-9f69-39256bf464cd | note | RECORD: Signed ITP & Test Reports
3692b2d5-c7e4-55f3-90a5-cbebc233d986 | note | IHP/AP
cc609a62-4df2-51a4-b6b1-bc840724da7e | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
9e689064-6953-575d-8309-6c093fb7d00c | date | Date Completed:
591accc9-6902-5e5f-9757-29f5822dfa19 | checkpoint | 2.9 - Trimming and level conformity
61509124-0ebf-5b78-8745-f05a38c4eab4 | note | FREQUENCY: Each lot as required
a17b198b-f0c1-55dd-8a4a-d54afc2b9c1c | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
0d7a5745-75d9-57e4-9081-7b79048b2506 | note | ○ Level tolerances: Range x (Mean value of all measurements) (Scale A) x = +5, -25mm (Scale B )x = +5, -15mm
ad920ce8-f8b7-53b3-8743-60328344a9de | note | ○ Max S (Standard deviation of all readings) (Scale A) = 12 mm (Scale B) = 15 mm
5e252ff1-5950-54c6-bf76-db5a1f002010 | note | ○ No. measurements (Scale A) 80 per lot (Scale B) 40 per lot
87493cb0-d115-51c4-9d1f-759d71102d10 | note | REFERENCE DOCUMENTS: VcRoads Std 204.03 (f,g,h) Table 204.031
d04f4af3-fe8c-5e49-bcac-93f66a7ec19d | note | METHOD: Survey
311b327e-4037-5495-95d9-fdd693c1be25 | note | RECORD: Signed ITP & Survey Report
1018ec42-1b82-5abf-96e9-81d3440f82b4 | note | SCP
92e60c36-bee9-5e0c-8f85-d4a9bc691cf3 | note | RESPONSIBILITY: SWA Project Manager/External Surveyor
3b911a52-4913-54fd-8ba4-e6fcbb275574 | date | Date Completed:
6654a5b9-b49f-507b-92a0-605d8a01ad64 | section | 3 - Testing Requirements
a28580b2-c64c-594e-aa92-fe80a16a2976 | checkpoint | 3.1 - Test Rolling
d3a1bc80-faee-5112-bc75-bec68db18977 | note | FREQUENCY: Each lot as required
4e918e84-6387-53fd-91c4-0ca52044fde4 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep. ( Cl 173) Plant to comply with requirements of Cl 173.03.
5aaa4854-fe7e-5cad-b4e1-74d41e8f3994 | note | ○ Pneumatic tyred plant nominated for test rolling procedures shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre.
4277ddd7-f14f-588f-b3b9-ea39086bd6ec | note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Section173.03 173.03 (ii)
6ba8ef5c-35b4-5365-a45f-95d31a5cef58 | note | METHOD: Visual Inspection
1a0d1f68-b539-5451-b907-0976dddbb2e2 | note | RECORD: Signed ITP
9b6dc80f-3f74-52a8-8bd4-abfbdd979797 | note | IHP/WP
9ead8112-2025-5ed7-be9d-429f573ab070 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
b2ea547c-739f-5d7f-aa8f-212f732da151 | date | Date Completed:
a75a64bb-3d89-50ed-a9d6-5291bb034737 | checkpoint | 3.2 - Compaction Testing
f6a27ea9-f413-5e1c-9775-326bd9c2ee19 | note | FREQUENCY: Each lot as required
cb715b59-c134-524b-89fc-b956d96a3462 | note | ACCEPTANCE CRITERIA: Ripped and re- compacted material below Cut Floor Level = minimum compaction 98%.
e62dc0ef-1dae-5206-971f-c837806fad71 | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 98%.
5d92ffe2-2202-5931-b8a7-a03620b229c9 | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where ﬁll is to be constructed = minimum compaction 95%.
ce30c178-8296-5470-93d3-337682e65b40 | note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Table 204.131
8cc9c55b-be60-5c5c-a496-fe978d289bd0 | note | METHOD: Compaction Test
1e3b7c0a-b2a1-539a-bacd-7cfd0f0697dc | note | RECORD: Signed ITP & Test Reports
56699200-6334-5d20-84a4-70d33c6231aa | note | IHP/AP/TP
a0e93b15-f5af-5c9a-8e7c-cf39d73bfe28 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representative
bfd3e807-29e4-5f56-ae7a-2ce38924e07a | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
dcd25591-fde7-5bcd-a09b-d3e6d47d71ec | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
16a05b1a-935d-5290-8681-c77a6eab76c0 | textbox | Print Name:
64743c84-a5c9-5c74-99f1-e395de6b42c8 | textbox | Position:
49bd4889-f620-5147-a465-3d6c08b91f49 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
03b6dd15-6a8e-58af-86fe-27776b93d631 | checklist | ITP-004 - Underground Drainage | itp | ITP-004 - Underground Drainage | 555a15e2-c394-4195-b3b7-2def244e05c1
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
aa5b427d-339a-5d3d-b6c5-84f70f776c33 | checkpoint | 1.1 - Obtain MOA and Traﬃc Management Plans. Ensure Traﬃc Management Plan is adhered to.
ff7f771d-f196-5e94-89c0-d98ee7bccdc5 | note | FREQUENCY: Prior to commencing works
f1e48edd-754f-5254-98e2-0d81f4bf1295 | note | ACCEPTANCE CRITERIA: Refer to the VicRoads Traﬃc Management speciﬁcation 166
846dc3d1-3f0d-548b-88ce-ec81a4516cfc | note | REFERENCE DOCUMENTS: Traﬃc Mgmt. Plan
3b32932d-65ad-5802-8d9b-f12f832e80a9 | note | METHOD: Visual Inspection
9af47316-48b4-5e62-a789-d9cb5127c919 | note | RECORD: Signed ITP
09237390-a739-5faf-b772-8dade004f4a6 | note | IHP
7c013968-a164-5048-9bf4-0e39e513a1eb | note | RESPONSIBILITY: SWA Project Manager
30b0e11b-b6b1-5617-ae1d-0998085e5877 | date | Date Completed:
277ed93f-4550-5150-83c9-df642f820a8c | checkpoint | 1.2 - Purchase of pre-cast pits, pipes and end-walls
195669b0-1473-5494-a15a-ad3ec8a39b49 | note | FREQUENCY: Approval prior to placement of order
31a43218-3e13-5342-b183-b8ec49858bb2 | note | ACCEPTANCE CRITERIA: Refer to Construction Drawings
5700c480-85eb-5218-93a3-706a1f664619 | note | REFERENCE DOCUMENTS: Vic roads Standard drawings
dd1103a1-592e-5fa2-a1df-403df97b4a5e | note | METHOD: Review and approval of documentation, Visual inspection
b1ea887b-e0bf-56d9-9b74-1e58a173bb73 | note | RECORD: Signed ITP
87e90362-6a1a-532a-b98e-3458a3a56f01 | note | IHP
ef83053c-2695-53b4-b1cd-2a6e14967af3 | note | RESPONSIBILITY: SWA Project Manager
4eee7202-5202-5afd-a007-1628a7ce0d0f | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
3fc2718d-49ae-5211-b493-7b1d37994476 | checkpoint | 2.1 - CONFORMITY WITH DRAWINGS - The Contractor shall set out the drainage work in accordance with the drawings or as speciﬁed.
41bc5e39-ebc3-5862-ae41-6030e1febc70 | note | FREQUENCY: Each lot as required
8048936d-695b-5cdd-937b-b38056a05933 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall conﬁrm the position of all culverts with the Superintendent.
44adf031-0957-5d70-9ecf-c9728a776289 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
2af47ceb-97b3-5f1e-8621-68cb1577ea32 | note | METHOD: Construction Drawings
4eb6ebae-de34-501e-b1c7-690696fc4379 | note | RECORD: Signed ITP
c1e9b9c5-bfe7-56fc-8315-e88f4513fc5d | note | IHP
0314b7e7-da94-50cc-96a9-00fc9f06bed8 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
b225dc7d-df7d-533f-8ab6-615287710640 | date | Date Completed:
2ef4dc01-6d04-55e0-b499-703d38ded273 | checkpoint | 2.2 - CONFORMITY WITH DRAWINGS – The culverts constructed shall be constructed true to line and level
2253bb94-74fd-544f-b1be-00da20521073 | note | FREQUENCY: Each Lot
d326f21e-5a8e-5f77-b41b-fd03ece16966 | note | ACCEPTANCE CRITERIA: Unless speciﬁed otherwise the tolerance on location of pipes compared to the design or a change to the design notiﬁed in accordance with this clause shall be:
91a11db4-0d59-5076-8514-b961491675e5 | note | (a) oﬀset of entry pits required to match lines of kerbs or barriers ±20 mm
7af79b61-d7d4-592d-b239-f1ea814f9603 | note | (b) plan location of pits other than oﬀsets to kerb lines or barriers ±100 mm
5ccb1813-f18a-572c-ad93-988c6e037d8b | note | (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
d89417c4-1dbd-54c6-a591-3542d3627404 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
6e29027b-260e-5746-8b1e-04e31e593e2a | note | METHOD: Construction Drawings
f646c043-e403-532e-bf52-ac5c9d1595e4 | note | RECORD: Signed ITP
5796186f-716a-5899-afe2-91ea32a06e83 | note | IHP
08433fe9-66f6-596e-b684-be188dd7aa3d | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
f4968ee5-7261-587f-a4c3-61303e64aad8 | date | Date Completed:
9229842c-f53c-55b8-95c3-6daceb99e979 | checkpoint | 2.3 - EXCAVATION
eb6a81b1-106b-5f34-acc5-de0ef1dc8f6b | note | FREQUENCY: Each Lot
d37c6318-756c-531a-b22b-17daa23f131a | note | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm
5f543bae-e0ac-5b82-80d5-ad5d368ef555 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 701.14
239f74ed-19b8-5b33-a3e6-4f71c526e866 | note | METHOD: On-site Measurement
c5554e91-31f3-535b-a926-8a87cca0db04 | note | RECORD: Signed ITP & Drainage Checklist
a828992a-5878-5fea-a175-7d8ac53ec858 | note | WP
33b10b9d-3efd-5adc-aff9-bbe3d9ff2872 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
d8375f6f-ff33-5a15-b156-fb2952ca0d6e | date | Date Completed:
84b19f5b-5c46-57cf-a2f6-06554dc3aa79 | checkpoint | 2.4 - CULVERT BEDDING - Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert
25edea32-d970-5686-9c14-edca3b9efbfc | note | FREQUENCY: Each Lot
eb66c574-bb8f-5179-b2c3-6a00493b25af | note | ACCEPTANCE CRITERIA: The compacted thickness of bedding material following any shaping necessary shall be not less than:
3388aab4-97b7-511f-94a8-f344513ebbc7 | note | ○ 100 mm where D < 1500 mm
7d4a4a5d-71ea-55d7-af83-c565b0b0ecd2 | note | ○ 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width.
63c746b0-d9c2-53e3-82b2-3869e08c7f7f | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.15
1efcf702-d6c4-5fc2-b96a-28f08dfcd303 | note | METHOD: Site Inspection
18a937f2-a3e1-5bfd-80bd-dcaa997371f6 | note | RECORD: Signed ITP
cfb493f4-4784-5d48-844f-4e73bfc61023 | note | WP
bfa05788-6b45-5bad-ac25-11dc14849300 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
164537f7-8e27-51d7-84f9-89a18d28af18 | date | Date Completed:
9d74312e-086b-5ab1-b8fa-c13e8a502894 | checkpoint | 2.5 - PLACEMENT OF FILLING
c1c0360c-17a2-5ff3-bc82-281da7c28cc7 | note | FREQUENCY: Each lot as required
bd9a776e-abe2-546a-b401-bb87129b5561 | note | ACCEPTANCE CRITERIA: (a) Unless the culvert is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
160d80d9-ff77-5f51-b798-2054f70cd708 | note | (I) Culvert Under Area not to be Paved
0520f71c-d372-5b7a-915f-3b14a6e7c495 | note | ○ The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
288ada38-b0ab-508b-a609-231cf2a5eb01 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.18
c11628d9-8c2f-547c-a3d4-bd3c29584dbd | note | METHOD: Site Inspection
34d13068-7144-586d-9cb4-8dc1e9561164 | note | RECORD: Signed ITP
fa434381-2d8a-5b79-8a37-a56f27a08b6b | note | WP
95987a52-448a-5ad6-ad46-d0a13403a993 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
96f4d2af-c83c-5fea-88d4-62590757ddd1 | date | Date Completed:
3f774b8d-db9a-51be-a68e-24815f5896cb | checkpoint | 2.6 - INSPECTION OF DRAINAGE LINES BENEATH PAVEMENTS
138dc408-69fc-5f5a-8457-3469d3d95724 | note | FREQUENCY: Each lot as required
9a2feca4-3283-5092-bfd0-a4678f117675 | note | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV).
4e9109f9-343f-5fbc-9da1-718231d95947 | note | ○ Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
87e7f08a-f96f-5d07-b90d-aa12b5d88b49 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.28
62e347ab-b426-508c-ae0c-1024c9cc5cfa | note | METHOD: Visual inspection
d7f8dc8d-3819-5d55-8f64-c2b409877f47 | note | RECORD: Signed ITP
8089c255-87cb-5470-a96e-b2c801bafb1d | note | HP/AP
c3e603f4-4c5b-53b7-8f4f-ee08d4470d78 | note | RESPONSIBILITY: Project Engineer/Clients Superinten dent
d5bd297f-9113-5a39-b980-f5e0b8f88b12 | date | Date Completed:
5d0bf3c2-9d31-5144-bcdd-4b712c1f0027 | signoff | AUTHORITY HOLDPOINT
554ac80d-3a13-5271-8a6f-e2f6eed39f0c | checkpoint | 2.7 - Where required installation of Geofabric or Jute matting and beaching material in swale drains
cd3f9388-74bb-5021-a6db-086733703b09 | note | FREQUENCY: After installation of pipes, pits, end-walls and placement of asphalt wearing coarse
bf175921-e803-564c-8f3d-1bf7d662556d | note | ACCEPTANCE CRITERIA: Rock used, should be an assortment of sizes where possible. The smallest rock size must be able to resist dislodgment in peak ﬂows. Rock shall be placed with a geo-textile liner.
a88ccc67-6170-5043-a577-bb75f2d995aa | note | REFERENCE DOCUMENTS: NIL
c4b9166f-c4a8-5869-8242-4ff325f26b11 | note | METHOD: Visual inspection
8d82beaf-77e0-5b9c-877d-eefb3b017b03 | note | RECORD: Signed ITP
bdadf9cc-a6a1-5f77-81ee-d96f0df941b1 | note | IHP
d4dafda0-0727-562c-994e-7c2f64c04999 | note | RESPONSIBILITY: Project Engineer/Si te Supervisor
aebf675d-db93-5925-94f6-6aaaedf55e39 | date | Date Completed:
6654a5b9-b49f-507b-92a0-605d8a01ad64 | section | 3 - Testing Requirements
d0124663-714e-56dc-8e0b-cd503b4b8a31 | checkpoint | 3.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION AND MOISTURE CONTENT - Bedding and backﬁll materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
38f7f3fd-186b-5a94-9d3c-d46cfddc8722 | note | FREQUENCY: 3 per Lot (A lot shall consist of one layer of bedding or backﬁll for a culvert length between adjacent pits or endwalls)
39406688-46e7-5934-88dd-11172fada3d6 | note | ACCEPTANCE CRITERIA: (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
fc9b0346-7df2-5e7c-8e79-36472f115322 | note | (b) Backﬁll
84515d71-0f2e-55eb-9c0a-e16782ff187a | note | (i) Material of Nominal Size 40 mm or Less After Compaction Backﬁll material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
73d39840-e6d7-5c0b-8fd4-8bafe562197f | note | (ii) Material of Nominal Size Greater than 40 mm After Compaction Backﬁll material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
396e2c2c-1b7b-578c-bd19-8bc8eb1b9057 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.19
b4b94626-f9df-5024-bf29-1e39dbd6c81e | note | METHOD: Lab Test
74d128c5-1452-5f90-beee-94ceb44c230b | note | RECORD: Signed ITP
3782413a-7cf5-5707-89ed-a514e9b0186e | note | IHP
020dfa56-df5b-5eee-81e0-d26e3b402d1a | note | RESPONSIBILITY: SWA Project Manager
1492241a-2e16-51e4-bc88-241b9eba531f | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
bd0e6189-8169-5e75-838d-b3124d3c7a13 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
0db37f49-dd06-5ab4-9403-1ca4a21edb57 | textbox | Print Name:
f9cbb62d-571f-5bfd-bb23-97eeb63cd4a6 | textbox | Position:
52ce646b-4fd7-5d88-bf27-a1d49b30da0a | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
676c0dc5-3d4c-4d0d-8c3d-cb430e079773 | checklist | ITP-005 - Crushed Rock Class 2 | itp | ITP-005 - Crushed Rock Class 2 | 258652c3-ab25-4286-9242-ba0b3a548900
a7c01852-e10f-4bbd-aedd-6f66b710dc41 | section | 1 - Preliminary Works
b8ff2abc-8817-464f-a7b6-584c55b03f47 | checkpoint | 1.1 - Crushed Rock Mix design
b893e869-4fea-5400-aef4-bd3a82fd8dc7 | note | FREQUENCY: Prior to Commencing Work
67a1cfd6-c73e-56f8-a9f6-2e053f32259e | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
3e86ac57-c71d-5ba6-90f9-ca14696ecb9c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.812.09
f9e83717-2ba4-5d33-8cf6-d883fde8e7c4 | note | INSPECTION/TEST METHOD: Document Review
a8ff5066-85e7-5680-97ab-2f75724d7517 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
9d4219f5-9e18-58e6-9fe3-e67172c10dfd | note | HP*
ad577942-127e-5a92-8410-9be1f2e8f5f2 | note | RESPONSIBILITY: Project Engineer
a0880a7f-0855-5d3c-b945-86610cea2d0c | date | Date Completed:
1d41ea1f-fae0-4d58-aabd-ad265610043d | section | 2 - Placing Fill
62b23fe3-ef1b-4226-a0fa-193d962d3393 | checkpoint | 2.1 - Transverse Joints
99bb88ae-007d-5048-9a2c-5ec460cb096b | note | FREQUENCY: Check prior to placing material
ef8118c1-bcf5-51a2-87af-c9ace2201fb8 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres
513d9fe7-554c-5df5-8c83-7902aae5ed13 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (c)
ce711816-e815-59c4-a1b7-a239bd67b54f | note | INSPECTION/TEST METHOD: Site Inspection
bddf9f8b-454c-5c35-9ed1-91fa38c002dc | note | RECORD OF CONFORMITY: Signed ITP
d75e896d-9eec-57e8-b314-ccbdd8537d11 | note | IP
f586b5e7-0b4e-56d7-aefa-20152cc9c2ab | note | RESPONSIBILITY: Project Engineer
887b7376-711a-5fd6-8b9d-053f298f192f | date | Date Completed:
5509e709-c808-4199-95a1-ae8ff6225b45 | checkpoint | 2.2 - Longitudinal Joints
fbb0310c-9af1-5603-9687-8de821920689 | note | FREQUENCY: Check prior to placing material
eaf2e228-595c-50b5-8c27-ec0253790e0c | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
fcdb5ca4-b7fa-5770-832c-ab5719f8233e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
d4ddedfc-bce5-57e1-bada-a02910b09773 | note | INSPECTION/TEST METHOD: Site Inspection
574d0f7d-1083-5251-8f97-f5db8827c0db | note | RECORD OF CONFORMITY: Signed ITP
73507be5-6e44-5ddf-a757-eaf129d3f3d3 | note | IP
631bcee7-5b63-5fd3-9736-dfe0750e8707 | note | RESPONSIBILITY: Project Engineer
b1b82ebf-6912-588e-94f8-737dad3086df | date | Date Completed:
ce405cb9-ac24-44b3-afda-0d4f4ca52ca2 | checkpoint | 2.3 - Lot Size
3aa867e1-dda0-5c81-89c6-0c8af05fe594 | note | FREQUENCY: Check prior to placing material
6aafaa08-1f0f-5648-a300-408bf1e2247a | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
d966c5bd-c1de-5d8d-993e-ef0b3e5ddc5e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii), Table 304.111
430e644e-1534-5f5e-814d-36fd5d921653 | note | INSPECTION/TEST METHOD: Site Inspection
6e063d09-2e39-5655-9615-da95d092240e | note | RECORD OF CONFORMITY: Signed ITP
517545a0-f6ff-5782-9046-0368a980a4bd | note | IP
d6adc4a8-2c74-5b51-bf7a-6691dd1dcfb8 | note | RESPONSIBILITY: Project Engineer
9fdf7d63-2128-5d29-ae66-7e5d3eaf5b22 | date | Date Completed:
fec62321-06cc-4b43-b613-d07f30dea7a4 | checkpoint | 2.4 - Proof Roll
98564637-b2a8-5c81-828c-92ecbfc88774 | note | FREQUENCY: After placing material
65742847-85c9-5bf5-90ca-f0eb0884d62d | note | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
14eb7bd1-1f96-5700-95b7-b36059300472 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv), Cl. 173
095f59d1-7069-509f-a14a-e5e641ddf06c | note | INSPECTION/TEST METHOD: Site Inspection
74149970-4aec-5e45-8e0d-4031673e3b5e | note | RECORD OF CONFORMITY: Signed ITP
a3107613-093c-55fd-be8b-1648b517d181 | note | HP
6a22060e-d6d8-537a-980a-51758196a342 | note | RESPONSIBILITY: Project Engineer / DTP / VIVA
a9901f72-1da7-57e6-9008-a3b637c8eda6 | date | Date Completed:
d392bc65-2cb9-4cca-8bf6-3b2cc505fb79 | signoff | AUTHORITY HOLDPOINT
702c65f0-5167-4d45-acb3-89fcfef6a9f5 | section | 3 - Testing Requirements
760c8a41-d630-46b3-ab1d-92c36a24881f | checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
aaa6f55f-6a82-5abe-ae03-58f08bcdc0dd | note | FREQUENCY: Prior to Testing
ef35cf70-4621-53cc-835b-7eeb1a7a767c | note | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
764eb108-3d66-54e9-86c8-3e33c977491a | note | ○ Scale B - Initially test every lot until 2 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
626562b0-88d3-59c8-893a-0e25990bca82 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161
5302b1e4-f270-5089-abdb-922dd00733e7 | note | VicRoads Spec.
c1e874a4-3260-58c5-b842-780e1c112129 | note | ○ Cl.304.08 (a)
b0260730-334d-55df-9ff1-c0cb65fef98d | note | ○ Cl.304.11 (b)
11781de8-482c-5606-836a-5d1335d409f6 | note | ○ Cl.304.11 (c)(i)
7994d65e-7a67-5006-8dda-0cc760e016c4 | note | ○ Table 304.111
5b5b9f26-5857-5c87-ad58-4ffe02a7dfd8 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
7ce88dad-0b39-51e8-81fd-26050bfb83b4 | note | RECORD OF CONFORMITY: Signed ITP
2d2ea3ca-b76d-5c82-ad53-8723bbf6f13a | note | IP
d54e14a1-0b0c-5a38-9c58-eef4a72d5727 | note | RESPONSIBILITY: Project Engineer
ff89c13a-28d9-5533-934c-56e6026f5818 | date | Date Completed:
9ea74c3a-7990-458e-b9cc-ce7cc9b8712d | checkpoint | 3.2 - Modified Compactive Effort
6d520bd6-29c1-5ae8-a162-753bcc917cfd | note | FREQUENCY: As per 3.1
5e57f232-a612-57d4-932b-c1c097534ae7 | note | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 97.0% (Scale B) 1 per every lot
a9999452-9cf3-525f-9e20-70f38502c08e | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.081
95657a30-dce7-59b9-b63a-069c9c861a1e | note | INSPECTION/TEST METHOD: Site Inspection
239d06e7-3529-593c-b79d-f381437f1d33 | note | RECORD OF CONFORMITY: Test Records
41a83d58-832c-53b9-9937-2ffee8e40fde | note | TP
7757315f-f41c-5022-97ec-f1595ac55fec | note | RESPONSIBILITY: Project Engineer
a098d406-1906-5696-911b-2c290a6cdd66 | date | Date Completed:
4c893940-8d55-4c22-a1af-df2263507712 | checkpoint | 3.3 - Survey Level Conformity
035cdcca-8e35-5d04-a09f-b093faaa878d | note | FREQUENCY: At completion
b7cbba40-6394-5634-b412-5374a394c976 | note | ACCEPTANCE CRITERIA: Scale B:
3acb5a60-ef2f-5cda-94dd-a27222405eaf | note | – Minimum number of measurements per lot: 40 For Upper
72394234-7e74-5e89-91a0-a64060b67633 | note | – Upper Subbase: Mean + 6mm to – 12mm with a maximum Standard Deviation of 8mm
9c01780e-4115-5185-91f9-a2ee5b5e7c5f | note | – Lower Subbase: Mean +8mm to –16mm with a maximum Standard Deviation of 10mm.
bdfba48c-1b4d-58fb-b2e5-9b06e6e47786 | note | – Base: Mean ± 8mm with a maximum Standard Deviation of 8mm.
eaf70417-84af-506b-a947-e6a3cd3c137d | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.061, Table 304.062
421504d5-8526-552c-95fd-53a5766adddf | note | INSPECTION/TEST METHOD: Site Inspection
0b013088-c6f3-51e1-9b2c-750bdad5e150 | note | RECORD OF CONFORMITY: Test Records
d57dff8a-6f0c-5686-b5f1-bb61b0a3b9d7 | note | TP
b3100ef7-497e-50db-9caf-be5607ba9d2d | note | RESPONSIBILITY: Project Engineer
144331fe-4309-5dac-863b-e46b2a9518e7 | date | Date Completed:
a3e83dc3-be84-49cb-8790-bfa87923f394 | checkpoint | Final Inspection
a94cec0c-2c8a-5a22-953d-d34b2e63d92e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
531f55e5-cfe3-5e9b-95a2-491feb947bed | textbox | Print Name:
9fa74147-ab4d-52ef-9e47-0b67345c502c | textbox | Position:
f2cbc9f7-36db-502d-9f76-0f669cefa1a6 | date | Date:
ae6e6015-0b51-417a-a7e7-3f280d803298 | signoff | Sign ITP
fab90c11-a510-5a00-9cd8-8b3b9620cbf2 | checklist | ITP-005 - Flexible Pavement Construction | itp | ITP-005 - Flexible Pavement Construction | 8e95ad02-824a-4de1-905c-ed068ecc0ebf
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
e0e726e1-03f5-5bd5-8794-646fdea2f249 | checkpoint | 1.1 - SET OUT OF WORKS
21a438d3-f799-5869-9ca0-65c3b2e95d5d | note | FREQUENCY: Each lot as required
1d06acbf-a00b-5e03-9db8-c71bc225cc9b | note | ACCEPTANCE CRITERIA: Ensure relevant construction drawing are being used to determine set-out of works.
e7ec4598-5998-59f4-a6da-3f7c62b4d1c4 | note | ○ Ensure all survey pegs are aligned max 40m apart and the oﬀset distances and heights are in accordance with relevant drawings
472ba5b7-b2fb-5b14-afce-13d6e376b05d | note | ○ Refence checking to be conducted with string lines
56cd3848-d046-5659-9cff-3b5220170d1e | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
3c2d0e5c-ad3e-51fb-98da-f6b89fada6e6 | note | METHOD: Survey set-out
46d63712-60bf-5ace-98dd-1bb84e6dab98 | note | RECORD: Signed ITP
21f50034-22b9-5a3f-a7a2-09ceb5f4bd7e | note | SCP
703fbd8e-ae1f-50f0-8dd9-fd0f1075f13b | note | RESPONSIBILITY: SWA Project Manager
2c71cf9a-452c-5dba-96a4-f047f6c8fbae | date | Date Completed:
264a16ad-2e71-5132-a15f-6a71ca088ced | checkpoint | 1.2 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
e0c1e4c3-01ae-5a28-a97c-457c30e6c254 | note | FREQUENCY: Prior to commencing any activity
83cee339-0a84-599d-96a0-5475fb179165 | note | ACCEPTANCE CRITERIA: Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number speciﬁed in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
77b93b7c-0603-5666-8f86-2d17e5e3bf3e | note | REFERENCE DOCUMENTS: Vicroads std sec 204.03
bb1ab119-fea3-5851-ae1a-f1ed4b3d8e0d | note | METHOD: Survey Report
f870a3d7-5a52-5e57-a3ad-fb8808c4ba5c | note | RECORD: Signed ITP
9a11a0fc-62d5-5c21-baed-7d41c3cfb678 | note | IHP
d54a04d6-e5f9-5007-a6a1-5f5743055cd1 | note | RESPONSIBILITY: SWA Project Manager
103858ec-6146-5004-8f4e-cc047cefe7fe | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
dbd9ce85-0c7a-550c-99ee-48caf50d3562 | checkpoint | 2.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (a) General
4f049f58-666a-5046-a5a3-8c374b9a2092 | note | FREQUENCY: Each lot as required
890cc7f0-2c5e-5912-a0df-e7880170454d | note | ACCEPTANCE CRITERIA: Material during compaction shall have a moisture content of not less than 85% of optimum. After completion of compaction of a layer, the moisture content of the material in the layer shall be maintained at a moisture content of not less than 85% of optimum until test rolling has been completed.
33ba4406-6891-5a3e-be9b-aeb2dd202059 | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
45aafbde-c218-53c8-ba9f-ec8067913673 | note | METHOD: Visual & Laboratory Report
21091960-9352-507b-9d8e-8277980a5e20 | note | RECORD: Signed ITP
6b7d5eae-9cf2-575f-ad7d-b90f11fad58e | note | IHP/AP
80f3b5fd-1d3f-5c4a-af15-dbc902752ec9 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
5b1c301b-eca4-5af8-918b-90a5383de1df | date | Date Completed:
c31cd46c-71a6-5377-9562-3f8dc0f6ef52 | checkpoint | 2.2 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (b) Material of Nominal Size 40 mm or Less
f0d761e5-1cf1-5154-9067-05b632345722 | note | FREQUENCY: Each Lot
73f4bc54-68aa-56d1-8e9f-b58949ad10f5 | note | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modiﬁed compactive eﬀort. The work shall be assessed for compliance with Scale B requirements being not less than 97%. See table 304.081.
58ca41af-e55f-53c8-ac78-0969bd212cab | note | ○ For work to be tested for compliance with Scale B requirements, the number of tests per lot shall be six. See table 304.121.
7298ed6a-a8d2-5300-ad8c-a877189c71ff | note | ○ The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm.
673b97e8-f973-55cc-a012-7eff9d3dd982 | note | ○ The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
2d522158-75e2-5ada-b75c-c6d64e3633b6 | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
5a2a1a0f-8eb3-5562-985f-a06d6a3bd2ca | note | METHOD: Laboratory Test Report
38b38ded-4382-55a9-8321-91cce0bafc89 | note | RECORD: Signed ITP
fc050c64-6bbd-5fcc-a1d3-60db57ebc55a | note | IHP/IP/AP
aa41352b-a014-580f-a92f-f3367cc11c4d | note | RESPONSIBILITY: SWA Project Manager/SWA Site supervisor/RRV Superintendent
091e976c-11b3-5010-bec3-26cdfc39bcbf | date | Date Completed:
0ab143a2-e650-5576-bff5-9a365a7ead39 | checkpoint | 2.3 - TEST ROLL PAVEMENT LAYER
cf26d6d1-0a57-51a5-8998-6140e6be89af | note | FREQUENCY: Each Lot
7021f6a6-d397-5d7a-891b-d587e34330a3 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any ﬁll on the prepared areas until the area has been reviewed by the Superintendent. The Contractor shall provide for the Superintendent to be present during all test rolling.
b77690bb-91cb-57fc-89d4-7c8858b0d4ec | note | REFERENCE DOCUMENTS: VcRoads Std Specs 173.03 & 204.12
ddebae22-3f6e-5344-8a8a-847524cc851a | note | METHOD: Proof roll
5502962f-5656-5b8c-b4cc-be0affcca612 | note | RECORD: Signed ITP & Test Report
1d60d458-0615-5369-8e39-1fa82e4810bb | note | HP/AP
fb4f3192-b1fb-5ea8-99b9-42ab1d8acccb | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
35502628-900b-5e3a-81f1-cd8fab79ff54 | date | Date Completed:
dfb368da-a096-5427-ab0d-4219cac63f72 | signoff | AUTHORITY HOLDPOINT
30dd4d76-cf89-5bbf-94c3-44642a49aa5b | checkpoint | 2.4 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
dd9451ef-7628-5777-b511-8406baf71479 | note | FREQUENCY: Each Lot
b5517203-2972-5415-a154-7513e172b6f0 | note | ACCEPTANCE CRITERIA: The surface level of the pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet either Scale B requirements as speciﬁed in Clause 304.12.
93744061-4d1c-5633-81ff-e0fcad3646da | note | ○ Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
7ca6e396-4048-5fbb-a817-d7b9b6aec8eb | note | ○ Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number speciﬁed in Table 304.061. Surface Level Tolerance as per Table 304.062
8e8eaa68-3058-5d05-bab8-40a44dbc94ad | note | REFERENCE DOCUMENTS: VcRoads Std Specs 304.06
1bb3836a-8681-55de-961b-4ea84c3730ab | note | METHOD: Survey report
c9b54e4d-138a-5902-a65d-40167a8a0199 | note | RECORD: Signed ITP
17e955f5-a405-5b78-9b63-88db0449b409 | note | IHP/WP
0ee07f49-db61-5573-aa0e-f85d91236efa | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
0e76f698-81d7-554d-acc6-0a5da44178f2 | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
7ac89bf9-222c-5771-bff6-eadc91bf12d7 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations
726d8fff-32d0-5a53-897e-89e54955aa0a | textbox | Print Name:
9fd2b4b9-a3d2-5ac2-ae5f-5981ed4b8a07 | textbox | Position:
2b92b7c0-85c8-53f5-8ecf-7a7cc9248cd9 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
124e85ba-1427-56c6-9cc1-ef7db652307f | checklist | ITP-006 - Kerb & Channel | itp | ITP-006 - Kerb & Channel | a4d29837-c0f6-4b8e-8931-9cd929c359d9
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
78f2eb97-4d27-5397-9616-d0974c63c400 | checkpoint | 1.1 - Check for correct documentation
406918ce-3cdc-5bf1-b99b-1cc0ce3670a6 | note | FREQUENCY: Prior to commencing any activity
e011307f-87f3-5b57-afc6-849b34cae3d6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
be8c534a-b509-5771-ac62-7b511d66b998 | note | – using the correct and complete set of drawings
c69f4138-b3f7-51db-b97d-ccc326af37c6 | note | – all drawings are the latest revision
822ffbea-10b5-5f82-8ab0-f8c159005040 | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
34936628-eb58-5204-b959-a44867dbf91e | note | METHOD: Drawing Register
79444e64-5635-591e-91f8-b477547447c6 | note | RECORD: Signed ITP
d9bd5ac5-3489-5b71-9430-2ce1611cfa4d | note | IHP
add5cad4-344d-5ff9-9b01-f3492d8fa430 | note | RESPONSIBILITY: Site Supervisor
f8ea5604-b840-516b-b9b6-3986295a792a | date | Date Completed:
457fc29c-5478-51c3-a60f-061f5ba4ad0d | checkpoint | 1.2 - Implementation of all measures and controls
f1ed7616-4da5-594e-89ed-b752ad56207f | note | FREQUENCY: Prior to commencing any activity
897e971e-0b58-53da-ba2b-45c29e989652 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
a01e5185-92e6-5d8d-a6f3-c9eea4ec684c | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
c3a498a8-cfc9-5cf9-91bd-4bdad6bfba9d | note | METHOD: Visual Inspection
47148980-a363-51fc-aec0-5235296d4922 | note | RECORD: Signed ITP
bc3fe039-08d6-5b5e-a8c2-555746084963 | note | IP
e13d9d0a-b15d-5f8b-bd51-dc48258f1cb3 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
2a2f6067-9e00-575e-b431-248df43cc440 | date | Date Completed:
73920d7e-e2c5-5db3-bfa8-d36b7058a4c5 | checkpoint | 1.3 - Setting Out
f103293e-2257-5261-bc5c-72da2d09ed65 | note | FREQUENCY: Prior to commencing any activity
2fed43cc-312a-53e7-8a8e-f9ece4210455 | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor. Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
31f53ffb-c188-501b-9f47-21af8c4b9fd6 | note | REFERENCE DOCUMENTS: Vicroads std sec 703.13
1688d011-d595-5d40-bfd1-813a57c0c5d8 | note | METHOD: Survey Setout
f132a59f-8e2b-5db4-ac00-1a50c25e51f6 | note | RECORD: Signed ITP
abe4a46c-5cab-59fd-919b-5f5eb81e9ca2 | note | IP
cf7c601a-6eea-58c4-92bf-cbcbc7a6625c | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
941f7e22-16ae-5d20-ab1b-03abed20d5b2 | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
b94cae42-558a-5a9a-960c-3da6f075764d | checkpoint | 2.1 - Excavation
fc4b5e5e-7efc-5785-b195-266e3c5e4d0b | note | FREQUENCY: Check prior to placing material
391c45c5-f8e1-5129-a718-7cde5ad901d0 | note | ACCEPTANCE CRITERIA: The base preparation for kerb and channel shall consist of a boxed out area to a depth of 355mm below FL and 1150mm wide. Excavation shall not extend more than 150mm from the edge of the adjacent face.
cd4e7867-48ed-52ef-8f01-7af0c0fe7913 | note | REFERENCE DOCUMENTS: Vicroads std sec 703.20
395c6ce3-2753-51a3-93ac-2c98f38853b7 | note | METHOD: Survey/Site Inspection
b6a9d6b7-6aa3-5b2d-9e12-f998914f0c63 | note | RECORD: Signed ITP
3851b852-2945-58a2-b5e1-49e85c93b11c | note | IP
2748247b-269e-5276-8976-c1df5a2cb9ee | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
275a27df-78e2-54bb-beba-bccd1405ef56 | date | Date Completed:
230b1f2d-ae16-5865-84cf-631a67835520 | checkpoint | 2.2 - Subgrade Inspection
7419fe17-5292-5f9b-af6e-6ab9f3ed0a53 | note | FREQUENCY: Check prior to placing material
b448cca9-b6ce-5da8-b0e3-7d05f86ef3be | note | ACCEPTANCE CRITERIA: Test roll subgrade to check for No visual deformation or springing. Where deformation is exhibited, the Engineer or Superintendent is to be notiﬁed immediately.
0728161c-0c6a-5ff6-b941-64cfbc2b7da1 | note | REFERENCE DOCUMENTS: Vicroads std sec 173.03, 173.03 (ii)
f39ed3b9-079b-58c8-9755-6fb9aba9ef11 | note | METHOD: Visual Inspection
e468e85e-66dc-585b-991d-a6061a47cd52 | note | RECORD: Signed ITP
68dbdd3b-1e7b-591b-9528-31a809df4c41 | note | IP
ba0308c4-4a24-5f91-9915-59aa7615f963 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
86650319-7ccf-5b27-a073-c105b613572c | date | Date Completed:
5b4520ab-04b3-50db-ac15-158652020b73 | checkpoint | 2.3 - Bedding Preparation
e59e6c97-83db-5648-ac91-397818f406a7 | note | FREQUENCY: Each lot as required
7ba6e700-5771-54d0-8877-7f24e9b6b106 | note | ACCEPTANCE CRITERIA: Bedding material to be used for base preparation shall consist of size 20mm Class 3 or Class 4 crushed rock at a minimum of 100mm compacted thickness. Preparation of ﬁnished base shall be 190mm below lip of kerb as per survey marks.
3f13d882-6cd5-5b8c-977a-a1143ab675b9 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21
41f35c2c-a05f-520f-a7ec-6ec733bf708f | note | METHOD: Site Inspection
fbe9548a-bbbd-542c-8d90-54fc5c63104e | note | RECORD: Signed ITP
ddd43e43-3217-5d2f-b08d-63fe96bf5a7a | note | IP
fdc53d79-8c28-5630-813c-dcc3012d51a1 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
55becea8-8fc6-5e8f-9292-936708566548 | date | Date Completed:
5f2a781c-c5ee-551d-9de8-efbb77367502 | checkpoint | 2.4 - Kerb Concrete Mixture/Strength
1a135d14-44b7-59ab-abdf-e5d70cf31fbd | note | FREQUENCY: Each lot as required
3f26fb6f-256e-598e-b9e6-32f4e8b8994e | note | ACCEPTANCE CRITERIA: Traﬃc routes a minimum of or equivalent to 320kg of cementitious binder material or geopolymer binder per m3 of concrete – VR 330/32
7b5cdbee-30f5-5e93-891b-da9cfc6152a2 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.05, 703.11
65ecbc29-e2f8-5f0c-9b01-3b2f4a5cf809 | note | METHOD: Delivery Dockets
257a7f1c-f457-59cb-8c77-b6d58c927c89 | note | RECORD: Signed ITP
87154659-50e1-5da3-a1fe-e622c69d60d0 | note | IP
3593b420-23e2-5fba-aa66-ea5339877f43 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
0655ebfd-b77c-57fd-9155-b251f8b36dbe | date | Date Completed:
b9296863-da55-50ca-b3a4-74c6b40da96f | checkpoint | 2.5 - Tolerances on Line, Level & Shape
8e4afeb6-97d5-5635-ad08-b6d52ddb3959 | note | FREQUENCY: Each lot as required
d8372740-cf9d-51c8-aef2-29373cca4e95 | note | ACCEPTANCE CRITERIA: All surfaces shall be ﬁnished in conformity with the lines, grades, thicknesses and cross sections shown on the drawings or as speciﬁed. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10mm. Except on curves or in shaped areas, the deviation of the ﬁnished work from a 3m straight edge shall not exceed 5mm at any point.
9a5ffbb5-5164-51dd-b467-84c02f5bad84 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
6158c054-13b7-53b6-8521-4c14420bbc7b | note | METHOD: Visual Inspection
ba02012e-f3de-5cee-947a-ccc94dab95a8 | note | RECORD: Signed ITP
8bc8d6a9-f2df-5f9f-9f39-9ee3ee69107b | note | IHP
7d102f00-ae1b-5335-bdd7-2293953dcd21 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
fbf4435c-3c54-5df9-91a3-a82a670999a0 | date | Date Completed:
5b03b7b4-4b8c-5fae-b01d-c6a211250c9e | checkpoint | 2.6 - Kerb and Channel Finish
152a4c81-2200-58c7-8846-475a98e97122 | note | FREQUENCY: Each lot as required
710f7d21-3cbf-56cd-8d40-0e5b7b49ca9e | note | ACCEPTANCE CRITERIA: All edging shall consist of a smooth, uniformed and of a trowel ﬁnish. The mortar used shall consist of two parts of ﬁne aggregate, one part cement and suﬃcient water to produce a mix of suitable consistency. Thickness of the rendering shall not exceed 3mm.
efff80fd-0242-5e39-80b8-c9f8160181d1 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21 (a)
d850c6d3-a71c-5054-84ea-71aeafd4b346 | note | METHOD: Visual Inspection
76ab2fe7-1bdf-5321-b5f0-3284d7615a29 | note | RECORD: Signed ITP
53219070-0f0e-5f92-92bc-22136a46688c | note | IHP
57dd1aee-e3f5-572b-a8dc-2d732d48fef2 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
394a1dec-5c62-5a2c-8294-8922811baf6e | date | Date Completed:
dbc95655-357b-5db7-8376-fa2faa5ef7c2 | checkpoint | 2.7 - Kerb Backﬁll
c74426ba-4f22-5b05-9f10-30fcfc2e71d4 | note | FREQUENCY: Each lot as required
7ca14e0d-b321-5913-b323-51a9714edbf0 | note | ACCEPTANCE CRITERIA: Once concrete has cured, topsoil which is free from perishable matter, shall be placed ﬁrmly compacted in layers less than 150mm thick and to a width of no less than 300mm behind the edging to the top of the edging.
53f8edff-f0ea-5e80-bed1-59c7560088b6 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.29
7bc19819-ca2e-5e79-894d-e29bd539afa5 | note | METHOD: Visual Inspection
080fb305-c66f-556d-a03a-33861058893c | note | RECORD: Signed ITP
2d9a91b8-51ff-5edb-b545-a8456e4f6752 | note | IHP
df133037-dd9a-5711-96ad-bf48ac9a8097 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
6bb7c0a6-e316-5ac0-94bc-a436be1504c3 | date | Date Completed:
6654a5b9-b49f-507b-92a0-605d8a01ad64 | section | 3 - Testing Requirements
b893228a-c23a-5236-a21c-016fbf1f0b68 | checkpoint | 3.1 - Compaction Testing
b307cbbb-e0f3-54c8-a277-335031719f5e | note | FREQUENCY: Each lot as required
2f6160d1-c830-5bc1-b0c3-4f14ddd3bb97 | note | ACCEPTANCE CRITERIA: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six. A small lot is classed as an area equivalent to or less than 500m2 and requires only 3 individual tests. Compaction testing for crushed rock material shall be no less than 98%.
b9b69829-6d11-5e75-9067-7720b2b6557b | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08 (b) Table 304.081, 173.04 (d)
6adc21e0-8da3-58ab-aefd-8685be89e42b | note | METHOD: Test Point
a92a55bc-a934-53b1-90dd-41b857704a5e | note | RECORD: Signed ITP
55bcf49e-48ab-5bbe-9874-4ef19631138f | note | TP/HP/AP
c3d35af1-f2f2-529e-bd5e-850d1d7fa0be | note | RESPONSIBILITY: External Geo tester/SWA Project Manager/RRV Superintendent
ccbb13b1-06f1-5589-940d-1c78307f3d56 | date | Date Completed:
95f4b835-9bd7-53a6-af27-329bf209b2e3 | signoff | AUTHORITY HOLDPOINT
2d7b071f-cd97-5d39-b004-e1989e93ef82 | checkpoint | 3.2 - Conformance Testing for concrete strength & consistency.
3f41a8b5-9b84-545e-a8f7-47afadee5d0b | note | FREQUENCY: Each lot as required
64bce072-3844-521b-a3a0-5dd2b3a16ba7 | note | ACCEPTANCE CRITERIA: The minimum compression strength requirements for each strength grade shall be as shown in Table 703.111
e6dbae4c-ba22-505f-9712-e8ae967f620b | note | REFERENCE DOCUMENTS: Vicroads std sec Table 703.111
c07a8be1-b11d-51db-9679-f6b7058ac38c | note | METHOD: Survey Report
a73228ac-bee6-5e95-a53a-30015f0e35a9 | note | RECORD: Signed ITP & Test Reports
e0effab5-22c2-5331-abf3-391f5ddfa888 | note | TP/HP/AP
fb96dc8c-7e23-5fe2-9ae0-dfdbcf9b46db | note | RESPONSIBILITY: External Surveyor/SWA Project Manager/RRV Superintendent
bc9f3d1f-b1b4-541c-8f87-805c1d330bcc | date | Date Completed:
e1586d20-1767-5b9a-969b-680a4a731b41 | signoff | AUTHORITY HOLDPOINT
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
8138864d-4a3b-5bda-986f-6aa83420317b | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
873f6803-4544-5ef3-a4f4-c6a4310767ef | textbox | Print Name:
db859f22-cc9e-5287-af0c-cf55b244179c | textbox | Position:
751dba85-2a55-5a4e-a2b7-ea4dee9eefbc | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
850ee71d-d2df-5dad-a93c-b836182b2248 | checklist | ITP-007 - Hot Mix Asphalt | itp | ITP-007 - Hot Mix Asphalt | 8a26ec7b-47e9-40ba-bcf0-db20d12d50e2
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
26d5d62f-8773-5d6d-81f7-d3753ca4498e | checkpoint | 1.1 - Site Inspection and Base Conditions
d688b9be-5b87-57c4-9401-8e4ee3044ced | note | FREQUENCY: Prior to commencing paving.
77fe2bc8-1442-5be1-96e4-22b2b5e30898 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from surface water. All manhole and valve covers have been raised or lowered to the new surface level of the pavement.
5db3395a-5a33-563d-af34-17c90380b207 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.1
9f664117-1f46-5641-8a55-271a2941339d | note | METHOD: Visual Inspection
f6b9ce53-7b0e-55f5-bf58-2190378470f2 | note | RECORD: Signed ITP
3149520a-eadf-5e65-84c7-25d8c44897df | note | WP
62204960-fdca-5390-8706-6d46b6c16a02 | note | RESPONSIBILITY: Site supervisor
7a542c34-35be-501d-bef9-f7c96b21f6bf | date | Date Completed:
4977d416-cdc2-5db9-a0a9-9fa87c56ca6a | checkpoint | 1.2 - Ambient Conditions for Asphalt Placement
0a2ecb52-16f0-520a-a241-548c9b5501b7 | note | FREQUENCY: Prior to commencing paving.
58b668e8-a984-5f99-847e-f7f7849aa2ec | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed if the majority of the surface area is below:
21a4db70-16bd-5874-b125-c5d207382d63 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
e74390b4-ae7a-5952-85e9-f515b4722f5a | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs.
c975c47b-f504-5bc5-af6d-5fc2f3139d57 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.13
b5ace85e-d10c-5e83-8616-5240a88f8e00 | note | METHOD: Calibrated thermometer
05794ef6-1210-5f5e-988c-9e216f5d1c6e | note | RECORD: Signed ITP
1fa6e8b4-45b7-5c03-9bd0-ad631acac909 | note | IP
b320e086-223b-5c4d-a615-12e62920d7f4 | note | RESPONSIBILITY: Project Engineer/Site supervisor
cc06b2f3-d3c5-5b1b-8572-83b09a446a34 | date | Date Completed:
258a39b8-19ff-5418-829d-82c7f06ce5e9 | checkpoint | 1.3 - Surface Preparation
4e54f265-bace-5007-9924-59ff70e7ba9d | note | FREQUENCY: Prior to commencing paving.
3ca451bd-60bc-5aa8-82ff-2fb8f95d4ae6 | note | ACCEPTANCE CRITERIA: The area to be paved is free of all loose and deleterious material
d7bca43d-b98f-5a72-b645-801e4af922e9 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.3
b7150c70-7401-5f10-a71c-de2898c7e3a7 | note | METHOD: Sweep Clean and Inspect
6deba588-d573-5826-8f7d-5cf57d2a7308 | note | RECORD: Signed ITP
4f8547f4-8f39-585e-846f-eb93a72dee5f | note | WP
97ac1dbb-d171-51cc-b773-9def1a760570 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
05dbeb64-1a43-5b0f-ab97-a2a9299cfea7 | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
3d8767f9-be0b-5aac-8f8d-8d8d30576afc | checkpoint | 2.1 - Application of Tack Coat
2bc89cc0-05fd-5d39-8173-cf3ac73aea87 | note | FREQUENCY: Prior to commencing paving
984a04d0-36e7-50cd-8190-d10f5be69ef0 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform ﬁlm over the surface area at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
b126fdc9-f32a-5128-a548-41a431071e21 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.15, AS2150 11
a513f9de-8a20-5afb-8cdb-fe7b7bf868e4 | note | METHOD: Visual Inspection & photo evidence
819b6f4c-677c-5939-bf3e-385c4c9c3ddf | note | RECORD: Signed ITP/Spray Record
085a77d8-e12c-5d16-97d2-38661c7775e2 | note | WP
db648bc6-04a9-5f5c-ac17-0872310e84da | note | RESPONSIBILITY: Project Engineer/Site Supervisor
9524c87e-3988-520f-8b62-836e7879ac95 | date | Date Completed:
d22d01c7-b271-511d-bf41-2fff8ae5a522 | checkpoint | 2.2 - Planned Joints
ba46facf-a072-5cc6-93b1-8ddeca9a627d | note | FREQUENCY: Prior to commencing paving
22cc8efb-d9e3-5cfa-9255-9ae523d70f8a | note | ACCEPTANCE CRITERIA: A site speciﬁc paving plan shall be generated by the contractor prior to asphalt commencement to adhere to the following: Transverse Joints: Oﬀset from layer to layer by at least 2m Longitudinal Joints: Oﬀset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an oﬀset from layer to layer of not less than 150mm.
ab9a16a0-8110-5e82-9f33-bbb12b923d13 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.17 (b) & (c)
95996cce-9371-5937-9658-016a41201d7a | note | METHOD: Measure and mark out runs and submit Paving Plan to Client if requested
3d58eaf1-61e9-5cc6-b381-2f3448a26604 | note | RECORD: Signed ITP/Job Sheet
00d39b2f-424d-567f-bfa5-6a0decd08391 | note | WP
9ec50226-d017-515d-846c-a3e479e4b999 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
dbb35a21-e66d-5201-a4d2-1dff79c94fad | date | Date Completed:
6661068e-fea7-5cf6-8f24-87de51d674b3 | checkpoint | 2.3 - Commencement of Placing
cca105be-6bd6-5600-ac6f-65bcc11a3079 | note | FREQUENCY: Prior to commencing Paving
683db6f9-07e7-55cd-8bb3-bdaa06b97f49 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub- base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Vicroads Superintendent.
068e27e3-051d-572c-8924-d5b1ea8f3f4a | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.18
b511a1d6-2391-58b3-a195-d66345ed525d | note | METHOD: Visual Inspection
53a5f474-6809-567f-bcda-a795f9214c82 | note | RECORD: Signed ITP
63aeb9c7-da48-5ccd-8879-363cd0e982d5 | note | HP
a51be06b-60e3-5c7c-91e1-0b8ed01b9320 | note | RESPONSIBILITY: SWA Project Engineer
2feae5b8-a61c-5937-9a35-e1a01f92a36d | date | Date Completed:
34e18449-c3fd-51e1-b56f-ccf521a5d073 | signoff | AUTHORITY HOLDPOINT
6011a022-02be-59a2-94b2-a549f045b1b4 | checkpoint | 2.4 - Delivery of Mix
35c6435e-3596-510a-ab77-9fe4f8e7b182 | note | FREQUENCY: Each Load
8dac07ce-4df2-5efe-83be-bf1ba1081dc2 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
9ef15b20-6680-5bdb-9cfb-9fa375011ac0 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.16, Table 407.081
ed145bdc-d3cd-59b4-a60d-32e90a0175ef | note | METHOD: Visual Inspection & Delivery Docket
31350090-570c-5cb2-8a93-d05f68c8ecf7 | note | RECORD: Signed ITP & Production Dockets
01d78e9e-b9b9-5b71-bbd4-212c346d7d27 | note | WP
bec095f5-a796-55ca-b444-42f5b4d59bea | note | RESPONSIBILITY: Project Engineer/Site Supervisor
19cc829a-5c9e-5a21-8524-84978ad9bf59 | date | Date Completed:
df52cdfd-6140-55da-9bdb-919ccff3ef0e | checkpoint | 2.5 - Traceability
82c1addb-3683-5b4c-93c1-01ea48344802 | note | FREQUENCY: Each Load
e1f1bbfe-0d5f-5c7f-83bc-c2f11703b555 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, oﬀset/lane and layer
7b7f2e40-84a3-555e-8ae0-489a7049337d | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
ee9c3476-6420-55a6-9993-a2d1de3442f4 | note | METHOD: Project Engineer/Site Supervisor
23c11b58-21bc-500e-a1c6-850486660080 | note | RECORD: Signed ITP & Traceability
e70ee5c4-d130-52b6-a5d5-7af94576eccc | note | IP
9adf5571-8d0c-5fdf-b3ae-6535c2707fa5 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
44a30b4e-f09a-5f2b-bfae-62dff848ba35 | date | Date Completed:
c2ae29b9-5806-569e-9a2b-c426503dac7f | checkpoint | 2.6 - Layer Thickness and Level Control
ff96ea57-e6b4-5e2f-b266-c33d5fc970c0 | note | FREQUENCY: Regularly during paving
b8b4c9e2-2100-5327-a3a9-c2ab0e694095 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or speciﬁcations
5a70b30b-e11f-5018-bb87-4345416cb836 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20
08d03c8b-a82b-5ccf-8737-a66353e78fcb | note | METHOD: Dips, string line, measurements oﬀ kerb
ad93486a-b761-59b7-8a32-3da121a65202 | note | RECORD: Signed ITP & Traceability
73b78505-8b06-529d-b7e6-0c4856c4aca5 | note | WP
34ac231a-8cb8-5f66-a3c2-d0bf25788dad | note | RESPONSIBILITY: Project Engineer/Site Supervisor
33018af0-6960-5889-8c7c-7c828282672d | date | Date Completed:
36fd9b7a-b6e8-5247-b9fc-beb7b3b74a89 | checkpoint | 2.7 - Paver Stoppages
002feb29-adaf-5658-ae69-f5df46cafaf1 | note | FREQUENCY: If paver stops
3e721a1b-0f43-56cf-805a-523cb54c3fba | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
942ba5fa-42f6-5275-9f04-0f4ea0d094da | note | Asphalt should be ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Max ramp grade:
a00ce693-9716-5d75-b53b-2000b9676a84 | note | ○ 40km/h – 20-1
d42553af-6974-50c2-90d8-9801971de2bf | note | ○ 60km/h – 30-1
cac18e2c-74bf-5902-8668-cfd79548b07f | note | ○ 80km/h – 40-1
b5595fd4-381d-5048-8c44-8b281365a04f | note | ○ >80km/h – 50-1
81117fe2-cc8b-5f28-91ac-5bc494815aca | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20 (c)
b2bc6f2f-ff8b-514c-8300-32611bfa4ad0 | note | METHOD: Thermometer
e73f5314-0277-5e7e-b7d9-f0cf640711b4 | note | RECORD: Signed ITP & Traceability
8a42da44-1238-560a-ad9a-d42ac4ae2cb9 | note | WP
1e0101a2-201b-53fd-bb91-8a1a1ca37140 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8ccf48ab-72e6-5fba-bf7d-c5a8ec70a402 | date | Date Completed:
7b5f6175-7f46-5e8e-9ee6-408a701b92a1 | checkpoint | 2.8 - Surface Finish of Wearing Course
4dfcca4d-6cd9-5059-96c5-7f49ee738a46 | note | FREQUENCY: During paving and after ﬁnal roll
69febd5b-5b7e-5aaa-8709-463fd2426c24 | note | ACCEPTANCE CRITERIA: The ﬁnished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
150e0736-0b04-54a4-8e7a-7931c1c79df7 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (i)
df87ffeb-c1aa-56b5-83c7-41217ac9ccdf | note | METHOD: Visual Inspection
9fea420f-2c0a-5f15-ba5e-3302a9a34645 | note | RECORD: Signed ITP & Traceability
984f1f0d-073b-5547-9c56-1bad2e6177d0 | note | WP
29c20c6b-d274-509f-bafb-d926f20bdb16 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
ad523783-fc01-5bf0-a6ee-655ee901c821 | date | Date Completed:
10f33595-9d77-50f4-8495-2fa4d6875210 | checkpoint | 2.9 - Kerb and Channel
07ca60f3-ee52-57e6-b0dd-5cb66e9cc014 | note | FREQUENCY: During paving and after ﬁnal roll
8645ebc8-f881-5f69-8a08-46d7a3097f08 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either ﬂush with or not more than 5 mm above the lip of the channel unless otherwise speciﬁed
8dd06cfd-fb12-53a9-8ad4-f0e267ff66ff | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (ii)
767fd6b1-2d01-5b59-84fe-65c38d519d41 | note | METHOD: Visual Inspection & Measurement
ccbd261d-642c-5fbb-887f-4c9d8bd42bbb | note | RECORD: Signed ITP & Traceability
d7fce216-ea7a-573d-b611-c9e33c6889d4 | note | WP
accfc560-ed8b-54d2-a681-96c53a9c120b | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8429c875-5a5e-5cce-ae99-b0f6f2a50ad8 | date | Date Completed:
d4973271-760f-5b31-af74-2ebb3b7ab3b1 | checkpoint | 2.10 - Alignment of layers not placed against concrete edge
627dfba2-fac7-556e-9e93-8665eddfa9ab | note | FREQUENCY: During paving and at completion of work
9f42c967-3d8b-50e2-b03a-b701b4fbb12b | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed oﬀset from centreline or design line. The rate of change of oﬀset of the edge of layer shall not be greater than 25mm in 10m
cb25d7fe-dae1-5e4a-946c-f9075c8adc68 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (iv)
93f531db-bdf6-5972-91cb-a8bcc1019e4c | note | METHOD: Alignment as marked by Surveyor and measured
263cd0dd-a3b4-55bc-b476-0f0d7811254b | note | RECORD: Survey Report
7ad599ca-07d1-5ee5-9751-8cf7ecdc9b38 | note | SCP
7db19754-8f98-5056-befa-eb8448c94030 | note | RESPONSIBILITY: Client Surveyor, Project Engineer, Site Supervisor
be21af9a-dbbb-5d73-923b-ce2e4ed1d78b | date | Date Completed:
26d72225-2718-546d-bfad-44cc023633ba | checkpoint | 2.11 - Width of layers not placed against concrete edge
4a9a14be-2086-57b2-9593-b9bf91e5b5b0 | note | FREQUENCY: During paving and at completion of work
b081645d-0eff-5ff6-94da-c8c81aba66a7 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or speciﬁed width of layer by more than 50mm or greater than the design or speciﬁed width by more than 100mm.
5682dcc8-6286-5be5-9903-fe928cd88306 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
e182e220-7601-562e-bf1d-b783541a2e5a | note | METHOD: Measurement
576e1c36-cb82-5e07-add9-c30db9da78dd | note | RECORD: Survey Report
7e12bf87-ce19-57c7-a3cd-c48f136371db | note | IP
701fd94e-b617-5779-a62e-9088f361468c | note | RESPONSIBILITY: Project Engineer/Site Supervisor
e05f32b5-a38f-5191-b348-2b4e005ae60a | date | Date Completed:
d7d138dc-b209-5f3f-9e52-54a34e093893 | checkpoint | 2.12 - Traﬃcking of Asphalt & Paving of multiple layers
297135e5-ed13-5bf2-b6b3-60822e7847e5 | note | FREQUENCY: During paving and at completion of work
8d32ab87-f6d9-51a3-8e39-5ddb6e23cb82 | note | ACCEPTANCE CRITERIA: Traﬃcking of asphalt or placement of asphalt over freshly laid asphalt layer is not permitted unless the majority of the asphalt has a surface temperature lower than 50°C
d9f9b24e-9138-5594-8bf9-8d9afacda926 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
08f0e70b-8783-508a-a289-8e3212659fc3 | note | METHOD: Measurement or suﬃcient time has lapsed
68f2edb5-423d-58f6-880b-ffe22f7d8951 | note | RECORD: This ITP
1a9d1188-0fef-5f2d-b2ce-39a176b42ce6 | note | IP
7f4e2eb8-984e-5863-aa73-35bf680251cf | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c0ea7700-500e-5ee0-81ff-63d8cd2a82fc | date | Date Completed:
6654a5b9-b49f-507b-92a0-605d8a01ad64 | section | 3 - Testing Requirements
6a8c7900-a2b5-5b4c-a9f2-c7a3c37ec233 | checkpoint | 3.1 - Compaction
3ea01a93-90b8-5aad-ab52-1f0ad5c4630d | note | FREQUENCY: Per Lot (6 shot test)
f36c22c2-771b-518e-9f9f-2e96e8204641 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
df530418-75cf-5498-a9e5-98a12f1077d2 | note | ○ 95.0% or greater Accept lot
a885aa2a-d150-5ded-be97-e54e3a8180ee | note | ○ 94.9% to 93.0% Lot may be accepted at reduced rate
8722fdb1-40ee-5b6c-abb6-5c54ceeb6058 | note | ○ 92.9% or less Remove and replace asphalt
7b0a66d6-9185-5c93-ad10-be01dcf44c4b | note | For layers ≥50mm, if characteristic thickness is:
4c3f1e16-ed84-5603-936e-2256cef26004 | note | ○ 96.0% or greater Accept lot
960a15fd-97c4-5533-bd6b-de6cc1e8d086 | note | ○ 95.0% to 94.0% Lot may be accepted at reduced rate.
1ba6fd39-3ae3-5145-8d5c-44343953e3dd | note | ○ 93.9% or less Remove and replace asphalt
e43ae737-0256-515e-8077-48ee79a67f65 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.221
85937a4b-7422-55a2-b459-567d8e37a27f | note | METHOD: Compaction Testing
48296b9b-c05b-522a-8bdf-b1b3e3e1d468 | note | RECORD: Asphalt Field Compaction Report
c9314ccd-99a3-56e3-99d9-ad7ee2ee0c09 | note | TP
2f032d04-b346-521b-a1d8-8762ffc48592 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician Veriﬁed by Project Engineer
ed7eab13-91ea-5ca6-93e8-5c612059edcf | date | Date Completed:
cbc56fa7-00d7-56ad-8ff1-adc73e4f310b | checkpoint | 3.2 - Surface Levels
a3b57793-0945-5ea8-9026-0401d2e010c9 | note | FREQUENCY: Each lot as required
c97caed1-4c69-5de5-813f-f2b9636177e1 | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
56a92c5a-65bf-53fe-9336-974dfc6b8971 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.222
d96e15c5-222a-5ebb-9cfc-9599336885ad | note | METHOD: Survey
b93cd5ab-2182-52e5-9651-43d28c3e9ba9 | note | RECORD: Signed ITP & Survey Reports
14cf22b7-2397-5b6a-903e-3f50db452276 | note | SCP
fa364c43-4d29-58d2-9f4a-d9e17cc7dac5 | note | RESPONSIBILITY: External Surveyor Project Engineer to verify
d05db9ed-8783-5625-8556-9a307514c7ca | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
17776558-95c5-52a4-b43c-e734ad34c2d6 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
12075917-4f55-5e71-a2da-d7268412a15a | textbox | Print Name:
59b83e06-98fd-57f0-a0b3-0202a69fc95c | textbox | Position:
58008f9d-4619-5f03-a977-6d42d33a406f | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
1da3da15-df67-53b8-8391-08ce244460db | checklist | ITP-008 - Line Marking | itp | ITP-008 - Line Marking | 1de5882a-7dde-4618-bf1c-3daf1cf0a34e
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
5cef2364-fc9a-55b3-897e-5719fb07fa24 | checkpoint | 1.1 - Line marking Conformance
6decc52f-f238-5406-ab45-b16481be0a0b | note | FREQUENCY: Prior to commencing any activity
7c288dfd-04f6-552e-b391-cad67fc8e389 | note | SPECIFICATION REFERENCE: 721.A05
0eed24db-71c4-56d9-8c7a-215ae2ec8619 | note | ACCEPTANCE CRITERIA: Materials to be used conform with speciﬁcation
fa4c2060-243b-501c-8e2f-27a76b3071ef | note | METHOD: Record Review
6433e9d9-b4ff-5fb3-90fa-e39d594a5687 | note | RECORDS: Material sheet
abe5d130-c2eb-59cf-932e-10707b24b6f6 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
a6bb2cbf-0d23-52b0-b090-753f9c10c343 | date | Date Completed:
c5e3f47c-1aa8-52ad-8554-cf927bf34df6 | checkpoint | 1.2 - Site preparation
d18fc51f-9df8-57ee-b89e-384f6558a56e | note | FREQUENCY: Prior to commencing any activity
d66cd9af-99fe-503e-b88f-bec56f029177 | note | SPECIFICATION REFERENCE: 721.A06
c4e4e470-6b2e-5cbb-b3a3-fb2a6752d2b4 | note | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings. Removal of any foreign material or debris.
94a82f71-9f08-575c-9f6c-bdbbbe4ed1bd | note | METHOD: Visual and photos
b39132fc-055b-52d3-8708-1e0fd0fa57a5 | note | RECORDS: Photos
c9307376-374c-5ff1-b4c2-6f24de01fc24 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
14672bcf-16ca-5aa0-a5d7-8cfe11bb7f1c | date | Date Completed:
10e8df30-8e3b-5e45-9098-f3d33006ff0a | checkpoint | 1.3 - Set-out of Pavement Markings
7bde258e-74c2-5c81-bf6b-35ad7ddc6081 | note | FREQUENCY: Prior to commencing any activity
de495b17-2a23-56c0-ad33-f7afc9581f62 | note | SPECIFICATION REFERENCE: 721.A09
6e1c40b2-5fcd-51d6-b2b3-7fb4bff75f4c | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
29c9a0d7-fe06-53d9-a7d2-a1303ed045e4 | note | METHOD: Visual and photos
c558960a-0248-57f7-90b1-384e21ba49ad | note | RECORDS: Photos
f1b399a1-dea7-51e6-87f2-19eb06a93111 | note | RESPONSIBILITY: IP - Contractor Representative, HP - SWA Representative
08893043-6dba-527a-9b46-af7ef49a05f5 | date | Date Completed:
42ac8a73-53d5-50a4-af62-d62c56b9c160 | signoff | AUTHORITY HOLDPOINT
4d771e39-83c7-5f41-a79c-a877901269cc | section | 2 - Installation
53d345a3-b074-53be-9960-4c84b68ad956 | checkpoint | 2.1 - Line marking Installation
c216f09e-e64f-5289-90ff-ea17db6088ce | note | FREQUENCY: During Construction
7b41ef96-e45e-5b58-8eba-c45bf7e440a0 | note | SPECIFICATION REFERENCE: 721.E01
1fbb8408-bf5f-5a16-a62c-f142b6eaf5bb | note | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
c7f74a36-d531-5906-8184-1de2656be786 | note | METHOD: Visual and photos
2de447ee-5a6f-56df-822b-09690da6d889 | note | RECORDS: Photos
83888801-2031-57f3-9d6e-cf2df5ddddfa | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
ecf7e8c7-cd15-594e-b258-61d9a4262581 | date | Date Completed:
d7536392-f7f1-5cf6-a9e1-10ecb3aafac4 | checkpoint | 2.2 - Glass bead Install
5455461d-d578-5fef-9098-a807025a435f | note | FREQUENCY: During line marking works
129c5718-be6b-5fc0-91c6-c9e6c29be098 | note | SPECIFICATION REFERENCE: 721.E01
ce56130a-5110-595a-aec7-42c6ca9abcef | note | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a ﬂuid state to ensure embedment. Glass beads to have uniform distribution.
351b2f21-f74a-5d7f-b7a2-9715036c0f93 | note | METHOD: Visual and photos
e9e028e9-191f-54b7-80e9-a5bf175842e5 | note | RECORDS: Photos
6d897b20-0225-53cb-9378-5dd5cfdc8b15 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
66e6e253-8acf-59ac-ae0d-5e39d27d0b8f | date | Date Completed:
92b4b64a-0442-5ccf-809c-1df2c0c9fc2b | section | 3 - Compliance
2e11042d-a62c-5dff-b90b-fcb515194edd | checkpoint | 3.1 - Completion Inspection
a78cba1d-391d-5576-b565-d7c818c9ae63 | note | FREQUENCY: Upon Construction
eca57be0-f036-5a9c-bdf8-e25656d8747b | note | SPECIFICATION REFERENCE: 721.E01
c016ebed-7ed6-50d5-901b-0940617d2880 | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects.
d3cc0d09-3bbe-5fda-a526-1c56c0b925f3 | note | ○ Edges and cuts-oﬀs shall be neat and sharp, and there shall be no visible run-oﬀ, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles
89a29f29-226a-5cf8-a981-41a43db99235 | note | METHOD: Visual and photos
e7353a58-a06a-51aa-8a5e-2b88791f02b0 | note | RECORDS: Photos
2139db14-7aa0-5b72-8de0-a3783d940be8 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
453e1ff4-6428-5952-a42b-9d525c515a66 | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
5d9c743b-b1d0-566a-9dda-72569b99b130 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
2275156b-b27e-564c-83c7-e53642e4cd9e | textbox | Print Name:
6b1dd9bd-aca6-522f-9252-6caa596d6f13 | textbox | Position:
3320fbd0-ce9f-544f-b805-702c0f697824 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
41b1572e-b2fb-53b0-8c57-7655a1fefb56 | checklist | ITP-009 - Road Signage Checklist | itp | ITP-009 - Road Signage Checklist | 4a03a7de-8397-44e8-8eb7-36796f59925e
1b96c8c3-d3cb-5511-bdc0-8ad038818b89 | checkpoint | Inspection Checklist Items
dc9b7c6f-a3ed-5493-8998-dbc970ea3834 | textbox | Sign Code & Dimensions
a917188f-ab1a-5f77-b82e-144aef0167e9 | textbox | Chainage Location
c5198dd8-98c3-59ae-a1b4-113408481183 | textbox | Number & Post per Assembly
2477ad5e-17d6-5890-b4ad-005a3ffec528 | textbox | Mounting Height (H) (mm) & Spacing b/w post(S) (mm)
98565e99-e225-56ba-bf92-09385b9da396 | textbox | Post Hole Depth (D) (mm)
64db3e30-c50c-5fe8-8663-c497b25407f1 | textbox | Fitting Type and Number of Fitting
dd0678d8-3635-54eb-bb12-b59c577f0e13 | date | Footing and Sign Installation Date
9600558b-1bcf-560a-b940-10cd212b3d9d | note | Photos
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
4c619913-70b2-59b9-8e85-7aa07009facc | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
7c9377e4-e5f8-5220-be1f-c2b39c3c57de | textbox | Print Name:
f6476e10-3a1a-5684-898c-a073d3a3fdf6 | textbox | Position:
bd7fa19e-daa1-5a8b-9ef3-03c4d76e0e2f | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
981e7153-3854-5c45-8bbb-2905670016f0 | checklist | ITP-010 - Guardrail | itp | ITP-010 - Guardrail | 959d7f0d-ee74-46fa-a68d-ba7171b95fc3
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
78f2eb97-4d27-5397-9616-d0974c63c400 | checkpoint | 1.1 - Check for correct documentation
0ec57c45-86f2-5bdc-b58b-a216f96427bf | note | FREQUENCY: Prior to commencing any activity
086cb6b8-35d8-503d-979c-02b0754ff62e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
ab817a45-c92b-5e09-af6c-7c7e05ebd0bf | note | – using the correct and complete set of drawings
0e87b665-1836-5f00-8bd9-0aff94e5fb43 | note | – all drawings are the latest revision..
aa50f204-8caf-51f3-b943-d67d410f8d74 | note | REFERENCE DOCUMENTS: Design Drawings
4a0abe65-ea75-56fc-871d-5432bf3fb90c | note | METHOD: Visual Inspection
251f8e93-1153-5553-8544-9e01118b4ab8 | note | RECORD: Signed ITP
03256eb2-10f7-5eb2-acbc-768daed6ab0d | note | IP
82c51713-01e0-5753-b05a-f8bc425c1a90 | note | RESPONSIBILITY: Project Manager/ Site Supervisor
6dcf91aa-ca4f-5cd5-bded-9751eee20558 | date | Date Completed:
457fc29c-5478-51c3-a60f-061f5ba4ad0d | checkpoint | 1.2 - Implementation of all measures and controls
5afcc918-dc4a-558f-aa76-735dfd2c28bb | note | FREQUENCY: Prior to commencing any activity
663cff31-6696-5aa8-af87-521b6453cf31 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS
6a2336c7-2787-58be-84c1-3df28befa56c | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
c37a8318-8c2d-5a69-8c75-a83252fb4bc3 | note | METHOD: Visual Inspection
f341f913-15fa-54c4-97bd-e055ff085002 | note | RECORD: Signed ITP
5742e225-b980-5fa7-b89e-fd6a8e25bfc2 | note | IP
12c453ab-0f00-53a1-9a99-d7a762d45f9b | note | RESPONSIBILITY: Project Manager/ Site Supervisor
179b0df0-6817-59e8-83a9-f173c1ad472a | date | Date Completed:
73920d7e-e2c5-5db3-bfa8-d36b7058a4c5 | checkpoint | 1.3 - Setting Out
4c70ffe9-0fd7-59db-aade-198edbbb95fa | note | FREQUENCY: Prior to commencing any activity
8dd0c908-2af4-5773-b10c-1cdd07379690 | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor.
caac9424-8219-5a49-be8c-0b27d7d96fdf | note | ○ Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
f0a37273-72f2-5e02-a92c-218a38f5abef | note | REFERENCE DOCUMENTS: Drawings 708.08
a0b2264e-1557-5811-a657-fa658781abaf | note | METHOD: Document Review
25ba3632-56f1-5b5b-b635-2d5d334c04af | note | RECORD: Signed ITP
f9e669d5-a8fc-5868-88b2-85fd11d2861b | note | IP
5f22be86-56b4-51c7-a4f6-77db6d3b4243 | note | RESPONSIBILITY: Project Manager/ Site Supervisor Superintendent
540fad9a-8918-51a5-bfb3-689327283865 | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
9579dbba-7fbc-5ddf-a026-c6bd5bf26814 | checkpoint | 2.1 - Supply of materials
07311716-27c3-59bc-8c66-34ff2ec8f1e8 | note | FREQUENCY: Each Delivery
41fd03e0-71a3-5cf0-8d71-d65231baead1 | note | ACCEPTANCE CRITERIA: All materials are to be on VicRoads current accepted products list and conform with the detailed design
8e743b2d-c7ea-5d17-8f27-b941961e81bb | note | REFERENCE DOCUMENTS: 708.04, 708.05 Detailed design
65b15744-9046-51d6-9b49-9c0cb11e31e5 | note | METHOD: Visual Inspection
70bdaa8e-43b7-5dea-8b64-f89f86506728 | note | RECORD: Signed ITP
1e7a1bf2-e8a9-5d1c-bb3b-ec9a92bfb1d2 | note | IP
d5b348f3-513f-539d-9466-d8c71722ef26 | note | RESPONSIBILITY: Project Manager/ Site Supervisor
0c0c4c74-906d-528e-b904-8c78909e065c | date | Date Completed:
a11c7727-374c-58fe-ae54-aad72e43d297 | checkpoint | 2.2 - Installation
85a5de76-58b8-5d60-aee8-b55099377790 | note | FREQUENCY: Each lot as required
8db5e8bf-9e53-5d1f-a2c4-2912b045a9c6 | note | ACCEPTANCE CRITERIA: The oﬀset, height and post spacing is to conform with VicRoads speciﬁcations and the detailed design
88f58727-1259-5f70-9b1b-a724f725415a | note | ○ Where the face of guardrail is less that 1m behind back of kerb, the mounting height should be measured from lip of kerb. Otherwise measure from ground level Fasteners are to be snug tightened to AS4100
c5f6a30b-5ebc-515c-b4c2-7a399533416b | note | REFERENCE DOCUMENTS: Detailed design 708.08 SD3661 AS4100
5f83d83c-6406-5083-9409-db6c8a43b72d | note | METHOD: Visual Inspection
fe660ed2-bef8-5c2e-9d8f-c860f088952e | note | RECORD: Signed ITP
b2c24674-080a-5153-8c78-959dfae3b2bb | note | IP
01ba80f2-36ab-5720-b70e-1c3e7a2f224c | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
cd466e90-8a5b-5335-b067-d55ed355d4d9 | date | Date Completed:
1a622dd6-72db-5c53-b748-bd2deb588d9c | checkpoint | 2.3 - End Treatments
51b415f8-bb9e-5625-823b-01f660682781 | note | FREQUENCY: Each lot as required
57c5859d-5b20-5d54-8805-88afb2bad015 | note | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed to VicRoads speciﬁcations
0bbb2739-8a95-53a2-ace1-5e372d6aed4b | note | REFERENCE DOCUMENTS: Detailed design 708.08
6ea32cbc-291c-531d-b0a3-17bcdbd44c54 | note | METHOD: Visual Inspection
370fc108-8336-590c-b227-ef32a7bac163 | note | RECORD: Signed ITP
623b922e-10a0-5aee-bbb3-be120111e4dd | note | IP
edfa7fad-f9b0-59fe-badc-78506f6adf76 | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
c070f63d-cad9-520d-a077-313ac75e4be6 | date | Date Completed:
7d961610-33b0-5075-8b0b-29fcab9d6e50 | checkpoint | 2.4 - Motorcycle rub rail
4d5697fd-9c4c-5f8f-a59d-ac37aa7b95a5 | note | FREQUENCY: Each lot as required
a748f548-eee9-5b61-873c-7ce62cbd9938 | note | ACCEPTANCE CRITERIA: Where speciﬁed, motorcycle rub rail is to be installed on the new length of guardrail
237b6204-7728-5f89-802a-f6314a444077 | note | REFERENCE DOCUMENTS: Detailed design 708.09
7509c32b-e1e2-562b-b3f5-6ad6425f2f4d | note | METHOD: Visual Inspection
e6c525e7-02f8-56aa-83bc-8a3ea15886d5 | note | RECORD: Signed ITP
54c65d0e-d8a3-539d-a84c-45b0a1bc4744 | note | IP
6ac946d1-567f-5d9d-8b3d-0ce869d45aaf | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
29a00349-f5ee-5795-8f98-7a256ef90ccf | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
6ca108b5-1937-510e-89f1-beae553f2df9 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
68028ba3-22e7-5c2e-bfd6-3aaf14cc3eb5 | textbox | Print Name:
d1dbdee0-8b8e-5e3e-80e4-a67262f3bc1a | textbox | Position:
59922202-9206-54e2-84fd-08300ad09ec6 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
071f267e-65d6-5ec1-ae3e-4fd51de41713 | checklist | ITP-015 - Drainage Checklist | itp | ITP-015 - Drainage Checklist | f6cd55d0-eaf3-43cc-a503-3c65808da246
13f7ffd1-5e39-5df6-8ea1-5ca3fe37ae75 | checkpoint | Pit Details
afd16bda-97e3-5754-8cbb-5ee0a29304bc | textbox | Pit No.
bb7ea087-37fb-5cd4-a859-16092d3bfe5f | textbox | Pit Type
3700b52b-7d10-594f-95f2-b8e9dab30909 | textbox | Dimension
41e518d5-d2c6-5512-b24c-a7bc2898354f | textbox | Inlet Level
2ab54a67-4535-5730-b9c8-a8be2f5c6bb4 | textbox | Outlet Level
c1384ddb-1ec4-550c-bd3c-4778cc89c5c9 | textbox | FSL
290caf0d-9fba-5a85-a0dd-73e9cb030aad | textbox | Pit Depth
f5136021-0cd5-516d-b858-1c4ccd860983 | checkpoint | Checklist Items
ac624d40-08bc-5426-9b5b-c423dd5c0b32 | textbox | Drainage Line Number
daa29e46-8508-5a48-b08d-f361bd3ae10f | textbox | Pipe Size
e4639f21-6947-5345-a311-15e53939e1f9 | textbox | Trench Width (mm)
499ecc76-afc3-516c-88d2-3c7a49542bfe | textbox | Minimum Cover (mm)
d2056b63-946c-5f28-b703-ec88f0006d41 | textbox | Beading Depth (mm)
ffd080c2-bbf6-53a0-9d39-930b9730536f | date | Start Date
515a47c7-7afb-50ee-b28d-2539758af222 | date | Finish Date
5fafde7d-7fad-516a-aec6-4672c04f8451 | checkpoint | Pipe/Pits/End Walls
3cfaf860-9b55-5617-b805-a33a0edf6914 | note | Pipes/Pits/End Wall in sound condition?
d4d0a798-2bbd-5bd2-86b0-698bcc3f625c | date | Start Date
829e1b3b-f075-58d3-bfe4-8c32bdbba046 | date | Finish Date
0eac159f-b12f-5d66-8d10-01cc4f217314 | checkpoint | Laying Direction
870fdf83-eae7-550c-8b8f-51b95043010a | note | The direction of Laying Satisfactory i.e Collar on Upstream?
ff9b4f1b-9a73-5a34-be7c-4fbdaac7d65d | date | Start Date
a56660c3-2851-551b-b087-3dbea48313df | date | Finish Date
66cf5018-577f-5abd-a910-ac97cbd0a061 | checkpoint | Rubber Joint
f90311b1-ba4f-5fec-b632-b87d0bcff459 | note | Rubber Joints in Satisfactory condition?
c4ef5e28-032f-5e32-96aa-dea191a1df86 | date | Start Date
3399d266-167e-5a7e-960e-a90cefa99f68 | date | Finish Date
284d6a6b-59fe-5706-b0ab-0ca0e8f7f5ad | checkpoint | Gap Filling
97d086c1-dac2-5af5-8835-2f81a6f7f8bc | note | All the holes have been mortared to satisfactory condition?
2d35c2c4-4f3d-540a-b840-2305de4e50f9 | date | Start Date
9d077d7d-e1de-5a54-b9ca-c5dc9f487873 | date | Finish Date
1e3d31a3-16a4-5503-92f7-d36c6b0d7d2e | checkpoint | Step Irons
6448d217-65bd-5977-b378-0e887266a884 | note | Step Irons Installed in the Pit greater than 1000mm?
1a6d2c1e-2d63-5ae4-aa0c-ccdb11fc4325 | date | Start Date
4334c58c-5249-5bd2-82b0-431bad66f96a | date | Finish Date
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
4e42773f-3821-5e50-a586-f0f5f566380c | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
6db91f04-ea88-5494-894e-9f5a266a884d | textbox | Print Name:
2d884928-1d04-5d03-b9a2-196391ae2f4d | textbox | Position:
85dc6342-20eb-5e07-af92-556a8c64f6fc | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
8fe6a39f-e81d-5b67-af95-beb08e12de40 | checklist | ITP-045 - General Concrete Paving | itp | ITP-045 - General Concrete Paving | 31e44898-df83-4487-b1cc-5d63c9e2acd3
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
78f2eb97-4d27-5397-9616-d0974c63c400 | checkpoint | 1.1 - Check for correct documentation
eee305db-0ad2-5699-b288-4788c2b43125 | note | FREQUENCY: Prior to commencing any activity
c8d7bea0-57cc-583c-9fd9-b621043824cf | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
6b9c67dd-4cb9-5f4b-9744-4e7527ee10ca | note | – using the correct and complete set of drawings
3efe8d84-93fb-583e-bc2b-451f4118c0b7 | note | – all drawings are the latest revision
31b372e6-c70b-5e8e-b17b-8f237045cce6 | note | REFERENCE DOCUMENTS: IFC Drawings
38ee64f2-e227-5668-bfab-9ec0daf653ba | note | METHOD: Visual Inspection
7f692d85-cf72-5493-8c74-aaef275660b4 | note | RECORD: Signed ITP
45436503-1205-5db6-96ee-9a9e0dfc19a0 | note | IHP
fdd44d80-f5cd-5032-bfb5-8f806677d98e | note | RESPONSIBILITY: SWA Project Manager
8f7436cd-24d0-54e5-af47-eaeee43eef71 | date | Date Completed:
457fc29c-5478-51c3-a60f-061f5ba4ad0d | checkpoint | 1.2 - Implementation of all measures and controls
9f91c3b5-48be-5d37-85a0-8256be9ca02d | note | FREQUENCY: Prior to commencing any activity
93c0e39a-a5f8-5024-8170-a9a032969438 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
0d4b03c9-0adb-53ab-befb-105153d6be76 | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
03b7fbd0-c5c4-5500-a36e-404816c634db | note | METHOD: Visual Inspection
0e717617-a77c-522a-8569-c6d075d69eab | note | RECORD: Signed ITP
88dddc8f-70a7-5945-a81b-4cb883b91b85 | note | IHP
2dab62d2-2af2-541a-baa5-45ecddeaafad | note | RESPONSIBILITY: SWA Project Manager
0c45d27c-a007-5bf8-8f0c-28f42159517f | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
8ca7bcd9-51c2-5af5-a939-2cb980971168 | checkpoint | 2.1 - Survey Set-Out
abae3e05-7160-545e-a830-bc34f458e2b8 | note | FREQUENCY: Prior to commencement of excavation.
b4301f2d-b7b3-5195-ad81-984de74540b5 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
02d60dce-893c-51bf-a329-de97b920bb44 | note | REFERENCE DOCUMENTS: Work Procedure
97460939-0a43-504b-87a3-7e7a2c0a03e2 | note | METHOD: Verify
f09ee51f-e536-52c2-9ac9-de3e2305bacb | note | RECORD: Signed ITP
12b8d6be-108e-5097-a66e-99ebd8a9eca4 | note | IP
d8157272-ebae-54db-a99c-80b3065efb5e | note | RESPONSIBILITY: SWA Project Manager
02b04572-69a8-53d1-818b-757e80e6a654 | date | Date Completed:
4fa02bcf-128c-52b5-bef2-2b0ba5d23d06 | checkpoint | 2.2 - Excavation Permit
03252232-fe2e-5a4d-b036-738dad4895a7 | note | FREQUENCY: Each Lot
8af09b81-6abb-5249-a7bb-ab137bc4f8cb | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
c07e38af-35e2-5e79-b28e-0fc068c3c13e | note | REFERENCE DOCUMENTS: Excavation Permit
4a361387-65a4-5272-b5ec-4388fde85aaf | note | METHOD: Verify
856122d7-7ff0-5172-91bd-85e294e46ccd | note | RECORD: Signed ITP
97cbc96f-7798-5c85-a32b-0160f8864d66 | note | IHP/IP
45a8e1bc-177e-530b-8779-e42edbb64f42 | note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
ab6dfcee-9cc6-5b21-bec3-6a58e2b39ce4 | date | Date Completed:
77bda8d2-d871-5513-9609-54c06848553d | checkpoint | 2.3 - Formwork
b3b985c0-28db-545c-8d82-3d36a4cfa80e | note | FREQUENCY: Each Lot
9ee77081-b54e-5159-bcb7-ea45c4ac6a7d | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
b760cfe0-e69e-511f-8e5e-33a77b7c533f | note | REFERENCE DOCUMENTS: AS 3610
89f51154-a6d6-5e74-8575-0ab43c80eb8e | note | METHOD: Site Inspection
84f7f7fe-b106-520f-8f37-4718d9860513 | note | RECORD: Signed ITP
e7d3d7a3-84e2-57cf-8274-2b32d9c52d50 | note | IP
ba5a65f5-ec86-5068-a12f-628344a3522f | note | RESPONSIBILITY: SWA Project Manager
43b7d9d1-2223-565c-8c60-93cfb407a4c2 | date | Date Completed:
0637ccf6-215a-5e75-ab68-744fb1bff0e1 | checkpoint | 2.4 - Reinforcement
d977ed63-365a-5784-8115-9cb77129d6b8 | note | FREQUENCY: Each Lot
9fbdaaf1-a7a8-5a80-a574-d0f94a16fe47 | note | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671. Minimum cover of 50mm.
deed33a2-cf34-5341-b812-33d94defdda1 | note | REFERENCE DOCUMENTS: AS/NZS 4671
bb66d9c4-36e8-5292-a3fb-894b1e131ce7 | note | METHOD: Visual Inspection
ab682694-8311-5184-8de8-d53d35473aa8 | note | RECORD: Signed ITP
b7836cc6-a210-5599-aefc-3a2b6b85f24e | note | IP
50cb1299-6081-5559-93fd-20d8e6674e5a | note | RESPONSIBILITY: SWA Project Manager
923e47b5-5730-54a5-aef7-ac426c05fb6c | date | Date Completed:
e20bed31-8e3d-5851-a8a1-9872e4a3742b | checkpoint | 2.5 - Temporary Drainage Provisions
24f4c914-4947-5a8f-8ec7-2ecca6acae77 | note | FREQUENCY: Prior to commencing
3169cfbd-1019-5fc7-a713-0752a938f562 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. Obtain written approval from relevant waterway authority.
a5994913-35dc-5e73-8d0d-3af76faf0e42 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
fa7ae607-c8e0-51db-8357-442afacae9ea | note | METHOD: Visual Inspection
3952a518-6b38-5987-9d53-9f2618de5399 | note | RECORD: Signed ITP
6a994837-f953-506c-b73a-23444f4627ea | note | IHP
b295128c-a848-5bda-828d-6927061ea0f0 | note | RESPONSIBILITY: SWA Project Manager
247db84d-0562-5b5f-b1c7-aadaf6b5769d | date | Date Completed:
c90b11c3-dfbd-5a48-abf1-a184be14e804 | checkpoint | 2.6 - Bedding
b86142db-7ed2-506c-8022-12f89d4cfec4 | note | FREQUENCY: Each lot as required
19ccc43e-9e69-5614-8486-9250ae584e49 | note | ACCEPTANCE CRITERIA: Crushed rock bedding material as per drawings
f9b52c92-bf19-5eca-a988-d11736b9bb1c | note | ○ Bedding trimmed, moistened, and compacted as necessary
4150a687-4a52-5cb5-9ddf-29e55bdcd3b6 | note | ○ Bedding compacted thickness: Footpaths and other surfacing ≥ 50mm
58cfa338-2c0a-5856-9c01-9fa94cae0523 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.18 IFC Drawings
8a81b5ba-6e5e-562a-b6e7-285e246fd04d | note | METHOD: Site Inspection/ Document Review
fc1ed9dd-34c1-5b3c-abb1-78b58b4fe61c | note | RECORD: Signed ITP
dbd7fe59-b8af-5708-bbd9-5d0d59c7e813 | note | IHP/AP
9424fe40-9803-541f-a6a3-27aa14256388 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
874afa84-ec5a-54d4-8a36-ee27ac2b52a5 | date | Date Completed:
dafeadec-2220-59e3-bbc5-78238f26162c | checkpoint | 2.7 - Concrete Placement
4f7d565d-7f57-5453-b26a-93912bc3bd78 | note | FREQUENCY: Each lot as required
acc00d4e-8e07-599d-a0fd-1db87aff3296 | note | ACCEPTANCE CRITERIA: Concrete strength as per drawing speciﬁcation
a663f449-dcd3-5701-bddf-3ba323dabc69 | note | ○ Comply with requirements of AS1379
665753b3-3f85-5bc6-9053-cd7aab90e78f | note | ○ Aggregates to comply with Table 703.051
1d6965d9-4404-563d-822a-7be694dfb7ac | note | ○ Extrusion machines cement content ≥ 320kg/m3
fad3e71a-cc88-5f5f-acc7-f5b89e5181d0 | note | ○ Surface pitting < 5mm diameter
9858029a-694f-585c-9191-dd273623ecd9 | note | ○ Concrete to be satisfactorily compacted. Proﬁle transitions between 10-20mm per metre.
2d590dc3-87de-56f6-98c5-7ae19cd651e3 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.04(b), VicRoads Std Specs 703.20, VicRoads Std Specs 703.21 IFC Drawings AS 1379
f6bee428-7f17-5475-aa09-5cfc7aad58e6 | note | METHOD: Visual Inspection
c09aa0fe-5e05-5d2e-9d3d-d1463ffac490 | note | RECORD: Signed ITP & Test Reports
d6565033-d887-5731-ad83-91bb7cb2a0b9 | note | IHP/AP/TP
cd559b5b-f877-5455-b216-12021ee4b89e | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
de0c3ad5-15ba-5d22-acab-0dc1ea949d0e | date | Date Completed:
3c8951bc-fb1d-55dd-9ffd-3a7869dd5df0 | checkpoint | 2.8 - Finish Surfaces
97d1d49e-0650-5d7a-a283-fe6beac811b7 | note | FREQUENCY: Each lot as required
2458e28b-0d1d-55df-bf30-2fd7e5864265 | note | ACCEPTANCE CRITERIA: Footpaths and other Surfacing: Wooden ﬂoat ﬁnish
01554e45-55e2-573e-8714-8a9355e842ad | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.22
e383673f-a8cf-5bbc-8153-de67e5b615ec | note | METHOD: Visual Inspection
a9b975bf-17ce-5878-b1d3-1130035dbc29 | note | RECORD: Signed ITP & Test Reports
d787be7c-1b20-5e06-b37a-a68c9f3e271a | note | IHP/AP
9b3c965a-a117-5631-95d7-940e51cba2e9 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
0d0ba586-677c-5291-8567-6edcec752a21 | date | Date Completed:
f0a3cd2b-c8ba-5f2a-bd8c-0bb6b423c27f | checkpoint | 2.9 - Tolerances
7e1f213e-c927-5e3a-bb54-588ffee96534 | note | FREQUENCY: Each lot as required
0039b4cc-3463-5e3d-9747-203a1732f40b | note | ACCEPTANCE CRITERIA: Match existing surfaces ± 5mm
c6d108b4-31ec-58dd-a1c9-0fdaf1cdb20e | note | Section dimensions:
76921a82-71b7-50fa-87ca-eb95f7c7e047 | note | ○ Within 5mm and 15mm for width; and
2f686c82-3021-5e91-86dc-383081391768 | note | ○ Within ±3mm for dimensions less than 25mm.
823267a9-7e77-531f-b955-7c5996bd3df5 | note | Concrete footpath:
423372ed-8a34-59a6-bb01-bacb34bc7c0a | note | ○ 150mm thick
1ac7b9db-405b-5a4b-9c53-d41690d3f1d5 | note | ○ SL72 reinforcement
2a0eae66-1f89-55b8-89cd-aca1468ee7b6 | note | Concrete Surfacing:
bd278de7-ae77-531c-8e6a-f98576d30908 | note | ○ Type 1 100mm
6a9a005c-a671-5582-88bc-e979a7ad5656 | note | ○ Type 2 150mm
59281743-6354-57b8-9065-4eb789c31dd4 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.13 IFC Drawings
fce9109c-59a6-57b8-a526-a376140eb285 | note | METHOD: Visual Inspection
cfca9fed-4e1f-5b37-ac15-be65df065258 | note | RECORD: Signed ITP
62a919a0-fbce-5427-bb9b-b5a2305a2328 | note | IHP
4f5590ec-c453-5983-b09d-f0a68b59cc58 | note | RESPONSIBILITY: SWA Project Manager
8b537dfe-da43-5a13-906f-d5e10c4d52d7 | date | Date Completed:
91c41ed5-0ba5-5b7e-b34b-7afbac17d4e2 | checkpoint | 2.10 - Joints
c0eda2c0-4fdb-5684-a781-2574ebefbc25 | note | FREQUENCY: Each lot as required
a1d0afd5-e008-5fe7-9428-81a406c1d340 | note | ACCEPTANCE CRITERIA: Footpaths and other surfacing:
00367f8a-f964-588f-ad0e-9aece009add2 | note | ○ Expansion joints at 12.5m regular intervals
c7bb1a40-deab-58bd-a61d-eaff096da0d4 | note | ○ Control joints at 2.5m regular intervals
3b81d342-8743-502f-8d9b-d1fef036eafe | note | ○ 20mm deep and 5mm wide
6890dbdb-92eb-5c26-9d1f-694580d3c34e | note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
28b948a1-deba-5b69-86f0-ce86f3b2389d | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.23
9dc6f66e-636b-5095-8f59-286d7cd20127 | note | METHOD: Visual Inspection
2c38b942-8492-52a6-861e-c17e97ea07ab | note | RECORD: Signed ITP
242f470e-e1d3-5f64-9745-98a9bb169abc | note | IHP
a8a79afc-d754-595c-a364-ffc1cd16cfb3 | note | RESPONSIBILITY: SWA Project Manager
398720d9-0b29-530a-9002-bd63a7e02063 | date | Date Completed:
dc2a1895-a01d-5fee-9752-491b58cbbe20 | checkpoint | 2.11 - Backﬁlling
f2fea800-ab53-551b-8af7-686702f2bbeb | note | FREQUENCY: Each lot as required
a9e9f3e1-8090-57d3-89ab-f537973b7684 | note | ACCEPTANCE CRITERIA: Topsoil compacted in layers < 150mm
7bff6008-e82e-5e36-923d-bb08df9da072 | note | ○ Width ≥ 300mm behind edging to top of edging
00c16956-63fb-5a9f-95b5-38084361c3e7 | note | ○ Topsoil placed after 3 days of concrete placement
c4bb5253-c4e9-57f6-9cb7-12ababf9993d | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.26
cb708d60-148c-5c77-b55b-8c03917beea2 | note | METHOD: Visual Inspection
a52af329-6691-5041-b433-630a748bddb0 | note | RECORD: Signed ITP
c6d14f8b-b636-5e39-bd6c-45c1d8bcbb50 | note | IHP
eb384a0c-84cf-5b91-acb2-e9ce86be90b0 | note | RESPONSIBILITY: SWA Project Manager
8d7ea636-fc0d-536a-8d62-d1c00989f915 | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
b61cd3df-1245-58d3-98da-582d5d4fb73e | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
ca92968e-fd7d-596f-b881-5c495579f796 | textbox | Print Name:
7536c187-d446-55b3-a24c-2c06c642217f | textbox | Position:
b45b5b7b-c0f3-5fb7-92e9-46c8c6e8a06c | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
03f66bb4-f5f3-461d-b781-a49c242883f1 | checklist | SWA-004 - Sprayed Bituminous Surfacing | itp | SWA-004 - Sprayed Bituminous Surfacing | 10022529-6488-4b47-8ab2-9e4eefa47067
93fa33f8-7709-4651-a627-7b7c9e2c601b | section | Details
61445f3d-639c-4a8c-8504-0d21de680733 | checkpoint | 1 - Preparation of sealing
cff9242f-fbf8-5414-a073-7c24f2147ca9 | note | SPECS REFERENCE: VR 408.02
d7002269-39bb-5c18-8acb-7d67cb836944 | note | DOCUMENTATION OR ACTION: Constructed to meet specified shape and level requirements Homogeneous and consistent with the material in the pavement base layer
03e69ba4-7cfd-5e10-a787-fc76737e851d | note | ○ Uniform in texture
997ca655-6d14-5f63-ae43-deefda2fe657 | note | ○ Free of tearing and scabbing Free of lamination on or within 75 mm of the finished surface
ee5eb2d6-c6e0-54ac-bd58-9dff98adee76 | note | ○ Level with adjacent sealed areas and edgings at the Joints
07fa5320-f833-52ca-a4d8-56e1d5423a70 | note | ○ A hard dense and tight surface capable of being swept with a rotary road broom or similar
22bec890-726e-545b-869f-9fe06789423a | note | ○ Free of looses and foreign materials
c96b2033-e4df-546e-bac8-fbb7867b0095 | note | ○ Dried back to the moisture content and embedment requirements specified in Clause 310.03
97c6f657-3ea3-5663-a1ba-4581d6e97bba | note | RESPONSIBILITY: Subcontractor
e9f9a715-c5a1-5aa8-b0d9-8eba4fdf9cc0 | date | Date:
53907519-1ab6-4476-9938-2962499da213 | checkpoint | 2 - Preparation Testing
7c634490-6015-538a-a348-f9d2cfe61861 | note | SPECS REFERENCE: VR 408.03
c56e711e-aff9-5a3d-b1ed-07ff2b29065a | note | DOCUMENTATION OR ACTION: Testing Scale B
44652329-ef93-515f-8534-88c1cd58a165 | note | ○ Maximum lot size 4000m2
8644e199-81a1-50c7-ae3b-880e86303553 | note | RESPONSIBILITY: Subcontractor
de0a892a-c892-5f26-b12e-41d9d924a6d9 | date | Date:
65490af4-83a4-4c27-aef5-6be9b8b7fdef | checkpoint | 3 - Commencement of Work
fef1d9b1-725a-5e37-96a4-f394d2fc4cf2 | note | SPECS REFERENCE: VR 408.03
a25ddcf7-7c52-5924-8844-b95750a8813e | note | DOCUMENTATION OR ACTION: HP - Work shall not commence until the contractor and the Superintendent have agreed that the road or pavement surface is fit and ready for surfacing no more than 24 prior to the work occurring.
1d32c36a-8ed9-5339-8a45-3d003584a501 | note | RESPONSIBILITY: HP VR Rep. AP
ff6d0caa-d896-5f33-8d7a-59f94181363d | note | ○ Site Eng
3b6e8706-a439-5fa4-badd-caae6bf1deea | note | ○ Superintendent
7782d94d-6c9f-564b-b7c9-10c4bd99bf72 | date | Date:
839c7d89-ca80-4cb2-bd8f-cef957b74b57 | signoff | AUTHORITY HOLDPOINT
b4a40e44-a39d-43e3-bf76-36129bdc832f | checkpoint | 4 - Limits of Work
e18accc4-2d19-5919-930f-f409a1b99a0e | note | SPECS REFERENCE: VR 408.04
7e243a63-d5e4-5050-aa9d-5db4b0edc39c | note | DOCUMENTATION OR ACTION: Limits of works shall be marked out as per drawing and table 408.161
2cce2553-e5cf-5d81-8814-5f1f40a8ee4f | note | RESPONSIBILITY: Subcontractor
387ae2b0-c89d-51a1-ba02-f295ab0bb789 | date | Date:
563edd87-7324-4f54-9e4f-fb1fa2a3cee5 | checkpoint | 5 - Materials
6db03085-d758-5c99-a3a4-a58934548ce5 | note | SPECS REFERENCE: VR 408.06 & 408.07
891f46eb-3c91-590e-91f2-325a15392390 | note | DOCUMENTATION OR ACTION: Materials to comply with specification, contractor to confirm materials to be used
64781f3f-a6ac-5604-a58a-f9a8ac13d58e | note | RESPONSIBILITY: Subcontractor
df73da13-cfa5-507a-b8d5-f3fd861f0aa5 | date | Date:
45b6c6a6-c68a-4e35-a8f2-c510f0620819 | checkpoint | 6 - Application
8f6b9b7f-0b2f-518a-a972-5bb9dd0cf155 | note | SPECS REFERENCE: VR 408.10
1a7e132d-8708-59b9-b608-c7a77e215fef | note | DOCUMENTATION OR ACTION: Supply Seal design to superintendent for review prior to application of seal and application rate not to be less than 0.1L/m2 for design
5ff11baa-48fd-572f-9990-0ce0ae2ffbad | note | ○ Minimum air and pavement temperature to e not less than 15 degree C
bf3a2abd-ad0f-559e-825e-5708f3e46793 | note | RESPONSIBILITY: HP Subcontractor
222ce37d-b482-598d-85d0-f9d23d9ab337 | note | ○ HP VR Rep. AP
bc32dd88-2348-57d0-ad19-95308a7838d4 | note | ○ Site Eng
57a265c7-a187-54d0-be46-3cef9c455607 | note | ○ Superintendent
e0022086-b80f-58a5-8ea7-c7ffa8f4bf63 | date | Date:
eeca1da1-4600-4fc1-8b3d-9b7029bf1987 | signoff | AUTHORITY HOLDPOINT
da74c6f9-4421-4d05-a8d4-c06a4df50890 | checkpoint | 7 - Removal of Loose Aggregate
79365212-2431-5aa9-af12-628355a4dd65 | note | SPECS REFERENCE: VR 408.11
eb58a75d-62c5-53eb-8e06-84bc5864fc28 | note | DOCUMENTATION OR ACTION: Aggregate to be removed within 48 hours of application.
11ba391d-064e-5d05-98a4-e0d9439ee920 | note | ○ Road to remain appropriately signed until aggregate is removed.
3a0ba5ad-9765-52d3-9646-aab916ec96ac | note | RESPONSIBILITY: Subcontractor
c9ee018a-9160-5029-9b7f-3344f79d7c27 | date | Date:
a7862975-0bb7-4178-9932-8669feafa809 | checkpoint | 8 - Acceptance of Loose Aggregate
6cdcba82-98f3-5cb4-ae57-8152ab7eb73a | note | SPECS REFERENCE: VR 408.12
93dde1d9-04d7-53ff-8580-4edafe0b6426 | note | DOCUMENTATION OR ACTION: ACCEPTANCE OF SEAL
7c66ee3b-9bd8-5e5d-94d1-0561220aee67 | note | ○ Accepted application rate shall not be 0.1L/m2 less than seal design rate
a9496df0-d14a-50ad-8ead-72b15f418dad | note | ○ Surface texture shall be based on visual assessment
97b29395-f65b-5e70-8a52-19d5e89bb215 | note | ○ Aggregate retention shall be based on visual assessment
acc827c7-f818-5b09-98ea-0c3e99ee1942 | note | ○ The seal shall appear visually uniform.
7e93cd0b-3a5f-5386-8179-375e0355db1a | note | RESPONSIBILITY: HP Subcontractor
48645473-3fca-5301-8600-9dbe96a446af | note | ○ HP VR Rep. AP
9a8b9bae-fc69-535f-8f39-29b0afcaba3e | note | ○ Site Eng
fde1ea6d-a8d3-5e63-a71a-21e8ea979b64 | note | ○ Superintendent
a359a989-ace0-54d9-a870-609bb7380fd8 | date | Date:
729f4191-3252-4a0e-bc0b-a5205e8e1d72 | signoff | AUTHORITY HOLDPOINT
4bbbd276-1409-4b7e-8cc3-003929e7fe06 | checkpoint | 9 - Maintenance of Seals (Repairs to Seal)
5c3eae87-5151-5708-9019-90ba14fcbfc7 | note | SPECS REFERENCE: VR 408.14
37ddc42b-f785-56b9-bfed-9e9f3f88e1cd | note | DOCUMENTATION OR ACTION: HP - Superintenden t to approve the proposed treatment to effect the above work before undertaking the work.
55c29598-be38-5343-ae21-2ba328f3f1cf | note | ○ HP - Where the treatment for protection or repair of a seal involves the application of a further seal coat the Superintenden t shall approve prior.
c2b7714b-6c69-5c9b-8e9d-623eb1cbb504 | note | RESPONSIBILITY: HP Subcontractor
6842f207-63a1-52b3-8781-affd1675d053 | note | ○ HP VR Rep. AP
15f70d05-08aa-5d97-9878-9eb73d7d720a | note | ○ Site Eng
92f41fee-4a70-532b-b1ce-dbad34bbdda3 | note | ○ Superintendent
cd1b0a17-c7fd-5944-b209-f82c5d70fd20 | date | Date:
a282a80b-0bb9-4165-a879-c6c00e36851b | signoff | AUTHORITY HOLDPOINT
0f4d7f4a-48ec-4de1-93ed-bba1db217d39 | checkpoint | Final Inspection
00d6ecf3-5858-5420-94a9-5dbf1851a393 | note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
35eaab8e-8b45-586c-ac1d-4c6fb0f8f6ba | textbox | Print Name:
96576342-c889-57f0-8c40-42beab02b0d3 | textbox | Position:
fe9f077d-c8a5-556a-b72b-6bbacf73c5a4 | date | Date:
e55d43e2-7d63-4b95-acde-9602d72b45bd | signoff | Sign ITP
606be79f-221c-5b48-9dca-bcec2e8b79ed | checklist | SWA-013 - Pre - Construction | itp | SWA-013 - Pre - Construction | b8738fa3-7d57-47cf-b2b4-798567fc0026
b2d83159-08e6-5c9d-a961-c21cb4456f84 | section | 1.0 - Pre-Construction Checklist
4fc3e0ad-f977-54c6-81dd-7b08502bf136 | checkpoint | 1.1 - Communication (1)
6ac75fb9-74e2-5fb2-85a3-84c4b8008c39 | note | ACTIVITY / DESCRIPTION: Community and emergency services
c678d74b-a672-592b-b979-1c99b7f696d5 | date | Date:
bb15b43f-69a0-5735-aba3-d508dc3c1dfc | checkpoint | 1.1 - Communication (2)
e55c5068-9fa4-5a1b-aa0a-6de36cbc5bf4 | note | ACTIVITY / DESCRIPTION: Emergency response plan
bda3f06a-3c3c-5018-af54-e0aff08de424 | date | Date:
b3859a9c-fc33-5200-ba37-62c016e88edb | checkpoint | 1.2 - Approved Construction Documentation (1)
9628d657-61bb-5a84-9ad5-12752bc1064a | note | ACTIVITY / DESCRIPTION: IFC drawings (PDF, hardcopy)
0d71f2f0-26f9-5995-bc5f-ccfbf607e17b | date | Date:
62496475-0e5e-5735-9b2d-ff3d2c818f3e | checkpoint | 1.2 - Approved Construction Documentation (2)
f343ec02-718c-59db-ab3a-25e80837e2df | note | ACTIVITY / DESCRIPTION: Digital (CAD) files (Surveyor)
60cef747-332a-5e37-80d6-c09065e0a958 | date | Date:
3cc842ef-03f0-5ce3-a3cf-d70a2ee247c0 | checkpoint | 1.2 - Approved Construction Documentation (3)
6486ac0a-36f4-5647-8cc9-8c58b9fc2796 | note | ACTIVITY / DESCRIPTION: Budget / Resource arrangement POs (incl. sub-contract agreements)
0951336e-809c-5108-957b-34c50eb0e7de | date | Date:
169fc211-abc1-565b-b02e-2123113df383 | checkpoint | 1.2 - Approved Construction Documentation (4)
a291999a-7702-54be-a784-596df5954215 | note | ACTIVITY / DESCRIPTION: Quantities / Specifications
aee31bd7-4cde-5a8f-a5ba-9514c271b1c7 | date | Date:
0c1abebb-8bd3-52d3-8cde-700416aaa7ad | checkpoint | 1.3 - Dilapidation Report (records and photographs) (1)
03636c61-da3d-5862-9ef7-a0e61d9ba316 | note | EXTERNAL REFERENCE: Hold Point (HP)
79639933-4198-5797-be20-6f279137add8 | note | ACTIVITY / DESCRIPTION: Residential (ie: structures, access/gate, letterbox, fence)
76df2442-44de-52f2-a7ee-9e1b2db476fd | date | Date:
ca372360-d710-5770-88f9-f083b3e9f62f | signoff | AUTHORITY HOLDPOINT
9a6352b0-50e1-5e4b-b6a5-3e7811e4b73a | checkpoint | 1.3 - Dilapidation Report (records and photographs) (2)
6e875f2f-1f6d-54b8-ad88-e8bac65328d1 | note | EXTERNAL REFERENCE: Hold Point (HP)
ad5b0201-e292-57e1-b0be-3814d7cd5e6f | note | ACTIVITY / DESCRIPTION: Business (ie: structures, access/fence/gate, signs/letterbox)
8118ed5e-26cf-5d2f-a5e1-25503267f92e | date | Date:
3a93edef-590b-5176-94a0-397633c9d559 | signoff | AUTHORITY HOLDPOINT
123d6bf2-c8b3-599b-94ec-15e82d53874d | checkpoint | 1.3 - Dilapidation Report (records and photographs) (3)
1825af1f-9911-5784-b310-f67d99f16c75 | note | EXTERNAL REFERENCE: Hold Point (HP)
34872f6b-7c88-59d7-8915-8ea569094049 | note | ACTIVITY / DESCRIPTION: Agricultural (ie: access, livestock, fence/gate)
b9ca6609-db0a-5eaa-9c75-18e375ab6eb3 | date | Date:
2e14c651-fc80-5b4a-bd29-3512017a1157 | signoff | AUTHORITY HOLDPOINT
363f3d0d-5dd8-5649-a38e-a0bddbd4c51f | checkpoint | 1.4 - Heritage / Cultural listed areas: (1)
67ed8b4e-48f9-57f8-a600-390c9bdd29c2 | note | EXTERNAL REFERENCE: Hold Point (HP)
fa5dd48c-18b6-528b-a52f-0ec372b0b2c3 | note | ACTIVITY / DESCRIPTION: "No Go Zone"
255ffa41-0fb6-50b0-be8a-005e04fba535 | date | Date:
733c6df6-42e2-5657-961b-1024edf89599 | signoff | AUTHORITY HOLDPOINT
52d14d69-fa07-5162-a859-1821c1f33c83 | checkpoint | 1.4 - Heritage / Cultural listed areas: (2)
aa5e5762-73d7-5990-869a-eae524283d11 | note | EXTERNAL REFERENCE: Hold Point (HP)
c0716d5a-f08e-5685-94f9-d746f9de8103 | note | ACTIVITY / DESCRIPTION: Tourist attraction
fb3f411a-7165-5bd9-81c8-65d0947b8412 | date | Date:
aee433d7-f9d4-5a4f-902c-18a076f853ea | signoff | AUTHORITY HOLDPOINT
a298a41a-792b-5625-a33c-1452f9cb50bd | checkpoint | 1.5 - Protected Environment (1)
c3537a7b-f353-5fa5-9655-321eb8f210b2 | note | EXTERNAL REFERENCE: Hold Point (HP)
d36c54d2-7b0e-55a0-96df-a1570770f991 | note | ACTIVITY / DESCRIPTION: Flora
63416b39-c036-5c4f-9cdd-9efbf878ddc8 | date | Date:
949e8670-1ad1-5759-9628-d18b3962f15b | signoff | AUTHORITY HOLDPOINT
14b01889-e344-5ade-881d-9527443df828 | checkpoint | 1.5 - Protected Environment (2)
e374ec65-344d-5f55-9163-0363f1fc82c8 | note | EXTERNAL REFERENCE: Hold Point (HP)
6874e82f-7eb2-55a8-a9e5-dca3b0fb7d8d | note | ACTIVITY / DESCRIPTION: Fauna
5628aec3-4ec4-5365-a8b6-d9c417458b93 | date | Date:
a806cca3-0da1-5f3e-9137-e49511e13742 | signoff | AUTHORITY HOLDPOINT
9628fbb0-5e58-51a7-9e83-e306352b1d2e | checkpoint | 1.5 - Protected Environment (3)
ab221c3f-e8c1-5fcc-9705-0d3c8e189157 | note | EXTERNAL REFERENCE: Hold Point (HP)
f016b3a2-6fac-5fc4-8857-7be2cfcc15e3 | note | ACTIVITY / DESCRIPTION: Water bodies
07f39192-f364-5554-8b65-d980b885953a | date | Date:
23d31775-434a-5394-a319-b2592be213ab | signoff | AUTHORITY HOLDPOINT
630240bb-14e8-5749-b2d2-8954a78b695c | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (1)
e0f4292e-52b6-5e42-a758-b0de3e089e54 | note | ACTIVITY / DESCRIPTION: Dial Before You Dig
1e1eb03f-76ab-5ba0-855e-bcb622315ec9 | date | Date:
f80fb2ce-63a3-5385-8539-29badaf7c2ff | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (2)
2e00c3ff-cbe8-5c74-af86-841465f410a7 | note | ACTIVITY / DESCRIPTION: Excavation Permit
2aec04a3-0aad-5ac9-b793-83d1ef151c2b | date | Date:
d73a1703-5ab5-59f1-80c1-317204987232 | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (3)
7533acb9-6cc7-596c-a296-26e31d51c11a | note | ACTIVITY / DESCRIPTION: Assess and arrange for Service location
13f705f3-bf35-53d8-8ca7-e84941343889 | date | Date:
09e8a0bd-1f3d-57f6-803b-0f48aba10250 | section | 2.0 - Pre-Commencement Checklist
09a2b3de-027a-5601-938e-5db460546be8 | checkpoint | 2.1 - Traffic Items (1)
55c62a7f-b4ab-5f3c-8def-280e4c917421 | note | ACTIVITY / DESCRIPTION: VMS boards
6ac3d201-2c28-52a7-a8b2-90c414058ae2 | date | Date:
931e4db6-fa85-551c-872e-381357d7b596 | checkpoint | 2.1 - Traffic Items (2)
5b9dd624-ae8f-581b-8874-6c737a56c425 | note | ACTIVITY / DESCRIPTION: TGS/TMP, MoA
ec18bf29-de58-576d-aabb-a088bed6a4ad | date | Date:
3e705a2f-43de-56c5-aae9-2a8b1cd1a773 | checkpoint | 2.2 - Site marks / references (1)
502435bf-bca4-55cb-b6da-3dd2a6dd1dcf | note | ACTIVITY / DESCRIPTION: Limit of Works
1705a55f-e283-55eb-a225-cf0b20ff39c8 | date | Date:
bf5a2eb1-6f6d-5986-969f-ed0f8c70bb23 | checkpoint | 2.2 - Site marks / references (2)
ce62becc-d90c-520d-97b2-d9ebc15c1536 | note | ACTIVITY / DESCRIPTION: Survey control point
1477e2f0-75ce-520a-97a9-db697eb6aa70 | date | Date:
7819aa13-83a6-56e0-82dc-67161b9a9b76 | checkpoint | 2.3 - Services, inspect/identify clash points: (1)
1de60d9c-e7ab-5885-a3f6-0366865fff98 | note | ACTIVITY / DESCRIPTION: Sewer, Water
f335f453-2ac9-58b4-b6b4-18bc46f26df7 | date | Date:
7296f66a-8e76-5871-9283-a9a21e7e8d25 | checkpoint | 2.3 - Services, inspect/identify clash points: (2)
c6d0efd6-f8c1-556b-9d3d-ae7f2b631821 | note | ACTIVITY / DESCRIPTION: Gas, Electricity
102be5f6-8768-518c-93a3-a2c773473a8f | date | Date:
9a0fcc69-3668-5c15-a6ca-91ededf6fc07 | checkpoint | 2.3 - Services, inspect/identify clash points: (3)
75076475-3b85-5121-ac0c-03db0e1eef54 | note | ACTIVITY / DESCRIPTION: Telecommunication
14f8a3e3-f9ec-5544-b28d-605ec91d8327 | date | Date:
a24228fa-78b8-5c90-88b4-ffc9700be614 | checkpoint | 2.3 - Services, inspect/identify clash points: (4)
5f3060bb-3bb1-5591-b921-d4f59a6a92a6 | note | ACTIVITY / DESCRIPTION: Drainage (ie: council/shire, Other state authority)
de24c3b0-6b49-5f90-8428-2c576569d3e0 | date | Date:
b48da278-70f9-5760-8050-ae93342082fa | checkpoint | 2.3 - Services, inspect/identify clash points: (5)
5cd070f3-4bc2-5d15-82ac-70e37c344a84 | textbox | ACTIVITY / DESCRIPTION: Other specify:
50d772c2-4165-5d56-8320-9c86a7d20b54 | date | Date:
9f5df32c-0781-554e-ab01-a593e7fcb3b0 | checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (1)
74683223-37ac-5f0b-9dc8-c59bbbb49457 | textbox | ACTIVITY / DESCRIPTION: O/H and U/G services flagged "No Go Zone"
082b5cea-cbd9-5d32-b47a-12a91485a800 | date | Date:
e3efc0a8-16a5-5596-84a1-1e66adf6bd04 | checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (2)
2d9b5ac8-2932-551d-afe9-cce406feb1b8 | textbox | ACTIVITY / DESCRIPTION: Trees(s) marked and approved for trimming or removal
6ddf181a-e8b1-5fc9-ab3d-1f6b4ab98b3e | date | Date:
68a4a80a-b84c-5ad0-bb9b-33814848d601 | checkpoint | 2.5 - SWMSs reviewed: (1)
91edcc50-d584-52ff-9a80-5cf97676facd | textbox | ACTIVITY / DESCRIPTION: Site-specific
f484d58c-c0a0-5b74-9e0c-44d3b5f26fef | date | Date:
14fc9cb2-1963-5087-af52-96411e05c1d0 | checkpoint | 2.5 - SWMSs reviewed: (2)
b108d9a3-d755-5fe7-a3ce-9b4c144ed150 | textbox | ACTIVITY / DESCRIPTION: Spotter required / arranged
241f3d92-8abd-5760-a197-07485a7903e6 | date | Date:
4bbdbbcd-53e6-582b-9ebf-412a8a2c384b | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (1)
000ad7b0-a0b3-5691-adc5-5fdb50559397 | textbox | ACTIVITY / DESCRIPTION: Sight and Clearance Distances:
49c34f83-a82c-5d2d-99ae-76a827d686e7 | date | Date:
4fb3fe3d-2615-531c-894d-134d05fa9e44 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (2)
845fa20d-5809-53bd-a769-4e8cf144dca5 | textbox | ACTIVITY / DESCRIPTION: Stop-slow areas, spotter, slips, confined space/work at height
8d29808c-5f6e-5d17-ab5d-12701fcc7f8a | date | Date:
07c218e2-d218-5982-b0c6-77b42e57d30e | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (3)
da8e0f5e-1206-53be-ae77-1b48e2a2c06f | textbox | ACTIVITY / DESCRIPTION: Vehicle access to properties
42516fb7-f459-51b6-a80b-3d181e45b9cf | date | Date:
5f33f279-b1ef-5404-a4c7-074c9bcea778 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (4)
5e983dd6-62b6-5c14-abdf-4a9d516d310a | textbox | ACTIVITY / DESCRIPTION: Proximity to Services: clearance requirements
78bb6672-239a-5d14-9e90-b6fff32dfc28 | date | Date:
81b2c664-740d-5448-bd1a-fdae47df441c | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (5)
e5327478-ff3b-525b-9d22-e123465c38a6 | textbox | ACTIVITY / DESCRIPTION: Proximity to Water: supply point, watertable/dam/river/coast/port
73da7c40-9c91-5b8e-8574-8dfb3ce76381 | date | Date:
abb4d79d-c3ff-5250-bffc-b4ead813a58b | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (6)
9b5ae601-5c84-5742-862a-02d344119001 | textbox | ACTIVITY / DESCRIPTION: Site compound/Plant parking, material stockpile area, "dumpsite"
de3f3c7e-21fa-52b6-8b20-c9dea9d405fa | date | Date:
d7be73a1-96ee-543f-9d6a-da9f3eb56961 | section | 3.0 - Construction
04c6e6f5-8a7c-53ba-8fb8-508a095038bb | checkpoint | 3.1 - Vegetation Removal (1)
c4f91f9b-460b-5bf7-9724-1d68269b5fd8 | note | EXTERNAL REFERENCE: Hold Point (HP)
9a06f88c-d3ba-509b-94eb-73443c6aa6a3 | note | ACTIVITY / DESCRIPTION: Spotter, Traffic Control
24caba61-85bc-5159-b0ec-72a77a683fad | date | Date:
91426355-0c6c-5b3d-8fc1-c9d9c1668208 | signoff | AUTHORITY HOLDPOINT
a473aca8-8c79-5fdf-b4fe-14896a29f1ac | checkpoint | 3.1 - Vegetation Removal (2)
2440ce69-0b95-549f-bf60-60b1909778d8 | note | EXTERNAL REFERENCE: Hold Point (HP)
87e8fdf3-58d0-5c59-bdc3-c912e2382397 | note | ACTIVITY / DESCRIPTION: Equipment, Access
9b81ac8f-b070-5323-9dca-acfbdb427325 | date | Date:
eb97adb4-1c8a-5365-8fd4-42fdba865a40 | signoff | AUTHORITY HOLDPOINT
56872da4-6472-5b90-9b0f-7b3c2c13ff4a | checkpoint | 3.1 - Vegetation Removal (3)
ccf59e41-4ab4-5852-a208-c13193b332ce | note | EXTERNAL REFERENCE: Hold Point (HP)
d042cc4b-aab0-544a-85f7-80f1ce6852a5 | note | ACTIVITY / DESCRIPTION: Soil erosion / water contamination
c63da54d-4452-5d56-aa26-80f408262e25 | date | Date:
5d04e02c-f31d-5f78-8848-826fc6d3d926 | signoff | AUTHORITY HOLDPOINT
d175339a-b6c9-5d40-82f7-b0bd4fa0651d | checkpoint | 3.2 - Contaminated Materials
f1271195-0f83-5568-b48c-aea50c41dd87 | note | ACTIVITY / DESCRIPTION: Contaminated Materials
ffafd4b5-54da-5bfe-801d-00e309038cf1 | date | Date:
4905149c-6cd5-553c-aa53-f8dd9f9209f8 | checkpoint | 3.3 - Traffic Items (1)
d3430d21-a698-50e9-8359-dc7188cd9a6e | note | EXTERNAL REFERENCE: Hold Point (HP)
52a94787-19b2-56c7-bb15-816a2990cbb0 | note | ACTIVITY / DESCRIPTION: External review: Road Safety Audit
70f42a74-ee1e-5d54-b8b0-1cde5b68b86f | date | Date:
857609ba-bcdd-52e5-9966-247a1e7ab2bd | signoff | AUTHORITY HOLDPOINT
4353c527-d5de-5bc4-8839-7a2a00fb9a79 | checkpoint | 3.3 - Traffic Items (2)
ec7ce81c-2ad7-50f3-9cbc-9f01a126af9d | note | EXTERNAL REFERENCE: Hold Point (HP)
580d0e38-7fdd-5696-a5d5-495e0cc60140 | note | ACTIVITY / DESCRIPTION: Internal review: adjust hold-time (traffic lights / traffic controller), flowbias, identify peak-hour period(s) / public transport / rubbish collection
c346f444-f86f-59e7-8e38-9f9909100dbd | date | Date:
18c5c9bc-dbb1-50b3-b62a-b4a9a6c31ec6 | signoff | AUTHORITY HOLDPOINT
023cd8e3-0a57-5f46-ab79-677a60bbcaea | checkpoint | 3.4 - Trenching works (1)
941db789-7b82-594b-bb6b-fcef0d6edb67 | note | ACTIVITY / DESCRIPTION: Review escape plan (routes)
6d62af35-d0f5-5ef6-b239-b452fd3decb6 | date | Date:
61f48a8a-fa99-5641-bbfe-b6f60ea0f347 | checkpoint | 3.4 - Trenching works (2)
b4ecbe1d-c4f4-56b2-aeff-6efdc65fdd2b | note | ACTIVITY / DESCRIPTION: Review ground / water conditions
619cc4c2-86a0-5d57-897a-31c5d6c53318 | date | Date:
50b067dd-e199-593f-948b-da80c5a99b37 | checkpoint | 3.4 - Trenching works (3)
540cea3b-7a41-5fa6-9f28-8540567fd217 | note | ACTIVITY / DESCRIPTION: Indentify Shoring / Benching requirements
12f019cc-0473-5500-a16e-4c48b4fd9135 | date | Date:
6e76b710-f980-5558-8431-29ac043efdf9 | checkpoint | 3.5 - Drainage Works (1)
206c1000-b617-500b-9644-e5b5617da94c | note | ACTIVITY / DESCRIPTION: Assess surface-water impact – flow-path / catchment / outlet
70024a33-18da-5be1-9e03-818c3b557391 | date | Date:
29c04c64-77ba-5d73-8906-4be090479ace | checkpoint | 3.5 - Drainage Works (2)
d8430f2c-7145-59d6-b01b-4d49402c154c | note | ACTIVITY / DESCRIPTION: Surface drainage (swale drain)
1e06ce8b-b227-5e32-b27a-c39c24c7bb90 | date | Date:
167a25d9-c42d-5c43-97ff-75a7dd8e647d | checkpoint | 3.5 - Drainage Works (3)
4cce8002-4d20-5487-8f39-429bf484f752 | note | ACTIVITY / DESCRIPTION: Sub-surface drain pipe and aggregate (agricultural drains / "agi pipe")
33acb2dc-5580-585c-86fc-a0d62281f5ab | date | Date:
0fbcb240-f41b-5f68-8c33-171bac159531 | checkpoint | 3.5 - Drainage Works (4)
ea0ce010-f16e-5655-b25a-79d53b30ded2 | note | ACTIVITY / DESCRIPTION: Review confined space entry
f6040a37-cd0a-5d2b-b12f-5777b19c46ac | date | Date:
3726bf23-5745-5680-8666-551d87ab6950 | checkpoint | 3.5 - Drainage Works (5)
055373e2-fcd2-5867-bae6-c62a3c9a7c4e | note | ACTIVITY / DESCRIPTION: Review lifting methods (load / equipment / plant / crane)
f396fea9-8948-5986-a2e1-3320dc2bbc80 | date | Date:
cfbebd2d-684d-51d0-9413-db270416aa3f | checkpoint | 3.5 - Drainage Works (6)
e5e82d46-11a8-5768-bb45-772759095f7e | note | ACTIVITY / DESCRIPTION: Levels
00326889-24e1-507e-9670-084aaf6e1b9c | date | Date:
7a26beac-4d87-59a2-a1e4-9fa8e1ed4230 | checkpoint | 3.5 - Drainage Works (7)
4398c1aa-7394-5b74-b0bf-a13b96671e33 | note | ACTIVITY / DESCRIPTION: Pit covers / Grates
e659082f-e4d6-5e1d-a61b-b6414277833e | date | Date:
9d8eb224-efef-5f72-bfe3-0050bdec094e | checkpoint | 3.6 - Structural Items (1)
3b525321-4f28-5639-add6-31ec82bc5df6 | note | EXTERNAL REFERENCE: Hold Point (HP)
be017c29-8f47-5668-bdae-a8405425460c | note | ACTIVITY / DESCRIPTION: Crown units / culvert
395b34ca-3ed7-5d85-be46-515ca8a56d07 | date | Date:
103f0129-b32e-57c2-af8b-a3f7add75fec | signoff | AUTHORITY HOLDPOINT
18eff7e7-e534-53e5-b1b2-f8c8a887abee | checkpoint | 3.6 - Structural Items (2)
caeee054-0a9f-552c-80b4-84f23d4ffd26 | note | EXTERNAL REFERENCE: Hold Point (HP)
43028459-d569-558f-948f-38217645075c | note | ACTIVITY / DESCRIPTION: Retaining structure works
807220dc-dd15-50c5-a8fc-c003c6fae476 | date | Date:
981296d4-9984-5161-a3ec-e5b6a05eedaa | signoff | AUTHORITY HOLDPOINT
a3537f1a-55ea-5962-bff5-bd495d5b3602 | checkpoint | 3.6 - Structural Items (3)
0df10fa0-c833-55e1-9193-0d7a4569cbd7 | note | EXTERNAL REFERENCE: Hold Point (HP)
303a4d60-fb15-5276-81ad-fab2e818ecb3 | note | ACTIVITY / DESCRIPTION: Bridge works
a8c8c7d3-a0f9-557d-86f0-ec9e894e650e | date | Date:
35993f22-ecb4-5eab-a0ae-5e4ce3edbe9f | signoff | AUTHORITY HOLDPOINT
4a190e24-251a-540e-82fd-c505ec372a23 | checkpoint | 3.7 - Concrete kerb works: (1)
85ba550e-6b28-5857-bc5e-ccbab8a99472 | note | ACTIVITY / DESCRIPTION: Alignment / level
ad6260d7-5ed9-59c9-acbc-d5ce0a530454 | date | Date:
afca6eb2-42e9-5871-a25d-9b2186c4710a | checkpoint | 3.7 - Concrete kerb works: (2)
196e60b1-5cf7-5548-a2a2-2f21dce71563 | note | ACTIVITY / DESCRIPTION: profile / finish
81cc87f6-e6c0-5e62-bc6d-46af70cb2f8e | date | Date:
7e73f34b-3b8d-56ba-85f1-8b0acbff2d39 | checkpoint | 3.8 - Concrete Works (1)
401cdf12-25f0-5fd8-9ee9-30975c3b2303 | note | EXTERNAL REFERENCE: Hold Point (HP)
12a4338e-180e-5542-ae61-a968ebe17b5a | note | ACTIVITY / DESCRIPTION:
30e9d4f6-b44a-5cd4-9e38-c9188dca2b01 | date | Date:
c47414f3-fa1c-50a3-8a33-3606072f8375 | signoff | AUTHORITY HOLDPOINT
02765cad-de6e-46a3-9a1b-e3f0c5053b0d | checkpoint | 3.8 - Concrete Works (1)
50a1f3c8-852d-5f7d-a90f-bbe760fbedbf | note | EXTERNAL REFERENCE: Hold Point (HP)
b8b5e787-b8a9-522f-bc42-7971fc89dbbd | note | ACTIVITY / DESCRIPTION: (in-situ & pre-cast) - Bedding material / blinding material
c90c15f0-ebc6-556f-a851-79e244f671c9 | date | Date:
9c56dcf1-b717-5818-a50f-ccce242b4a1c | signoff | AUTHORITY HOLDPOINT
0c625859-86f9-5ab1-8026-930a4904a79f | checkpoint | 3.8 - Concrete Works (2)
3d269fdf-cde3-5045-b197-b495c7bf1264 | note | EXTERNAL REFERENCE: Hold Point (HP)
1f8d3ea8-ab2f-5a5a-8252-be864ae88514 | note | ACTIVITY / DESCRIPTION: (in-situ) - Formwork, duct-work
8f5b6cbd-ad5a-5282-b1f1-8450ee22c61c | date | Date:
2371a583-9885-5764-b61b-e0237cf48e85 | signoff | AUTHORITY HOLDPOINT
6ef3bea8-ad11-53ff-87b1-4cead0bd366b | checkpoint | 3.8 - Concrete Works (3)
f8c6660a-0b26-5d62-98ea-ddc73be56ed4 | note | EXTERNAL REFERENCE: Hold Point (HP)
e1f3c380-ce16-557f-9480-15d08544bce7 | note | ACTIVITY / DESCRIPTION: (pre-cast) Alignment/dimensions
f7e3ff3c-d599-5193-8553-3425282b40b2 | date | Date:
993f861b-8184-575d-a544-05aa52939e09 | signoff | AUTHORITY HOLDPOINT
c1dbc150-73c9-5965-80c0-2f873810e14c | checkpoint | 3.8 - Concrete Works (4)
538b3710-fbf1-576a-9efb-9cda272d4314 | note | EXTERNAL REFERENCE: Hold Point (HP)
14e24089-3285-5a04-be40-c2f11bbf4886 | note | ACTIVITY / DESCRIPTION: (in-situ) - Rebar layout
b1c808e3-525b-5745-880b-ed644c29343e | date | Date:
e6bfc1c5-771c-5a8e-9052-3af4acdb8bc2 | signoff | AUTHORITY HOLDPOINT
942dfb61-1ce6-5e95-8cfc-77270dad5ca4 | checkpoint | 3.8 - Concrete Works (5)
4362a75c-8d17-58f2-a2b9-37e835138dc9 | note | EXTERNAL REFERENCE: Hold Point (HP)
517c09cb-52a7-55c1-af1d-c19b4061c574 | note | ACTIVITY / DESCRIPTION: (in-situ) - Concrete mix / Compaction / Placement method(s)
ba98caf0-cd34-5675-a817-86ab1e308f91 | date | Date:
311b0aa1-f9bc-5a84-a199-e568fd5128ba | signoff | AUTHORITY HOLDPOINT
01d97373-6e1a-5d6e-a4f2-840588cfd4c7 | checkpoint | 3.8 - Concrete Works (6)
bab3caaf-3e29-5150-9f97-102d3d7e3f11 | note | EXTERNAL REFERENCE: Hold Point (HP)
b0f820c0-a955-5788-bfbb-884b9b202c56 | note | ACTIVITY / DESCRIPTION: (pre-cast) - Lift points / placement method
2088c290-f00d-5619-969f-6f3235b7382d | date | Date:
9d766382-17f8-52ba-9eee-e55f692560e3 | signoff | AUTHORITY HOLDPOINT
7d7720d5-504d-5ab0-b356-0cd8ce894f2c | checkpoint | 3.8 - Concrete Works (7)
dfe49555-ae54-5b30-b62e-f56301f61a2c | note | EXTERNAL REFERENCE: Hold Point (HP)
d03928cd-fe9d-5ac9-b157-dcd34632c6ea | note | ACTIVITY / DESCRIPTION: (in-situ & precast) - Pre-stress works (where applicable)
ed14191b-2a26-5984-b326-bb45015ed9c3 | date | Date:
51f5e363-c5b1-50af-a638-b352658a5b58 | signoff | AUTHORITY HOLDPOINT
bedaf76c-4d8b-5d5e-8d2f-fa65048a13a4 | checkpoint | 3.8 - Concrete Works (8)
8884b095-83d5-5ce6-8d8d-80eaf4306d63 | note | EXTERNAL REFERENCE: Hold Point (HP)
17cf4daa-0a6f-5fb4-9b7c-5f129acf634d | note | ACTIVITY / DESCRIPTION: (in-situ & precast) Finish
6e271065-4fde-52f2-8ee8-97b76b48f1f6 | date | Date:
354cc997-dc12-595c-9a05-016bebf4b960 | signoff | AUTHORITY HOLDPOINT
93698472-379c-5500-a64d-b7a3cb16f38e | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (1)
e73589a9-ec36-54cd-9029-5ee29ce1deec | note | EXTERNAL REFERENCE: Hold Point (HP)
1b3a26cc-7010-5158-ab72-bbdbee1bd096 | note | ACTIVITY / DESCRIPTION: Require in-situ testing / laboratory report (where required)
75b4e119-6301-5b94-b8ce-839b4666ce1f | date | Date:
6bc4eedf-e450-520b-bfaf-d5317605fe58 | signoff | AUTHORITY HOLDPOINT
dcb10286-482f-510a-982d-dfd99d52eddb | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (2)
8b2306d3-92b6-5476-83a2-281a1b1190f1 | note | EXTERNAL REFERENCE: Hold Point (HP)
e70bb6c6-d7ea-5908-a5dd-e5a62cd09130 | note | ACTIVITY / DESCRIPTION: Material dockets (ie: Lime / Cement)
f937da68-feb6-5804-b46e-17e5c22c049a | date | Date:
12e36667-97e2-5e02-aefe-014aab282531 | signoff | AUTHORITY HOLDPOINT
53406d98-ee22-59ae-8672-fac588b98ff4 | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (3)
90496a06-77d2-58e8-a89d-fb4b7d1f7ecf | note | EXTERNAL REFERENCE: Hold Point (HP)
6bce577a-706e-5a14-aafe-da3385ac4755 | note | ACTIVITY / DESCRIPTION: Density results
c1445df0-8e52-5f7f-96e1-74811d8d9e30 | date | Date:
8b042285-4fe9-5d5a-b6ad-5abf9e9e0d5a | signoff | AUTHORITY HOLDPOINT
5a27f415-647a-5b80-8931-502afee8cc56 | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (4)
e51627c3-a02b-5a2c-867d-795095cde3c8 | note | EXTERNAL REFERENCE: Hold Point (HP)
fd110d90-715a-5e18-9914-c7a94602cd50 | note | ACTIVITY / DESCRIPTION: Proof-roll
f3628880-a322-519a-a4fb-4d030a922d59 | date | Date:
5a9332b9-2fb9-5487-9b70-34c59a2f3316 | signoff | AUTHORITY HOLDPOINT
aae52039-2989-5bd7-9b81-6683ad24c2ea | checkpoint | 3.10 - Pavement Works (1)
b0e21f3b-781c-567f-9184-cedcd7dba172 | note | EXTERNAL REFERENCE: Hold Point (HP)
5b32bd42-1cfa-5ce5-b6d4-e6b7b8432557 | note | ACTIVITY / DESCRIPTION: Density results
981e0eb1-3b86-5839-a78d-f4ca87dddfb8 | date | Date:
3ca88ab2-46fa-5c97-8abb-c033f56603d6 | signoff | AUTHORITY HOLDPOINT
1ac8e438-da3c-51af-a12d-c6c12c6d4be1 | checkpoint | 3.10 - Pavement Works (2)
de3488c1-cb69-51df-9b46-9083c7620eb3 | note | EXTERNAL REFERENCE: Hold Point (HP)
4460a507-b9c6-5ecf-94c7-151aeee07db0 | note | ACTIVITY / DESCRIPTION: Proof-roll / Test Rolling
13da7516-ddc1-5ea8-864c-3925ea208098 | date | Date:
842111af-844a-5ca6-b2df-690c4ede6adf | signoff | AUTHORITY HOLDPOINT
5b55a4f2-7c30-57f3-928c-f1d66d85f6ee | checkpoint | 3.10 - Pavement Works (3)
7f373744-f16a-59ab-8365-8d1b2626e0d1 | note | EXTERNAL REFERENCE: Hold Point (HP)
ebf648f9-2a90-524a-9a17-27d3e7fcc4ed | note | ACTIVITY / DESCRIPTION: Dryback results (NB: required prior to sealing works)
447c7ffb-ccd8-547d-8638-4bf69813c694 | date | Date:
19b8ffce-c57c-5d26-8996-ccd499fa3e7d | signoff | AUTHORITY HOLDPOINT
0c75ec88-90e7-5b67-91ca-be734b9d492e | checkpoint | 3.10 - Pavement Works (4)
3fef4dd5-2ef3-59f8-927a-73fce94b43d5 | note | EXTERNAL REFERENCE: Hold Point (HP)
cf83917c-4162-5eb0-8ed4-456ddbf42093 | note | ACTIVITY / DESCRIPTION: Ball Penetration Test
7f10fe4e-729a-547e-a479-92f014ea1436 | date | Date:
7bf6d8fa-9777-541d-8864-153db73b402b | signoff | AUTHORITY HOLDPOINT
3518b0fc-b416-527c-82c1-27c1de20e1e9 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (1)
d038a06b-3e2a-5e9c-bf71-de2b832e1b7f | note | ACTIVITY / DESCRIPTION: Level & Location (ie: clearance requirement)
43daad50-b548-5b48-a1ad-7365ecc21eef | date | Date:
735aab93-d698-5845-afa5-724bacfe6674 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (2)
575b00ff-78d5-57f8-a161-2d17d6d112c3 | note | ACTIVITY / DESCRIPTION: Approved equipment for installation
765441c7-7694-5c75-a283-4c365041838c | date | Date:
42559c48-cc6d-5a80-9fd0-9a5d9976d007 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (3)
a46320d2-7f1e-5097-a48d-6447073a73da | note | ACTIVITY / DESCRIPTION: Pit and conduit (ie: clearance requirement)
561ad1d9-de3b-57fe-9f7f-e9a880990643 | date | Date:
279cfb92-5524-5ca3-9b73-71d938404b24 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (4)
25963336-1eba-572e-b0e9-e5b299512e7c | note | ACTIVITY / DESCRIPTION: Audits by relevant authority / hand-over procedure
3e25cae7-33e3-5629-9827-724e49802f46 | date | Date:
22d5166f-e1df-58fd-992e-efada75e8532 | checkpoint | 3.12 - Pavement Surface Works (1)
b6eaf2b8-9418-57ed-b6c3-2eacb3f58fb4 | note | EXTERNAL REFERENCE: Hold Point (HP)
0ab970b0-5923-5246-afca-a41d27053472 | note | ACTIVITY / DESCRIPTION: Seal (ie: suitable material, spray-sheet details)
b377244e-049f-565e-b5ab-9b6c17b108f6 | date | Date:
bdd95225-7f71-5084-a039-d89b440aac6c | signoff | AUTHORITY HOLDPOINT
951b0751-eecd-5a60-8068-307cf2f4f0ed | checkpoint | 3.12 - Pavement Surface Works (2)
b846e4a9-d9b0-5d0f-8d23-23db84ef0d0c | note | EXTERNAL REFERENCE: Hold Point (HP)
9bf5d3da-5e55-5f80-8075-102e2cd4bdbd | note | ACTIVITY / DESCRIPTION: Asphalt (ie: material dockets)
96810742-a4c1-5113-a84e-f2d7a6584165 | date | Date:
e89a9cc3-79c2-5186-8847-3e0b1bbc5103 | signoff | AUTHORITY HOLDPOINT
97379716-9c47-5d54-812d-47cf5b06c392 | checkpoint | 3.13 - Landscape (1)
398e27fa-a911-566f-a856-c1ead55abbe6 | note | ACTIVITY / DESCRIPTION: Seed / Grass
2afa04d7-980a-5c03-b9a5-80f631a38a8f | date | Date:
7b886802-0d02-5a9f-9ad8-da4205e6e194 | checkpoint | 3.13 - Landscape (2)
087d861a-ac33-5a99-9133-2da489077fdb | note | ACTIVITY / DESCRIPTION: Hydro-seed / Hydromulch
ced50251-08f1-5808-a1b4-ff6e82306766 | date | Date:
cf35ef9b-77b8-5179-9be8-dc768c2d627e | checkpoint | 3.13 - Landscape (3)
851c9681-9923-5889-8551-1992519214c2 | note | ACTIVITY / DESCRIPTION: Street furniture
52496859-46bb-5845-886a-71886ad7d6ba | date | Date:
906c7998-319d-50c7-bb07-c155bca1e8b3 | checkpoint | 3.13 - Landscape (4)
307cf2ee-fa00-58a1-8d27-d9f5b40676fe | note | ACTIVITY / DESCRIPTION: Maintenance arrangement / period: 3 / 6 / 12 / 18 / 24 months
3d76ca1d-49f4-530b-ae11-4b845347c14c | date | Date:
6617e321-c217-5ab8-9c71-9bd7fc26c64b | section | 4.0 - Practical Completion
6fb7bb23-6dc6-5cc1-b38f-5d21fc3731e0 | checkpoint | 4.1 - Road Fixtures (1)
a78b448f-3d6b-5115-bf91-68755dbd1d50 | note | EXTERNAL REFERENCE: Hold Point (HP)
491ff107-7508-5ded-bcd7-46dc66d1889c | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
c3234fb8-5a01-54b2-8c31-df4d3772bb61 | date | Date:
ed95d064-cbff-54e7-a314-1d9a50b260ce | signoff | AUTHORITY HOLDPOINT
cda61ea7-d8bf-531b-93e6-b76ccc167a28 | checkpoint | 4.1 - Road Fixtures (2)
68e0deb5-ff03-5ad4-a55e-aa978e856497 | note | EXTERNAL REFERENCE: Hold Point (HP)
4c2e81e9-4907-5868-b8d1-d123752e8ef6 | note | ACTIVITY / DESCRIPTION: Signs
2b632d02-8e86-56ae-9497-1942b780189c | date | Date:
0d76150a-4665-56d4-b923-0760dac6a411 | signoff | AUTHORITY HOLDPOINT
a18bf6e9-148e-5c29-8561-db6238147f98 | checkpoint | 4.1 - Road Fixtures (3)
8460d55e-5f83-5331-ab37-22230156ea0b | note | EXTERNAL REFERENCE: Hold Point (HP)
88345f33-bc9b-505b-98a5-80a9327974ed | note | ACTIVITY / DESCRIPTION: Guide posts
30bfad2f-388f-5f9b-92ba-6d644b77d9e8 | date | Date:
1cd99bde-61ac-5002-9398-3902940ed822 | signoff | AUTHORITY HOLDPOINT
c5695b91-8cf4-572e-9c57-e58004694939 | checkpoint | 4.2 - Safety Barrier Works (1)
45a477e3-6218-5f97-9aec-324bc41f1015 | note | EXTERNAL REFERENCE: Hold Point (HP)
f7ea3589-d893-5f22-8fb1-b84637152666 | note | ACTIVITY / DESCRIPTION: Guardrail
f44c2698-72a0-5bb0-9da0-24d0e9af787d | date | Date:
bf5b8e40-7255-5a5a-9db0-6401fbe79e5a | signoff | AUTHORITY HOLDPOINT
30a71c59-ad05-53e3-a7f9-1e1c56e4a846 | checkpoint | 4.2 - Safety Barrier Works (2)
5816b8bc-7785-502f-93d7-b22dd3287534 | note | EXTERNAL REFERENCE: Hold Point (HP)
6d99b1d0-3c0e-52c2-b183-fbdcf96608c4 | note | ACTIVITY / DESCRIPTION: Wire-rope
d834a3c0-472e-5f71-a98c-db0213e7605a | date | Date:
0d3e1168-a42c-5219-bba7-8cee3a7a2f5c | signoff | AUTHORITY HOLDPOINT
791b0a0c-dbb3-540d-a589-69fa39a4913c | checkpoint | 4.2 - Safety Barrier Works (3)
95c4c178-aad0-5b49-958e-e6d0d0d481b1 | note | EXTERNAL REFERENCE: Hold Point (HP)
2d487db0-bf78-5a7f-ad16-57cea40f5505 | note | ACTIVITY / DESCRIPTION: Motorcycle-safe fixtures
c650ada4-30b7-578a-b8e5-f31b1ba00970 | date | Date:
15999a7a-3d03-5469-a6db-913beb6374ff | signoff | AUTHORITY HOLDPOINT
85c5688a-3665-525a-8f0b-51ce1c8ce4ba | checkpoint | 4.3 - Fences and Gates
8912adce-b3ab-5d7e-8c53-a6455556f9c2 | note | ACTIVITY / DESCRIPTION: Fences and Gates
da41faa5-b8d9-57fb-b5a4-91fce97a9ed7 | date | Date:
aeb9f816-a3f8-52f0-b67c-c44686b0b735 | checkpoint | 4.4 - Quality Ride Test
6930f8cd-1a69-5aeb-8223-009d731a03c5 | note | EXTERNAL REFERENCE: Hold Point (HP)
b7076034-b179-54d3-a933-b8d5ceb054f0 | note | ACTIVITY / DESCRIPTION: Quality Ride Test
1284124b-0fc7-5008-9461-e2d2bf5cf373 | date | Date:
b7b7d7d0-bf51-5cf5-a92d-4a6fe712f993 | signoff | AUTHORITY HOLDPOINT
329676c7-e061-5a56-a75d-10d228394296 | section | 5.0
c4fa4f04-e0ab-56b5-a9a3-67111a83ef99 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (1)
dff99e57-221f-5d1e-8fb6-c9aafa0555bf | note | EXTERNAL REFERENCE: Hold Point (HP)
8eedd16b-1f11-57f6-9019-0bdbc003a50b | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
09948306-f65b-5d5a-a0b7-328132f80554 | date | Date:
1e0a1d0e-6302-5136-a54b-bb75dad8852a | signoff | AUTHORITY HOLDPOINT
e3e6566b-2b7c-598a-ab84-5aec11baa9d3 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (2)
4bb23012-1b28-5815-847a-52fce7be4eac | note | EXTERNAL REFERENCE: Hold Point (HP)
de297435-d6a4-5eab-9aaa-3271b9fbf73a | note | ACTIVITY / DESCRIPTION: Signs, guide posts
503f7189-fc53-5a4d-86b7-2acb91f9cf01 | date | Date:
779aaedb-5d89-5b6f-bed1-d17c91bd2048 | signoff | AUTHORITY HOLDPOINT
b9dc7589-ae80-5f70-9e0d-40e0324e2287 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (3)
39ec032c-277e-50b6-b1aa-1447b14abf8f | note | EXTERNAL REFERENCE: Hold Point (HP)
91679e6d-2a25-531d-9495-cb4792238201 | note | ACTIVITY / DESCRIPTION: Seal / Asphalt surface
136e4b81-c14c-55b1-91b7-266d280b636a | date | Date:
7292b3de-8ed0-5de7-ad30-40502dd9d94c | signoff | AUTHORITY HOLDPOINT
aae25a75-f669-5e45-8fa4-48bcb753eec5 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (4)
fbce7819-e701-5581-a44f-36c502e9a0d9 | note | EXTERNAL REFERENCE: Hold Point (HP)
4d3ba9f5-d460-5173-b974-75d6edf1a06f | note | ACTIVITY / DESCRIPTION: Landscape (where applicable)
e560aa7e-540e-5ad9-9d8b-16f7d9db106c | date | Date:
7221322e-81a1-5f8e-9f03-5fd99ff21a58 | signoff | AUTHORITY HOLDPOINT
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
30e35763-5253-53b3-a77e-c12431fd0cb6 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
cb9f02e9-9908-55ca-8cd9-4341da118c0d | textbox | Print Name:
d84717bd-2a80-5c3a-b881-8158314def49 | textbox | Position:
0f7b88f2-0a7d-540b-889a-2ecfe760bed4 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-001- Type 2 Rock Beaching | itp | ITP-001- Type 2 Rock Beaching |  | e367927c-9d04-40f5-a566-8d5430cbff59
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
808b448a-7737-5d1d-ba60-38d993100bac | note | FREQUENCY: Prior to commencing any activity
2dc4a8f5-0855-53ce-a338-d2df8cd4b88e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
ccaa59aa-676a-547e-83e4-433baafe4478 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
f40cd27a-06d3-59fe-9247-c9de9084967b | note | INSPECTION/TEST METHOD: Visual inspection
02a25b79-bf84-5d2f-bb2a-659daaaa9c26 | note | RECORD OF CONFORMITY: ITP Signed
7886af08-3b14-5775-8198-49bcb526f7a7 | note | HP*
ab4ac7de-d1fa-5c7a-8386-d1dde43e86ad | note | RESPONSIBILITY: Project Engineer/ Site Foreman
19e44794-0bb4-5fd8-855d-75422d4f166d | date | Date Completed:
| checkpoint | 1.2 - Materials
6e343c2b-2022-5340-bddf-d381958ffb15 | note | FREQUENCY: Prior to commencing any activity
0bfe239a-511c-5f10-a66a-b6be291e31ed | note | ACCEPTANCE CRITERIA: Prior to the commencement of work, the Contractor shall nominate the source of the proposed materials, supply specified test results and provide a representative sample for approval by the Superintendent.
60909052-109f-5323-8d67-9e4996fbc769 | note | ○ Rock for Type 2 beaching shall consist of field or quarry rock. The rocks shall be uniform in colour.
7d7d68df-4624-5dd6-8290-4071329a89ba | note | ○ All rocks shall have a mass of between 10kg and 40kg and at least 60% by number shall be over 25kg. Rocks shall be of such size that the layer of beaching is not less than 150mm thick.
1945c9df-3751-5d14-bc4b-83038fdb4b0e | note | REFERENCE DOCUMENTS: 713.03
00f97aae-45d6-5f7f-8fee-8beb2e3d66ac | note | INSPECTION/TEST METHOD: Test certificates, material data sheets and health and safety data sheets
e7dbf6bc-34b0-5895-9af8-1226430a42d1 | note | RECORD OF CONFORMITY: ITP Signed
70c4f4d0-4d7d-5e19-bb01-0b9a02257280 | note | HP
3ed8fd46-b71b-5aee-89a4-712906b8d271 | note | RESPONSIBILITY: Project Engineer/ Superintendent
2937ca18-c369-5cee-bcda-7a7d179dded1 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Submission of Safety Documentation
e06f5721-a45c-5e38-a4f7-66fa9003aef0 | note | FREQUENCY: Prior to commencing any activity
02ea5d7d-59d8-5682-bb56-2162cdc19cd2 | note | ACCEPTANCE CRITERIA: The completed job safety assessment and the Safe Work Method Statement shall be submitted to the Superintendent for review.
9062f5d7-e6cb-55e9-b282-da0e4b4bc3c6 | note | REFERENCE DOCUMENTS: 713.05
f5073265-8cea-58bb-adff-82eec475dbb4 | note | INSPECTION/TEST METHOD: Job Safety Sheet, SWMS
072c5b9f-ea9e-5d7f-bd99-8927b3ba453d | note | RECORD OF CONFORMITY: ITP Signed
e28d574f-b5e4-5c65-87de-d93af05973c9 | note | HP
77f31968-e088-5cc4-beee-2bc98a51a533 | note | RESPONSIBILITY: Project Engineer/ Superintendent
43abe7cc-97f1-5f09-a480-35ebb2e54093 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Construction Works
| checkpoint | 2.1 - Preparation of Underlying Surface
8dcb2449-cd86-5533-9723-bf63e2918bf3 | note | FREQUENCY: Each Lot
be869f7c-7191-577a-836b-abfffbe1da63 | note | ACCEPTANCE CRITERIA: Areas on which beaching is to be placed shall be compacted and trimmed as required to provide a finished surface level of beaching in accordance with the drawings. Any scours or hollows in the surface shall be filled with compacted Class 4 crushed rock
694e75f5-2ac2-5842-9140-186fe668831f | note | REFERENCE DOCUMENTS: 713.04
8e5cd846-7bd4-565a-84dc-050c253836d5 | note | INSPECTION/TEST METHOD: Visual inspection
00667624-b31a-5e5c-8564-870827618376 | note | RECORD OF CONFORMITY: ITP Signed
cadd1f59-03aa-528d-83f0-1597f4ff2c0f | note | HP*
8a4f5d0b-908d-5182-9416-2987807456fa | note | RESPONSIBILITY: Project Engineer/
23be73ca-6e19-5f33-bfd6-19d1b4c64b86 | date | Date Completed:
| checkpoint | 2.2 - Placement of Type 2 Beaching
170decde-1e7d-591f-9b5a-151cb225613b | note | FREQUENCY: Each Lot
ef8ebd48-d034-51e0-8d76-5ab7c3c6cba4 | note | ACCEPTANCE CRITERIA: Width of joints may vary between 10mm and 60mm, with an average not exceeding 40mm. Level difference between edges of adjacent rocks shall not exceed 40mm. The joint pattern shall be randon and the joints kept free from debris before grouting.
1b3abdcd-baae-53f0-b6cb-863fa8ba73e2 | note | REFERENCE DOCUMENTS: 713.05
a8a166f1-08db-587f-9121-90fd243e2e39 | note | INSPECTION/TEST METHOD: Visual inspection
51f06767-880b-5f50-938d-03bfc178a059 | note | RECORD OF CONFORMITY: ITP Signed
e4b36c02-5246-5faa-bec4-6b32f0028da0 | note | HP*
19766c38-a9c8-5d6f-8ab6-f35c0762a42c | note | RESPONSIBILITY: Project Engineer/
62fa7e76-1c54-5fa1-9215-f9b1e14df84f | date | Date Completed:
| checkpoint | 2.3 - Grouting
c9633fbe-58de-5f54-9c54-228af0654e28 | note | FREQUENCY: Each Lot
30bcea71-d477-572a-a6ba-5d568a65f1aa | note | ACCEPTANCE CRITERIA: Grouting with mortar shall be carried out when the air temperature is above 5 deg C and work shall be kept moist for three days after grouting.
a0964503-9a23-515a-b1bc-7b2a4c36d294 | note | ○ Joint mortar shall consist of one part portland cement and three parts sand by volume, and be thoroughly mixed with water to produce grout of suitable consistency. Propriety cementitious mortars with equivalent performance may be used if approved by the Superintendent.
d791d360-3204-529b-b7ba-ba1b52b79b55 | note | ○ Grouted rock beaching (Type 2) shall be initially placed on a bed of mortar which infiltrates joints and final grouting shall ensure that mortar is firmly tamped into joints to fill the joints to 20 mm below the general top of beaching level.
b4ce28fc-a011-58a4-89c1-962bcf6da6a9 | note | ○ The joints shall be neatly finished by filling with mortar. The final level of the mortar shall not be within 10 mm of the finished rock surface. Care shall be taken to keep the exposed rock face clean. Brooming of mortar across the face of the rocks will not be permitted.
f372495b-cd86-5ca9-bebe-02479c442d42 | note | REFERENCE DOCUMENTS: 713.06
85d3e9e6-1139-5a16-8b8a-ec31c333bc91 | note | INSPECTION/TEST METHOD: Visual inspection
2e7bcef3-7a29-5454-b888-f6d6690f1aca | note | RECORD OF CONFORMITY: ITP Signed
c48d8e20-2ab6-51c0-ab66-bef86e125a14 | note | HP*
cee11b83-f0f3-5b3d-96d0-fb888187f104 | note | RESPONSIBILITY: Project Engineer/
a8b3a1cc-c5d5-5a6a-b123-f99a87ee20d1 | date | Date Completed:
| checkpoint | 2.4 - Perimeter and Toe Walls
f988f4ed-957f-5e08-bc49-f521301b69e5 | note | FREQUENCY: Each Lot
2b00a095-5e77-5574-a245-b35845510e35 | note | ACCEPTANCE CRITERIA: Concrete perimeter walls shall be constructed around exposed edges of the beaching. Concrete used for this purpose shall be N20 strength grade complying with Section 703.
111eeaa1-39a0-5f3a-8f7e-972382e23e7a | note | ○ Toe walls shall be 300 mm wide by 400 mm deep at the front face and reinforced with L8TM trench mesh top and bottom. The upper surface of the toe wall shall slope upwards at either the slope of the rock beaching or the adjacent verge as shown on the drawings. Side walls and other perimeter walls shall be 150 mm wide by 250 mm deep. The top of the walls shall be continuous with the beaching.
11173686-00dd-5324-85a9-fb9d05470d1d | note | REFERENCE DOCUMENTS: 713.07
c639a46f-01d7-54e8-bc83-257dc79d9c74 | note | INSPECTION/TEST METHOD: Visual inspection
e612eee0-3b13-5a7d-9a5c-84ec640d1a4f | note | RECORD OF CONFORMITY: ITP Signed
ddcfc15b-f735-52a4-9847-5e59df49ef7f | note | HP*
353924fd-2cdd-510e-a9d5-c832770630f7 | note | RESPONSIBILITY: Project Engineer/
c50b084b-568d-52b3-8b8a-d5f9ce73d978 | date | Date Completed:
| checkpoint | Final Inspection
1ceea555-fa52-5f21-bcb1-a88ae1e1b661 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
73b3f4c4-6bc8-54b7-b6d6-848ebfa36ca0 | textbox | Print Name:
29ffe012-f325-5459-9d13-11fa478cabce | textbox | Position:
5ee35848-6155-562d-bb91-337b4a02db6c | date | Date:
| signoff | Sign ITP
| checklist | ITP-002 - Cast-in-Place Socketed Piles (With Permanent Casing) | itp | ITP-002 - Cast-in-Place Socketed Piles (With Permanent Casing) |  | 36b23a47-a532-4ddc-93b8-7b89a09e7d05
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
1b695283-3f3a-5635-95ed-5c92e5efac38 | note | FREQUENCY: Prior to commencing any activity
36cb3620-e6c6-51f6-8400-eaef15084c78 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
70ee4c83-0b88-5319-a740-5c315fdcaa1d | note | REFERENCE DOCUMENTS: Drawings and drawing registers
39d0f0ac-82eb-5750-b38a-69b31476cd09 | note | INSPECTION/TEST METHOD: Visual inspection
6354a8ec-c3e3-505d-ba6c-331a4cbab200 | note | RECORD OF CONFORMITY: ITP Signed
ef48719a-c785-5ddc-8abb-e824acdfc03f | note | HP*
8b03eb07-4697-5467-a0b3-e01dfed1163e | note | RESPONSIBILITY: Project Engineer/ Site Foreman
9ff421bd-c517-577a-a3a0-499424dd1c92 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
fefd57ff-8704-567c-9876-5aee40930938 | note | FREQUENCY: Prior to commencing any activity
f7f15690-6722-5997-b101-8e97b2df1fae | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
ff84c057-d53e-5382-a1ad-4610d005df1e | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
098b60ca-fdd6-5c5e-8bb6-f6cf957d630c | note | INSPECTION/TEST METHOD: Visual inspection
8f25669c-a4aa-5783-9b41-052a22a12045 | note | RECORD OF CONFORMITY: ITP Signed
4430bf6b-befa-5bc4-84e7-13220c10816a | note | HP*
739ce980-cb3a-5727-b7b5-6bbfcffe972a | note | RESPONSIBILITY: Project Engineer/ Site Foreman
f33e3ae5-1413-5e55-a4f8-90272d6fff60 | date | Date Completed:
| checkpoint | 1.2 - Materials
fb8a0f8b-f715-50f5-8ef0-3aa584d517c0 | note | FREQUENCY: Prior to commencing any activity
368f7233-b965-5bf6-a762-bc10d37ed5db | note | ACCEPTANCE CRITERIA: The contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
0a0d823b-9ac2-5439-9153-5184a2e5d177 | note | ○ Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS.
ecae21c5-74a1-5132-83b7-4770bc5ac828 | note | ○ Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing.
7a49edb5-06a5-5ae6-8c46-d9e55c59a4b8 | note | ○ Ensure that materials on-site are sufficient for the completion of works.
82bfe4b2-8fe1-5081-ba1e-faaeea2e515f | note | REFERENCE DOCUMENTS: Design Drawings, VR Section 610 & 611
a178df5b-4afd-5d2d-af4f-df15ba410ed8 | note | INSPECTION/TEST METHOD: Document Review
cfb7264b-3087-5b87-8cc9-67103b380295 | note | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Material Data Sheets.
7bb25d92-a1a7-5c93-95cf-3d6d357e8848 | note | HP
237f1ff2-0ee1-582e-8638-fa393991d811 | note | RESPONSIBILITY: Project Engineer/ Superintendent
75476a02-143f-5980-bac5-f0f02026e338 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Construction Works
| checkpoint | 2.1 - Indentification of Services
9a6bc639-79f6-5b75-917a-a271168b40ff | note | FREQUENCY: Prior to commencing any activity
a58a4b41-ba40-5722-a640-4038ec9f5038 | note | ACCEPTANCE CRITERIA: Ensure any underground service locations have been identified and marker on-site. Ensure any required approvals/permits have been received by service authorities prior to commencing works.
9e74e709-fabd-5947-8cb1-e17eb2f44b58 | note | REFERENCE DOCUMENTS: DBYD
1c13b4cc-cfa0-5149-b4e5-18be8e638ab8 | note | INSPECTION/TEST METHOD: Visual inspection
59e6a966-6b45-58d2-9ed2-24520b92f8da | note | RECORD OF CONFORMITY: ITP Signed
a6ad3404-476c-5102-a545-600254957f24 | note | HP*
b3e11321-58e4-5223-94b1-a94396d0a78c | note | RESPONSIBILITY: Project Engineer
1ee91796-eb4a-5f75-bdc9-7543493800e8 | date | Date Completed:
| checkpoint | 2.2 - Set Out of Piles
40e5eb32-c104-51d9-8d37-742b5813e29f | note | FREQUENCY: Each Lot
a5516bea-f021-591d-a150-85b7da89e153 | note | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
4b28dd4d-7b08-5293-b1c6-bb5669ca35e0 | note | REFERENCE DOCUMENTS: Design Drawings & Survey Data
cd79c9fc-fb5a-500e-8ae9-8dbd7df0351c | note | INSPECTION/TEST METHOD: Visual inspection
a5f0ec5a-4d4d-5135-b6ca-4147ae71889a | note | RECORD OF CONFORMITY: ITP Signed
3f48a9a2-3340-5370-958e-0197c1f72c8c | note | HP*
499603ba-18cf-586c-b9d9-15ce767feac3 | note | RESPONSIBILITY: Project Engineer
b44522de-b237-57f8-9208-57484b0937d2 | date | Date Completed:
| checkpoint | 2.3 - Protection of Adjacent Piles
7aed22bb-fa06-5968-8b5e-59382c9e15ff | note | FREQUENCY: Each Lot
96f64146-9067-5c03-861f-12cbd81bc9ad | note | ACCEPTANCE CRITERIA: No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained the strength of 15 Mpa.
10b37cc5-40df-5228-a995-db0236175060 | note | REFERENCE DOCUMENTS: VR Section 608.05
3293eb35-2017-5d29-805a-7477f60a902b | note | INSPECTION/TEST METHOD: Visual Inspection
0d21d542-1742-5799-8c42-4c6cbcf8b135 | note | RECORD OF CONFORMITY: ITP Signed
3700327b-2a5b-5056-9446-3d19c74d7687 | note | WP
0136de9c-af23-56c0-9e40-b2c1940d47eb | note | RESPONSIBILITY: Project Engineer
da1d15e4-289f-5c93-a012-9d286c8a6aa9 | date | Date Completed:
| checkpoint | 2.4 - Inspection of Piles
a509b9eb-4667-5d42-b784-059cfd222c78 | note | FREQUENCY: Each Lot
b6e52bed-64be-5efe-9740-788a2cfd8e3a | note | ACCEPTANCE CRITERIA: The rock sockets should be constructed in full-time presence of a Geotechnical Engineer who can confirm that the design sub-surface strength parameters are appropriate and provide advice if unexpected conditions are encountered.
9e0dc729-ce8e-5b37-8736-55a69e061e43 | note | ○ Following formation of the socket, the pile shall be de‑watered to enable inspection by the Superintendent (or the Contractor’s geotechnical representative in design and construct contracts) of the geology of the sides and base of the socket and to ensure that the base is free of debris.
ce6aae43-3dff-5a48-a4b0-0ff5e9ffac25 | note | ○ Reinforcement and/or concrete shall not be placed prior to this inspection.
d866cd29-9e90-52ae-8bed-5dc4229420c6 | note | REFERENCE DOCUMENTS: VR Section 608.04, Design Drawings
2251d06d-6d0f-526c-86ed-73b08b51f2f2 | note | INSPECTION/TEST METHOD: Visual inspection
53c507a6-8417-5b83-ba11-f7e6e660332a | note | RECORD OF CONFORMITY: ITP Signed
e0362ef9-fdb0-51f2-ad83-e28067fcb0d1 | note | HP
6d580f31-0713-51f6-81c1-4439d82c07ee | note | RESPONSIBILITY: Project Engineer/ Geotechnical Engineer/ Superintendent
1ec25ff4-0462-5b12-bd00-e62d2e05a514 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Placement of Steel Reinforcement
c251b3d5-62db-5904-a986-d18fc9fba657 | note | FREQUENCY: Each Lot
c00c1339-a1e2-5679-999d-977b93171602 | note | ACCEPTANCE CRITERIA: Ensure steel reinforcement complies with the relevant specification and design drawings.
9b0fdbe7-351f-51b2-a954-f17e32baa9bd | note | ○ Spacers and supports to be placed at intervals less than 2m along cages to ensure minimum cover.
4cd4546b-bb95-5981-bd76-e96cae9c115c | note | ○ Ensure 75mm cover on all reinforcement unless noted otherwise on the design drawings. Ensure 75mm cover to CHS steel casing as denoted on the design drawings.
2c1f45dd-09a3-575d-a475-7c752b8dbb12 | note | REFERENCE DOCUMENTS: VR Sections 608 & 611 / Design Drawings
bda7d562-30e2-5913-b6fe-75edf08e2f9f | note | INSPECTION/TEST METHOD: Visual inspection
3a6c66f4-0df1-5c59-9120-5e9ab83efe37 | note | RECORD OF CONFORMITY: ITP Signed
e8375911-8e1b-51d8-a807-91708b2d36d3 | note | HP*
bd111ad3-1e28-5c69-b451-3333fc4103aa | note | RESPONSIBILITY: Project Engineer
9c0b1878-7a65-5a99-90ff-56fa5724dbdd | date | Date Completed:
| checkpoint | 2.6 - Placement of Concrete
3c8d078d-ea21-5542-8cdf-1a1088e10bf8 | note | FREQUENCY: Each Lot
0f4473a0-e3ca-5555-8210-f481554d5b4d | note | ACCEPTANCE CRITERIA: Ensure concrete being used for bored piles complies with the relevant specification and design drawings.
48f3d4fa-05ec-596a-9fae-b2924254641d | note | ○ During concreting, the outlet of the tremie pipe or pump discharge hose shall be kept a minimum of 2m below the top surface of the concrete at all times. If water is in the socket, the socket shall be backfilled with concrete tremied from the base of the hole.
2220e9d3-5234-5aef-94fb-4e799e5736b9 | note | ○ Concreting shall be continued until sound concrete appears a minimum of 400mm above the required cut-off level. The pile concrete shall not be cut back to its required level until a mimimum of 24 hours after completion of placement of concrete.
62a456e4-733e-5025-abcc-102322b6abbf | note | ○ Concrete placed under water shall be self compacting concrete (SCC) in accordance with the requirements of clause 610.07, clause 610.13 and clause 610.18(c).
bae6495b-3b2e-5279-8bce-b8dd309543d0 | note | ○ The concrete shall be of such consistency, and shall be placed in such a manner, that pockets of air or water or ground materials are not entrapped in the concrete, and the space between the reinforcement and the side walls of the hole are completely filled with compacted concrete.
e1321b01-5bca-51a4-9588-5116651d1601 | note | REFERENCE DOCUMENTS: VR Section 608.07 / Design Drawings
7366514d-8c65-537e-a1db-f4f3985cb913 | note | INSPECTION/TEST METHOD: Visual inspection
92784ec5-61cb-536a-955e-d2447a158368 | note | RECORD OF CONFORMITY: ITP Signed
1add2476-0e98-5292-834f-b5e51737718b | note | HP
d84148f2-4782-55ce-a10a-9487f89b21c3 | note | RESPONSIBILITY: Project Engineer
74b771f6-9d33-5377-aeb7-bc0bb19ff3da | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Quality Control Testing
| checkpoint | 3.1 - Concrete Testing
4bdc8980-3090-5f62-905a-ebf20032bd7c | note | FREQUENCY: Each Lot
59e328e2-d76a-51c8-86cf-02c34ab72fe9 | note | ACCEPTANCE CRITERIA: All concrete shall be sampled and tested in accordance with AS 1012.
a8a402f2-b35b-5901-8e25-142bee2f7703 | note | ○ The minimum number of test samples shall be in accordance with Table 610.161 in the VicRoads Standard.
fe8807e0-45de-5014-8bd3-1fbaa4d52481 | note | REFERENCE DOCUMENTS: VR Section 610.16
a39b5da2-16ee-5f95-ba22-245c27ecb3b2 | note | INSPECTION/TEST METHOD: Test Point
4b4cca52-e253-52cb-ab58-e8ed1d3bf6c6 | note | RECORD OF CONFORMITY: ITP Signed
9a86d261-2deb-5df8-b2f4-1e6477a30e55 | note | HP*
0758f92e-ced2-50e5-a4a9-bb8794f71b98 | note | RESPONSIBILITY: Project Engineer
11d588c9-b75b-5f42-a1ee-c99689c80b91 | date | Date Completed:
| checkpoint | 3.2 - Pile Integrity Testing
52be8305-e553-552a-926d-af1c0ae0c88f | note | FREQUENCY: First six piles followed by every third pile thereafter.
555cff6a-ab5e-5e34-a9a4-260b55d4f0a7 | note | ACCEPTANCE CRITERIA: Integrity testing shall be carried out in accordance with test methods specifed in AS 2159. All testing shall be undertaken by a prequalified consultant in accordance with the VR scheme for prequalificaiton and approval of the Superintendent. The contractor shall provide details of the pile testing consultant to the Superintendent for review at least 2 weeks prior to the testing.
0fd639ec-c82b-550b-8da7-838215671849 | note | ○ Integrity testing shall not be carried out until the concrete has achieved a compressive strength of 25MPa and not before 7 days after casting of the pile.
94e51616-84d1-5f99-91d3-a7e1dca6c633 | note | REFERENCE DOCUMENTS: VR Section 608.08
a0cffd66-794b-5b8e-be97-6ec825bbc3db | note | INSPECTION/TEST METHOD: Test Point
c80b3b6f-4376-591d-9721-41d1dc0e16b8 | note | RECORD OF CONFORMITY: ITP Signed
a7829c62-5a45-5dcb-9692-52812e893570 | note | HP
02164752-a657-5fff-af1d-3a963f8bc53b | note | RESPONSIBILITY: Project Engineer/ Superintendent
aa70a1ee-e637-590b-9909-bc6a60479ae3 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
5b0e4983-6417-56de-be71-d53dd31cb7bf | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3f8569b0-11ec-5581-a026-8992da3ef44b | textbox | Print Name:
bf7821c0-711c-57e8-ad6b-8f142dacfcaf | textbox | Position:
d55b8504-1e03-521d-8c2e-654f46fc0e60 | date | Date:
| signoff | Sign ITP
| checklist | ITP-003 - Construction of Structural Concrete | itp | ITP-003 - Construction of Structural Concrete |  | abc3f41c-d2d3-4fe2-9019-cd85a6b60796
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
995a4964-2f0e-563b-b9f9-a836277c61fb | note | FREQUENCY: Prior to commencing any activity
c5fc6833-b50b-5cac-a8c8-b6bf856ec68a | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
efab8c67-891d-5782-8fa9-e73cced99459 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
37424c98-9e7c-576e-91bc-2f4f63a94d6d | note | INSPECTION/TEST METHOD: Visual inspection
86185def-d003-510e-b810-61da2f7e6c57 | note | RECORD OF CONFORMITY: ITP Signed
6f5aca1d-f777-5a29-9334-7675bb26e4b1 | note | HP*
bbdc9ade-8011-594a-9cb2-92263e87ccae | note | RESPONSIBILITY: Project Engineer/ Site Foreman
eaf12091-1510-50a2-936d-f88a7754e6b8 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
a5ad7f0d-ace2-59b9-a62c-8b4ad35ec4e0 | note | FREQUENCY: Prior to commencing any activity
29e1d7a1-dc70-5af7-8114-981d9136b719 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
ed178f5e-0134-5b44-94a6-b4905bb13f72 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
d70cd53f-294d-5190-bae7-b78a2ed41380 | note | INSPECTION/TEST METHOD: Visual inspection
7cca409d-793d-547e-9049-5e99245c5d41 | note | RECORD OF CONFORMITY: ITP Signed
29639933-3d2a-542c-9811-825b86ccca4c | note | HP*
6e98f6e7-bbae-5b31-b1e2-33ec4c8ac9aa | note | RESPONSIBILITY: Project Engineer/ Site Foreman
eee8ddc4-a1c2-55c5-8db2-5d2ac34af897 | date | Date Completed:
| checkpoint | 1.3 - Materials
9024f21a-46da-50ab-b7cc-0f7856e1d2e7 | note | FREQUENCY: Prior to commencing any activity
816c6c76-026b-50db-9ca3-b304cae4f313 | note | ACCEPTANCE CRITERIA: The contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. This shall include full details of the proposed methods of curing.
759d573d-6589-58ca-8ff9-c7eedddb790d | note | ○ Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS.
2009747b-ae24-5e73-930d-991f18e3df6e | note | ○ Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing.
335f1d1a-bc3f-51b9-a411-c7d341f04cb6 | note | ○ Ensure that materials on-site are sufficient for the completion of works.
2ee92cc6-0a41-533d-b66b-428541b2863b | note | REFERENCE DOCUMENTS: Design Drawings, VR Section 610 & 611
6b6567ee-bdde-54bc-8a4b-b156583ef7e4 | note | INSPECTION/TEST METHOD: Document Review
196c803c-4c13-5174-8fee-16d0468b700d | note | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Material Data Sheets.
3a4cf6ea-9b27-5305-9e59-ee326237b21f | note | HP
b59f91d4-37db-59fb-8e11-b7369d770f66 | note | RESPONSIBILITY: Project Engineer/ Superintendent
7d3d0e7b-04f0-531c-9207-2cb4968797bb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Submission of Preliminary Documentation
ac6619cb-86a9-5fde-9815-61d8afa01e94 | note | FREQUENCY: Prior to commencing any activity
5461249b-078d-561b-b0e1-7598fb72b01c | note | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent for review the following:
bbe29ff6-f848-54ec-aa25-853b7441939d | note | – Full details of the proposed hot or cold weather concreting procedure, not less than two weeks prior to placement of concrete.
b3de7a85-52f1-585f-b52d-97c9a841d5d2 | note | – Detailed WMS, ITPs, & Checklists for all concrete construction works not less than 4 weeks prior to the placement of concrete.
d645828d-6fb6-5217-bda8-98cd098a517a | note | – Full details of the proposed methods of curing, as part of the concrete mix design submission, not less than 4 weeks prior to placement of concrete.
13704932-3367-5226-94e9-ce603c8a29a3 | note | REFERENCE DOCUMENTS: VR Specificaiton 610.17, 610.18 & 610.23
17ce5454-65fa-5aa6-82bd-b4d18fb99ded | note | INSPECTION/TEST METHOD: Document Review
9ee4f50e-8e04-514f-b56c-e780d16d9b37 | note | RECORD OF CONFORMITY: ITP Signed, Submitted Documentation
d071638b-0d1e-5a6e-a06a-3dc778d45c87 | note | HP
544eb032-0963-55e3-94cd-1ef29bdda840 | note | RESPONSIBILITY: Project Engineer/ Superintendent
c4bba466-6b77-529a-8300-d03c03fb4238 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey & Set Out
eb8200da-328c-5cfa-bd16-67cee3ff2050 | note | FREQUENCY: Each Lot
da16da90-8939-55fa-b398-e80c773917b9 | note | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
3246773f-626d-5f06-8c30-12f708aca25d | note | REFERENCE DOCUMENTS: Design Drawings & Survey Date
768f932d-cdeb-5be3-8e44-1dd1489ac076 | note | INSPECTION/TEST METHOD: Visual inspection
4f12e4e3-6dbf-5ecc-9af4-c109dbf9b54a | note | RECORD OF CONFORMITY: ITP Signed
555a71ee-1766-55a0-b211-8406f87a9500 | note | HP*
f2602ddb-eeb4-5ddf-9670-ac11d4c17ed8 | note | RESPONSIBILITY: Project Engineer
8f36bead-f6d8-56ef-9de6-da52c0481a82 | date | Date Completed:
| checkpoint | 2.2 - Placement of Steel Reinforcement
eb60b1a3-2108-5bec-91c6-0e9a8741aea0 | note | FREQUENCY: Each Lot
e8f305e2-0cbd-5db1-9f3f-6e0116debbd5 | note | ACCEPTANCE CRITERIA: Ensure steel reinforcement complies with the relevant specification and design drawings.
2677713f-c714-5acd-89e6-7beaec8112eb | note | ○ Reinforcement placement shall be coordinated with formwork erection such that is can be placed to the correct size, location, diameter, number and spacing as shown on the drawings.
14db3fa2-f56f-522b-93dc-2ee451cddc95 | note | ○ If required, re-bending of steel reinforcement shall not commence until the procedure has been reviewed and approved by the Superintendent, and shall be witnessed by the Superintendent's representative.
fea9ca7d-c6aa-54d7-882c-3567ce50f4c7 | note | ○ Splices in reinforcement shall be made only in the position shown on the drawings or as otherwise approved by the superintendent. Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commmence until the welding procedure has been qualified and reviewed by the Superintendent.
b7c65153-3bea-5af9-bf5b-64dd636824e1 | note | ○ Ensure reinforcement to be embedded shall be free of mortar, oil, dirt, rust, grease, paint, tar or any other contaminants.
5dac6511-68a5-580f-87fa-7db172ce4936 | note | ○ Ensure 70mm cover on all steel reinforcement unless noted otherwise on the design drawings.
116b217e-41f4-58ad-a701-da467a256a7b | note | REFERENCE DOCUMENTS: VR Section 611
c30e9466-3a7e-5eb3-96ba-a3b0811ed718 | note | INSPECTION/TEST METHOD: Visual inspection
058a1192-bb31-5b74-93cd-54d36a6f8481 | note | RECORD OF CONFORMITY: ITP Signed
7a18ad96-d20d-5a8a-ab96-b3906bd5b38c | note | HP
d679fcf0-e296-56ee-88e1-05156c1908c7 | note | RESPONSIBILITY: Project Engineer/ Superintendent
49e5e17f-14dc-5d7f-afe3-e3dc4d0c4809 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Formwork
a6e2ebb0-efea-598a-80c7-36c8aaef68b4 | note | FREQUENCY: Each Lot
74dd4d43-431e-5e07-86fa-960daf5444dd | note | ACCEPTANCE CRITERIA: Formwork, including supporting systems, shall be constructed in a fashion that ensures the specified quality of concrete finish is achieved. Forms shall be clean and free of majore surface defects.
dfa263d2-037a-5f77-8478-8ab02c4e6ddd | note | ○ Formwork shall be constructed and shall be sufficient stiffness to tolerate the rate of concrete placement and high frequency vibration, and shall be of uniform stiffness to avoid causing varying vibration aplitudes over the formwork surfaces during compaction of concrete.
b250fd84-7e25-5338-88a9-f9af0589a82f | note | ○ All corners shall have 20 x 20 mm fillets or chamfers unless noted otherwise.
1a1c244d-633b-5d66-becb-acae01fee3bd | note | ○ Formwork shall not be placed in locations where steel reinforcement and other fixtures cannot be inspected and/or will be left open until inspections have been completed.
a15a78c1-599c-5f6b-8767-7a8ca9ef1b33 | note | ○ The application of any load shall not proceed until the signed Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewd and accepted by the the Superintendent.
b362ae2e-c829-57e7-9415-464a02dd6f58 | note | REFERENCE DOCUMENTS: VR Section 614
0f1af587-2148-5981-a3ee-8e5519ee1dc0 | note | INSPECTION/TEST METHOD: Visual inspection
183feea5-7e3f-5510-bb92-964e36a17125 | note | RECORD OF CONFORMITY: ITP Signed / Certificate of Compliance - Formwork Inspection
08741cf9-e17d-59e0-8002-5104c1af3f9b | note | HP
6364ea7a-e051-5f65-92f1-2070159b5f66 | note | RESPONSIBILITY: Project Engineer
386e9155-c780-540f-b85c-cd9289092734 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Placement of Concrete
4f7b157c-fc01-54a0-a87f-03f3eefec54d | note | FREQUENCY: Each Lot
0e64153c-bb71-54cd-a3bb-dbc958b30271 | note | ACCEPTANCE CRITERIA: Ensure concrete being used for bored piles complies with the relevant specification and design drawings.
cc2e2bc6-aed2-5807-b95c-14a1f98dd3ab | note | ○ Ensure that the forms, reinforcement, any stressing materials and embedments has been checked against the specifciation and design drawings by the Superintendent.
cadb0a7e-2e41-5cee-b7d8-e61c8f386d69 | note | ○ Air and concrete temperatures shall be recorded. Concrete shall only be placed under the following conditions:
2cde97b4-827d-5e64-803a-f60a4d18aac9 | note | – Air temperature 5 to 35 deg C.
5885786b-df36-5036-a9f5-fa4e58b56097 | note | – Concrete temperature 10 to 30 deg C.
2de6d075-279f-55a5-ac9e-72865299aeff | textbox | Measured Air Temperature:
9c235c50-8c55-53ef-828c-b606bc29ae3e | textbox | Measured Concrete Temperature:
b58a7ce0-ef9d-5206-817b-572964ec8266 | note | ○ Concrete shall be placed from a height not exceeding 2m. Concrete pumping shall be used where access is restricted. Prior to the commencement of placing concrete by pumping, the initial discharge of concrete shall be pumped to waste until a consistent workable mix is discharged.
8fce1d76-dc25-59cc-8989-9627db34ade6 | note | ○ In continuous concrete pours the maximum time lag between truck loads on site shall not exceed 25 minutes.
62daf742-683b-5ced-b389-74d900216f18 | note | REFERENCE DOCUMENTS: VR Section 608.07
85239f00-7b9c-5853-a63b-f0eed4741fef | note | INSPECTION/TEST METHOD: Visual inspection
6f9daebc-17d1-5adf-9d42-07e3c51a1020 | note | RECORD OF CONFORMITY: ITP Signed
294b37bd-8191-5372-b73e-15edddfe523e | note | HP
1e1b8712-ba15-5a94-9af5-1a203a3500bd | note | RESPONSIBILITY: Project Engineer/ Superintendent
f0ebe6e1-a6b0-5d6b-bcea-00fd99b9995a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Traceability of Concrete
4fac26e7-bdaf-54b5-a655-d6a9033e6a13 | note | FREQUENCY: Each Lot
36b405c9-c402-5859-84f1-51fb80a13294 | note | ACCEPTANCE CRITERIA: All concrete batches (truckloads) used in the works shall be traceable from the batch plant to its general location in the structure by a unique lot number.
f7eed7b7-2597-5350-9ba9-f5623985984f | note | REFERENCE DOCUMENTS: VR Section 610.14
1406014a-74fb-5881-b3c7-e4d85b465156 | note | INSPECTION/TEST METHOD: Visual inspection
383ce4aa-961c-56ad-b257-14c8ea37c77b | note | RECORD OF CONFORMITY: ITP Signed, Concrete Delivery Dockets
08a12334-3605-5d2b-b8dd-2162182b04a9 | note | HP*
a257559c-400e-571e-9664-6a2b422d2c8b | note | RESPONSIBILITY: Project Engineer
8b62ba67-44cb-5676-a99c-5b64d78d7e3b | date | Date Completed:
| checkpoint | 2.6 - Removal of Formwork
abeaaee7-5376-59ea-b68d-8ae0c1827989 | note | FREQUENCY: Each Lot
357a7f0f-68a9-5c37-af5d-fcb5bb2c4c19 | note | ACCEPTANCE CRITERIA: Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation and shall remain in position and undisturbed until the minimum removal times given in VicRoads Table 610.251 have elapsed, after completion of the placing of concrete.
83a911b2-f9f0-58c9-9ee7-88d755c06e96 | note | REFERENCE DOCUMENTS: VR Section 610.25
a37d32f0-78ed-55a8-9dd6-b8cdd4617c9c | note | INSPECTION/TEST METHOD: Visual inspection
54173cb7-e839-5503-b732-33068c026528 | note | RECORD OF CONFORMITY: ITP Signed
017931ab-aa1f-55d5-b0fb-9b8821acc1db | note | HP*
3a926bca-a34b-5874-9313-f4a2915d0a00 | note | RESPONSIBILITY: Project Engineer
2ef939e4-79b6-5b4a-b0a6-0182b4fe967f | date | Date Completed:
| checkpoint | 2.7 - Curing
785f3a97-974d-516b-973a-66381426b199 | note | FREQUENCY: Each Lot
fe69fe09-0aa9-5620-96cb-d2309e1f9d57 | note | ACCEPTANCE CRITERIA: Ensure the method and period of curing is in accordance with specifications agreed with the client.
f5871e62-4b56-5ad9-96d5-9794d115c93f | note | ○ The contractor shall ensure that records of temperature monitoring during the curing period are available for review by the Superintendent.
c4f7b96b-1651-5d26-9b34-b04f31ed6abe | textbox | Measured Curing Temperature:
cb9e4ca6-811b-5291-9fbd-7b5a57a40deb | note | REFERENCE DOCUMENTS: VR Section 610.23
f552a98a-8569-5293-b151-6c8a8350910f | note | INSPECTION/TEST METHOD: Visual inspection
67cf941f-44e1-5c61-b90d-8a73b2781d9a | note | RECORD OF CONFORMITY: ITP Signed
8b531abf-7ebf-5b05-ad91-fa44d7d22c44 | note | HP*
38e435f6-9369-5499-b770-c4cb94adffe4 | note | RESPONSIBILITY: Project Engineer
445f3d09-5344-5115-a076-a9cf70f84665 | date | Date Completed:
| checkpoint | 2.8 - Dimensional Tolerances
eb1398e0-6f5d-5e53-86c6-72a770c73d7e | note | FREQUENCY: Each Lot
5ed1e0e7-4e3a-559d-bf36-a55bd1e7c6f3 | note | ACCEPTANCE CRITERIA: Dimensional tolerances shall be checked against the requirements in accordance with specications agreed with the client.
a4a913f5-5499-52b9-bc21-316e90ea26a3 | note | ○ The concrete shall be inspected for quality of finish and compliance with the surface class requirements.
3a71623b-3608-5742-8ee6-fe2ae5a7d941 | note | REFERENCE DOCUMENTS: VR Section 610.47
e1ecaccf-eecf-5965-bf4b-5f7611fdabfe | note | INSPECTION/TEST METHOD: Visual inspection
15cde8ef-0068-5dce-aa9f-46f723205c37 | note | RECORD OF CONFORMITY: ITP Signed
2fb585d3-6a88-5e22-85d7-7b8ef08645c2 | note | HP*
e93f5c51-c720-5d96-8a83-9b65862eaf98 | note | RESPONSIBILITY: Project Engineer
12e516cd-0f56-54b6-bfbc-5572b99d3a1a | date | Date Completed:
| section | 3 - Quality Control Testing
| checkpoint | 3.1 - Concrete Testing
c8280206-ce5b-59d5-a604-1da01a2e6b88 | note | FREQUENCY: Prior to commencing any activity
22079bc5-f9a5-5b22-a88d-33b9a0d5bef4 | note | ACCEPTANCE CRITERIA: All concrete shall be sampled and tested in accordance with AS 1012.
f16fbe0d-649d-5616-8ba0-205397797df0 | note | ○ The minimum number of test samples shall be in accordance with Table 610.161 in the VicRoads Standard.
c92c6aa7-3b54-5af4-a654-b331e67871e2 | note | REFERENCE DOCUMENTS: VR Section 610.16
883c7fc2-7eb1-5474-a369-28d409f971de | note | INSPECTION/TEST METHOD: Test Point
ec9dec6d-52d0-5382-a1de-d0d0b69bed01 | note | RECORD OF CONFORMITY: ITP Signed
4887419c-0599-5497-8413-07a099a0c751 | note | HP*
a07e8914-badd-552c-84e3-d24bb52ad48f | note | RESPONSIBILITY: Project Engineer
cb5969aa-7b4a-5383-ae89-6ad1322ac1bc | date | Date Completed:
| checkpoint | Final Inspection
e749af0d-3463-5af1-9a5f-cfea15325fbb | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1a3caded-cbd0-5349-b05a-92d804319d2b | textbox | Print Name:
f0382fc1-5223-522b-8974-73ea9274527f | textbox | Position:
70fe37e3-2bb2-5002-a077-5c37ab6cd5b8 | date | Date:
| signoff | Sign ITP
| checklist | ITP-004 - Fabrication of PSC Planks | itp | ITP-004 - Fabrication of PSC Planks |  | bdf279c4-1622-4e65-99fa-595f8a031bfa
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
720d0760-43e6-5437-b96c-95248b858447 | note | FREQUENCY: Prior to commencing any activity
1895e3ab-ca7f-5521-b55f-c331772aa277 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
3f8e844a-d10d-510d-9c8b-977e8b82e3cf | note | REFERENCE DOCUMENTS: Drawings and drawing registers
342750c5-9640-5ae9-9489-6314da1cb244 | note | INSPECTION / TEST METHOD: Visual inspection
ab1c8a4c-c325-57bc-aec7-05f7404ab569 | note | RECORD OF CONFORMITY: ITP Signed
bf4a4c33-7ab8-55c4-ad02-b3ae13fcfc76 | note | HP*
c7040b5c-3e0d-5d70-b945-d0dffaeecb1f | note | RESPONSIBILITY: Project Engineer/ Site Foreman
cb56e293-2544-5959-a88a-3660824c4868 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
2cb52671-ee62-531b-8206-b0111b5a06e1 | note | FREQUENCY: Prior to commencing any activity
ff34abef-9507-5eff-ade0-cbeb954ca0cb | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
6d16e030-55ff-53a9-9340-44beac3bb81d | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
696bc4aa-c694-548c-b891-6b2ff62bc97e | note | INSPECTION / TEST METHOD: Visual inspection
06eb1c7e-ea26-5faf-843d-9d293017092b | note | RECORD OF CONFORMITY: ITP Signed
49f03848-2010-5d7e-83e9-8db07b8288c3 | note | HP*
4454879a-6e2e-598a-b349-237522a83bd4 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
4c81183d-bb0e-57c5-b213-14375c05e82e | date | Date Completed:
| checkpoint | 1.3 - Materials
ad0fa886-42f7-57b9-a831-e54673b788fd | note | FREQUENCY: Prior to commencing any activity
dc9d4e69-c0cf-5ce2-afb8-0bc1a22547c4 | note | ACCEPTANCE CRITERIA: Ensure correct concrete mix being used in accordance with design drawings and specifications.
1b8c0c5a-41a6-5635-af45-a148174b47c5 | note | ○ Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS.
a70e17dc-1c93-55f5-b60c-00a38d7cb93c | note | REFERENCE DOCUMENTS: Design Drawings, VR Section 620
052a82d4-0542-5113-96f5-7ed76948b4ce | note | INSPECTION / TEST METHOD: Document Review
ce5923d8-9d44-56ea-a20c-28b940c9a1ae | note | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Material Data Sheets.
8ddf191a-fd37-5869-8ab6-8149ef9c26fc | note | HP*
e5fd9adf-55f9-5268-99cc-f1a45df5ce78 | note | RESPONSIBILITY: Project Engineer/ Superintendent
2ae93b0d-ef56-52d1-8ce0-f709ae7e42e7 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Forms
2b7ee515-b8bc-592d-8355-b27bb4f1647c | note | FREQUENCY: Each Lot
fcf4dfbc-df33-5047-b355-5fdfb64ea84c | note | ACCEPTANCE CRITERIA: Forms shall be manufacutred from steel, except where otherwise approved by the Superintendent.
37286885-d2b2-5db0-bd13-90d8e0a7f750 | note | ○ The formwork shall be constucted to as to produce a product in accordance with the design drawings, and with the surface finish and tolerances specified in Section 610.
27a424ce-5927-54f1-9272-1c784cd9974d | note | REFERENCE DOCUMENTS: Design Drawings , VR Section 620, 610.
ba225242-ca30-545c-b0c7-a86fb7e16883 | note | INSPECTION / TEST METHOD: Visual inspection
12fd7ce6-2625-5101-b1c4-16e1f6bf5750 | note | RECORD OF CONFORMITY: ITP Signed
1c188e05-3396-5fcc-8c2e-8b450ba87a86 | note | HP*
88c57c14-c51b-5472-977f-fdd97f900540 | note | RESPONSIBILITY: Project Engineer
12186718-acac-5e63-bce4-1a25d24e5935 | date | Date Completed:
| checkpoint | 2.2 - Projecting Reinforcement
588c540f-15bf-5e25-b3ea-8bb21126ae41 | note | FREQUENCY: Each Lot
47caa200-9f2f-5dd7-ae07-8130d0f9ccc4 | note | ACCEPTANCE CRITERIA: Ensure projecting reinforcement is in accordance with that shown on the design drawings and is in good condition.
8ac57275-5618-537c-9012-785e8ba0be8e | note | REFERENCE DOCUMENTS: VR Section 620.03
f50175d2-456c-532e-a503-ddcd2675c53e | note | INSPECTION / TEST METHOD: Visual inspection
758e8789-8fa6-51e2-9b80-bf137d13141f | note | RECORD OF CONFORMITY: ITP Signed
96235ebc-20dd-529e-a5b5-d9ce5c92a86d | note | HP*
289bc020-51e0-5d97-ac9b-910758b944e9 | note | RESPONSIBILITY: Project Engineer/ Superintendent
b6a1e9d4-714c-5d93-9baa-6d7712eb2023 | date | Date Completed:
| checkpoint | 2.3 - Marking
9e9a2290-c290-56ba-9ea0-760e9604950e | note | FREQUENCY: Each Lot
abcc6485-3f16-5d6d-a82d-be3d9e37beee | note | ACCEPTANCE CRITERIA: Ensure the identification number, date of casting, the manufacturuers name or registered mark and the maximum mass shall be marked on every precast unit.
1dacb10c-10fd-5629-8dc6-4c3f70643790 | note | REFERENCE DOCUMENTS: VR Section 620.06
2c08deb8-3a5c-50f0-a85c-c90482f52b32 | note | INSPECTION / TEST METHOD: Visual inspection
6dfa4697-681f-50b4-a4dc-674fdaff128e | note | RECORD OF CONFORMITY: ITP Signed / Certificate of Compliance - Formwork Inspection
99e0b2b9-594e-589b-abee-031531d28f07 | note | HP*
22c4f1a0-372c-50e3-8981-f5c791da6b23 | note | RESPONSIBILITY: Project Engineer
fcd63786-e6fe-5163-8df9-6976f491d182 | date | Date Completed:
| checkpoint | 2.4 - Handling & Storage
cf16a248-08f9-5f17-8be1-daf336c19333 | note | FREQUENCY: Each Lot
50cb3150-2e71-5aa7-ba83-0778c0384b1f | note | ACCEPTANCE CRITERIA: The units shall be supported on bearers clear of the ground. Bearers shall support the units over their full width and be placed perpendicular to the longitudinal axis of the unit.
2eda5c28-066a-5e9b-b0ef-1c4a9f405ce9 | note | REFERENCE DOCUMENTS: VR Section 620.07
5b5c9a3f-1e39-5020-b034-cf7ddc520e2c | note | INSPECTION / TEST METHOD: Visual inspection
f12e156f-c178-5969-a274-16cb22043f80 | note | RECORD OF CONFORMITY: ITP Signed
b171b48b-f426-50a9-a44b-5a737284561c | note | HP*
41e925c4-5c01-5563-b7f5-09a9fdaa3d2a | note | RESPONSIBILITY: Project Engineer/ Superintendent
61fe4dc8-2ad3-5368-baf7-04670a9a1a52 | date | Date Completed:
| checkpoint | 2.5 - Transporting
ee4993fa-84d5-5928-9460-0fc002c59f16 | note | FREQUENCY: Each Lot
5c8e9ec6-bd7c-5ecf-aabc-afe6fc0a22f6 | note | ACCEPTANCE CRITERIA: Units shall not be transported from the precast yard until specified 28 day concrete compressive strength has been achieved, and not before 7 days after casting.
15c3bd43-b75b-5ac7-b9db-af2fc90559a3 | note | ○ No beam shall be transported and erected if it has a bow in excess of 1 in 400 of the length or 75mm whichever is the lesser. Should the bow at any time exceed the maximum allowable limit steps shall be taken to ensure the safety of the unit throughout the journey.
f35c53bf-cb1b-5977-bdb3-22c18be6b100 | note | REFERENCE DOCUMENTS: VR Section 610.14
ae6443cd-c012-551c-b9fa-7c33ade65565 | note | INSPECTION / TEST METHOD: Visual inspection
74028281-3f64-5b5f-808d-8b0ccb87f1d9 | note | RECORD OF CONFORMITY: ITP Signed, Concrete Delivery Dockets
783f1e40-4cab-5852-b634-165148a3cb0a | note | HP*
f42d901a-0166-586d-8032-99d593fda8d6 | note | RESPONSIBILITY: Project Engineer
8778ef5b-d784-56a3-bc78-f576b9a43f9f | date | Date Completed:
| checkpoint | Final Inspection
c3a0ea45-6e4f-5c6f-b850-aee5376971a6 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
2026eea6-cd2a-50d1-8050-28243bf46130 | textbox | Print Name:
de9a23e6-ea33-575e-b08c-2f019fa18dfe | textbox | Position:
94e5c15f-49c1-54a5-a6cc-393738c3ce49 | date | Date:
| signoff | Sign ITP
acf6ff21-0134-4991-9cb2-76e8f426d63c | checklist | ITP-004b - Fabrication of PSC Planks Rev2 | itp | ITP-004b - Fabrication of PSC Planks |  | 777b7878-3188-46c0-8221-30ee9087fcf3
af43b2c6-20e7-40ce-a462-5abdfe039cbf | section | 1 - Preliminary Works
35db4db9-3796-46f3-99ce-a4b046cf2ac4 | checkpoint | 1.1 - Check for correct documentation
6ed29bb2-32e5-58e1-8c03-3fdba4dc15aa | note | FREQUENCY: Prior to commencing any activity
605283ad-a3a4-5523-93aa-a94b52cdcdc3 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
60384701-de50-5be8-95ef-29fb35c9686b | note | REFERENCE DOCUMENTS: Drawings and drawing registers
9842cfd3-4707-5b6c-a164-9f5ed1e580c5 | note | INSPECTION/TEST METHOD: Visual inspection
d9fbbc2f-01ad-52c1-9bdd-f1ba24e1671a | note | RECORD OF CONFORMITY: ITP Signed
a0ecf2ed-b7de-5ac2-9012-b6e90d8d4031 | note | HP*
c4aae725-f011-5524-9f51-f6b2ecac4414 | note | RESPONSIBILITY: Project Engineer/ Supervisor
b771259d-8883-5a53-a355-8c629da8d431 | date | Date Completed:
461bf421-4b25-4373-9c4d-c26823dbe49c | checkpoint | 1.2 - Implementation of all measures and controls
bfe01841-c317-5fc4-9700-bedf73b96a0c | note | FREQUENCY: Prior to commencing any activity
ba751761-a29b-5e0e-979d-74f3f3d6a2b2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
8b38e13f-9d5f-502d-a9f3-44e920094313 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
73f42530-a457-57a4-b021-d22e78c21278 | note | INSPECTION/TEST METHOD: Visual inspection
073f4203-4c87-5103-ac16-d1724abbac91 | note | RECORD OF CONFORMITY: ITP Signed
445c9ef6-832c-5f43-bccd-b45d59c6f509 | note | HP*
91c476df-1dc9-5324-ae69-39b0ed8e715e | note | RESPONSIBILITY: Project Engineer/ Supervisor
8357419f-6df8-5b2d-a89d-44eec9aed31e | date | Date Completed:
9a4c5652-8b4f-4c09-8214-adeacead6800 | checkpoint | 1.3 - Materials
e6e9740f-15db-53f1-bea8-2853287f77ab | note | FREQUENCY: Prior to commencing any activity
2594fdaa-3c69-5bd1-aa76-8183032bc853 | note | ACCEPTANCE CRITERIA: Ensure correct concrete mix being used in accordance with design drawings and specifications.
e4f02de9-1d99-5550-b605-c6847bc53225 | note | ○ Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS.
e8716825-227d-56ba-9ecb-b897bf1e636f | note | REFERENCE DOCUMENTS: Design Drawings, VR Section 620
5d7b5f30-db54-5572-b2df-c93cf18d48db | note | INSPECTION/TEST METHOD: Document Review
4f1c3601-7349-5a38-a564-6b06293f53f1 | note | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Material Data Sheets.
81de1030-079d-54db-be7f-00a791e7e1df | note | HP*
b9579cac-bc18-5d35-8ade-f0e88b5933f8 | note | RESPONSIBILITY: Project Engineer/ Supervisor
950bedbb-f6b6-547c-94ec-d9184afaa648 | date | Date Completed:
7ee80026-0ca0-4492-94e5-948b6ec1ec48 | checkpoint | 1.4 - Calibration of Prestressing Equipment
247465c3-b3f0-5f27-a4a7-2cac8dddb0ff | note | FREQUENCY: Prior to commencing any activity
63f760ec-8ea9-523b-8c47-4601624caefb | note | ACCEPTANCE CRITERIA: Ensure the contractor holds current calibration certificates conforming to the requirements of AS 2193 Grade B for the jack and pressure gauges or other force measuing devies.
fffe07e4-514c-50ad-b778-49b168dfa2fa | note | REFERENCE DOCUMENTS: VR Section 622.06
18f9a560-1cdf-5771-b5f0-e16a1942171f | note | INSPECTION/TEST METHOD: Document Review
83f6b61a-9ad3-5a2b-8e99-63c2d00218bd | note | RECORD OF CONFORMITY: ITP Signed, Calibration Certificates
9d5652bb-9cec-5cb8-a8b3-72b5313132cb | note | HP*
89903d66-13ed-5adc-b9a9-94575795e198 | note | RESPONSIBILITY: Project Engineer
8e422604-08a9-5247-a7ae-d85b3f4bf9ba | date | Date Completed:
c14c33dc-211b-4973-8bf4-6a39a4167d55 | checkpoint | 1.5 - Submission of proposed method of transfer of prestress
51a0d966-e50b-562a-85cd-c8ee861c0b75 | note | FREQUENCY: Prior to commencing any activity
7885af1e-8a4b-5d14-9997-05c50f4eda67 | note | ACCEPTANCE CRITERIA: Ensure submission of the details of the proposed method of transfer of prestress to the Superintendent for review.
5a1756f3-ee73-5129-b9b6-30c0552ad3e2 | note | REFERENCE DOCUMENTS: VR Section 622.08
822b88c5-5b9a-554e-8be3-33a4a478d4dc | note | INSPECTION/TEST METHOD: Document Review
8c6ff8c4-e576-5d63-a9eb-7b6b77e119c9 | note | RECORD OF CONFORMITY: ITP Signed
0ab0a2c6-01a5-57f1-9096-1e831c652e2f | note | HP
39b824d2-fc03-5b15-853f-61099d53f226 | note | RESPONSIBILITY: Project Engineer/ Superintendent
1bc5410a-e4df-56f3-8415-ee7503585ecd | date | Date Completed:
a2ab742a-3545-48b7-9bdb-1fcbdd7098a8 | signoff | AUTHORITY HOLDPOINT
c2afd87b-297c-4596-a5f2-2e6008e59c5e | checkpoint | 1.6 - Notification of Superintendent prior to stressing operations
dee5a9d1-47a1-5745-8a5f-ed90b731f6d4 | note | FREQUENCY: Prior to commencing any activity
89f590f5-2db9-574e-ad55-1ab45e221cbb | note | ACCEPTANCE CRITERIA: The Superintendent shall be given seven days notice of stressing operations.
36b34915-8dd5-57b8-a723-3c48e0e0765c | note | ○ All stressing operations shall take place in the presence of the designated Precast Concrete Surveillance Officer.
1760dc66-3b4d-50b6-941b-bf3081281fcc | note | REFERENCE DOCUMENTS: VR Section 622.06
af034a51-1c29-5951-85ab-cf4105d26783 | note | INSPECTION/TEST METHOD: Document Review
098e8831-624f-53d5-8a9a-b74a562e9245 | note | RECORD OF CONFORMITY: ITP Signed
28c8c112-048e-54fd-94dc-dcc02add2d24 | note | HP
cab6051b-f409-57ce-902e-04d33c423de5 | note | RESPONSIBILITY: Project Engineer/ Supervisor
85a6a81e-4e98-5781-9d1a-120a607b328c | date | Date Completed:
f0628378-9cdb-4e0c-a2e3-339a822f98ec | signoff | AUTHORITY HOLDPOINT
852daf89-e712-4b07-9222-6b796f4a8013 | section | 2 - Construction Works
71878ca6-80c7-42d1-ae7f-0828f8499e3f | checkpoint | 2.1 - Forms
bbbce5c8-3fcc-5238-937f-98b0c44a73f3 | note | FREQUENCY: Each Lot
35c19c5b-475e-59c6-9b86-1dcfe5139567 | note | ACCEPTANCE CRITERIA: Forms shall be manufacutred from steel, except where otherwise approved by the Superintendent.
be2c262e-8d4f-5499-94cf-09f586356e58 | note | ○ The formwork shall be constucted to as to produce a product in accordance with the design drawings, and with the surface finish and tolerances specified in Section 610.
d088447f-2dd5-58f8-86e7-0f96f73d2bb2 | note | ○ Casting bed to be inspected by designated Precast Concrete Surveillance Officer.
8c92bb71-afe2-5817-b10a-f88b6650698d | note | REFERENCE DOCUMENTS: Design Drawings , VR Section 620, 610.
9e173c59-3a37-51dc-a65b-a3b0572c8e2c | note | INSPECTION/TEST METHOD: Visual inspection
e56cf3da-8152-56a0-901a-299fe0100487 | note | RECORD OF CONFORMITY: ITP Signed
06fe1469-f6cd-5276-ad2e-34f552b70f93 | note | HP*
60458cfc-df2b-5b95-b868-465cc5a04e15 | note | RESPONSIBILITY: Project Engineer
dd9ae77b-a221-5b08-b759-a77045dad2ff | date | Date Completed:
13e55d3c-b99b-491c-aa10-88b96c9529db | checkpoint | 2.2 - Stressing operations
f774a81e-b6d6-50db-a53b-83934a4bfa2d | note | FREQUENCY: Each Lot
549831e9-d16a-5430-91e7-6e7be50ccb1b | note | ACCEPTANCE CRITERIA: All stressing operations shall take place in the presence of the designated Precast Concrete Surveillance Officer,
1141827f-7ad7-50b4-bc3c-f0ff59cbea42 | note | REFERENCE DOCUMENTS: VR Section 622.06
0aacc4b0-0881-51a1-b50e-ac658fd599fb | note | INSPECTION/TEST METHOD: Visual Inspection
37982b30-f29e-5eb4-babc-7112e471ab21 | note | RECORD OF CONFORMITY: ITP Signed
5e00960b-cef9-5bcc-ba83-839c61105610 | note | HP*
5c0e4747-2193-5a8a-a119-cde5ef7255a7 | note | RESPONSIBILITY: Project Engineer/ Supervisor
abe111ec-24d2-5cfb-85b7-ed65638e9ccf | date | Date Completed:
7252be66-0266-4895-ac84-87900709b74a | checkpoint | 2.3 - Pre-pour inspection
45954987-f806-5bd3-8468-52cf996c8409 | note | FREQUENCY: Each Lot
9107a62b-2d54-50ee-bb97-4a770cec4e5b | note | ACCEPTANCE CRITERIA: Ensure the completion of the Inspection Test Checklist (ITC) by the designated Precast Concrete Surveillance Officer.
b230ff81-26c2-500f-8ca4-a2ea859f7431 | note | REFERENCE DOCUMENTS: VR Section 622.06
090f6a6b-1b83-5410-91d7-46a90b376e95 | note | INSPECTION/TEST METHOD: Visual Inspection
095924d8-ca4c-59d4-8493-0fe4787a1e67 | note | RECORD OF CONFORMITY: ITP Signed, ITC Complete
6a6b9a32-974f-5311-ac25-3bb57751f353 | note | HP*
580fe62c-e194-5049-b7e4-726b92b90e35 | note | RESPONSIBILITY: Project Engineer/ Supervisor
3590de3b-5162-5bdd-a159-70a7b399ede9 | date | Date Completed:
b0fd16b5-2b14-4f21-baae-538614556af3 | checkpoint | 2.4 - Data to be recorded
c6f2421e-d59e-53c6-9c34-3115957d8087 | note | FREQUENCY: Each Lot
122dc8b0-2f3b-5463-ba16-974b6e984bd9 | note | ACCEPTANCE CRITERIA: Ensure the following data is recorded and forwarded to the Superintendent prior to delivery of the pre-stressed units to the site:
42f041e9-72f3-5c12-82e0-8608a472f3c0 | textbox | ID No. of each unit
fb707a38-9c83-5eec-a8db-1d072fa9e495 | textbox | ID No. of prestressing equipment
fc00fa49-eb5c-5672-a29b-874785b6d781 | textbox | Calibration certificates for prestressing equipment
456b19ff-61cb-5f50-a03b-a7a2f1445b6a | textbox | ID No. for each tendon
a5c4a79f-bb4d-5227-ab6e-a09f88ae1242 | textbox | Sag take-up force:
f1c0dd14-ad0a-530e-8e6c-e2e56202ff11 | textbox | Elongation at take-up force:
946921d0-124f-5d85-965e-19cd15a9de82 | textbox | Obtained elongation at completion of tensioning:
73d4d129-e469-5ac5-93b2-97c30804de8d | textbox | Obtained tendon force at completion of tensioning:
2fa99a18-270b-5aef-a229-a35588b8e498 | textbox | Elongation after release of jack:
ada27e52-ea69-5d9c-8a19-ac56e3294d6c | textbox | Tendon pull-in on completion:
cbd7ec21-4904-570c-a732-640d11c33c18 | textbox | Compressive strength of concrete at time of transfer of prestress:
189e3422-678c-5009-b372-0e2fb4a2fbb4 | textbox | Steam curing charts
c51074ef-f0a9-5255-a048-c7c8db836999 | textbox | Hog measure following transfer of prestress:
7fd669a7-19a0-53c2-a4a7-bdc0d2c54235 | note | REFERENCE DOCUMENTS: VR Section 622.09
368cc617-eda0-51c7-9598-ece5a33d5228 | note | INSPECTION/TEST METHOD: Data Record
1828489a-a323-5cc3-a69a-eb8acf9cfb61 | note | RECORD OF CONFORMITY: ITP Signed, Record of Data
42e7e242-5cfe-5f7b-8e20-d72b1d068dfd | note | HP
d22f9fa3-587e-5950-b9ee-2bb60f34c617 | note | RESPONSIBILITY: Project Engineer/ Supervisor / Superintendent
12e6ef37-1cd5-5a99-9ce8-045dee5b8ab4 | date | Date Completed:
b8c397eb-1ba3-4676-8911-615beb65d34d | signoff | AUTHORITY HOLDPOINT
ef39d4aa-196c-4687-99e3-08b429a7a42d | checkpoint | 2.5 - Projecting reinforcement
30870e8d-2262-5e3d-a1a0-627e0da4b585 | note | FREQUENCY: Each Lot
970ae10e-e4e2-589a-ac32-74f90aa5024a | note | ACCEPTANCE CRITERIA: Ensure projecting reinforcement is in accordance with that shown on the design drawings and is in good condition.
2e78bb18-29c6-5037-ac8e-39c43ad1e5ff | note | REFERENCE DOCUMENTS: VR Section 620.03
b5012389-df94-5448-99e2-6b82285cd530 | note | INSPECTION/TEST METHOD: Visual inspection
07c561e4-bda1-59ee-99dc-71ff015f4797 | note | RECORD OF CONFORMITY: ITP Signed
7d6af11e-64ac-5f13-9765-064df681be11 | note | HP*
0e0f84f1-81d5-5e2b-8eac-8f14d9ab73c6 | note | RESPONSIBILITY: Project Engineer/ Superintendent
671bd940-6420-50eb-8824-c1332b7e54e7 | date | Date Completed:
ad0222ac-5af0-4f31-8e1e-82ba49fefe35 | checkpoint | 2.6 - Marking
3bcf5b57-74b6-5527-82e7-8981d6cefa2b | note | FREQUENCY: Each Lot
a2a09aa4-e6c6-5943-b3cb-285859817049 | note | ACCEPTANCE CRITERIA: Ensure the identification number, date of casting, the manufacturuers name or registered mark and the maximum mass shall be marked on every precast unit.
dac25e16-534b-5971-b43b-fd9e6ce77ff2 | note | REFERENCE DOCUMENTS: VR Section 620.06
b4b5586d-171f-54c4-a078-60050d185e37 | note | INSPECTION/TEST METHOD: Visual inspection
f63e1806-bff3-5e73-ad28-5060c5ea9f57 | note | RECORD OF CONFORMITY: ITP Signed / Certificate of Compliance - Formwork Inspection
d976b062-6575-58c7-a2c1-827edc7f0fe4 | note | HP*
c64e9f72-4115-5976-8e60-491a59939b70 | note | RESPONSIBILITY: Project Engineer
2545bf92-97f9-51cf-af80-33e200b6ec8d | date | Date Completed:
96c1b8bd-d935-4b77-9016-d107182c6a4d | checkpoint | 2.7 - Handling & Storage
5afcaea2-4250-5f81-ba18-313ddb961586 | note | FREQUENCY: Each Lot
56bf39a3-a54d-517b-8e20-3f67742c572f | note | ACCEPTANCE CRITERIA: The units shall be supported on bearers clear of the ground. Bearers shall support the units over their full width and be placed perpendicular to the longitudinal axis of the unit.
88055cdd-6d8e-5a5c-80c7-346567203b0a | note | REFERENCE DOCUMENTS: VR Section 620.07
aa9b9294-477f-527b-bf02-645b0eb471d2 | note | INSPECTION/TEST METHOD: Visual inspection
20c5b80b-236b-5768-bbcb-8998fdfe54b7 | note | RECORD OF CONFORMITY: ITP Signed
316561af-6e4a-5680-a875-2b97bd58c7dd | note | HP*
d9349559-b9c8-5f80-928b-0661117d8287 | note | RESPONSIBILITY: Project Engineer/ Superintendent
1ddb0007-f415-5dcc-b7a0-077c1d8fcd19 | date | Date Completed:
9b11a417-df61-465b-832a-d3431cf5c436 | checkpoint | 2.8 - Transporting
f0021758-e30b-5f1d-b9b7-a55d20ad11a2 | note | FREQUENCY: Each Lot
1cc8f34d-44d3-507e-8ee3-24012bb8aea8 | note | ACCEPTANCE CRITERIA: Units shall not be transported from the precast yard until specified 28 day concrete compressive strength has been achieved, and not before 7 days after casting.
fa694239-6c51-5fdb-ba2f-7ce195df1a54 | note | ○ No beam shall be transported and erected if it has a bow in excess of 1 in 400 of the length or 75mm whichever is the lesser. Should the bow at any time exceed the maximum allowable limit steps shall be taken to ensure the safety of the unit throughout the journey.
dbbd65ec-0a90-514d-a26c-aa3b0aac656f | note | REFERENCE DOCUMENTS: VR Section 610.14
d7dde9de-5b43-571c-8d62-953337dc4f02 | note | INSPECTION/TEST METHOD: Visual inspection
3bcca52d-9789-5196-aa5c-13b456f870d7 | note | RECORD OF CONFORMITY: ITP Signed, Concrete Test Reports
0c0ac93b-5a2c-5640-b49b-bc8a325d117f | note | HP*
31d46116-86c8-528d-8e53-5e43ca6ad9df | note | RESPONSIBILITY: Project Engineer
b1605783-3d81-539c-95cd-b388361831dc | date | Date Completed:
76eb0af4-fd23-48ae-b148-c64381b4f63f | checkpoint | Final Inspection
aabf7726-1f13-53ed-b29d-8526d27bb437 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b7aedf8d-e79a-5d06-9b95-5f7aa08050c3 | textbox | Print Name:
49b93626-fc2c-5ddf-b82a-176f7e056165 | textbox | Position:
623d45c2-09d2-5f7f-b99f-c1460f9d8127 | date | Date:
702661d8-df6e-4cac-8a0c-e56db303ce07 | signoff | Sign ITP
| checklist | ITP-005 - Off-Structure Bored Piles | itp | ITP-005 - Off-Structure Bored Piles |  | 634c52a4-4962-4f7e-862e-59c69052c8b1
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
4e4b0c92-67ac-58d2-833f-3564ee9c840c | note | FREQUENCY: Prior to commencing any activity
4754d6d2-973e-5619-ba8c-a7ca505f2bad | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
aa4a0ebf-210a-519d-b512-a4e66f0e8cff | note | REFERENCE DOCUMENTS: Drawings and drawing registers
37ae0676-052a-574c-8260-77bcc8c27ba0 | note | INSPECTION/TEST METHOD: Visual inspection
c5821888-5fab-505e-8e14-e1eca67f1e9f | note | RECORD OF CONFORMITY: ITP Signed
24a5cc9b-79c7-55c4-be76-bc3c777606c7 | note | HP*
6f5c2b80-639d-5858-a21b-3b0efcb84671 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
973a2675-01f9-5125-92f6-2e39037f5fe0 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
9fbddf21-4998-5683-b70c-dafe1653110d | note | FREQUENCY: Prior to commencing any activity
b8a4332c-4765-5038-8267-16a79ae60c30 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
d9415f3c-8fef-5e8e-880c-46f4fcb47865 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
589c5af0-f0ee-5f8c-95e8-cb7750534235 | note | INSPECTION/TEST METHOD: Visual inspection
15e6f275-63fa-5b9c-8a71-719d3d306f79 | note | RECORD OF CONFORMITY: ITP Signed
5974cc25-70e0-5811-be4b-17e035757a19 | note | HP*
b00bbaab-0120-54b9-8381-bd823527ae74 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
e2052d42-b750-5897-9719-17a54fb1aefe | date | Date Completed:
| checkpoint | 1.3 - Materials
fea6513e-6b85-5463-ac12-741d4897b8c3 | note | FREQUENCY: Prior to commencing any activity
ecce9b30-504c-5c58-8389-88a64904245a | note | ACCEPTANCE CRITERIA: The contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
aeca392f-7102-59dc-a3ae-fb254679c532 | note | ○ Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS.
87a0b1fd-53cb-5e47-9cef-eb8232995e09 | note | ○ Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing.
4f62a43f-742f-5a2a-8afc-e7cd7eef1d92 | note | ○ Ensure that materials on-site are sufficient for the completion of works.
9c39fafc-7a8e-5f85-bdb0-21eaf95fb1e7 | note | REFERENCE DOCUMENTS: Design Drawings, VR Section 610 & 611
59522605-c650-5b04-8cdf-11dddfc11fda | note | INSPECTION/TEST METHOD: Document Review
890076af-6426-5f58-b626-1e4bada779dc | note | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Material Data Sheets.
08a2e366-b5fc-5581-812b-a22c11e26067 | note | HP
e48097e3-eacd-5730-ad98-34902124604a | note | RESPONSIBILITY: Project Engineer/ Site Foreman
1bfa7c9a-b1f4-58ce-861e-31b427063cef | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Construction Works
| checkpoint | 2.1 - Indentification of Services
f80d555f-a5d2-5c3d-b01a-6fb37e748ce4 | note | FREQUENCY: Prior to commencing any activity
6562a315-ee8c-5917-adbc-b9b23910c44e | note | ACCEPTANCE CRITERIA: Ensure any underground service locations have been identified and marker on-site. Ensure any required approvals/permits have been received by service authorities prior to commencing works.
7bf2a5b7-615f-5532-b572-170be5fd8fa5 | note | REFERENCE DOCUMENTS: DBYD
8538852e-e475-53bf-8376-7f5e5f2094d4 | note | INSPECTION/TEST METHOD: Visual Inpsection
efec813c-d2ec-5b8d-ac47-ea8e08e82a4a | note | RECORD OF CONFORMITY: ITP Signed
cd6741be-38e8-5a43-bf8b-502244221471 | note | HP*
4f0df677-d964-50b1-a95c-3dcfa306563c | note | RESPONSIBILITY: Project Engineer
fd7616a6-2bba-5c21-a894-813fd0ad8be6 | date | Date Completed:
| checkpoint | 2.2 - Set Out of Piles
dc32a3fc-c3d9-586c-9678-95f58db5330b | note | FREQUENCY: Each Lot
9807e1d0-e319-5328-b8f7-934f406fa0ad | note | ACCEPTANCE CRITERIA: The Superintendent shall review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
1707ec08-2117-511f-ac09-ec8e7304a52e | note | REFERENCE DOCUMENTS: Design Drawings & Survey Data
a4edbf2a-5f38-50ae-a1c2-500fee1f5014 | note | INSPECTION/TEST METHOD: Visual inspection
322a15f7-a2b5-528f-8ccd-9c0b02904799 | note | RECORD OF CONFORMITY: ITP Signed
8c3d2af1-1826-5ebb-8e85-f869a0660361 | note | HP*
05f19c18-10b7-52f6-94bd-dbe6f67fcd5b | note | RESPONSIBILITY: Project Engineer
6edb5ac5-e04e-5615-b10e-1c87df43d7e0 | date | Date Completed:
| checkpoint | 2.3 - Protection of Adjacent Piles
a40e50d1-eb4f-5f10-8066-f536e6f1c9b7 | note | FREQUENCY: Each Lot
ff2d7fd3-0e14-579a-917a-306c76f7e6e7 | note | ACCEPTANCE CRITERIA: No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained the strength of 15 Mpa.
60fe490f-3954-5152-9dbf-a07b80495801 | note | REFERENCE DOCUMENTS: VR Section 608.05
c9e6583e-fcd5-5f6c-8e08-cccf6a45c953 | note | INSPECTION/TEST METHOD: Visual Inspection
a4024990-ba24-59f6-8827-a31c58ac3f36 | note | RECORD OF CONFORMITY: ITP Signed
a31a4dc3-d093-5097-9ba3-54317973b9f6 | note | HP*
63230783-7e04-51a3-bbe7-2d04940bd7a7 | note | RESPONSIBILITY: Project Engineer
78a36b02-947d-548d-8b2a-ade7ef2b7514 | date | Date Completed:
| checkpoint | 2.4 - Inspection of Piles
a6ee56b2-1412-57d7-8e05-e853931a465e | note | FREQUENCY: Each Lot
b3f57728-6f7a-5fb9-ac31-1ec5ea1d351f | note | ACCEPTANCE CRITERIA: Reinforcement/concrete shall not be placed until the pile walls and base have been inspected by the Superintendent to confirm founding materails are of strength to satisfy design assumptions. Concrete to be cast within 24 hrs of acceptance of any pile sockets.
db3073be-62f8-5ddd-b743-b29d61a6b19e | note | REFERENCE DOCUMENTS: VR Section 606.05
f272daf1-fed7-5ff9-b74a-f62ae9c5fbf7 | note | INSPECTION/TEST METHOD: Visual inspection
ba70811f-1780-5237-88a6-89264a9f2009 | note | RECORD OF CONFORMITY: ITP Signed
4b433fd8-8952-577b-9e93-97bfeb403f83 | note | HP
fcd3f6fc-41c0-5eb6-802e-3a309bf1c830 | note | RESPONSIBILITY: Project Engineer /Superintendent
122e0660-194f-51c6-875b-ced9b70ccf30 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Placement of Steel Reinforcement
49c6b0b1-97b3-5230-9a01-6609825bfc50 | note | FREQUENCY: Each Lot
9473bdfd-aee4-5a8a-8c5e-a9bd95dbfad5 | note | ACCEPTANCE CRITERIA: Ensure steel reinforcement complies with the relevant specification and design drawings.
c8359c9b-3502-574a-bc05-6e56b8afc692 | note | ○ Spacers and supports to be placed at intervals less than 2m along cages to ensure minimum cover.
de55ee08-9c6f-5b72-a1ca-2c516f0b799a | note | ○ Rag bolts to be pre-assembled and secured at the correct distances and levels prior to placement of concrete.
47f91f7d-4609-51f1-8c8d-a279eebc9e01 | note | ○ Ensure 75mm cover on all reinforcement unless noted otherwise on the design drawings.
7287521d-cb50-5707-9011-f08c83e55442 | note | REFERENCE DOCUMENTS: Design Drawings, VR Section 611 & 606.06
21742bb1-dae8-5efa-be66-dc0535fb7ff8 | note | INSPECTION/TEST METHOD: Visual inspection
8b7c01e4-1714-55ae-a2e5-ad222ddba906 | note | RECORD OF CONFORMITY: ITP Signed
85de8233-3e85-5085-ae1a-1f62752fe137 | note | HP*
99c1dd21-f14a-5e2a-9593-742e09047dd8 | note | RESPONSIBILITY: Project Engineer
436e99da-4a8c-576b-ab5c-8ddb668305ba | date | Date Completed:
| checkpoint | 2.6 - Placement of Concrete
d7604e82-d934-5b95-ade5-c58b0cf37dcc | note | FREQUENCY: Each Lot
906e1799-31b2-5d45-900e-59790c344859 | note | ACCEPTANCE CRITERIA: Ensure concrete being used for bored piles complies with the relevant specification and design drawings.
73aa4851-df70-5905-b89f-8a5edfa4e3b6 | note | ○ Ensure piles are free from loose debris and contaminants prior to placement of concrete.
f9e5a07c-97ad-5586-a143-2629d024000f | note | ○ During concreting, the outlet of the tremie pipe or pump discharge hose shall be kept a minimum of 2m below the top surface of the concrete at all times. If water is in the socket, the socket shall be backfilled with concrete tremied from the base of the hole.
cc4403ed-1c50-5125-a30d-308f852b1791 | note | ○ Piles shall be concreted within 24hrs of completion of the pile excavation and shall be poured with a continuous supply of concrete.
9c64d9b3-369e-5987-b253-86c4bfc65e7f | note | REFERENCE DOCUMENTS: Design Drawings, VR Section 610 & 606.06
7f104729-1bc8-5788-b7ac-7743c4afa263 | note | INSPECTION/TEST METHOD: Visual inspection
6c5c6df7-98ac-55a5-9135-5b2b7d789a73 | note | RECORD OF CONFORMITY: ITP Signed
8b38e2d2-791f-5945-add8-91fe398f527c | note | HP
a8b2b533-f7fb-5813-8ba1-c658ddbc8cd9 | note | RESPONSIBILITY: Project Engineer /Superintendent
3f793d8f-dc67-533e-8038-cd3f26fe094a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Quality Control Testing
| checkpoint | 3.1 - Concrete Testing
a9707194-3257-5e7f-8c97-da3b29536b3c | note | FREQUENCY: Each Lot
65041544-5e70-5479-9100-bf0511335f63 | note | ACCEPTANCE CRITERIA: All concrete shall be sampled and tested in accordance with AS 1012.
77f4bc73-fbd6-5491-8730-1a0a8865f3bd | note | ○ The minimum number of test samples shall be in accordance with Table 610.161 in the VicRoads Standard.
35cf50b5-bebc-5295-83df-7955d11bf646 | note | REFERENCE DOCUMENTS: VR Section 610.16
8a03a48f-ce25-5372-a2c3-886616d18741 | note | INSPECTION/TEST METHOD: Test Point
428173e8-abb2-550a-8ff6-3af92c227c1c | note | RECORD OF CONFORMITY: ITP Signed
0eecd48f-7de5-590b-b4f8-76f467700866 | note | HP*
2234a59f-65e1-5e2b-a078-0ca89ce0402f | note | RESPONSIBILITY: Project Engineer
39fa42f7-992a-569a-9790-c7db757c3e14 | date | Date Completed:
| checkpoint | 3.2 - Pile Integrity Testing
264db7d6-48c2-53c6-97c0-355cb623d5f0 | note | FREQUENCY: First six piles followed by every third pile thereafter.
d04fabce-4160-5927-999d-97241fefdd06 | note | ACCEPTANCE CRITERIA: Integrity testing shall be carried out in accordance with test methods specifed in AS 2159. All testing shall be undertaken by a prequalified consultant in accordance with the VR scheme for prequalificaiton and approval of the Superintendent. The contractor shall provide details of the pile testing consultant to the Superintendent for review at least 2 weeks prior to the testing.
0ef2d285-5e9e-5c6d-853b-1e8226667b95 | note | ○ Integrity testing shall not be carried out until the concrete has achieved a compressive strength of 25MPa and not before 7 days after casting of the pile.
e32ff24e-b7d2-5e28-b5f7-a95778a0f6b1 | note | REFERENCE DOCUMENTS: VR Section 606.07
eea6a132-6606-5ae7-a406-ae2d8299be1e | note | INSPECTION/TEST METHOD: Test Point
04442546-8318-5966-948c-c8d2f8c22593 | note | RECORD OF CONFORMITY: ITP Signed
a128ab95-430f-5842-9f75-42676b21dcbe | note | HP*
aae47b04-b363-5f26-8692-c91a189c1d92 | note | RESPONSIBILITY: Project Engineer
08b9a09d-29bf-55be-af82-f07115fae162 | date | Date Completed:
| checkpoint | Final Inspection
557f939d-c75e-5ff3-b1bb-f58c8daeec47 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b0d17104-de9b-55d3-9e85-727d3e36c2c3 | textbox | Print Name:
71ebde63-5ae3-5d2d-87da-cd9df41bfd25 | textbox | Position:
b33331cf-ec9c-50e3-827e-bfbadf26b11e | date | Date:
| signoff | Sign ITP
| checklist | ITP-008 - Placement of Crushed Rock | itp | ITP-008 - Placement of Crushed Rock |  | cd6b2e2a-6ad6-456b-8867-608a20973608
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
3ecb94ff-2cae-508d-8cf6-eafbdcd24b14 | note | FREQUENCY: Prior to Commencing
d577ffb6-823d-5cd4-8d1f-e3aa3379c6ac | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most up-to-date revision of the design drawings.
8f3ab8cf-48d6-5740-9514-8efcd1958fe2 | note | REFERENCE DOCUMENTS: Drawings and Drawings Register
b2f42cd8-3b0a-5280-8912-24dcbc46c6d2 | note | INSPECTION/TEST METHOD: Visual Inspection
442438b2-a87b-52cb-8004-4b5690c03b76 | note | RECORD OF CONFORMITY: Signed ITP
92baf330-efef-51d9-821d-8a0a03cf9bc4 | note | HP*
7ed280df-5ee2-52eb-984b-e42e1f2df927 | note | RESPONSIBILITY: Site Engineer
ad78ea22-7b85-5ba0-9465-9a2d2da21b5a | date | Date Completed:
| checkpoint | 1.2 - Material Mix Design
a34d69bf-1166-5fa8-b616-d74d195d2db1 | note | FREQUENCY: Prior to Commencing
ad88132e-4802-5412-8900-1fc076039584 | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
b1869070-9c34-5b92-b1b6-ff269f66e8d4 | note | REFERENCE DOCUMENTS: Cl.812.04
c14e4d83-af1d-53c6-aebb-9dec04573af6 | note | INSPECTION/TEST METHOD: Document review
d609ab5d-1528-5b48-b6bf-4c535e0d1305 | note | RECORD OF CONFORMITY: Mix Design Approval
c8a7d3ac-3abc-5130-b1d7-d29bc9967cd7 | note | HP
2d9d216d-e265-5afc-86fb-c3c0ebdb3819 | note | RESPONSIBILITY: Site Engineer & Superintendent
4c7746b8-ad13-5ca1-a0be-12c2f803438e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Implementation of all measures and controls
786d0b17-ed61-5485-bafe-34d1ea59d527 | note | FREQUENCY: Prior to Commencing
abad250e-5693-5b66-bcaf-bf95ad21366f | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, ECP, ERA, QMP, SWMS.
0c47eb2e-8b7b-5ba8-9653-3c93973fc88e | note | REFERENCE DOCUMENTS: IFC Drawings EMP, ECP, ERA, QMP, SWMS.
7774233a-6626-58f1-96d9-480fea004349 | note | INSPECTION/TEST METHOD: Document review & Site inspection
b68302f4-0f12-5fa1-88a1-c6fd00a97c58 | note | RECORD OF CONFORMITY: Signed ITP
c6ec7e3b-762c-57ca-993a-95b5f2356b95 | note | HP*
60737b01-48b5-55a9-ab89-f18ce7b8630c | note | RESPONSIBILITY: Site Engineer / Site Foreman
9ba08947-8c15-5ff8-bed8-d53103cc35e0 | date | Date Completed:
| section | 2 - Placing Fill
| checkpoint | 2.1 - Transverse Joints
e0ec7910-abba-5187-b807-8debd2b4b440 | note | FREQUENCY: Check prior to placing material
0c41aab4-891e-5231-82ef-2652459ce25b | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
5a49da1a-f502-5a67-94dd-1ac2959131f0 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08
96f5be13-1cf3-5a78-b8f2-ecf631d07b1b | note | INSPECTION/TEST METHOD: Site Inspection
7057041e-4c34-5806-a0de-b2647e8b3f79 | note | RECORD OF CONFORMITY: Signed ITP
4d4f6bd7-43b9-566c-bf15-cdf19a259d23 | note | IP
b3dccc9d-0787-54c6-9839-8e39581f9241 | note | RESPONSIBILITY: Site Engineer
225865ec-c219-5efb-b886-9db231fd7dcd | date | Date Completed:
| checkpoint | 2.2 - Longitudinal Joints
3fe6e048-d55d-53ab-93e3-093039acb3c3 | note | FREQUENCY: Check prior to placing material
5157bd6f-52a2-5235-90de-f4ff00ad0436 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
8d29c77b-da67-526e-a292-4ddaca7b0e0d | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08
af303aa8-45d5-572d-8d58-c83d53022754 | note | INSPECTION/TEST METHOD: Site Inspection
3b655ee1-958d-5eae-b084-917f2068ec53 | note | RECORD OF CONFORMITY: Signed ITP
849de597-3e86-5503-8b32-9e7e9e23a9fa | note | IP
3accb92c-4957-5a1c-860e-19d948afbbe9 | note | RESPONSIBILITY: Site Engineer
a6de807e-0e8a-5fdc-963e-2cdef51d0c11 | date | Date Completed:
| checkpoint | 2.3 - Lot Size
57e476af-be5d-5958-86d3-e30e8a29f129 | note | FREQUENCY: Check prior to placing material
c6eb70ef-c933-5939-a47a-ddf1ddd00c35 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
d8bd7fed-dc89-5d58-9b7c-2f3628533e57 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.09
a24dd524-2896-524e-b603-f0f19d31d6cd | note | INSPECTION/TEST METHOD: Site Inspection
d2748a10-954c-5a42-a3f5-736822307dca | note | RECORD OF CONFORMITY: Signed ITP
e2e5137e-41a3-5883-bf44-d1fc4e0703c5 | note | IP
574e2258-9501-5a2b-9744-b01042e9c746 | note | RESPONSIBILITY: Site Engineer
802f4e02-e436-5a5b-be9a-b867f2715ad8 | date | Date Completed:
| checkpoint | 2.3 - Layer Thickness
68a038e6-3b55-5112-a063-9ff02ff21672 | note | FREQUENCY: Each Lot
e0e150d6-37d1-5472-9eaf-1db56eedf899 | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150mm and the maximum thickness of any subbase layer shall not exceed 200mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
a0c469ba-e3bf-528e-ba72-6e27a841501f | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.09
450e67d1-3302-5df9-a84a-c2da6d1e6729 | note | INSPECTION/TEST METHOD: Site Inspection
a2a20e31-6f20-5505-8713-8ebbd82ebdbc | note | RECORD OF CONFORMITY: Signed ITP
6b92f0e8-0fae-5098-a820-0987f032cbb7 | note | IP
f395e7b2-48c0-5b1b-8fd3-b9e47cff32d9 | note | RESPONSIBILITY: Site Engineer
60f23ef2-d866-5b55-8e57-aea522e097d6 | date | Date Completed:
| checkpoint | 2.4 - Proof Roll
1a34a3db-57d1-5a2b-a5d3-8002fcce2d2c | note | FREQUENCY: Proof roll each layer
3ff6bf5f-fbe7-5df8-a6c4-f6b9bddb8189 | note | ACCEPTANCE CRITERIA: No visible deformation or spinging in presence of Superintendent's representative.
f9a86ff8-5611-5e3b-bab5-ae2a0f074397 | note | ○ Proof rolling plant to comply with requirements of Cl. 173.03.
9e64866a-8dc6-5370-8fb4-940199350751 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 173
79d8c33f-7235-55b5-835a-4d50215c3b9d | note | INSPECTION/TEST METHOD: Site Inspection
601fb7d0-5733-5613-8b24-b0131a555ef3 | note | RECORD OF CONFORMITY: Signed ITP
274f169e-e6a8-5987-9afe-77f5ff7c35d6 | note | HP/ WP
a35bd0c0-70ab-51bb-b711-5751ae675e43 | note | RESPONSIBILITY: Site Engineer & Superintendent
5af72df0-6bff-5b3d-b59c-1306e65ce227 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
117548f6-c328-5879-84cf-4fbe7cde9f22 | note | FREQUENCY: Prior to Testing
226090d8-2b8e-50ae-9bf4-78a309fd701e | note | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
e9f49a64-8ad2-5d5f-b96c-36e362831114 | note | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
1b12774d-58f6-5a9e-9694-a9c73d3bbe2f | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161, VicRoads Spec. Cl.304.11, Cl.304.12
667654e3-b6c2-5f66-87f9-270fd8e9e8b6 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
aa1cc431-c184-5aaf-85d7-ae0ce742d713 | note | RECORD OF CONFORMITY: Signed ITP
96fc3f65-7b60-5e1f-b04c-eaf3a04aa303 | note | IP
e74faa1e-be9e-5fae-b22a-fe313d9d955b | note | RESPONSIBILITY: Site Engineer
8f2aafa3-8de8-5a3b-afee-09f5a2ce000d | date | Date Completed:
| checkpoint | 3.2 - Compaction Testing
b0f69419-b98d-5a95-a5d5-ed7a9249524d | note | FREQUENCY: Every lot, every second lot (reduced frequency)
ef88ca73-0103-5dfa-ac7b-60294abcc4aa | note | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 98.0% (Scale A) 6 lot test Initial FrequencyTest No. ________- > 97.0%
32159187-69e8-5aa8-a275-99a19236fbfb | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.09
1327c5f0-7147-5d20-826f-b49495aff277 | note | INSPECTION/TEST METHOD: Site Inspection
2d068a36-07c5-57d8-8589-9cba39542b01 | note | RECORD OF CONFORMITY: ITP Signed, Test Reports
663ea29c-4311-59ea-a629-9ed05331a90c | note | TP
d36934c9-e406-5e59-9b96-b20d20cf34e1 | note | RESPONSIBILITY: Site Engineer
27554750-9f7e-5c93-94bf-599ca4d6a6c6 | date | Date Completed:
| checkpoint | 3.3 - Material Grading - Post Compaction
2f8788ae-d26e-52d9-ad1e-f8e67003e99d | note | FREQUENCY: Every lot, every second lot (reduced frequency)
02295323-be17-5947-9330-91b50ac23407 | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
0bf9380f-b46f-5edf-af96-2fbab94ddd5d | note | – Class 4: N/A
513b6eec-cabc-5a95-8c31-38ecffac7b07 | note | – Class 3 - As per Table 304.101 VR Spec.
511a518c-6875-5ccb-bb6c-98364c03385c | note | – Class 2 - As per Table 304.101 - VR Spec.
1ac75040-ddbc-5121-9a91-b60ecd1cf971 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.11, Table 304.111
0077417e-dd30-5c8f-aff7-1fc3201bd351 | note | INSPECTION/TEST METHOD: Test Point
d1c6c070-bbf8-5810-84c7-48c2cdbdac4b | note | RECORD OF CONFORMITY: ITP Signed, Test Reports
52ccc5d5-f095-5c25-907b-3cf001b8417f | note | TP
d3bff384-7bd7-57c0-b87e-5d9dca7d3ceb | note | RESPONSIBILITY: Site Engineer
c3371131-50ad-5fe1-824c-1da30dbba986 | date | Date Completed:
| checkpoint | 3.4 - Plasticity Index - Post Compaction
263ef5fa-28db-5bfc-8144-5e562340d03f | note | FREQUENCY: Every lot, every second lot (reduced frequency)
63fd889b-6977-5e47-bc48-9ac2a267035d | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
a2cdbaca-7733-515e-b4f5-2db342ee8402 | note | – Class 4: N/A
f87ba485-d410-585a-a38d-c89ab8dc26c6 | note | – Class 3: 0 to 10.
e3d8f440-7cf7-5600-aa75-ff7011549d6f | note | – Class 2 - 0 to 6.
5d45d40e-03f8-5049-9370-bd07cec67a3b | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.11, Table 304.113
536b9f23-5d15-52fd-b9b9-f9b545edb90d | note | INSPECTION/TEST METHOD: Test Point
49b06542-7750-5969-86c0-24163a076ae2 | note | RECORD OF CONFORMITY: Test Records
580af953-f05f-539c-af4c-5422c05f2087 | note | TP
26167e29-e6ee-500c-9fef-7add87917134 | note | RESPONSIBILITY: Site Engineer
bf239f1d-fe30-5874-8da7-66db1dc79014 | date | Date Completed:
| checkpoint | 3.5 - Survey Conformance
f437331b-1618-5d87-9ce2-182f95ae04d7 | note | FREQUENCY: At completion
c58327e1-fbb3-5783-b8e6-5e5e349a6635 | note | ACCEPTANCE CRITERIA: Layer to be finished smooth and uniform surface and after compaction shall conform within the following limits:
7ebd6b8b-89c9-53ef-9a01-77aba05f21f2 | note | ○ Shape: No point deviation > 8mm from 3m straight edge in any direction.
cc326a01-1904-5463-a22d-65e5662ebdc4 | note | ○ Surface level tolerance: Range x = +6, -10mm.
05b2b586-3226-5f80-a815-a41236a9cfc6 | note | ○ Max S = 10mm
fc5de92c-040e-5486-bfd1-2ef5266ae1f2 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.071, Table 304.072
9c0a051b-589e-58fb-a844-017faab58573 | note | INSPECTION/TEST METHOD: Survey
fed9eb35-fe45-5899-a0dd-7092ba7b2c85 | note | RECORD OF CONFORMITY: Test Records
83b15e38-678c-5dad-8f00-07342344269d | note | SCP
70c0dcd9-278a-5365-b726-0b6506a655e2 | note | RESPONSIBILITY: Site Engineer/ Surveyor
3aa2883f-5b6d-506b-a7c7-e47f19e8ebbf | date | Date Completed:
| checkpoint | Final Inspection
514cf3b7-18e6-544a-9e09-da8d6cd7dd0e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d5889ed3-5bcf-557e-83e5-8edce41624ae | textbox | Print Name:
f4655af6-f8b8-5b62-a57f-7151bc5c32af | textbox | Position:
af622ab6-d4f1-5ac6-aaed-3f48730927e0 | date | Date:
| signoff | Sign ITP
| checklist | ITP-009 - Cement Treated Crushed Rock Subbase | itp | ITP-009 - Cement Treated Crushed Rock Subbase |  | 735c05c1-c47a-4e13-8bdf-0b9ddf62724c
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
d79aa1a1-4e82-5249-8821-42072f6baa8b | note | FREQUENCY: Prior to commencing any activity
245b3946-c13d-5682-b7af-3f899d58fa86 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
87d4031f-6a9b-56c4-b1e1-f187daedf494 | note | – using the correct and complete set of drawings
6eb40224-efb4-5fc1-8987-17bc7ed47da2 | note | – all drawings are the latest revision
178d0736-3921-55e0-bf8a-e85e3e123c88 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
f693c311-fe7a-51c8-8544-1391cea12a1b | note | INSPECTION/TEST METHOD: Visual inspection
03924224-aaf6-5f3a-a176-822fd33b4317 | note | RECORD OF CONFORMITY: This ITP signed
eb36ef35-0e39-5bdd-8873-eba4ac745683 | note | HP*
47fb0840-1b71-5989-8fd1-d75ce1987a53 | note | RESPONSIBILITY: Project Engineer / Site Foreman
5c491d0e-92f2-5203-805f-1ef2981afcbb | date | Date Completed:
| checkpoint | 1.2 - Material Mix Design
e913d7f5-791b-5758-92f6-cb4f4e69096b | note | FREQUENCY: Prior to commencing any activity
7b0c44ea-0bf5-5716-bb40-6f194902fd2d | note | ACCEPTANCE CRITERIA: Material proposed for import as Class 3 sub-base material meets the requirements of VR Section 812 or 820. Obtain material compliance data from the supplier and submit to VRs for review
73c1bd03-57b6-519c-8d2d-538b866562de | note | REFERENCE DOCUMENTS: Cl 812.04, Section 820.04 to 820.09, RC 500.02
e9126599-f15d-58f6-a07f-ecd32d613447 | note | INSPECTION/TEST METHOD: Document Review
908e9a7f-4a02-52cb-9203-692a467f07ec | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval - Quarry Dockets
0237d1e5-83f7-5c6d-ade1-282ccacab932 | note | HP
a5a24840-0869-5702-85ad-bd933a4fab58 | note | RESPONSIBILITY: Project Engineer /Superintendent
6b2b2794-ad50-5d01-ae94-2c1d63db705a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Implementation of all measures and controls
9bc47587-95eb-5867-8c36-52b742870be8 | note | FREQUENCY: Prior to commencing any activity
534517a3-d6a6-59d9-a527-3915727b13e7 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
22831eb7-8d61-521c-8043-3d87c7231e13 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e86e892b-b642-5762-bf88-600e699c3c87 | note | INSPECTION/TEST METHOD: Visual Inspection
0a6c4705-03b0-56c6-9b51-365fe9a909ef | note | RECORD OF CONFORMITY: This ITP signed
bc6a7cd0-b39b-5b32-87ec-dcab49c68163 | note | HP*
9ded7d8e-33d2-50c1-b63f-ee65559f6b38 | note | RESPONSIBILITY: Project Engineer / Site Foreman
beb6f2d9-f619-5691-9f0e-41702e05ffec | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Materials
f9fbf718-9d55-5819-85ca-d6d268905195 | note | FREQUENCY: Each Lot
26e54934-7a99-5800-b405-f61e000deb67 | note | ACCEPTANCE CRITERIA: The Contractor shall supply all materials required to construct the cementitious treated pavement subbase. The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815.
4e25cd06-1a98-5771-abc9-92735d6f4652 | note | REFERENCE DOCUMENTS: Cl 306.04
7fefe578-df48-517f-8309-b93def3779f3 | note | INSPECTION/TEST METHOD: Visual Inspection
34475d76-5528-58cd-b5b9-8ae55dd4b754 | note | RECORD OF CONFORMITY: This ITP signed off
a59fa404-7d3e-55ac-8d79-43dd1287122a | note | IP
4f35b5df-d857-5de4-8453-11390b7ad8ce | note | RESPONSIBILITY: Project Engineer / Site Foreman
3709d1da-b396-5929-948d-c29b79cad52d | date | Date Completed:
| checkpoint | 2.2 - Moisture Content
feb54ebb-ae8b-5544-838d-400a03d174fd | note | FREQUENCY: Each Lot
376cef3c-cfc5-5036-831d-8a4f592c34b4 | note | ACCEPTANCE CRITERIA: The moisture content of the material at the time of spreading and compaction, expressed as a percentage by mass, shall be within plus 0.5% and minus 1.0 % from the Modified optimum moisture content.
7783a3a5-07b0-55b6-851d-6c7c3a8e1a33 | note | REFERENCE DOCUMENTS: Cl 306.05
c30721d1-8aee-5071-8250-b1bd244aff67 | note | INSPECTION/TEST METHOD: Visual Inspection
8abcff09-a3dc-5440-9e3f-ee6a0280db1e | note | RECORD OF CONFORMITY: This ITP signed off
95989450-cde0-5716-8893-08450e12b022 | note | IP
b662ccd8-dbd5-54f4-8e75-8b692b88a6ca | note | RESPONSIBILITY: Project Engineer / Site Foreman
691c425f-787a-5a10-8bce-c9d103c82c86 | date | Date Completed:
| checkpoint | 2.3 - Jointing
4978fd38-c084-530b-99e0-2b85b66a3c63 | note | FREQUENCY: Each Lot
7fa6e4b6-7bd6-5d57-9791-b5cd4c263843 | note | ACCEPTANCE CRITERIA: The layout of joints shall conform to the following requirements unless otherwise approved by the Superintendent:
6f85e817-11df-5d61-9b2e-1a4101443b5b | note | (a) material shall be spread in such a manner as to minimise the number of joints;
ba1378a2-6d07-5a1e-9c11-91b2e6b55656 | note | (b) in any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
faa754c0-e8db-523d-a357-0bb5ac57d66d | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
c4f2bf2b-2959-5573-a40b-4967bb42bccf | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
d00bc6f7-219b-5e92-9e83-69d65e2b7815 | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lane lines or within 300 mm of the centre of a traffic lane.
b2046f2e-2e9c-51f2-bee8-69599a2ca375 | note | REFERENCE DOCUMENTS: Cl 306.08
fcf92ce8-0bc6-52ba-a930-abde0e626d1d | note | INSPECTION/TEST METHOD: Site Inspection
4513a93f-4854-55e9-9444-4c9d04e47cd1 | note | RECORD OF CONFORMITY: Signed ITP
fed3bdab-52e8-54eb-a93e-daba46708d04 | note | IP
e975aafa-a9f6-5cfd-a0f7-cdc351a863bf | note | RESPONSIBILITY: Project Engineer / Site Foreman
9f3963b4-bc2b-56f9-a9d2-bd367ca840f2 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Test Rolling
3a89ccd6-42d1-5b03-9b35-fed8bdbe52df | note | FREQUENCY: Each lot
958af3bc-c472-5458-9216-d308ec39a7aa | note | ACCEPTANCE CRITERIA: Test rolling may be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
01eca82f-d516-5d19-94c0-b72360dd4711 | note | REFERENCE DOCUMENTS: CL 306.09
08743265-bbc3-560e-97b6-b5dc3f63a325 | note | INSPECTION/TEST METHOD:
dd2f0f12-6cda-5bd8-8bee-67a9649fee03 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
76ee8a77-00ee-5358-8f22-a0a9cff30a95 | note | TP
f1443a83-3ee0-5576-80d8-85d438e460a5 | note | RESPONSIBILITY: Engineer / Superintendent / foreman
bc5bba11-e6c9-5a0c-9e79-f4f7b2d99c58 | date | Date Completed:
| checkpoint | 3.2 - Compaction
d67c59bc-4bbe-54c9-8ea3-8d6c6935d3b0 | note | FREQUENCY: Each lot
b42f7fb3-3f5e-5a23-bd7d-c90895da5215 | note | ACCEPTANCE CRITERIA: Testing and Acceptance of Compaction
8f9d7ad3-b090-530b-b0a5-56a6664bf9c5 | note | ○ The work represented by the lot will be accepted as far as compaction is concerned if the mean density ratio for the lot is not less than 96.0%.
969d9708-dfbf-5a36-881e-578c07de3850 | note | ○ If the mean of the individual density ratio test values for the lot is less than 96.0%, but greater than or equal to 92% the work represented by the lot may be accepted but the method of rectification and/or redesign of the pavement shall be approved by the Superintendent. Alternatively, the Superintendent may accept the work at a reduced rate calculated using the formula:
fd1a2aee-dfe7-5256-af58-331570013795 | note | REFERENCE DOCUMENTS: CL 306.09
7ea25365-ed63-5e70-ab0c-5d9e39af75fd | note | INSPECTION/TEST METHOD: Compaction test and Visual
350baff6-587e-5c87-8e4f-f9af2ee1b295 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
050e87ca-b188-5f8e-b0a6-6ed921264f18 | note | TP
0df83388-fa73-5548-a4df-3713819b93bc | note | RESPONSIBILITY: Engineer / Superintendent / foreman
986ceef1-4bbe-5429-a7d7-6d3d6042d611 | date | Date Completed:
| checkpoint | 3.3 - Survey Conformance
5ba50551-4633-5c33-af64-b386c721ec39 | note | FREQUENCY: Each lot
72d08c92-f847-58e4-99b6-55edc966590c | note | ACCEPTANCE CRITERIA: Pavement subbase shall be finished to a smooth and uniform surface and shall, after compaction, conform within the following limits to the levels, lines, grades, thicknesses and cross sections as specified or shown on the drawings.
27e55447-6355-5ab9-975e-1d86eb2fb288 | note | (a) Width and Alignment: The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
4de13669-92b7-50c8-b103-8bdd297da6b2 | note | (b) Surface Level of Subgrade and Pavement: The surface level of the subgrade and pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet requirements as specified in Clause 306.12.
fd977c0a-345f-5220-a7f6-e6f0e0778edc | note | ○ Surface level tolerances: Range x = +6, -12mm
d3d3609f-80e7-5993-9e63-57f13b37cc83 | note | REFERENCE DOCUMENTS: Cl 306
12037a08-4df7-5ffd-b8b4-5524e8331d62 | note | INSPECTION/TEST METHOD: String Sheets
57b419ea-2fd0-5780-bca3-cc2a29477cfe | note | RECORD OF CONFORMITY: String Report / Visiual and ITP Signoff
b82202e9-f42f-5fb0-b192-f7ed818f0842 | note | SCP
6aadafaa-0c8c-5786-bd06-b48ddf36cb4c | note | RESPONSIBILITY: Engineer / Superintendent / foreman
4ef7afa1-e4a2-5363-8531-78b55722057c | date | Date Completed:
| checkpoint | 3.4 - Curing
26683241-3be5-5514-9e71-1eeef1df494d | note | FREQUENCY: Each lot
7514ecfd-c252-5d49-9eab-ae1c1c6ee70e | note | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Specified
8ea50291-4877-5d28-b013-ffa5ce123162 | note | ○ The surface of each compacted layer shall be kept moist for a period of seven days 1-3 days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
af71b51e-2465-54b9-ac16-86c9a2c5c81c | note | ○ Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
3d10bde7-eecf-5178-a08e-05019b686f70 | note | ○ The subbase shall be kept in good order and condition and free from contamination.
2a5af582-bf06-5375-a577-bcc6e7dc0ae2 | note | REFERENCE DOCUMENTS: Cl 306.11
c94384f2-2268-592b-beb8-b098609723e3 | note | INSPECTION/TEST METHOD: Compaction test and Visual
c08868a5-787e-593f-a99f-775d9b4b84f4 | note | RECORD OF CONFORMITY: This ITP signed off;
d7dcaa23-bce9-53b7-bd48-393bbb95651d | note | IP
a968c262-fdbd-52c6-8934-e95bf5f4414f | note | RESPONSIBILITY: Project Engineer / Site Foreman
49b6d928-6b4e-5fb3-a361-5533d6a339be | date | Date Completed:
| checkpoint | Final Inspection
814e6863-6c18-5ae8-b7bf-2573874ff4f9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1c1de43f-5632-5d98-a5b5-098c86f3a9de | textbox | Print Name:
d0621a5f-fb58-5bdc-8572-dcc43ab3bb7f | textbox | Position:
b638d7fd-75ab-5830-8d10-70e16499af1a | date | Date:
| signoff | Sign ITP
| checklist | ITP-010 - Hot Mix Asphalt | itp | ITP-010 - Hot Mix Asphalt |  | 165326d9-b837-48db-8a5c-6b1553412a4d
| section | 1 - Construction Works
| checkpoint | 1.1 - Submission of Mix Design
8fd2acf1-43da-5b69-a265-3e63aeefa53e | note | FREQUENCY: Prior to commencing paving
8d1028b1-374b-5053-8b33-cc3a83df8f52 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
90d371c8-e3f5-5e33-9a6a-a16eb44c371d | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
6da12f82-2f2e-5cf7-b616-27e7583423c8 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
13fb1fe9-2584-5d72-8e8b-bf2536db4392 | note | RECORD OF CONFORMITY: VR approval, Completed ITP
ff6c265f-f4b9-5848-ae42-78b17f5bfac3 | note | HP
afd1f5b5-8676-5155-953c-f4429db0f418 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
0482bd5d-7b31-5634-8c5d-e47898787ea9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Implementation of all measures and controls
b6537698-5ab2-5bb5-b6f6-9caf166a14a2 | note | FREQUENCY: Prior to commencing any activity
ddfeaaac-d885-53c8-b565-30bfd4251b3e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
2b12f0cd-75cc-57e6-8caa-b60766f72333 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
860ea9f5-31f3-5ea2-a813-3eb85f12a29b | note | INSPECTION/TEST METHOD: Visual Inspection
fe433e7d-9974-5b8d-bc33-a3dd4f6869c2 | note | RECORD OF CONFORMITY: This ITP signed off
036481ff-6710-5d55-a240-0e26ddf76a9e | note | HP*
027e643d-b9ee-5642-97b6-7b744e7c5a1a | note | RESPONSIBILITY: Site Engineer / Site Foreman
cba69d87-5e9a-5aeb-a8c4-a22c685abab3 | date | Date Completed:
| checkpoint | 1.3 - Site Inspection and Base Condition
112e712e-37bd-5365-8278-76367c018df2 | note | FREQUENCY: Prior to commencing paving
6bdede4a-b9a4-5179-845b-ea082fcea370 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
a539ae63-d97c-5a0c-9138-e0d6cc0b77a0 | note | REFERENCE DOCUMENTS: VicRoads Spec 407.14, AS2150 10.1, AS2150 10.3, Completed ITP-008/009
f17431cc-5d83-56c7-9c25-7fa021230a33 | note | INSPECTION/TEST METHOD: Visual Inspection
06bccce2-d7ad-53be-84bb-6defcb74ed97 | note | RECORD OF CONFORMITY: ITP Signed
d04c00f4-fa3b-5c07-83fd-34c493097960 | note | WP
b5845c14-205d-5af2-9ae4-ac27921f0e75 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
602881a2-337a-5599-845f-569992159939 | date | Date Completed:
| checkpoint | 1.4 - Ambient Conditions for Placing
ec77288c-b8e8-5543-a177-cb13407f4ea8 | note | FREQUENCY: Prior to commencing paving
075b43d7-d69c-58af-a1d4-bd80d3ec6ef9 | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
6815a5f1-51ff-5991-9cce-0bdb474454e2 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
edffba7b-0d83-562f-84d3-61c98593b4a9 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
df14e439-3fc2-57c6-b1f5-c23d33a36227 | note | REFERENCE DOCUMENTS: VicRoads Spec. 407.13
2b93cfde-e293-5eae-849f-f7c6e830d118 | note | INSPECTION/TEST METHOD: Verify
b8936103-c7f0-50e9-a68d-ea9dbe0d61e0 | note | RECORD OF CONFORMITY: Thermometer
0efdf0ac-efde-55e5-9cd4-bf9367c9d8cd | note | IP
34fe9765-b877-519c-82dc-3115962e66ce | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
5f7abf66-0e70-59a3-be28-adff15dbcaae | date | Date Completed:
| checkpoint | 1.5 - Planning of Joints
34234ab5-0fd5-5b37-9401-0ac3a6c6b44e | note | FREQUENCY: Prior to commencing paving
e5a2236d-d372-574d-9c13-82361c5cf982 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
f7f445ef-9d58-593f-bdc5-a23913139f00 | note | ○ Transverse Joints Offset from layer to layer by at least 2m
ec754e52-6ae7-50a5-a835-07e72d54b66a | note | ○ Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane.
16b858cb-1f9f-59f6-a9b5-95079d1a0177 | note | ○ Wearing course shall be on lane lines.
ac98c418-4155-5bc5-8f1e-f3aa2396a238 | note | REFERENCE DOCUMENTS: VicRoads Spec 407.17 (b) & (c), Pavement Drawings
9a62364e-c1e9-5316-b244-1d7d8948d42e | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
f621603e-b95e-55b8-b00b-4d3db583bdd3 | note | RECORD OF CONFORMITY: Paving Plan
31c345c1-1430-50c4-b158-4bf8ab7e90ef | note | WP
ed312651-5901-5965-ad07-5d1a1649b47e | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
ffac984a-7a20-5611-a5a3-f16a59827e70 | date | Date Completed:
| section | 2 - Asphalt Placement works
| checkpoint | 2.1 - Commencement of Placing
183b0a4c-79e0-52f1-967f-6c9c548adb34 | note | FREQUENCY: Prior to commencing Paving
f5aeecb9-e403-54bd-bdbe-54080f631315 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
9847fae6-7849-5875-b6e6-3d157a629bc3 | note | REFERENCE DOCUMENTS: VicRoads Spec 407.18
daeeb296-66f8-5fcf-8588-6a43b1dcf6cf | note | INSPECTION/TEST METHOD: Visual Inspection
3af121e2-8274-573f-8683-58f90f5639a5 | note | RECORD OF CONFORMITY: ITP Signed
46bede2e-c09f-5113-b300-51bea6fd8dfc | note | HP
c02d763a-baa2-54fd-9e6c-9bb5478abecb | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
3a89e1a9-c750-52c4-93f5-5ab92d8f6a47 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Delivery of Mix
acf5145f-481c-5c49-9574-11b8b57675ce | note | FREQUENCY: Each load
cb5a1b4c-5faf-52f6-bd69-cdd43e548505 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
2c8fcd4f-d223-5ffe-be74-66c7e9aaea83 | note | REFERENCE DOCUMENTS: VicRoads Spec 407.16, Table 407.081
ea91ca7a-4882-5ca8-9b0c-c6874dcb61ba | note | INSPECTION/TEST METHOD: Visual Inspection
1f3876d2-cd9b-5acd-9c9c-62dc11349a81 | note | RECORD OF CONFORMITY: Delivery Docket
ab09f414-93fc-5231-a205-0b4b33ef9606 | note | WP
e1db6439-1e0e-5cc1-914d-7bc1d10843e2 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
98b5e5b3-5b34-5e2b-adca-a59e6a76b16b | date | Date Completed:
| checkpoint | 2.3 - Traceability
8560a259-9871-5cea-879f-6757e3e896de | note | FREQUENCY: Each lot
9bb8dee2-04f2-54b9-9286-8189094fcb7d | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
d5204b2c-048c-5950-8ca0-7cabca099cee | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
f4716aa9-c1ef-505d-b916-345e9d96328d | note | INSPECTION/TEST METHOD: Verify
dd0f07fe-c044-5756-9408-c0a8ba5f8f90 | note | RECORD OF CONFORMITY: Daily Lot Record
316cf71a-5be8-537a-8057-88758ef50e97 | note | IP
4dab3b38-30c8-5ad1-b72b-84945065a5a7 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
43b6cd5b-bc07-5740-8cb7-5d96b8f665ab | date | Date Completed:
| checkpoint | 2.4 - Layer Thickness and Level Control
2f7dfbfd-5129-53e8-a90d-5745b6a10a22 | note | FREQUENCY: Regularly during paving
eabacdf9-3c04-53f3-b939-92be99fd661f | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
33d4d1b0-1670-50db-85d5-ba00f9957d19 | note | REFERENCE DOCUMENTS: VicRoads Spec 407.20 (a) & (b), Drawings
93326ae0-34b3-51b4-8336-754b4bcea4e9 | note | INSPECTION/TEST METHOD: Verify
ae8a4162-f974-5bf8-a7f1-77cf06ecc87b | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
f4d9892f-a3ca-5e9c-8365-afa9d2c68d6e | note | WP
828c2744-c89c-5c8c-a769-68c43ffb1a63 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
cceb9047-8e8e-5510-8ff3-2d432df60911 | date | Date Completed:
| checkpoint | 2.5 - Surface Finish of Wearing Course
71daa2ae-1b24-57d5-99b1-d208db28ef09 | note | FREQUENCY: During paving and after final roll
1f492b3c-feb1-5b41-8d01-62415bed9ff4 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
5c1ce839-3b48-5031-bb3e-8eb710d45880 | note | REFERENCE DOCUMENTS: VicRoads Spec 407.23 (a)(i)
d89f2ab0-8ba0-5b1a-adbb-b892a8f63621 | note | INSPECTION/TEST METHOD: Visual Inspection
00cf221c-8502-5ee2-8e45-ba2a1dbcb606 | note | RECORD OF CONFORMITY: ITP Signed
3a60b336-5a6c-5c62-a3d0-3083216bc5cc | note | WP
47f3879a-57c0-5379-b1c5-108d65c578bc | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
ca8bb7dc-80c9-51f7-a9a8-b2be645777a1 | date | Date Completed:
| checkpoint | 2.6 - Kerb and Channel
0d1c8314-7b80-5893-b8dd-3434a2f3cedb | note | FREQUENCY: During paving and after final roll
7ee7a961-3fd5-560b-b448-10b4c0ebcf18 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
88ea8552-ee68-5071-96f8-6cbf7ef8b6f8 | note | REFERENCE DOCUMENTS: VicRoads Spec. 407.23 (a)(ii)
28b483af-dc17-5eab-bd4b-9b1b82449ec2 | note | INSPECTION/TEST METHOD: Visual Inspection
ad579586-0662-5d43-b220-4c98bce8d4da | note | RECORD OF CONFORMITY: ITP Signed
9714861f-1dad-58ae-8ad6-5bca8da35d23 | note | WP
092096ab-ec35-5a7c-944a-0e47834f80d8 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
27dcdfd7-36eb-525f-ae7b-283a3df9fcb6 | date | Date Completed:
| checkpoint | 2.7 - Alignment of layers not placed against concrete edge
a9edb242-8cf5-55f3-9631-7183b01da74a | note | FREQUENCY: During paving and at completion of work
d3b931c6-bb02-50aa-83bd-46e69b7ab9f6 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
02e77725-8ee1-5667-88eb-dd1439d4842b | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
fef28914-f842-57a7-9496-b3ec9bb5dc91 | note | REFERENCE DOCUMENTS: VicRoads Spec 407.23 (a)(iv), Drawings
d774f91b-ac24-5c0b-a08d-36ac0398d539 | note | INSPECTION/TEST METHOD: Visual Inspection
fc4567ff-539d-5c3c-aac0-8c7d752f45bd | note | RECORD OF CONFORMITY: ITP Signed
f8911aaf-9299-5472-a1fa-41e8b385d0ad | note | IP
9801cb73-ae6d-5e42-9740-8238c224e050 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
6336781b-e6fc-57d1-a1f7-90043f9de541 | date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Compaction
87bbe6ef-9cec-5a08-9226-e8f9eebc863e | note | FREQUENCY: Per Lot
91a04876-bd89-5df1-aa19-27880f6bc375 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
f45659f9-e7ba-527f-823e-6a1e751faf52 | note | ○ 94.0% or greater Accept lot
fc238f3e-f67f-57aa-92fd-f4d9390b7f46 | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
3770bf60-8d21-529f-abac-4f3fffb7e3b7 | note | For layers ≥50mm, if characteristic thickness is:
42336275-de20-5850-9de1-04fdc9ecf1a7 | note | ○ 96.0% or greater Accept lot
b6052c62-8075-57f8-813f-c548261bb15a | note | ○ 91.0% to 95.9% Lot may be accepted at reduced rate
4ce658d4-c227-583f-b125-cc0a175f8c0e | note | REFERENCE DOCUMENTS: VicRoads Spec Table 407.221
015f5102-3240-572b-83ad-6019ea10034a | note | INSPECTION/TEST METHOD: Verify
c2a3a7b0-b249-5f7f-9177-d8c1dbfcfed4 | note | RECORD OF CONFORMITY: Test Report
c078aeac-ce77-50d6-9bed-766bbaf30c65 | note | TP
75257f2d-b428-59d4-9854-a7aafa85e3a6 | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
53fe2ef4-34e3-567f-9819-5a6e9a5cb4c4 | date | Date Completed:
| checkpoint | 3.2 - Level Conformance
520f17ff-86e3-5ddf-b72f-c285f1fbebe4 | note | FREQUENCY: Per Lot
4ddb29fa-fc17-5cf2-9816-77455fe04cfc | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm
aae64156-9ccd-5a8f-9101-1c126a4654b7 | note | REFERENCE DOCUMENTS: VicRoads Spec Table 407.232
37182fcd-07cd-5ec5-89a5-b72b46314cc3 | note | INSPECTION/TEST METHOD: String Sheet
f983029f-ab1e-5d18-a122-6d0403952144 | note | RECORD OF CONFORMITY: Survey Conformance
2206f0d0-20d1-5933-bf2d-9af3c74e01f2 | note | SCP
68eee505-efd9-5089-a912-f1118e18a77a | note | RESPONSIBILITY: Site Engineer/ Supervisor
e28fcb89-6df7-5a65-be67-50c40ff47bd8 | date | Date Completed:
| checkpoint | Final Inspection
355608c0-9e80-558c-974b-d39a747fd951 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
70ab3dbc-85cd-53fe-b6ac-06af28f5da00 | textbox | Print Name:
bd01ab2c-b606-5e78-89d1-a1c3189a686a | textbox | Position:
81803609-9fd2-5ba9-bad4-165b4a5b60d3 | date | Date:
| signoff | Sign ITP
| checklist | ITP-011 - Type B Guardfence Installation | itp | ITP-011 - Type B Guardfence Installation |  | a3fcb7ad-1830-45c7-b2a1-fc046d6d72b5
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
58fdb6d6-ce91-5c94-a0d4-f23ae24e2916 | note | FREQUENCY: Prior to commencing any activity
73bedbc1-ea7e-5cdf-8bdb-df21601c8177 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
1167a120-cc14-5789-8d11-3d5b90844046 | note | REFERENCE DOCUMENTS: Design Drawings & Drawings Register
305c3598-7191-5b64-9185-8219b2f96129 | note | INSPECTION/TEST METHOD: Visual inspection
6e238d4b-7aee-5ccd-988d-e1dc7349ff93 | note | RECORD OF CONFORMITY: ITP Signed
cdd305b6-9e51-5349-96c7-318e2cf60314 | note | HP*
e217180e-ca9f-56e1-8efa-1777a29e152d | note | RESPONSIBILITY: Project Engineer/ Site Foreman
062d5abe-8459-5abd-9d20-c5e593584a0e | date | Date Completed:
| checkpoint | 1.2 - Materials
ad4915bf-b1f8-5543-8a32-987fee842317 | note | FREQUENCY: Prior to commencing any activity
47ce1596-5c64-562d-885e-4788e717414a | note | ACCEPTANCE CRITERIA: All materials are to be used must be on VicRoads current accepted products list (RDN06-04) and confirm with the detailed design.
0f73d54e-4c54-5705-8e46-59dea38fb38c | note | ○ The contractor shall submit to the Superintendent all test certificates related to the supply of steel for the works at least 14 days prior to commencement of installation.
6b5c9580-9588-51ca-b01d-602c8216a1dc | note | REFERENCE DOCUMENTS: VR Section 708.04 & 708.05
19a7a9f6-f310-5568-b72c-35077bb81e8f | note | INSPECTION/TEST METHOD: HP
872cf2a0-444b-5fae-bfa9-2a2e47b5e25f | note | RECORD OF CONFORMITY: ITP Signed, Certificate of Materials
84475027-b355-591e-84fe-087d3b96cec5 | note | HP
1cb4f3b1-c64f-5a0a-a1d3-bcfad50d7555 | note | RESPONSIBILITY: Project Engineer/ Superintendent
7c3fa634-7cf4-59cf-8b61-6232ae701169 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Construction Works
| checkpoint | 2.1 - Identification of Services
d1fc1844-434b-53a1-9db2-269b0498b11f | note | FREQUENCY: Prior to commencing any activity
786ab474-480d-5a57-810a-226e33f57e08 | note | ACCEPTANCE CRITERIA: Ensure any locations have been identified and marked on site. Ensure any approvals are in place with service providers prior to commencing install.
8b47d5e2-7eb6-5afd-8db1-4ff1800efcba | note | REFERENCE DOCUMENTS: DBYD
ef2b8db5-8f31-58a4-898a-c9c69c317763 | note | INSPECTION/TEST METHOD: Witness Point
fe25be1d-6933-5f51-93be-396ca80be678 | note | RECORD OF CONFORMITY: ITP Signed
62914c73-825f-53bb-aae4-2597ba0f4d98 | note | HP*
cb747389-8ee0-57fc-9f69-a92658dbdc0f | note | RESPONSIBILITY: Project Engineer/ Site Foreman
56f790cb-1721-521b-9ac8-c4929e15297a | date | Date Completed:
| checkpoint | 2.3 - Setout
85d56fcb-15c9-508a-955a-dcdeb2331a69 | note | FREQUENCY: Prior to commencing any activity
bc1467df-1fb6-513f-b100-12b25965b49b | note | ACCEPTANCE CRITERIA: Contractor to confirm with the superintendent the required location and length of all guard fence alignments.
e54a84f6-2567-5727-ab80-37a8ee22a131 | note | REFERENCE DOCUMENTS: Design Drawings, VR Section 708.08
8e004957-076c-54dd-a175-4f56ce9d24cd | note | INSPECTION/TEST METHOD: Visual inspection
897957db-60c7-5320-a23c-7f1685b6dc14 | note | RECORD OF CONFORMITY: ITP Signed
3a71e9af-55d4-51a5-b727-9a1f29840c28 | note | HP
e8cf8a3a-26b0-5df6-9b5b-b2f85ae7692b | note | RESPONSIBILITY: Project Engineer
66350837-9356-51f1-9d09-bb17f28fbc91 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Installation
76c295a7-31a2-5654-8284-ec710ab00e32 | note | FREQUENCY: Each Lot
d56fcfd8-37dd-57fc-b0e2-56a0e19d20e6 | note | ACCEPTANCE CRITERIA: Guard fence system to be installed in accordance with design drawings, manufacturer guidelines, and within tolerances set out in VicRoads Standard Section 708.07 (d).
dc0364ee-c6d5-5f36-968f-1634a0ca85a0 | note | REFERENCE DOCUMENTS: Design Drawings, Manufacturer Guidelines, VR Section 708.07.
1a0f2a40-a396-5f6e-8ffe-7b7b56307cd6 | note | INSPECTION/TEST METHOD: Visual inspection
d34599b8-a7bb-54eb-bbdd-cceb8aea8581 | note | RECORD OF CONFORMITY: ITP Signed
32ad86e5-63ff-52fb-ad1e-ee006acf96a0 | note | IP
aca23fcc-c033-5e1d-aabf-88b7a4233406 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
b3a264ba-d725-58d5-8731-e82109edc420 | date | Date Completed:
| checkpoint | 2.5 - End Treatments
c9e6a44a-9dd8-5101-b2c4-72a361024eb1 | note | FREQUENCY: Each Lot
12d33114-149e-58af-9815-42c8a7d3291e | note | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed in accordance with design drawings, manufacturer guidelines, and specifications.
d0a34760-41f2-55d1-88f0-a70219210aef | note | REFERENCE DOCUMENTS: Design Drawings, Manufacturer Guidelines, VR Section 708.07.
74d4c7b9-2aae-5a09-928d-f18419cb4613 | note | INSPECTION/TEST METHOD: Visual inspection
8626e207-20d7-54bc-8e65-5def975d51b1 | note | RECORD OF CONFORMITY: ITP Signed
9323c023-b2fa-571c-8e64-7714918b18a6 | note | IP
478aef69-3084-5f88-ba43-31a3788a6040 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
c7c0bd39-9728-5800-92f3-bea9ace55a2b | date | Date Completed:
| checkpoint | 2.6 - Installation of Delineators
79ed5195-63b3-5e98-86ce-3877d893d1e3 | note | FREQUENCY: Each Lot
f2716b91-bc7c-53f6-babb-62b42ccfb807 | note | ACCEPTANCE CRITERIA: Contractor to supply and fasten delineators on left hand side (red) and right-hand side (yellow).
f76aa335-3d06-51fe-905f-5b9892ea00bf | note | REFERENCE DOCUMENTS: VR Section 708.07
3c9310a2-ce29-5106-9090-11c44002dc31 | note | INSPECTION/TEST METHOD: Visual inspection
b01de269-eb9f-58b5-a2c9-27ff33bb76d3 | note | RECORD OF CONFORMITY: ITP Signed
649ac3df-905a-514a-8e31-61857ee325be | note | IP
14afdf33-0f77-5c06-93fe-3f5d8f55b914 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
17087b9b-4b4e-5523-9d08-f53767d9857b | date | Date Completed:
| section | 3 - Testing and Quality Control
| checkpoint | 3.1 - Submission of Certificate of Compliance (CoC)
0eb75073-780b-5be7-9d95-fa49d1c3fb14 | note | FREQUENCY: Upon completion of install
0bfb312c-dfac-5d97-a786-1b577f6ad993 | note | ACCEPTANCE CRITERIA: Contractor to submit the CoC to the Superintended from guard fence supplier.
493ecec7-e8aa-5e12-8776-3fbf3c224e5d | note | REFERENCE DOCUMENTS: VR Section 708
37f16aed-a1a4-5dc7-96c6-204116fda9ac | note | INSPECTION/TEST METHOD: Test Point
ff3c52e2-d2c6-5c36-ada2-cab950233774 | note | RECORD OF CONFORMITY: ITP Signed
26d0fd0d-9f6a-5411-907c-940e0daa5f42 | note | TP
8076cb59-7418-52fa-9e42-b84847023217 | note | RESPONSIBILITY: Project Engineer/ Superintendent
50c257be-5837-541f-825f-036720ce1f7e | date | Date Completed:
| checkpoint | 3.2 - Submission of Material Test Certificate
b0760873-e6a8-53fe-9bd7-3a4f5d25f273 | note | FREQUENCY: Each Lot
cb5141e3-19c7-5407-b1f7-9f8683367922 | note | ACCEPTANCE CRITERIA: Contractor to submit test certificate to superintendent from guard fence supplier.
950eb267-9a11-5ada-8894-1b6a9f9c7c49 | note | REFERENCE DOCUMENTS: VR Section 708
bf0e162c-0640-557e-acc0-26c8240e02c9 | note | INSPECTION/TEST METHOD: Test Point
4105ffda-a0ca-5655-82d3-f24c6b5c9379 | note | RECORD OF CONFORMITY: ITP Signed
d0f4911a-4e3a-569f-b968-39881dc8181b | note | TP
998517bd-4b3d-5247-9a81-91a63a56d475 | note | RESPONSIBILITY: Project Engineer/ Superintendent
d3e4b0a3-fd42-5b35-917e-dc1c47476b97 | date | Date Completed:
| checkpoint | Final Inspection
9c1ca522-68a1-5f14-aeef-9b1d0b40ce2f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
197e31cf-5c9f-5c7f-99b3-4b873b7b64d5 | textbox | Print Name:
bf6588b2-f43b-5efe-b0be-6fcbca4f0029 | textbox | Position:
7036207d-cd84-55b2-bebb-e61f548d5a39 | date | Date:
| signoff | Sign ITP
| checklist | ITP-012 - Subsurface Drainage | itp | ITP-012 - Subsurface Drainage |  | b50dbbee-8124-4f79-9a57-318164da9865
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
0920e470-64c7-5478-92d6-cc4a49080046 | note | FREQUENCY: Prior to commencing any activity
6dc79816-e8cd-58ce-994b-a28db1cbd503 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
87e72ed0-9009-5c7b-862c-d2cbcd01cb27 | note | – using the correct and complete set of drawings
784aef8f-b71c-5d74-8a88-102b1bcf87d3 | note | – all drawings are the latest revision
dbe548a0-9e04-5289-a4f9-d961ba15272f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2f0da3d3-830a-5f02-b05f-30a125b10d18 | note | INSPECTION/TEST METHOD: Visual inspection
36d73d02-c12a-5db4-811c-ee195e8ab504 | note | RECORD OF CONFORMITY: This ITP signed off
86747c95-0bf7-5a6c-ada4-250f2c2f29eb | note | HP*
a08c8414-9752-5e2d-a9ee-1b6d40af9a44 | note | RESPONSIBILITY: Site Engineer / Site Foreman
3a759b2f-a211-5661-9fc6-7bf43e47f114 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
1bd74be9-eb53-5bd9-bbd0-46e6294d5e51 | note | FREQUENCY: Prior to commencing any activity
a53e40ad-9646-5daf-a28b-00128c98ae18 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, EMP, ECP, ERA, SWMS
5b291697-2058-550d-a2ad-ef6bb3007c94 | note | REFERENCE DOCUMENTS: QMP, EMP, ECP, ERA, SWMS
3dadae19-73dc-5c41-a904-d97cb0f6acd1 | note | INSPECTION/TEST METHOD: Visual Inspection
9f719a1a-8da5-5150-9aaa-64ee515c0103 | note | RECORD OF CONFORMITY: This ITP signed off
14bc5054-bf1a-5cbb-8bef-07522cff02b9 | note | HP*
548345f6-871b-5b38-a477-6df5e80f2cb4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
53fe5ba3-ddb4-59e1-b4dd-8fe4fab7c599 | date | Date Completed:
| checkpoint | 1.3 - Placement of no fines concrete
e551bcee-0e9f-5682-9e79-0cd1aadb0079 | note | FREQUENCY: Prior to works commencing
b4c374b2-6236-5464-92f2-a2573e9cc431 | note | ACCEPTANCE CRITERIA: Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete. The method of compaction shall be in accordance with the Contractor's quality procedures
cbb8539f-427e-5f13-8a5e-8ae8fcf43513 | note | REFERENCE DOCUMENTS: VicRoads Spec 702.09 (g)
35b1db8e-8c87-5f17-b5b3-2426bdf63d94 | note | INSPECTION/TEST METHOD: Verify
acd1a1ae-c59d-5d28-af73-64e92b7ac78b | note | RECORD OF CONFORMITY: This ITP signed off
2d35d639-0967-5ea4-8b23-7585afd13e0b | note | HP
ce5c508b-5015-560a-84c7-ff228776711b | note | RESPONSIBILITY: Site Engineer/ Superintendent
fa8fd634-6f67-516f-83b3-ca36cbcaa83f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Material Classification
0e8eb69f-a497-54d1-b6dc-e6e5851f47ca | note | FREQUENCY: Each Lot
3fd643b8-79a1-554f-81ad-3d50f972572f | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes: 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
6297a6ca-c168-528a-873c-5332bc25b8a5 | note | ○ Granular filter material for bedding and backfill: Trench backfilled with no fines concrete filter medium complying with Cl 702.05
5d7fa7b4-cb74-56f0-9996-8d713e323e28 | note | ○ Geotextiles: Shall comply with Cl 702.06.
4c9bd30a-6fbb-5c28-aea9-3e7b8c21f155 | note | ○ Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
d705094f-ce68-52a8-8672-3b1cf955e7b3 | note | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
9a68362b-4bfd-5fa1-b8de-1f2dbf05dcd3 | note | ○ Flushout risers: Constructed to the detail of SD 1631
aaf734d7-1050-537b-b4a2-34d96517b69a | note | REFERENCE DOCUMENTS: VicRoads Spec 702.04, 702.05, 702.06
d8ef9aa4-83a6-5503-bf97-ccf9f6ce88c3 | note | INSPECTION/TEST METHOD: Verify
a4f02bc5-f2cf-57bc-bb96-08280886cac9 | note | RECORD OF CONFORMITY: This ITP signed off
c317ca78-37a0-5e1d-bac1-27fc5cd29d38 | note | WP
26ea11d8-d39e-56ab-b266-5c652304ce2b | note | RESPONSIBILITY: Site Engineer
4fa93a6d-b6a8-510d-b8c6-fb0d4177c736 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation Permit
bc0f557b-c119-5b17-80c7-2d2b6c1496c5 | note | FREQUENCY: Each lot
69fdbf2e-8ae1-582c-a7e7-77c27d4aebef | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
24d840b2-491f-5d7a-9c38-280922f18372 | note | ○ Plant and equipment shall be appropriate for the task.
b2828df7-83b2-5a96-82ba-85fa4dab61aa | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
d240aa68-2f58-57dc-b46e-34dabb28a9cb | note | REFERENCE DOCUMENTS: Excavation permit
0379cb63-6553-5649-bb85-8e13c9df2559 | note | INSPECTION/TEST METHOD: Verify
6921539b-22c5-59b9-9cd7-0af88822b9ed | note | RECORD OF CONFORMITY: This ITP Signed Off
77506840-1850-5778-82b0-137219f188df | note | HP*
c26b9800-2bd5-504d-9ec6-cb779ed54890 | note | RESPONSIBILITY: Site Engineer
f6f8c516-9ba6-5482-b0ac-f946c281d44d | date | Date Completed:
| checkpoint | 2.2 - Excavation of Trench
9f16f3ce-6b19-5fbb-bdb0-7eff06b00687 | note | FREQUENCY: Each Lot
594a4450-9e37-5f2e-a6ae-2e7c068765f6 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
d2c20505-91e4-5efa-8a6e-45c33b565397 | note | REFERENCE DOCUMENTS: VicRoads Spec 702.08
8d04595e-2810-5085-8648-e01e84119eb1 | note | INSPECTION/TEST METHOD: Visual Inspection
204bdcc5-af16-57a4-b4d4-ed001c1e61a7 | note | RECORD OF CONFORMITY: This ITP signed off
5de54893-a1e6-5425-aa94-eda4fadcb4bb | note | HP
156db5fe-4fcd-5295-84f6-b367bae0b9bf | note | RESPONSIBILITY: Site Engineer/ Superintendent
c9c1d5db-11c6-50c1-879b-8cfcbd37083c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Placement of bedding
a472b4b8-f9a2-5507-95de-a025fdbf8c9c | note | FREQUENCY: Each Lot
ce686d95-91e1-5558-8147-d4835e320539 | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
8dd43890-0189-583c-8d2c-82f8ceaed60d | note | REFERENCE DOCUMENTS: VicRoads Spec 702.09 (c )
07760cde-146f-5b73-827a-049d2c2bfcdb | note | INSPECTION/TEST METHOD: Visual Inspection
4bf3c946-a310-5be0-875c-2242cad1efdc | note | RECORD OF CONFORMITY: This ITP signed off
134a8244-febb-586c-88e5-c0507d54e1e3 | note | IP
392cde47-52d8-5050-8345-cd1f83e541e4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c4875aba-cfa5-5a66-866c-857fc7fbbed8 | date | Date Completed:
| checkpoint | 2.4 - Placing pipes and geofabric (if required)
03a6fe25-e6ea-568a-81bd-2fe4a25b9402 | note | FREQUENCY: Each Lot
91af4394-5d2f-57d5-93f1-e8fd42b098e0 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
5cc1dc76-f97e-5958-b2a5-20c2c7d9b4a5 | note | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
7488dd18-a6dc-5aa9-8ede-98fdaf2ef1cf | note | REFERENCE DOCUMENTS: VicRoads Spec 702.09
5add63d2-ca5a-5ed1-a0d7-f110419b0006 | note | INSPECTION/TEST METHOD: Visual Inspection
e6c65eed-e632-5142-807b-81ec98e34770 | note | RECORD OF CONFORMITY: This ITP signed off
0a02e3ee-acf3-540b-a417-99a6b6da86a8 | note | WP
953cdac1-cc90-5d26-83a0-11170cf7f157 | note | RESPONSIBILITY: Site Engineer / Site Foreman
7c5d2e94-821d-5669-bf19-47e84f8c4caf | date | Date Completed:
| checkpoint | 2.5 - Placement of backfill
bac4c5cf-cd62-54bd-8c8f-8491ec7fe1e9 | note | FREQUENCY: Each Lot
5e9b261b-9486-52d4-a32d-d2e1b673f45c | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
abec7f07-ffd3-50b1-a1cf-dd9fa5e01f66 | note | REFERENCE DOCUMENTS: VicRoads Spec 702.09 (g)
dc87dd17-ffc0-5e49-9620-274bde3d33ec | note | INSPECTION/TEST METHOD: Visual inspection
d12ae72f-a9d8-542f-92bb-fca89d552f22 | note | RECORD OF CONFORMITY: This ITP signed off
84ac7847-8e17-5d46-b16b-c8bed35d9c6b | note | IP
faa184b5-2436-5883-8955-280bf1ba5dcb | note | RESPONSIBILITY: Site Engineer / Site Foreman
c0ec21ba-93b0-59d0-99bd-a4f233f4b446 | date | Date Completed:
| checkpoint | 2.6 - Install Pits and Flushouts
68488bd8-20f3-5be9-af59-1de22ef991a1 | note | FREQUENCY: Each Lot
da435315-7a83-54ea-a67a-43a1f19430b5 | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
adc572a6-8b31-533b-85e7-ba6fdb669707 | note | REFERENCE DOCUMENTS: VicRoads Spec 702.1
7168e7c0-294d-5cd1-9652-2ebc65f78073 | note | INSPECTION/TEST METHOD: Verify
b9c9e89b-00d5-52e7-be1c-07c6db086185 | note | RECORD OF CONFORMITY: This ITP signed off
dd1f3471-a678-507e-9335-3f75f3c8e507 | note | WP
d4c204cf-ed05-50b9-a8ba-9b1dffbb2c44 | note | RESPONSIBILITY: Site Engineer / Site Foreman
7a65bec4-1431-5972-ac0e-eb520f77f7e3 | date | Date Completed:
| checkpoint | 2.7 - Flushing Test
b4a297ad-d2dc-5de0-99f8-d62ad6e843e8 | note | FREQUENCY: At completion of stage
f49911f2-aa09-597a-9f46-54f00b3f758e | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
6d71a83e-b412-57c6-91d9-70cc9951981f | note | REFERENCE DOCUMENTS: VicRoads Spec 702.09(h)
6e1bcdb9-1a21-549c-9d8c-d0fd652d3ef7 | note | INSPECTION/TEST METHOD: Site inspection
d60e7cec-81d0-5d64-868a-cb689f36f327 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
c54ab05d-d434-51df-bc7a-83f6091c501a | note | WP
ceaee312-6e30-5138-a3de-67e8808db300 | note | RESPONSIBILITY: Site Engineer/ Superintendent
a8dffcd2-1f09-543c-b383-eb885102a5ba | date | Date Completed:
| checkpoint | 2.8 - CCTV
439ba6c5-0c60-58b7-87d8-f9b4fc603a05 | note | FREQUENCY: At completion of stage
f3c0dfd4-959c-5d8a-b91f-9646668a87b9 | note | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Superintendent.
b7d10f55-009a-5aad-9b11-3db6a1a9e361 | note | REFERENCE DOCUMENTS: VicRoads Spec 702.09(i)
625e0e5d-34ae-5c25-9032-a3ef440e68a5 | note | INSPECTION/TEST METHOD: Site inspection
073bc112-a1dc-5623-997c-e9bf54d7d9e2 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
a5920a15-e4f6-563c-a65d-225aeee13b8d | note | HP
74e50b86-49b8-5a52-81ee-de76ad388f60 | note | RESPONSIBILITY: Site Engineer/ Superintendent
a0f6181e-d6ef-56f6-b679-84e52842c18c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
14233df8-8916-5ce5-b0f3-59d46f0eec3b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
ab779906-48db-5ccc-a260-3c4164abcb86 | textbox | Print Name:
bdc2045c-bc21-5d7d-a1b0-03a517ae877e | textbox | Position:
a349b428-ad82-5fd6-91d1-6fe43af2c297 | date | Date:
| signoff | Sign ITP
| checklist | ITP-013 - Precast Stormwater Drainage | itp | ITP-013 - Precast Stormwater Drainage |  | 441639b5-5800-42af-b0bc-b801542098fc
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
11d1a750-c05d-5914-9eae-a1d127f1175e | note | FREQUENCY: Prior to commencing any activity
563da571-3e60-5c59-99fc-ad2f49f1e529 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
997d42d8-b752-5304-9780-afe0c4afdaef | note | – using the correct and complete set of drawings
d7ad1b2b-b833-503c-8146-0473fbdfe4ea | note | – all drawings are the latest revision
da50e8c6-cca8-5676-b830-d8cbb730b2e8 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
85ed3128-ddb2-5f1e-b3a1-d9912ebc109c | note | INSPECTION/TEST METHOD: Visual inspection
55734a81-5d30-5f86-b386-b6a2d0ee13f9 | note | RECORD OF CONFORMITY: This ITP signed off
a667c195-c91f-519c-875e-4caae022d255 | note | HP*
20918069-8183-5da3-8740-ab01656fc616 | note | RESPONSIBILITY: Project Engineer / Site Foreman
a28ffb91-7d68-5139-9964-f5fa478d47b0 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
7b9af0aa-e4f0-5e42-99f4-dae1b55001db | note | FREQUENCY: Prior to commencing any activity
3e22c939-a0ac-5c6c-ba30-7916da46a37c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, EMP, ECP, TMP, SMP, JSEA, SWMS & ITP
2103ef94-5373-5710-a1b8-014267d683c6 | note | REFERENCE DOCUMENTS: QMP, EMP, ECP, TMP, SMP, JSEA, SWMS, ITP
3ae998e8-5fe4-578a-af6f-0f57725b752e | note | INSPECTION/TEST METHOD: Visual Inspection
47ae38b8-58c2-57d6-bca9-968e0c1bd57f | note | RECORD OF CONFORMITY: This ITP signed off
d727b509-56e1-571c-ac1c-15b87831ffa6 | note | HP*
b55e6c6f-b020-5cec-94d5-86ebccb4e283 | note | RESPONSIBILITY: Project Engineer / Site Foreman
aa0133e4-7e23-596a-a4a8-866828be1f28 | date | Date Completed:
| checkpoint | 1.3 - Precast Materials Inspection
486cbea8-8c7f-584a-858b-69515bbc01a6 | note | FREQUENCY: Each Delivery
7b817b4f-28a3-590b-8992-519c4b23dfce | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
2b9a3a28-7ef1-55f6-bdbd-f44e9404f5aa | note | REFERENCE DOCUMENTS: 701.04b
a5ec37c6-aea6-55bf-b3b7-441653cc4777 | note | INSPECTION/TEST METHOD: Visual Inspection
f8a2109f-3dd5-59f4-9a8c-54199b822b73 | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
32362bec-b77c-597f-b2f9-758d1f00e067 | note | IP
b33123c9-9012-5cf8-b49d-8596c88eadd5 | note | RESPONSIBILITY: Project Engineer
4acd13ae-b500-5ed1-8c04-bb9363ce637f | date | Date Completed:
| checkpoint | 1.4 - Precast Pipe Compliance
413db0a0-70c4-55f7-b561-e244b3896e03 | note | FREQUENCY: Prior to Commencing
cd961df3-0fa1-5394-a1fc-b1d06e2f73be | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
29ee71cb-160f-5a18-b7c0-5598b6b54595 | note | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
4a4c2e41-5da5-5e84-9f34-97e17616bd4f | note | REFERENCE DOCUMENTS: VicRoads Spec.
cacf4ede-c82d-5432-83bf-a2bb436272d4 | note | ○ Cl.619
cebc34aa-c591-55e4-a948-29693d0b37af | note | ○ Cl. 701.04(a)
da2253b4-d917-50f1-83a7-ca9cec17ba47 | note | ○ Cl. 701.04(b)(i)
910eb7e3-b929-52f3-8d67-83e8522d3b0d | note | ○ Cl. 705.04(d)
c450b17b-5edb-5d79-a634-f25920c03dcb | note | ○ Cl. 705.11
af9f2965-c58d-55ee-a166-ac6cefbc822e | note | ○ AS4058
6e91e136-2759-5596-8caf-17fb0796930c | note | ○ AS4680
22098894-8515-5139-9aa9-95e491cb1efa | note | INSPECTION/TEST METHOD: Document review & Site inspection
69193e30-7dcf-5dff-9782-303389e29578 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
4ba7915e-f154-5f18-bff5-bf07156eb701 | note | IP
6c2b1dfa-e4fc-52ca-980a-c4b18a39cdde | note | RESPONSIBILITY: Project Engineer
697638cb-7ece-552a-b415-f03da1593669 | date | Date Completed:
| checkpoint | 1.5 - Bedding material classification
a12bc97e-c0c0-5d44-bb3a-a1ff24ab7643 | note | FREQUENCY: Prior to start
89572e1c-4c11-50fb-8c00-cce0d2a7f0e1 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
bd2eceba-f1c5-58b6-915c-1350421156c7 | note | ○ 100% passing 19mm sieve.
fb0ed5bf-cd04-5a61-bbe2-4045a376beb8 | note | ○ 5%-40% passing 0.075mm.
c37042ed-21c1-5a6e-aa6f-336de33bcc3a | note | ○ PI = 20 max.
0734b755-3540-51be-9d64-c322b4b0582c | note | REFERENCE DOCUMENTS: 701.04e, Table 701.041, Table 701.042, Table 701.231
1f4d3d0e-c143-5cae-a52b-69dc79188c71 | note | INSPECTION/TEST METHOD: Verify
7ea47330-6fbf-53bb-8d14-47081b78bbc3 | note | RECORD OF CONFORMITY: Test Reports from supplier
06b3a25a-441c-5c55-92f6-07574dd11a6d | note | TP
c04f0fb6-8c26-5060-a2b3-e7a7bfc5175a | note | RESPONSIBILITY: Project Engineer
06c3f1a9-34d1-5f28-8ff2-7237b744efed | date | Date Completed:
| checkpoint | 1.6 - Backfill material Classification
e3db18d4-1a5d-558b-ab4e-dae92265f49f | note | FREQUENCY: Prior to start
30a15cb2-652e-5977-9eb7-13a950dddb98 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
4bc6875e-3130-5052-894a-2e4636cfe6c6 | note | ○ 100% passing 37.5mm sieve.
eff6726a-cd44-5f52-990d-06d827b2197a | note | ○ 5%-40% passing 0.075mm sieve.
ee0428af-5f11-5269-8a3f-4e19787a325e | note | ○ PI = 20 max.
70003f21-60e0-55f6-9b9e-ee093f5fd7fa | note | REFERENCE DOCUMENTS: 701.04e, Table 701.041, Table 701.042, Table 701.231
2eaa9966-5219-5d1c-9752-c9283d5606d7 | note | INSPECTION/TEST METHOD: Verify
bfedcc6c-7454-5354-a9a0-004c85d703f1 | note | RECORD OF CONFORMITY: Test Reports from supplier
e4257b18-664e-56b4-8f80-db2ee73b73f2 | note | TP
53095172-d941-56e7-b534-33280c77a6c7 | note | RESPONSIBILITY: Project Engineer
8e9db50c-f532-567e-96d6-a0ad4f9a459e | date | Date Completed:
| checkpoint | 1.7 - Mortar material classification
22dab840-6088-5bab-a855-94a4f2465a56 | note | FREQUENCY: Prior to start
606f5250-3eb1-5e6e-a571-8021b883f43e | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
bcc930e9-2981-585d-aeb5-c8391fd45eec | note | REFERENCE DOCUMENTS: 610.33
c994570f-a04c-559c-8914-222341148a0d | note | INSPECTION/TEST METHOD: Verify
ffae478a-ed0f-5daf-8359-01f8af8c4edb | note | RECORD OF CONFORMITY: Test Reports from supplier
a2b6365f-58f4-5149-aa6a-1daf2abd838b | note | TP
4b23684c-6218-52bf-8709-47619aaa343b | note | RESPONSIBILITY: Project Engineer
8750d33a-c158-591a-8d34-4817073dd6f4 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation Permit
f1839bd9-0062-5bb8-9a55-f07e7b2a2318 | note | FREQUENCY: Each lot
0fcb79f5-c31a-591e-82f5-1580ecb9f78b | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
45098dab-5299-5ba9-ae0d-203b8a12a15b | note | ○ Plant and equipment shall be appropriate for the task.
6a086e55-7a47-5707-9a28-8ade090157dd | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
4c249a16-97cc-52b6-acbd-a0ebb6d0c06c | note | REFERENCE DOCUMENTS: Excavation permit
ffb8fe84-6db1-596d-9f05-4f9dc21f1210 | note | INSPECTION/TEST METHOD: Verify
252af119-bc1c-59b6-8d1d-a77cb6064250 | note | RECORD OF CONFORMITY: ITP Signed
f20412ed-d08f-515e-8a20-eb34f6fab499 | note | HP*
920b0612-4138-5abd-ad11-ceb5f92fa784 | note | RESPONSIBILITY: Project Engineer
bc5e4640-c5e5-5332-b84a-6c8b55d5be73 | date | Date Completed:
| checkpoint | 2.2 - Set out drainage
737a68e4-51e6-5cde-8ff7-e4834b318269 | note | FREQUENCY: Prior to excavation
cbde015f-8ca8-5d75-b6f4-1e13cb8a10d8 | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
4b775a73-b1b7-5274-a7fb-a59d62eafc03 | note | REFERENCE DOCUMENTS: Drawings 701.10
cd3f971f-4941-5d53-9bd9-d6d8ad27149e | note | INSPECTION/TEST METHOD: Visual Inspection
c64d5a9c-9058-5597-85a4-a14b32ed9a81 | note | RECORD OF CONFORMITY: ITP Signed
b5b64e8f-7e33-5363-99c2-4362d5fbed41 | note | HP
59bc6a32-651e-5346-931e-47fcd0e0565a | note | RESPONSIBILITY: Engineer / Forman & Superintendent
bdee86f5-e51c-582c-93a8-7233f6a958bc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Excavation (pipes)
796de272-e050-5648-b54b-3234081d357c | note | FREQUENCY: Each Trench
b26af1b8-020c-5950-a8dc-8dc92cedc122 | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical.
0ef8ad5c-c5f4-5f7d-857f-ed4d03cfc948 | note | Depth of trench:
60989cd6-3137-5917-9bd5-724e8bd5f9da | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
e270ee42-2812-58dc-a0b3-d9a3062f788e | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
90dbcc1a-0d3b-5ea1-bb1d-0fc0928e48a5 | note | REFERENCE DOCUMENTS: 701.15, Table 701.151
b0751e17-5a26-51a3-b083-31831cc50b88 | note | INSPECTION/TEST METHOD: Visual Inspection
287342b6-e100-59e1-b488-ba7fcdc2061c | note | RECORD OF CONFORMITY: ITP Signed
85b27faa-8dff-543a-9fbe-b3e3eec026bc | note | IP
ffc12175-bb4c-59ae-9d52-5864dfed91e7 | note | RESPONSIBILITY: Site Foreman
64de83b0-3f34-5217-a498-4035be6f9856 | date | Date Completed:
| checkpoint | 2.4 - Compact base of trench
ed1b5358-bc9a-5576-9080-b3ff803e6f42 | note | FREQUENCY: Each Trench
45d7d56a-c090-5753-87ce-da35261980a8 | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
8de5392e-b9bd-54cc-bdc0-07f48c04c80e | note | REFERENCE DOCUMENTS: 701.1
06999dd3-6fb7-5512-8f7c-4fd36f6c13b7 | note | INSPECTION/TEST METHOD: Visual Inspection
8992c60a-00e3-5315-8009-e53b8e4da31c | note | RECORD OF CONFORMITY: ITP Signed
cafc07f1-13ac-5849-9b2c-6470066442f0 | note | IP
4829457c-821f-5e4e-985f-576e8a0afe74 | note | RESPONSIBILITY: Project Engineer
e4cf72c8-7ad1-5781-9f45-9e959872a13e | date | Date Completed:
| checkpoint | 2.5 - Place bedding material & compact
26e926fe-ec9d-544c-9e12-823f60b33f1c | note | FREQUENCY: Each Trench
eeae1a16-5305-5728-b5d7-d828d288dbb6 | note | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
ba59c769-97f8-5e1f-a207-935cca53b3a5 | note | ○ 100mm under pipes.
dee4c275-add2-5697-a8ec-2905be4ab758 | note | ○ 80mm (earth foundation)
195c44e5-28bd-5862-a1c6-4482a41c689c | note | ○ 150mm (rock foundation)
ae4b4e89-c759-5aea-8270-9cd9f3550f59 | note | REFERENCE DOCUMENTS: 701.19
960009e3-d8d2-5716-8656-5e737d5bc701 | note | INSPECTION/TEST METHOD: Visual Inspection
ea2af319-bda9-554a-86af-6c5d093949e5 | note | RECORD OF CONFORMITY: ITP Signed
1ce5a7de-6bbf-5b55-b6b7-683312a0313a | note | IP
9c15b3d4-8d30-5cb2-beb4-d7e8884c5557 | note | RESPONSIBILITY: Project Engineer
5aed3913-0dde-54ed-ae54-28dde9d2bc71 | date | Date Completed:
| checkpoint | 2.6 - Place pipes
126a89e5-8c44-5ecc-9766-7ec49e6de972 | note | FREQUENCY: Each Line/Pit
4cfd494f-4408-58fb-8c4d-36e39821c44c | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding line, levels and compaction requirements have been satisfied
7911bcfa-becb-5923-923f-f2c6ed506ab0 | note | REFERENCE DOCUMENTS: Drawings 701.17
af4be6f1-3956-50eb-8845-5b4f7b248e0e | note | INSPECTION/TEST METHOD: Visual Inspection
65d6e451-309a-5c8e-a5e4-4176ec9401d8 | note | RECORD OF CONFORMITY: ITP Signed
c5098280-a9a6-568f-973a-62327b099ddc | note | IP
ffd8a0f6-3e3e-5893-be08-f225b20c94d6 | note | RESPONSIBILITY: Project Engineer / Site Foreman
9e8af480-e4cf-5079-9d08-df85ad95c92e | date | Date Completed:
| checkpoint | 2.7 - Jointing pipe sections
55b93b03-c5b0-56f1-8fe3-f27b71379950 | note | FREQUENCY: Each Line
f795ccc0-e94c-5689-be6c-34900de92d37 | note | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
9b63cdf9-7c1d-5a65-adad-3a6810c7efa2 | note | REFERENCE DOCUMENTS: 701.18
538acac3-f2eb-5647-a611-5264f717232f | note | INSPECTION/TEST METHOD: Visual Inspection
63c5e290-8022-52e3-8ba3-a1ddb46a127a | note | RECORD OF CONFORMITY: ITP Signed
ccf0419f-85d5-5d52-a808-2ae7d64677ec | note | IP
d62beebb-0e2f-5c33-ba35-bd8d0c38f235 | note | RESPONSIBILITY: Project Engineer / Site Foreman
d3af9b57-cebc-5bb0-bcad-99fa28c90b27 | date | Date Completed:
| checkpoint | 2.8 - Place & compact backfill material over pipes
31e2328f-fff7-5e68-a38d-7ef2351f0a86 | note | FREQUENCY: Each lot
0e5b4f2e-9221-5fa8-852f-f1f6e9cad25a | note | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
e22e1751-41a4-5604-8e17-b2dbabf85561 | note | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
cace2b2a-b2cd-5713-b427-7608cd13d38b | note | ○ Loose layer thickness <= 150mm.
0c8823d7-735c-5116-be78-4c252946d5c1 | note | ○ 1 lot = 150mm layer
266585e7-ecb4-5017-930c-d0d177767215 | note | REFERENCE DOCUMENTS: 701.14, 701.15
39a3640a-d92c-531e-8b72-bb5cd5b38807 | note | INSPECTION/TEST METHOD: Visual Inspection
e87f0f3d-31cb-549b-afb2-5d032036d9d1 | note | RECORD OF CONFORMITY: ITP Signed
fff1c9a2-19bf-554c-ab0e-c3341a252c88 | note | IP
9de2dcea-b6e7-5f85-ba1d-ddd69b2d54a0 | note | RESPONSIBILITY: Site Engineer / Site Foreman
75ea65c0-bbd5-532f-b900-f57d03ddb378 | date | Date Completed:
| checkpoint | 2.9 - Repairs to damaged pipes
49ba0d0b-cffe-5cf9-8f74-f6370c405b55 | note | FREQUENCY: Each damaged pipe
82f0c0ab-efa4-5fc4-831e-fc4102f6db51 | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures.
ccbb3c50-e72a-5355-a9f7-b3956788fc1e | note | ○ All repair procedures undertaken in accordance with Cl 701.25
7cfd7ad2-5882-571d-b26e-dd21f5d82126 | note | REFERENCE DOCUMENTS: 701.31
f7854787-bb89-5e49-bd3b-8541a96c46b9 | note | INSPECTION/TEST METHOD: Verify
0cbeb840-d782-580b-85c6-7611cd55b40b | note | RECORD OF CONFORMITY: ITP Signed
4cd6ff0c-aa97-5682-99d1-b69f9dc945c1 | note | HP
19d6d9f3-a774-5840-aa56-b84c4838e039 | note | RESPONSIBILITY: Engineer / Forman & Superintendent
0188109a-fd18-5638-9665-8fa8e3ba6c08 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Testing & Completion
| checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
b04074b7-a436-5bc7-90f4-2b6df93c5528 | note | FREQUENCY: As required/requested
1b6d707c-7975-5d69-90d6-eced5712c4bf | note | ACCEPTANCE CRITERIA: Backfill material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placment of the overlaying layer.
5362d9a4-0686-517c-9b8c-4b42ea5dbaca | note | ○ Bedding material shall be compacted to refusal using hand held mechnical equipment.
4b3dfbc9-74f3-538d-90e1-515885f4d92d | note | ○ Backfill material which will have a nominal size after compaction of 40mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92%.
f7b4084c-fd98-527d-88dc-ef24090a5230 | note | REFERENCE DOCUMENTS: 701.2
86b08dce-5640-5c01-8795-a79fa329deb8 | note | INSPECTION/TEST METHOD: Verify
ee2a9e7c-0505-5a71-aaa8-12b39bf4e257 | note | RECORD OF CONFORMITY: Test Reports
e224bfa1-0a9c-551b-8cab-6440dfa6b391 | note | TP
ded79e58-b848-599b-a6a8-8de79fcd3121 | note | RESPONSIBILITY: Project Engineer
14598620-f81c-519a-852a-1ab9ccaa4f76 | date | Date Completed:
| checkpoint | 3.2 - Inspection of Drainage Lines
84b5ef1d-d9b3-5738-8e36-5e3b174619b8 | note | FREQUENCY: As required/requested
6c01722f-f1e5-5495-9e28-4823ca6ebf3d | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
5cbfeaf0-fc2b-5182-802f-3149860d92aa | note | REFERENCE DOCUMENTS: 701.3
eb52c177-61ae-5951-9b31-47ccab231d45 | note | INSPECTION/TEST METHOD: Verify
445107ee-fbd5-58db-a5b1-40efd247c471 | note | RECORD OF CONFORMITY: Test Reports
4007a156-fb2a-5605-86a3-4ad9c2259944 | note | TP
1c532ab2-547d-561f-a1b9-f2c406a02a99 | note | RESPONSIBILITY: Project Engineer
6c88df60-d12b-51a8-af93-990b0ed42dd6 | date | Date Completed:
| checkpoint | Final Inspection
cd699bd4-47c5-53a7-a8c7-0aced1a41586 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d705e1db-b5ab-5f03-b001-2aa98c58133c | textbox | Print Name:
520b51e9-a82d-52c8-9ed8-da66950a79e2 | textbox | Position:
59fd9713-ed08-5c82-ab0e-d4003bba45b6 | date | Date:
| signoff | Sign ITP
| checklist | ITP-014 - Kerb and Channel | itp | ITP-014 - Kerb and Channel |  | 437f7ee4-e238-49d8-96d2-b4bbf0d9fb59
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
22763f92-6e42-523d-9424-cc21a743df52 | note | FREQUENCY: Prior to commencing any activity
02cccea0-0fd3-59e5-8610-2480edc96561 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
dccd97df-e089-577e-a58c-eecc403aaff9 | note | – using the correct and complete set of drawings
62311dba-ae6a-52fd-989b-142a1dbc3680 | note | – all drawings are the latest revision
52ba455e-87b7-5f71-815f-bd9aeb229a8f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
1734e3d2-3928-5eff-8d32-475473ccca7b | note | INSPECTION/TEST METHOD: Visual inspection
c5e131d8-6314-5061-b289-78e328042d9e | note | RECORD OF CONFORMITY: ITP Signed
7a14ee82-db96-5a8c-834b-047fc8358f34 | note | HP*
94a28c37-2623-548a-b0fe-b404e2f8a145 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
8e08f5ab-2a68-55d2-81c5-e736c73b137b | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
5ae94e51-05b0-507c-be71-4ff31da5bbc0 | note | FREQUENCY: Prior to commencing any activity
521767ed-2085-521f-b496-784f8ed0c925 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, ECP, ERA, QMP, SWMS
5db91792-be81-5e97-9d15-9999bbe40ba8 | note | REFERENCE DOCUMENTS: EMP, ECP, ERA, QMP, SWMS
30308556-63e5-5dac-a455-c8a9ff9c3c40 | note | INSPECTION/TEST METHOD: Visual inspection
4781ba39-3ada-5bd1-a391-728de659805a | note | RECORD OF CONFORMITY: ITP Signed
1664b5d7-b129-5635-bb48-396cf69471fe | note | HP*
0b520f8d-abc1-58a9-9302-471d646dd0f6 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
af017f19-6e01-5b04-a2e5-eb13e9fe71de | date | Date Completed:
| checkpoint | 1.3 - Mix Design
eaadf5fe-e02d-5bb6-8c57-5df64127347a | note | FREQUENCY: Prior to commencing any activity
c4b53951-0ed6-54ad-9504-a49401219a21 | note | ACCEPTANCE CRITERIA: Approved VR mix design to be used. Details to be sent to the superintendent for approval prior to commencing works.
94e05a71-805a-55a1-b9a7-3fe927476eb1 | note | REFERENCE DOCUMENTS: AS 1379, 703.07, 703.05, 703.23
62f6cae3-cdd4-5823-9342-3455f5d39dc7 | note | INSPECTION/TEST METHOD: Verify
dd9125b6-1dd0-5dff-86e9-9397f200a2d1 | note | RECORD OF CONFORMITY: ITP Signed, Mix design approval
b55b9ffe-2a00-51cb-8e47-622fa11490ca | note | HP
56103d99-1c4c-5ba5-af98-35bf018bcbaf | note | RESPONSIBILITY: Site Engineer/ Superintendent
249f551e-8230-526e-bfb6-6ead876022fd | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
8873538b-b087-5a6f-a3fb-91c79230bea7 | note | FREQUENCY: Prior to start
7e9d2a6d-8b31-5b5f-b40b-ef05d3814d21 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
d95a61eb-3dad-5e5e-88f3-cf7c7b7337a2 | note | REFERENCE DOCUMENTS: 703.17
4396f4a4-806e-559d-a498-6581741c4087 | note | INSPECTION/TEST METHOD: Verify
6fbf0d3f-1e98-551e-b2c0-ec5489801fba | note | RECORD OF CONFORMITY: ITP Signed
feee75e2-c6a3-5d8a-be74-afe37a36f15c | note | HP
e60d8d30-a78b-5d4c-8d72-acd0ddd2f26d | note | RESPONSIBILITY: Site Engineer/ Superintendent
18e32077-cb6f-5623-9290-a52890e026f0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Temporary Drainage Provisions
95b13389-0b00-5452-addd-cbcaafc22e1d | note | FREQUENCY: If Required
5632fe7e-df3d-5169-acb5-d87677956204 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
cb9440b5-336c-5c71-80a7-727a9fc5cbd6 | note | REFERENCE DOCUMENTS: 703.18
3f3fe6c4-047e-50d3-8d34-e9575cf43901 | note | INSPECTION/TEST METHOD: Visual inspection
134acd51-581c-5e91-9040-83a742b003d8 | note | RECORD OF CONFORMITY: ITP Signed
441a46a7-c07e-5f31-a5ba-ef261a5fdfcc | note | WP
27c05826-fb6c-5261-aaa6-da8b66f21c43 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
8142e8f2-5e52-559c-ad79-66461bbb5008 | date | Date Completed:
| checkpoint | 2.3 - Bedding
6b3ab883-0cba-5157-b6cd-e5e0024a7fd3 | note | FREQUENCY: Each lot
f67be4e4-a5a9-53e2-a9c0-d50bfe12a7b1 | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
6538c102-c1fb-5e7b-9ad1-ff82016c366c | note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
9dfe1867-e129-544b-a9e5-140be31b65cd | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
6d931d04-5e26-59bc-84ad-66cdcb68ae91 | note | REFERENCE DOCUMENTS: 703.21
54c51697-cd37-57bd-b45e-99ab9aa64e85 | note | INSPECTION/TEST METHOD: Visual inspection
d900fe30-7d1d-588f-8e51-053b492adaad | note | RECORD OF CONFORMITY: ITP Signed
30ba87d9-1656-55af-8560-21a2db3e78ec | note | WP
a538f0b4-f5e0-59a7-a5b7-32f0dfb1aa4f | note | RESPONSIBILITY: Site Engineer/ Superintendent
39d4e6bf-e5cf-5234-a3a6-59636a9ba992 | date | Date Completed:
| checkpoint | 2.4 - Reinforcement
f60c6b21-cc65-5646-b970-7e278ff8daeb | note | FREQUENCY: Each lot
3a9145f8-6a92-52bd-9016-36311e8d2fd3 | note | ACCEPTANCE CRITERIA: Provide SL81 mesh cut to suit width centrally located.
59c3616d-8dce-510a-b590-9df0ccd331e6 | note | REFERENCE DOCUMENTS: Design Drawings
58daed13-f7a9-5cda-a2b9-5c6018b79b70 | note | INSPECTION/TEST METHOD: Visual Inspection
8598f507-b840-5080-bb44-146020b9be33 | note | RECORD OF CONFORMITY: ITP Signed
b2cd6b86-821e-53de-92e1-e191b3914eac | note | HP*
e3f789f5-d483-50bf-832e-4179cec4e76a | note | RESPONSIBILITY: Site Engineer/ Site Foreman
5b9e54c1-500a-5644-bffe-91526c28118c | date | Date Completed:
| checkpoint | 2.5 - Pre-concrete check
f6df936e-6563-5ff3-9b85-e5618995c891 | note | FREQUENCY: Each lot
4527cc3f-f4bf-5c93-a843-cb7389b1d00e | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
4fb9ccea-f426-52a5-9e54-8eb535e2e958 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
0507726b-627a-5a0b-8c7e-34e23a9aa189 | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
7aaf9930-ed45-5d63-9077-e89da5488ca4 | note | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
c7d784b4-f457-5501-96de-cd7f5cab4a25 | note | REFERENCE DOCUMENTS: 703.08, 610.17(a)(b)(c)
24d86c5b-9357-55de-ae3e-2c0f96113348 | note | INSPECTION/TEST METHOD: Verify
54217e5a-a3a9-5a5b-98fd-e5d8e8af2c8c | note | RECORD OF CONFORMITY: ITP Signed
2879f5fb-c198-5d71-a15a-81046e15ff26 | textbox | Ambient Temperature |  |  | °C
3bbbed63-c06f-5f84-85b0-4bf0aa028336 | textbox | Concrete Temperature |  |  | °C
a5da04c9-6b0b-5207-983d-e39aecfb7594 | note | HP*/ WP
8cf2947b-b128-5f7b-af18-e741807cc658 | note | RESPONSIBILITY: Site Engineer/ Superintendent
95a30c7d-d228-5d40-bfee-bdfc39cf47cb | date | Date Completed:
| checkpoint | 2.6 - Concrete Placement
c3e1c027-056c-5d98-97ef-f6688c824029 | note | FREQUENCY: Each lot
d250d4fc-0ff8-5a75-83a1-26ab2ad998db | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
b81e62aa-5fb0-5c84-844b-bc50351f2127 | note | REFERENCE DOCUMENTS: VicRoads Spec. 703.23
2e4066c2-a186-5f06-be95-51dc7994c09c | note | INSPECTION/TEST METHOD: Site Inspection
93b767b1-6a0e-5e9f-a495-3308c45103aa | note | RECORD OF CONFORMITY: ITP Signed
14694072-1291-5f34-a9bb-ee5db44bbe83 | note | IP
6144dae7-93d9-5c6d-a719-c49c40da04dd | note | RESPONSIBILITY: Site Engineer
8c2a6495-f904-5127-b6a1-b32a44b4b8c3 | date | Date Completed:
| checkpoint | 2.7 - Finish Surfaces
2568e6a1-b9d2-5b31-a79b-e94e24a315e2 | note | FREQUENCY: Each Lot
e4ddb4ff-b3b7-58ff-ae6d-f4cd168860a6 | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
c6e5498f-b776-5bfb-a0b7-b414fb45772d | note | ○ Ensure 40mm chamfer as displayed on the design drawings.
df8d9bff-5f90-52e2-a5ac-3103242003bf | note | ○ Concrete to have a neat appearance and uniform colour.
ac1647ee-71d9-5723-83b1-530234aa8133 | note | REFERENCE DOCUMENTS: Design Drawings, 703.25
5300306e-91b2-50c3-81d9-101fa6720f5b | note | INSPECTION/TEST METHOD: Visual inspection
e5c59cb8-c625-51db-ad9e-cbca055487d8 | note | RECORD OF CONFORMITY: ITP Signed
d217e9e9-cf84-5508-95df-9910d8f0e052 | note | IP
ff2a6d1f-7220-55f1-afa3-acb21878a7d9 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
3a5cb2e6-e87d-584c-8f8d-db305757c8c3 | date | Date Completed:
| checkpoint | 2.8 - Tolerances
6013bee2-282d-5bb8-bea4-5f0ac27436ff | note | FREQUENCY: Each Lot
6d0bc69c-f76f-53ec-8aae-4fe25fe29ed6 | note | ACCEPTANCE CRITERIA: Match existing surfaces to within 5mm from dimensions shown on drawings. Section dimensions to be within 5mm and 15mm for width, for dimensions less than 25mm tolerance to be ± 3.
60d7ff8f-d50d-5e7b-a518-67f188909258 | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
ba15130a-a74a-5e3c-8b4b-57312b441394 | note | REFERENCE DOCUMENTS: 703.15
4838b112-9a39-5420-9356-22875673c3bb | note | INSPECTION/TEST METHOD: Verify
836cea1b-d0bb-5247-a590-4162a58b4035 | note | RECORD OF CONFORMITY: ITP Signed
e3dff710-2914-5cab-97fd-0ec5a774b944 | note | SCP
d4c7eb26-d20d-5c5e-b867-d6b1f9f09e62 | note | RESPONSIBILITY: Site Engineer/ Surveyor
5bfc0418-6649-5d93-999a-f97e0a633e93 | date | Date Completed:
| checkpoint | 2.9 - Joints
1ea8f4b8-6196-5171-9a14-b0783505ce5f | note | FREQUENCY: Each joint
840414b6-388b-509f-a5c2-ff5c072b9ae8 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
288d0716-2b82-548b-9ec3-d52f9987a182 | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
576a943f-9a8c-5cd6-8027-5e1bb50da3cd | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
f87989ae-1926-54c1-a72c-2e3307032afd | note | REFERENCE DOCUMENTS: 703.26
51889af4-eb0d-5bbc-92c9-095cbe829634 | note | INSPECTION/TEST METHOD: Verify
7b4bb929-be5b-5357-ad45-b92a4cfeceed | note | RECORD OF CONFORMITY: ITP Signed
e96813b3-c71d-5b23-b770-edff468c1f58 | note | IP
6c0d78ef-0a5b-5b8d-87a5-b7b36d372e97 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
94f2179b-fc13-5999-9b20-433d35198c80 | date | Date Completed:
| checkpoint | 2.10 - Backfilling
99772884-5de0-5c3f-affe-9332a18caa13 | note | FREQUENCY: Each Lot
d44386b6-cf07-519d-a844-f3403135a5c0 | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
571e415d-0a51-59e7-b3de-3e0e9f72b17a | note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
14f33f50-0a69-5c2b-b7c4-acface3fd2b9 | note | ○ Layers shall not exceed 150mm compacted depth.
2c3e4f1a-2fc3-5397-85f0-654ae4df1fea | note | REFERENCE DOCUMENTS: 703.29
32992463-bf07-5cf5-833c-aa1e9bea6cce | note | INSPECTION/TEST METHOD: Verify
4594e3d8-fa04-59de-bf2b-61e9fdc6d672 | note | RECORD OF CONFORMITY: ITP Signed
1b5e7cbf-86bd-5327-8e43-cef9963a7c87 | note | IP
6043cbdb-9f6d-578b-8858-6294bf2459dc | note | RESPONSIBILITY: Site Engineer
7e3a2630-1ce5-50f9-b152-7fc9ff123a69 | date | Date Completed:
| checkpoint | Final Inspection
6c18ac92-f3e0-54c7-b884-7ca3d63f484b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
56d951c1-9ba3-5315-8108-b8f3ad9f7b3e | textbox | Print Name:
63e16402-7b82-583d-870c-aaee5c13d250 | textbox | Position:
2871068e-7112-5ea2-8ff0-557bc267d831 | date | Date:
| signoff | Sign ITP