## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
acf6ff21-0134-4991-9cb2-76e8f426d63c | checklist | ITP-004b - Fabrication of PSC Planks Rev2 | itp | ITP-004b - Fabrication of PSC Planks |  | 777b7878-3188-46c0-8221-30ee9087fcf3
af43b2c6-20e7-40ce-a462-5abdfe039cbf | section | 1 - Preliminary Works
35db4db9-3796-46f3-99ce-a4b046cf2ac4 | checkpoint | 1.1 - Check for correct documentation
6ed29bb2-32e5-58e1-8c03-3fdba4dc15aa | note | FREQUENCY: Prior to commencing any activity
605283ad-a3a4-5523-93aa-a94b52cdcdc3 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
60384701-de50-5be8-95ef-29fb35c9686b | note | REFERENCE DOCUMENTS: Drawings and drawing registers
9842cfd3-4707-5b6c-a164-9f5ed1e580c5 | note | INSPECTION/TEST METHOD: Visual inspection
d9fbbc2f-01ad-52c1-9bdd-f1ba24e1671a | note | RECORD OF CONFORMITY: ITP Signed
a0ecf2ed-b7de-5ac2-9012-b6e90d8d4031 | note | HP*
c4aae725-f011-5524-9f51-f6b2ecac4414 | note | RESPONSIBILITY: Project Engineer/ Supervisor
b771259d-8883-5a53-a355-8c629da8d431 | date | Date Completed:
461bf421-4b25-4373-9c4d-c26823dbe49c | checkpoint | 1.2 - Implementation of all measures and controls
bfe01841-c317-5fc4-9700-bedf73b96a0c | note | FREQUENCY: Prior to commencing any activity
ba751761-a29b-5e0e-979d-74f3f3d6a2b2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
8b38e13f-9d5f-502d-a9f3-44e920094313 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
73f42530-a457-57a4-b021-d22e78c21278 | note | INSPECTION/TEST METHOD: Visual inspection
073f4203-4c87-5103-ac16-d1724abbac91 | note | RECORD OF CONFORMITY: ITP Signed
445c9ef6-832c-5f43-bccd-b45d59c6f509 | note | HP*
91c476df-1dc9-5324-ae69-39b0ed8e715e | note | RESPONSIBILITY: Project Engineer/ Supervisor
8357419f-6df8-5b2d-a89d-44eec9aed31e | date | Date Completed:
9a4c5652-8b4f-4c09-8214-adeacead6800 | checkpoint | 1.3 - Materials
e6e9740f-15db-53f1-bea8-2853287f77ab | note | FREQUENCY: Prior to commencing any activity
2594fdaa-3c69-5bd1-aa76-8183032bc853 | note | ACCEPTANCE CRITERIA: Ensure correct concrete mix being used in accordance with design drawings and specifications.
e4f02de9-1d99-5550-b605-c6847bc53225 | note | ○ Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS.
e8716825-227d-56ba-9ecb-b897bf1e636f | note | REFERENCE DOCUMENTS: Design Drawings, VR Section 620
5d7b5f30-db54-5572-b2df-c93cf18d48db | note | INSPECTION/TEST METHOD: Document Review
4f1c3601-7349-5a38-a564-6b06293f53f1 | note | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Material Data Sheets.
81de1030-079d-54db-be7f-00a791e7e1df | note | HP*
b9579cac-bc18-5d35-8ade-f0e88b5933f8 | note | RESPONSIBILITY: Project Engineer/ Supervisor
950bedbb-f6b6-547c-94ec-d9184afaa648 | date | Date Completed:
7ee80026-0ca0-4492-94e5-948b6ec1ec48 | checkpoint | 1.4 - Calibration of Prestressing Equipment
247465c3-b3f0-5f27-a4a7-2cac8dddb0ff | note | FREQUENCY: Prior to commencing any activity
63f760ec-8ea9-523b-8c47-4601624caefb | note | ACCEPTANCE CRITERIA: Ensure the contractor holds current calibration certificates conforming to the requirements of AS 2193 Grade B for the jack and pressure gauges or other force measuing devies.
fffe07e4-514c-50ad-b778-49b168dfa2fa | note | REFERENCE DOCUMENTS: VR Section 622.06
18f9a560-1cdf-5771-b5f0-e16a1942171f | note | INSPECTION/TEST METHOD: Document Review
83f6b61a-9ad3-5a2b-8e99-63c2d00218bd | note | RECORD OF CONFORMITY: ITP Signed, Calibration Certificates
9d5652bb-9cec-5cb8-a8b3-72b5313132cb | note | HP*
89903d66-13ed-5adc-b9a9-94575795e198 | note | RESPONSIBILITY: Project Engineer
8e422604-08a9-5247-a7ae-d85b3f4bf9ba | date | Date Completed:
c14c33dc-211b-4973-8bf4-6a39a4167d55 | checkpoint | 1.5 - Submission of proposed method of transfer of prestress
51a0d966-e50b-562a-85cd-c8ee861c0b75 | note | FREQUENCY: Prior to commencing any activity
7885af1e-8a4b-5d14-9997-05c50f4eda67 | note | ACCEPTANCE CRITERIA: Ensure submission of the details of the proposed method of transfer of prestress to the Superintendent for review.
5a1756f3-ee73-5129-b9b6-30c0552ad3e2 | note | REFERENCE DOCUMENTS: VR Section 622.08
822b88c5-5b9a-554e-8be3-33a4a478d4dc | note | INSPECTION/TEST METHOD: Document Review
8c6ff8c4-e576-5d63-a9eb-7b6b77e119c9 | note | RECORD OF CONFORMITY: ITP Signed
0ab0a2c6-01a5-57f1-9096-1e831c652e2f | note | HP
39b824d2-fc03-5b15-853f-61099d53f226 | note | RESPONSIBILITY: Project Engineer/ Superintendent
1bc5410a-e4df-56f3-8415-ee7503585ecd | date | Date Completed:
a2ab742a-3545-48b7-9bdb-1fcbdd7098a8 | signoff | AUTHORITY HOLDPOINT
c2afd87b-297c-4596-a5f2-2e6008e59c5e | checkpoint | 1.6 - Notification of Superintendent prior to stressing operations
dee5a9d1-47a1-5745-8a5f-ed90b731f6d4 | note | FREQUENCY: Prior to commencing any activity
89f590f5-2db9-574e-ad55-1ab45e221cbb | note | ACCEPTANCE CRITERIA: The Superintendent shall be given seven days notice of stressing operations.
36b34915-8dd5-57b8-a723-3c48e0e0765c | note | ○ All stressing operations shall take place in the presence of the designated Precast Concrete Surveillance Officer.
1760dc66-3b4d-50b6-941b-bf3081281fcc | note | REFERENCE DOCUMENTS: VR Section 622.06
af034a51-1c29-5951-85ab-cf4105d26783 | note | INSPECTION/TEST METHOD: Document Review
098e8831-624f-53d5-8a9a-b74a562e9245 | note | RECORD OF CONFORMITY: ITP Signed
28c8c112-048e-54fd-94dc-dcc02add2d24 | note | HP
cab6051b-f409-57ce-902e-04d33c423de5 | note | RESPONSIBILITY: Project Engineer/ Supervisor
85a6a81e-4e98-5781-9d1a-120a607b328c | date | Date Completed:
f0628378-9cdb-4e0c-a2e3-339a822f98ec | signoff | AUTHORITY HOLDPOINT
852daf89-e712-4b07-9222-6b796f4a8013 | section | 2 - Construction Works
71878ca6-80c7-42d1-ae7f-0828f8499e3f | checkpoint | 2.1 - Forms
bbbce5c8-3fcc-5238-937f-98b0c44a73f3 | note | FREQUENCY: Each Lot
35c19c5b-475e-59c6-9b86-1dcfe5139567 | note | ACCEPTANCE CRITERIA: Forms shall be manufacutred from steel, except where otherwise approved by the Superintendent.
be2c262e-8d4f-5499-94cf-09f586356e58 | note | ○ The formwork shall be constucted to as to produce a product in accordance with the design drawings, and with the surface finish and tolerances specified in Section 610.
d088447f-2dd5-58f8-86e7-0f96f73d2bb2 | note | ○ Casting bed to be inspected by designated Precast Concrete Surveillance Officer.
8c92bb71-afe2-5817-b10a-f88b6650698d | note | REFERENCE DOCUMENTS: Design Drawings , VR Section 620, 610.
9e173c59-3a37-51dc-a65b-a3b0572c8e2c | note | INSPECTION/TEST METHOD: Visual inspection
e56cf3da-8152-56a0-901a-299fe0100487 | note | RECORD OF CONFORMITY: ITP Signed
06fe1469-f6cd-5276-ad2e-34f552b70f93 | note | HP*
60458cfc-df2b-5b95-b868-465cc5a04e15 | note | RESPONSIBILITY: Project Engineer
dd9ae77b-a221-5b08-b759-a77045dad2ff | date | Date Completed:
13e55d3c-b99b-491c-aa10-88b96c9529db | checkpoint | 2.2 - Stressing operations
f774a81e-b6d6-50db-a53b-83934a4bfa2d | note | FREQUENCY: Each Lot
549831e9-d16a-5430-91e7-6e7be50ccb1b | note | ACCEPTANCE CRITERIA: All stressing operations shall take place in the presence of the designated Precast Concrete Surveillance Officer,
1141827f-7ad7-50b4-bc3c-f0ff59cbea42 | note | REFERENCE DOCUMENTS: VR Section 622.06
0aacc4b0-0881-51a1-b50e-ac658fd599fb | note | INSPECTION/TEST METHOD: Visual Inspection
37982b30-f29e-5eb4-babc-7112e471ab21 | note | RECORD OF CONFORMITY: ITP Signed
5e00960b-cef9-5bcc-ba83-839c61105610 | note | HP*
5c0e4747-2193-5a8a-a119-cde5ef7255a7 | note | RESPONSIBILITY: Project Engineer/ Supervisor
abe111ec-24d2-5cfb-85b7-ed65638e9ccf | date | Date Completed:
7252be66-0266-4895-ac84-87900709b74a | checkpoint | 2.3 - Pre-pour inspection
45954987-f806-5bd3-8468-52cf996c8409 | note | FREQUENCY: Each Lot
9107a62b-2d54-50ee-bb97-4a770cec4e5b | note | ACCEPTANCE CRITERIA: Ensure the completion of the Inspection Test Checklist (ITC) by the designated Precast Concrete Surveillance Officer.
b230ff81-26c2-500f-8ca4-a2ea859f7431 | note | REFERENCE DOCUMENTS: VR Section 622.06
090f6a6b-1b83-5410-91d7-46a90b376e95 | note | INSPECTION/TEST METHOD: Visual Inspection
095924d8-ca4c-59d4-8493-0fe4787a1e67 | note | RECORD OF CONFORMITY: ITP Signed, ITC Complete
6a6b9a32-974f-5311-ac25-3bb57751f353 | note | HP*
580fe62c-e194-5049-b7e4-726b92b90e35 | note | RESPONSIBILITY: Project Engineer/ Supervisor
3590de3b-5162-5bdd-a159-70a7b399ede9 | date | Date Completed:
b0fd16b5-2b14-4f21-baae-538614556af3 | checkpoint | 2.4 - Data to be recorded
c6f2421e-d59e-53c6-9c34-3115957d8087 | note | FREQUENCY: Each Lot
122dc8b0-2f3b-5463-ba16-974b6e984bd9 | note | ACCEPTANCE CRITERIA: Ensure the following data is recorded and forwarded to the Superintendent prior to delivery of the pre-stressed units to the site:
42f041e9-72f3-5c12-82e0-8608a472f3c0 | textbox | ID No. of each unit
fb707a38-9c83-5eec-a8db-1d072fa9e495 | textbox | ID No. of prestressing equipment
fc00fa49-eb5c-5672-a29b-874785b6d781 | textbox | Calibration certificates for prestressing equipment
456b19ff-61cb-5f50-a03b-a7a2f1445b6a | textbox | ID No. for each tendon
a5c4a79f-bb4d-5227-ab6e-a09f88ae1242 | textbox | Sag take-up force:
f1c0dd14-ad0a-530e-8e6c-e2e56202ff11 | textbox | Elongation at take-up force:
946921d0-124f-5d85-965e-19cd15a9de82 | textbox | Obtained elongation at completion of tensioning:
73d4d129-e469-5ac5-93b2-97c30804de8d | textbox | Obtained tendon force at completion of tensioning:
2fa99a18-270b-5aef-a229-a35588b8e498 | textbox | Elongation after release of jack:
ada27e52-ea69-5d9c-8a19-ac56e3294d6c | textbox | Tendon pull-in on completion:
cbd7ec21-4904-570c-a732-640d11c33c18 | textbox | Compressive strength of concrete at time of transfer of prestress:
189e3422-678c-5009-b372-0e2fb4a2fbb4 | textbox | Steam curing charts
c51074ef-f0a9-5255-a048-c7c8db836999 | textbox | Hog measure following transfer of prestress:
7fd669a7-19a0-53c2-a4a7-bdc0d2c54235 | note | REFERENCE DOCUMENTS: VR Section 622.09
368cc617-eda0-51c7-9598-ece5a33d5228 | note | INSPECTION/TEST METHOD: Data Record
1828489a-a323-5cc3-a69a-eb8acf9cfb61 | note | RECORD OF CONFORMITY: ITP Signed, Record of Data
42e7e242-5cfe-5f7b-8e20-d72b1d068dfd | note | HP
d22f9fa3-587e-5950-b9ee-2bb60f34c617 | note | RESPONSIBILITY: Project Engineer/ Supervisor / Superintendent
12e6ef37-1cd5-5a99-9ce8-045dee5b8ab4 | date | Date Completed:
b8c397eb-1ba3-4676-8911-615beb65d34d | signoff | AUTHORITY HOLDPOINT
ef39d4aa-196c-4687-99e3-08b429a7a42d | checkpoint | 2.5 - Projecting reinforcement
30870e8d-2262-5e3d-a1a0-627e0da4b585 | note | FREQUENCY: Each Lot
970ae10e-e4e2-589a-ac32-74f90aa5024a | note | ACCEPTANCE CRITERIA: Ensure projecting reinforcement is in accordance with that shown on the design drawings and is in good condition.
2e78bb18-29c6-5037-ac8e-39c43ad1e5ff | note | REFERENCE DOCUMENTS: VR Section 620.03
b5012389-df94-5448-99e2-6b82285cd530 | note | INSPECTION/TEST METHOD: Visual inspection
07c561e4-bda1-59ee-99dc-71ff015f4797 | note | RECORD OF CONFORMITY: ITP Signed
7d6af11e-64ac-5f13-9765-064df681be11 | note | HP*
0e0f84f1-81d5-5e2b-8eac-8f14d9ab73c6 | note | RESPONSIBILITY: Project Engineer/ Superintendent
671bd940-6420-50eb-8824-c1332b7e54e7 | date | Date Completed:
ad0222ac-5af0-4f31-8e1e-82ba49fefe35 | checkpoint | 2.6 - Marking
3bcf5b57-74b6-5527-82e7-8981d6cefa2b | note | FREQUENCY: Each Lot
a2a09aa4-e6c6-5943-b3cb-285859817049 | note | ACCEPTANCE CRITERIA: Ensure the identification number, date of casting, the manufacturuers name or registered mark and the maximum mass shall be marked on every precast unit.
dac25e16-534b-5971-b43b-fd9e6ce77ff2 | note | REFERENCE DOCUMENTS: VR Section 620.06
b4b5586d-171f-54c4-a078-60050d185e37 | note | INSPECTION/TEST METHOD: Visual inspection
f63e1806-bff3-5e73-ad28-5060c5ea9f57 | note | RECORD OF CONFORMITY: ITP Signed / Certificate of Compliance - Formwork Inspection
d976b062-6575-58c7-a2c1-827edc7f0fe4 | note | HP*
c64e9f72-4115-5976-8e60-491a59939b70 | note | RESPONSIBILITY: Project Engineer
2545bf92-97f9-51cf-af80-33e200b6ec8d | date | Date Completed:
96c1b8bd-d935-4b77-9016-d107182c6a4d | checkpoint | 2.7 - Handling & Storage
5afcaea2-4250-5f81-ba18-313ddb961586 | note | FREQUENCY: Each Lot
56bf39a3-a54d-517b-8e20-3f67742c572f | note | ACCEPTANCE CRITERIA: The units shall be supported on bearers clear of the ground. Bearers shall support the units over their full width and be placed perpendicular to the longitudinal axis of the unit.
88055cdd-6d8e-5a5c-80c7-346567203b0a | note | REFERENCE DOCUMENTS: VR Section 620.07
aa9b9294-477f-527b-bf02-645b0eb471d2 | note | INSPECTION/TEST METHOD: Visual inspection
20c5b80b-236b-5768-bbcb-8998fdfe54b7 | note | RECORD OF CONFORMITY: ITP Signed
316561af-6e4a-5680-a875-2b97bd58c7dd | note | HP*
d9349559-b9c8-5f80-928b-0661117d8287 | note | RESPONSIBILITY: Project Engineer/ Superintendent
1ddb0007-f415-5dcc-b7a0-077c1d8fcd19 | date | Date Completed:
9b11a417-df61-465b-832a-d3431cf5c436 | checkpoint | 2.8 - Transporting
f0021758-e30b-5f1d-b9b7-a55d20ad11a2 | note | FREQUENCY: Each Lot
1cc8f34d-44d3-507e-8ee3-24012bb8aea8 | note | ACCEPTANCE CRITERIA: Units shall not be transported from the precast yard until specified 28 day concrete compressive strength has been achieved, and not before 7 days after casting.
fa694239-6c51-5fdb-ba2f-7ce195df1a54 | note | ○ No beam shall be transported and erected if it has a bow in excess of 1 in 400 of the length or 75mm whichever is the lesser. Should the bow at any time exceed the maximum allowable limit steps shall be taken to ensure the safety of the unit throughout the journey.
dbbd65ec-0a90-514d-a26c-aa3b0aac656f | note | REFERENCE DOCUMENTS: VR Section 610.14
d7dde9de-5b43-571c-8d62-953337dc4f02 | note | INSPECTION/TEST METHOD: Visual inspection
3bcca52d-9789-5196-aa5c-13b456f870d7 | note | RECORD OF CONFORMITY: ITP Signed, Concrete Test Reports
0c0ac93b-5a2c-5640-b49b-bc8a325d117f | note | HP*
31d46116-86c8-528d-8e53-5e43ca6ad9df | note | RESPONSIBILITY: Project Engineer
b1605783-3d81-539c-95cd-b388361831dc | date | Date Completed:
76eb0af4-fd23-48ae-b148-c64381b4f63f | checkpoint | Final Inspection
aabf7726-1f13-53ed-b29d-8526d27bb437 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b7aedf8d-e79a-5d06-9b95-5f7aa08050c3 | textbox | Print Name:
49b93626-fc2c-5ddf-b82a-176f7e056165 | textbox | Position:
623d45c2-09d2-5f7f-b99f-c1460f9d8127 | date | Date:
702661d8-df6e-4cac-8a0c-e56db303ce07 | signoff | Sign ITP