## Sheet1
3.1.1. | PTT | PTT shall define the planned excavation limits and support types (RESS) prior to each defined period of excavation in each heading or bench face. Tunnel excavation shall not commence on a shift until PTT has been signed off | Technical Specifications C0650 Tunnel Sequential Excavation Section 5.1 | PTT form | Every advance or as agreed in DRM | N/A | H | H | PTT | 3.1.1. - PTT | Description - PTT shall define the planned excavation limits and support types (RESS) prior to each defined period of excavation in each heading or bench face. Tunnel excavation shall not commence on a shift until PTT has been signed off | Method/Description - PTT form | Test frequency - Every advance or as agreed in DRM | Conformance Criteria - N/A | Constructor - H | CPS - H | Lab - | IOM - | Verifying Records - PTT | 3.1.1. - PTT
3.1.2. | Face Mapping | Recommend the required support type based on the Actual Ground Conditions. Determine any corrective measures required to ensure safety and stability of the excavation. Identify if the ground conditions depart from the expected range of conditions for which a support type has been designed and notify the Designer if new design is required. | Technical Specifications C0650 Tunnel Sequential Excavation Section 5.1 | Geological mapping record | Every advance or as agreed in DRM | N/A | H | H | Required Excavation and support sheet | 3.1.2. - Face Mapping | Description - Recommend the required support type based on the Actual Ground Conditions. Determine any corrective measures required to ensure safety and stability of the excavation. Identify if the ground conditions depart from the expected range of conditions for which a support type has been designed and notify the Designer if new design is required. | Method/Description - Geological mapping record | Test frequency - Every advance or as agreed in DRM | Conformance Criteria - N/A | Constructor - H | CPS - H | Lab - | IOM - | Verifying Records - Required Excavation and support sheet | Description - PTT shall define the planned excavation limits and support types (RESS) prior to each defined period of excavation in each heading or bench face. Tunnel excavation shall not commence on a shift until PTT has been signed off
3.1.3. | E-line control | Control the E-Line before, during and after excavation is finished | Drawing MMMA-DES-TUN-E1-DRG-8119 | Surveyor to set out and record as built. VMT system to provide e-line guidance | Every advance | Over excavation tolerance -0/+150mm | H | W | As-built Report | 3.1.3. - E-line control | Description - Control the E-Line before, during and after excavation is finished | Method/Description - Surveyor to set out and record as built. VMT system to provide e-line guidance | Test frequency - Every advance | Conformance Criteria - Over excavation tolerance -0/+150mm | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - As-built Report | Method/Description - PTT form
3.2.1. | Delivery docket Check | Check delivery docket to ensure the mix used is the correct mix | N/A | Document Review | Prior to any shotcrete application | N/A | H | R | Delivery docket | 3.2.1. - Delivery docket Check | Description - Check delivery docket to ensure the mix used is the correct mix | Method/Description - Document Review | Test frequency - Prior to any shotcrete application | Conformance Criteria - N/A | Constructor - H | CPS - R | Lab - | IOM - | Verifying Records - Delivery docket | Test frequency - Every advance or as agreed in DRM
3.2.2. | Rock Surface Preparation | Prepare all surfaces to be shotcreted prior to application of shotcrete | Technical Specification - C0650 - Tunnel Civil Works Section 5.4 | Visual Inspection | Prior to spraying | Surface clean and free of loose material, pre-wet surface immediately prior to spraying. Any residual flowing or seeping water shall be controlled using channels, chases, pipes, or other approved means. | H | W | Cut CheckSHeet | 3.2.2. - Rock Surface Preparation | Description - Prepare all surfaces to be shotcreted prior to application of shotcrete | Method/Description - Visual Inspection | Test frequency - Prior to spraying | Conformance Criteria - Surface clean and free of loose material, pre-wet surface immediately prior to spraying. Any residual flowing or seeping water shall be controlled using channels, chases, pipes, or other approved means. | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Cut CheckSHeet | Conformance Criteria - N/A
3.2.3. | Shotcrete Surface Preparation | Prepare all surfaces to be shotcreted prior to application of shotcrete | Technical Specification - C0650 - Tunnel Civil Works Section 5.4 | Visual Inspection | Prior to spraying | Surface clean and free of loose material, loose shotcrete rebound removed. Pre-wet surface immediately prior to spraying. Spalled, cracked, loose or contaminated shotcrete removed. | H | W | Cut CheckSHeet | 3.2.3. - Shotcrete Surface Preparation | Description - Prepare all surfaces to be shotcreted prior to application of shotcrete | Method/Description - Visual Inspection | Test frequency - Prior to spraying | Conformance Criteria - Surface clean and free of loose material, loose shotcrete rebound removed. Pre-wet surface immediately prior to spraying. Spalled, cracked, loose or contaminated shotcrete removed. | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Cut CheckSHeet | Constructor - H
3.2.4. | Temperature check | Check the temperature of the shotcrete is within acceptable range between 5°C and 35°C. The ambient temperature shoule be more than or equal 5ᴼC. | Technical Specification - C0651 - Tunnel Shotcrete Clause 5.4 NZS 3109: 1997 | thermometer | Each mixer truck prior to discharging | Between 5°C and 35°C | H | R | Shotcrete Installation Record refer to Item 3.2 | 3.2.4. - Temperature check | Description - Check the temperature of the shotcrete is within acceptable range between 5°C and 35°C. The ambient temperature shoule be more than or equal 5ᴼC. | Method/Description - thermometer | Test frequency - Each mixer truck prior to discharging | Conformance Criteria - Between 5°C and 35°C | Constructor - H | CPS - R | Lab - | IOM - | Verifying Records - Shotcrete Installation Record refer to Item 3.2 | CPS - H
3.2.5. | Slump check | Slump to be within the alocated tolerance | NZS 3112.1 Technical Specification - C0651 - Tunnel Shotcrete Clause Clause 5.4 | slump test | Each delivery truck prior to discharging | 220mm ± 20mm | H | R | Shotcrete Record | 3.2.5. - Slump check | Description - Slump to be within the alocated tolerance | Method/Description - slump test | Test frequency - Each delivery truck prior to discharging | Conformance Criteria - 220mm ± 20mm | Constructor - H | CPS - R | Lab - | IOM - | Verifying Records - Shotcrete Record | Lab -
3.2.6. | Personnel Entry | Test prior to each personnel entry and/or face advance. Test results must be verified once a month during construction. | BS EN 14488-2 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 | Penetrometer test | Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction. | Min 1MPa for man entry (providing the shotcrete layer is 75mm thick, rockbolts have been installed and the rockbolt grout compressive strength is min 3MPa) | H | W | Penetrometer test results refer to Item 3.3 | 3.2.6. - Personnel Entry | Description - Test prior to each personnel entry and/or face advance. Test results must be verified once a month during construction. | Method/Description - Penetrometer test | Test frequency - Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction. | Conformance Criteria - Min 1MPa for man entry (providing the shotcrete layer is 75mm thick, rockbolts have been installed and the rockbolt grout compressive strength is min 3MPa) | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Penetrometer test results refer to Item 3.3 | IOM -
3.2.7. | Beam End Test (early age compressive strength) | Safe shotcrete strength before next advancement to max. advance length | Technical Specification - C0651 - Tunnel Shotcrete Table 6.1 and 6.4 ASTM C116 | field test | Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction. | Min. 1.00 MPa at 3 Hours Min. 5.00 MPa at 6 Hours Min. 7.00 MPa at 12 Hours Min. 12.00 MPa at 24-36 Hours | H | W | Beam End Test Results refer to Item 3.3 | 3.2.7. - Beam End Test (early age compressive strength) | Description - Safe shotcrete strength before next advancement to max. advance length | Method/Description - field test | Test frequency - Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction. | Conformance Criteria - Min. 1.00 MPa at 3 Hours Min. 5.00 MPa at 6 Hours Min. 7.00 MPa at 12 Hours Min. 12.00 MPa at 24-36 Hours | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Beam End Test Results refer to Item 3.3 | Verifying Records - PTT
3.2.8. | compressive strength (cast sample) | To prove compressive strength compliance requirement | NZS3112 Technical Specification - C0651 - Tunnel Shotcrete Table 6.1 and 6.4 | certified lab test | 1 test (I test shall include 4 cored specimen, 3 tested and 1 spare) for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter | Min. 35 MPa at 28 days | W | R | IANZ lab test report | 3.2.8. - compressive strength (cast sample) | Description - To prove compressive strength compliance requirement | Method/Description - certified lab test | Test frequency - 1 test (I test shall include 4 cored specimen, 3 tested and 1 spare) for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter | Conformance Criteria - Min. 35 MPa at 28 days | Constructor - W | CPS - R | Lab - | IOM - | Verifying Records - IANZ lab test report | 3.1.2. - Face Mapping
3.2.9. | compressive strength (cored sample) | To prove compressive strength compliance requirement | NZS3112 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 | certified lab test | 1 test for every 50m3 of sprayed shotcrete | Min. 20 MPa at 7 days Min. 35 MPa at 28 days Min. 35 MPa at 90 days | W | R | IANZ lab test report | 3.2.9. - compressive strength (cored sample) | Description - To prove compressive strength compliance requirement | Method/Description - certified lab test | Test frequency - 1 test for every 50m3 of sprayed shotcrete | Conformance Criteria - Min. 20 MPa at 7 days Min. 35 MPa at 28 days Min. 35 MPa at 90 days | Constructor - W | CPS - R | Lab - | IOM - | Verifying Records - IANZ lab test report | Description - Recommend the required support type based on the Actual Ground Conditions. Determine any corrective measures required to ensure safety and stability of the excavation. Identify if the ground conditions depart from the expected range of conditions for which a support type has been designed and notify the Designer if new design is required.
3.2.10. | Residual Flexural Tensile Strength | To prove compliance with flexural strength requirements | BS EN 14651: 2005 + A1: 2007 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 and 6.1 | certified lab test | 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter | Min. FR,1 of 1.25MPa and FR,4 at 1MPa | W | R | IANZ lab test report | 3.2.10. - Residual Flexural Tensile Strength | Description - To prove compliance with flexural strength requirements | Method/Description - certified lab test | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter | Conformance Criteria - Min. FR,1 of 1.25MPa and FR,4 at 1MPa | Constructor - W | CPS - R | Lab - | IOM - | Verifying Records - IANZ lab test report | Method/Description - Geological mapping record
3.2.11. | Drying Shrinkage Testing | To prove compliance with shrinkage requirements | AS1012.13 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 and 6.1 | certified lab test | 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter | Max 850 micro strain | W | R | IANZ lab test report | 3.2.11. - Drying Shrinkage Testing | Description - To prove compliance with shrinkage requirements | Method/Description - certified lab test | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter | Conformance Criteria - Max 850 micro strain | Constructor - W | CPS - R | Lab - | IOM - | Verifying Records - IANZ lab test report | Test frequency - Every advance or as agreed in DRM
3.2.12. | Permeability testing | to prove compliance with permeability requirements | BS EN 12390-8 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4. and 6.1 | certified lab test | 3 tests for the first 50m3 of shotcrete then 1 test every 1 month thereafter | Maximum allowable penetration 25mm | W | R | IANZ lab test report | 3.2.12. - Permeability testing | Description - to prove compliance with permeability requirements | Method/Description - certified lab test | Test frequency - 3 tests for the first 50m3 of shotcrete then 1 test every 1 month thereafter | Conformance Criteria - Maximum allowable penetration 25mm | Constructor - W | CPS - R | Lab - | IOM - | Verifying Records - IANZ lab test report | Conformance Criteria - N/A
3.2.13. | Steel fibre content | To prove compliance with fibre content test requirement | BS EN 14488-7 (fresh concrete) Technical Specification - C0651 - Tunnel Shotcrete Section 4.8 | certified lab test | 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter | Minimum 35kg/m3 | H | R | IANZ lab test report | 3.2.13. - Steel fibre content | Description - To prove compliance with fibre content test requirement | Method/Description - certified lab test | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter | Conformance Criteria - Minimum 35kg/m3 | Constructor - H | CPS - R | Lab - | IOM - | Verifying Records - IANZ lab test report | Constructor - H
3.2.14. | Relative density | To prove compliance with the relative density requirement | NZS 3112.1 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 and 6.1 | certified lab test | 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter | Minimum 98% of the density measured from base mix | H | R | IANZ lab test report | 3.2.14. - Relative density | Description - To prove compliance with the relative density requirement | Method/Description - certified lab test | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter | Conformance Criteria - Minimum 98% of the density measured from base mix | Constructor - H | CPS - R | Lab - | IOM - | Verifying Records - IANZ lab test report | CPS - H
3.2.15. | Layer thickness, Tunnel Lining Intrados, C-Line | Provide control means to verify the thickness of final shotcrete layer | Technical Specification C0650 - Tunnel Sequential Excavation, section 5.7 Drawing MMA-DES-TUN-E1-DRG-8119 Drawing MMA-DES-TUN-E1-DRG-8130 | Survey scans, deep pins | As-builts shall be taken of EACH layer of shotcrete | Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8130 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8119 | H | R | As-built Report | 3.2.15. - Layer thickness, Tunnel Lining Intrados, C-Line | Description - Provide control means to verify the thickness of final shotcrete layer | Method/Description - Survey scans, deep pins | Test frequency - As-builts shall be taken of EACH layer of shotcrete | Conformance Criteria - Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8130 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8119 | Constructor - H | CPS - R | Lab - | IOM - | Verifying Records - As-built Report | Lab -
3.2.16. | Construction joints | Construction joints in the shotcrete lining top heading/bench shall be inspected by the Designer’s Representative as required by the Drawings. | Technical Specification - C0651 - Tunnel Shotcrete Clause 3.2 Table 3.1 | Visual Inspection | Every Construction Joints | Hold point released by CPS | H | H | Site Inspection Report Shotcrete Checklist | 3.2.16. - Construction joints | Description - Construction joints in the shotcrete lining top heading/bench shall be inspected by the Designer’s Representative as required by the Drawings. | Method/Description - Visual Inspection | Test frequency - Every Construction Joints | Conformance Criteria - Hold point released by CPS | Constructor - H | CPS - H | Lab - | IOM - | Verifying Records - Site Inspection Report Shotcrete Checklist | IOM -
3.2.17. | Curing | Curing to be carried out in accordance with the Specification | Technical Specification - C0651 - Tunnel Shotcrete Clause 5.5 |  | Each Spray |  | H | R | Shotcrete Checklist | 3.2.17. - Curing | Description - Curing to be carried out in accordance with the Specification | Method/Description - | Test frequency - Each Spray | Conformance Criteria - | Constructor - H | CPS - R | Lab - | IOM - | Verifying Records - Shotcrete Checklist | Verifying Records - Required Excavation and support sheet
3.2.18. | Defects and Repair | The final layer of shotcrete shall be inspected for any defects and repaired accordingly. At the completion of the lining, all core holes in the lining (resulting from testing or inspection) shall be backfilled with non-shrink mortar of an equivalent strength and fire resistance properties unless otherwise specified. The surface of the restored hole shall be similar to the surrounding surface in texture and colour. | Technical Specification C0650 - Tunnel Sequential Excavation, section 5.6 | Visual Inspection | Every defect on Every advance | Crack CHAR(LESS)0.5mm ,Crack >0.5mm -Non corformance report | H | W | Post spray inspection record | 3.2.18. - Defects and Repair | Description - The final layer of shotcrete shall be inspected for any defects and repaired accordingly. At the completion of the lining, all core holes in the lining (resulting from testing or inspection) shall be backfilled with non-shrink mortar of an equivalent strength and fire resistance properties unless otherwise specified. The surface of the restored hole shall be similar to the surrounding surface in texture and colour. | Method/Description - Visual Inspection | Test frequency - Every defect on Every advance | Conformance Criteria - Crack CHAR(LESS)0.5mm ,Crack >0.5mm -Non corformance report | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Post spray inspection record | 3.1.3. - E-line control
3.3.1. | Reinforcing mesh for primary lining | To prove position, cover and overlap are achieved | Drawing MMMA-DES-TUN-E1-DRG-8011 | Visual inspection and survey | Every advance | Longitudinal and transverse overlap of 250mm ( one mesh square plus 50mm) Min. cover 65mm at the extrados and 85mm at the intrados | H | W | Check sheet | 3.3.1. - Reinforcing mesh for primary lining | Description - To prove position, cover and overlap are achieved | Method/Description - Visual inspection and survey | Test frequency - Every advance | Conformance Criteria - Longitudinal and transverse overlap of 250mm ( one mesh square plus 50mm) Min. cover 65mm at the extrados and 85mm at the intrados | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Check sheet | Description - Control the E-Line before, during and after excavation is finished
3.4.1. | Drilling | Bolts shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. | Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3 Drawing MMMA-DES-TUN-E1-DRG-8011 | Survey | Each bolt | Rockbolts shall be installed perpendicular to the excavation face unless stated otherwise. Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular. Position Tolerence +150,-150mm No overdrill tolerance -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. | H | W | Drilling log | 3.4.1. - Drilling | Description - Bolts shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. | Method/Description - Survey | Test frequency - Each bolt | Conformance Criteria - Rockbolts shall be installed perpendicular to the excavation face unless stated otherwise. Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular. Position Tolerence +150,-150mm No overdrill tolerance -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Drilling log | Method/Description - Surveyor to set out and record as built. VMT system to provide e-line guidance
3.4.2. | Installation | Record all information on installation (position, hole length and dianeterm length of the bolt…) | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3 | Review | Each bolt | Rockbolts to be clean and free from rust or any other physical damage at the time of installation -Type of bolts, diameter, length, location, spacing and orientation according to detailed design -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. | H | W | Drilling log | 3.4.2. - Installation | Description - Record all information on installation (position, hole length and dianeterm length of the bolt…) | Method/Description - Review | Test frequency - Each bolt | Conformance Criteria - Rockbolts to be clean and free from rust or any other physical damage at the time of installation -Type of bolts, diameter, length, location, spacing and orientation according to detailed design -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Drilling log | Test frequency - Every advance
3.4.3. | Grouting mixing | To ensure correct practice | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.4.1 NZ 3109 | Review | Every batch prior to grouting | Target w/c ratio as per MAR | H | W | Grouting records | 3.4.3. - Grouting mixing | Description - To ensure correct practice | Method/Description - Review | Test frequency - Every batch prior to grouting | Conformance Criteria - Target w/c ratio as per MAR | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Grouting records | Conformance Criteria - Over excavation tolerance -0/+150mm
3.4.4. | Grout test | Testing specimen to measure UCS | Technical Specification C0652 - Tunnel Rock Reinforcement section 6.4 NZ 3112.4:1986 | Compressive strength test | Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days) | min 20MPa at 1 day min 40MPa at 28 days The average compressive strength determined from any group of cubes shall exceed the specified characterisitc strength by: 1MPa at 1 day 3MPa at 28 days | H | W | Test results | 3.4.4. - Grout test | Description - Testing specimen to measure UCS | Method/Description - Compressive strength test | Test frequency - Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days) | Conformance Criteria - min 20MPa at 1 day min 40MPa at 28 days The average compressive strength determined from any group of cubes shall exceed the specified characterisitc strength by: 1MPa at 1 day 3MPa at 28 days | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Test results | Constructor - H
3.4.5. | Resin | To ensure correct practice and full encapsulation | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.4.2 | Review | Each bolt | Sufficient number of resin cartridges to be used with each rock reinforcement installation in accordance with the approved project specific procedure developed during the trials. daily records of all grouting works to be kept | H | W | Grouting records | 3.4.5. - Resin | Description - To ensure correct practice and full encapsulation | Method/Description - Review | Test frequency - Each bolt | Conformance Criteria - Sufficient number of resin cartridges to be used with each rock reinforcement installation in accordance with the approved project specific procedure developed during the trials. daily records of all grouting works to be kept | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Grouting records | CPS - W
3.4.6. | Pull test | Demonstrate that the installed rock reinforcements can provide at least the design working load capacity. . | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.5 | Test | 1. First three installations of both rock bolts and rock dowels in each ground type as present in production. 2. 5% of the next 100 installations of rock bolts and rock dowels, proportionately throughout the ground types presenting. 3. 2.5% of the remaining bolts and dowels proportionately throughout the ground types presenting Note: 3 neighbouring installations of rock reinforcement surrounding a failed rock bolt or dowel test (and test frequency to revert back to 5% for the next 100 and 2.5% for the remaining installations) | The bolt or dowel is deemed acceptable if, during the cycle, the displacement of the bolt or dowel head relative to the measuring datum (after allowing for any temperature changes) does not exceed the criteria for 100% of the working load, as set out in Table 6.4 of the specification. Failure criteria: 2% Maximum Permissible Displacement or failure to maintain specified loads or ongoing creep of the rock bolt or rock dowel | H | W | Testing records | 3.4.6. - Pull test | Description - Demonstrate that the installed rock reinforcements can provide at least the design working load capacity. . | Method/Description - Test | Test frequency - 1. First three installations of both rock bolts and rock dowels in each ground type as present in production. 2. 5% of the next 100 installations of rock bolts and rock dowels, proportionately throughout the ground types presenting. 3. 2.5% of the remaining bolts and dowels proportionately throughout the ground types presenting Note: 3 neighbouring installations of rock reinforcement surrounding a failed rock bolt or dowel test (and test frequency to revert back to 5% for the next 100 and 2.5% for the remaining installations) | Conformance Criteria - The bolt or dowel is deemed acceptable if, during the cycle, the displacement of the bolt or dowel head relative to the measuring datum (after allowing for any temperature changes) does not exceed the criteria for 100% of the working load, as set out in Table 6.4 of the specification. Failure criteria: 2% Maximum Permissible Displacement or failure to maintain specified loads or ongoing creep of the rock bolt or rock dowel | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Testing records | Lab -
3.5.1. | Drilling | Spiles shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. | Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3 | Survey | Each spile | Positional tolerance of portal spile bars not to exceed 25mm in any direction -Setout angle shall be as per drawing. Max. angular tolerance not to exceed 1 in 60. | H | W | Drilling record ,Survey Report | 3.5.1. - Drilling | Description - Spiles shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. | Method/Description - Survey | Test frequency - Each spile | Conformance Criteria - Positional tolerance of portal spile bars not to exceed 25mm in any direction -Setout angle shall be as per drawing. Max. angular tolerance not to exceed 1 in 60. | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Drilling record ,Survey Report | IOM -
3.5.2. | Installation | Record information on installation. | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3 | Review | Each bolt | -Spiles shall be free of dirt, detrimental rust or any other deleterious substance. - Type of spile, diameter, length, location, spacing and orientation according to detailed design. | H | W | Rock Bolt Installation Record | 3.5.2. - Installation | Description - Record information on installation. | Method/Description - Review | Test frequency - Each bolt | Conformance Criteria - -Spiles shall be free of dirt, detrimental rust or any other deleterious substance. - Type of spile, diameter, length, location, spacing and orientation according to detailed design. | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Rock Bolt Installation Record | Verifying Records - As-built Report
3.5.3. | Grouting mixing | To ensure correct practice and w/c ratio check | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.4.1 NZ 3109 | Review | Every batch prior to grouting | Target w/c ratio as per MAR | H | W | Rock Bolt Installation Record | 3.5.3. - Grouting mixing | Description - To ensure correct practice and w/c ratio check | Method/Description - Review | Test frequency - Every batch prior to grouting | Conformance Criteria - Target w/c ratio as per MAR | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Rock Bolt Installation Record | 3.2.1. - Delivery docket Check
3.5.4. | Grout test | Testing specimen to measure UCS | Technical Specification C0652 - Tunnel Rock Reinforcement section 6.4 NZ 3112.4:1986 | Compressive strength test | Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days) | min 20MPa at 1 day min 40MPa at 28 days The average compressive strength determined from any group of cubes shall excess the specified characterisitc strength by: 1MPa at 1 day 3MPa at 28 days | H | W | IANZ lab test report | 3.5.4. - Grout test | Description - Testing specimen to measure UCS | Method/Description - Compressive strength test | Test frequency - Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days) | Conformance Criteria - min 20MPa at 1 day min 40MPa at 28 days The average compressive strength determined from any group of cubes shall excess the specified characterisitc strength by: 1MPa at 1 day 3MPa at 28 days | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - IANZ lab test report | Description - Check delivery docket to ensure the mix used is the correct mix
3.6.1. | Drilling | Dowels shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. | Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3 | Survey | Each dowel | Dowels shall be installed perpendicular to the excavation face unless stated otherwise. Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular. Position Tolerence +150,-150mm No overdrill tolerance -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. | H | W | Rock Bolt Installation Record/Check list /As built Survey | 3.6.1. - Drilling | Description - Dowels shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. | Method/Description - Survey | Test frequency - Each dowel | Conformance Criteria - Dowels shall be installed perpendicular to the excavation face unless stated otherwise. Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular. Position Tolerence +150,-150mm No overdrill tolerance -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Rock Bolt Installation Record/Check list /As built Survey | Method/Description - Document Review
3.6.2. | Installation | Dowels shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3 | Review | Each dowel | dowels to be clean or any other physical damage at the time of installation -Type of bolts, diameter, length, location, spacing and orientation according to detailed design -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. | H | W | Rock Bolt Installation Record | 3.6.2. - Installation | Description - Dowels shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. | Method/Description - Review | Test frequency - Each dowel | Conformance Criteria - dowels to be clean or any other physical damage at the time of installation -Type of bolts, diameter, length, location, spacing and orientation according to detailed design -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Rock Bolt Installation Record | Test frequency - Prior to any shotcrete application
3.6.3. | Grouting | To ensure correct practice and w/c ratio check | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.4.1 NZ 3109 | Review | Every batch prior to grouting | Target w/c ratio as per MAR | H | W | Rock Bolt Installation Record | 3.6.3. - Grouting | Description - To ensure correct practice and w/c ratio check | Method/Description - Review | Test frequency - Every batch prior to grouting | Conformance Criteria - Target w/c ratio as per MAR | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Rock Bolt Installation Record | Conformance Criteria - N/A
|  | Testing specimen to measure UCS | Technical Specification C0652 - Tunnel Rock Reinforcement section 6.4 NZ 3112.4:1986 | Compressive strength test | Every batch prior to grouting (three cubes at 1 day, three cubes at 28 days) | min 20MPa at 1 day, and average to exceed specified strength by 1MPa min 40MPa at 28 days, and average to exceed specified strength | H | W | IANZ lab test report | - | Description - Testing specimen to measure UCS | Method/Description - Compressive strength test | Test frequency - Every batch prior to grouting (three cubes at 1 day, three cubes at 28 days) | Conformance Criteria - min 20MPa at 1 day, and average to exceed specified strength by 1MPa min 40MPa at 28 days, and average to exceed specified strength | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - IANZ lab test report | Constructor - H
3.7.1. | Drilling probe holes | Record information during drilling Check the water inflow during and after drilling | Technical specification C0650 - Tunnel Sequential Excavation, section 5.5 | Geological monitoring | Maintain minimum one probe at 20 m ahead of the face at all times | -Hole diameter minimum 50 mm - Not less than three probe holes shall be maintained a minimum of 6m ahead of the excavation face at all times and with at least 1 probe hole maintained a minimum 20m ahead of the excavation face at all times | H | W | Probe holes record ,Survey As built report | 3.7.1. - Drilling probe holes | Description - Record information during drilling Check the water inflow during and after drilling | Method/Description - Geological monitoring | Test frequency - Maintain minimum one probe at 20 m ahead of the face at all times | Conformance Criteria - -Hole diameter minimum 50 mm - Not less than three probe holes shall be maintained a minimum of 6m ahead of the excavation face at all times and with at least 1 probe hole maintained a minimum 20m ahead of the excavation face at all times | Constructor - H | CPS - W | Lab - | IOM - | Verifying Records - Probe holes record ,Survey As built report | CPS - R
3.8.1. | Tunnel convergency (Extensometer) | Monitoring and reading records of the tunnel extensometer | Technical Specification C0660 - Tunnel Convergence Monitoring | Review | from excavation face >100m = Monthly 40m-100m = Weekly 15m - 40m = 2x weekly CHAR(LESS)15m = daily |  | H | R | Monitoring Report | 3.8.1. - Tunnel convergency (Extensometer) | Description - Monitoring and reading records of the tunnel extensometer | Method/Description - Review | Test frequency - from excavation face >100m = Monthly 40m-100m = Weekly 15m - 40m = 2x weekly CHAR(LESS)15m = daily | Conformance Criteria - | Constructor - H | CPS - R | Lab - | IOM - | Verifying Records - Monitoring Report | Lab -
3.8.2. | In-Tunnel Optical Survey Convergence | Monitoring and reading records on the tunnel optical survey targets | Technical Specification C0660 - Tunnel Convergence Monitoring | Review | from excavation face >100m = Monthly 40m-100m = Weekly 15m - 40m = 2x weekly CHAR(LESS)15m = daily |  | H | R | Monitoring Report | 3.8.2. - In-Tunnel Optical Survey Convergence | Description - Monitoring and reading records on the tunnel optical survey targets | Method/Description - Review | Test frequency - from excavation face >100m = Monthly 40m-100m = Weekly 15m - 40m = 2x weekly CHAR(LESS)15m = daily | Conformance Criteria - | Constructor - H | CPS - R | Lab - | IOM - | Verifying Records - Monitoring Report | IOM -
3.9.1 | Strip drain installations | Record location and ensure correct installation | Technical Specification C0653 - Tunnel Groundwater Control Systems Section 5 | Review |  | Location and quantity of the strip drains shall be as instructed on site by the Designer's representative | H | R | Excavation and shotcrete check sheet,Survey as built record | 3.9.1 - Strip drain installations | Description - Record location and ensure correct installation | Method/Description - Review | Test frequency - | Conformance Criteria - Location and quantity of the strip drains shall be as instructed on site by the Designer's representative | Constructor - H | CPS - R | Lab - | IOM - | Verifying Records - Excavation and shotcrete check sheet,Survey as built record | Verifying Records - Delivery docket
3.9.2 | Groundwater (rectification) | Where the inflow into the tunnel exceeds the design criteria,appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative. | Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6 | Visual Inspection | Ongoing | Shall not be exceed 3L/m of length/day averaged over a 100m length of tunnel. Where exceeded, the post-installation groundwater methodology is to be followed. | H | H | Installation Checksheet | 3.9.2 - Groundwater (rectification) | Description - Where the inflow into the tunnel exceeds the design criteria,appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative. | Method/Description - Visual Inspection | Test frequency - Ongoing | Conformance Criteria - Shall not be exceed 3L/m of length/day averaged over a 100m length of tunnel. Where exceeded, the post-installation groundwater methodology is to be followed. | Constructor - H | CPS - H | Lab - | IOM - | Verifying Records - Installation Checksheet | 3.2.2. - Rock Surface Preparation
Description - Prepare all surfaces to be shotcreted prior to application of shotcrete
Method/Description - Visual Inspection
Test frequency - Prior to spraying
Conformance Criteria - Surface clean and free of loose material, pre-wet surface immediately prior to spraying. Any residual flowing or seeping water shall be controlled using channels, chases, pipes, or other approved means.
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Cut CheckSHeet
3.2.3. - Shotcrete Surface Preparation
Description - Prepare all surfaces to be shotcreted prior to application of shotcrete
Method/Description - Visual Inspection
Test frequency - Prior to spraying
Conformance Criteria - Surface clean and free of loose material, loose shotcrete rebound removed. Pre-wet surface immediately prior to spraying. Spalled, cracked, loose or contaminated shotcrete removed.
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Cut CheckSHeet
3.2.4. - Temperature check
Description - Check the temperature of the shotcrete is within acceptable range between 5°C and 35°C. The ambient temperature shoule be more than or equal 5ᴼC.
Method/Description - thermometer
Test frequency - Each mixer truck prior to discharging
Conformance Criteria - Between 5°C and 35°C
Constructor - H
CPS - R
Lab -
IOM -
Verifying Records - Shotcrete Installation Record refer to Item 3.2
3.2.5. - Slump check
Description - Slump to be within the alocated tolerance
Method/Description - slump test
Test frequency - Each delivery truck prior to discharging
Conformance Criteria - 220mm ± 20mm
Constructor - H
CPS - R
Lab -
IOM -
Verifying Records - Shotcrete Record
3.2.6. - Personnel Entry
Description - Test prior to each personnel entry and/or face advance. Test results must be verified once a month during construction.
Method/Description - Penetrometer test
Test frequency - Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction.
Conformance Criteria - Min 1MPa for man entry (providing the shotcrete layer is 75mm thick, rockbolts have been installed and the rockbolt grout compressive strength is min 3MPa)
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Penetrometer test results refer to Item 3.3
3.2.7. - Beam End Test (early age compressive strength)
Description - Safe shotcrete strength before next advancement to max. advance length
Method/Description - field test
Test frequency - Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction.
Conformance Criteria - Min. 1.00 MPa at 3 Hours Min. 5.00 MPa at 6 Hours Min. 7.00 MPa at 12 Hours Min. 12.00 MPa at 24-36 Hours
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Beam End Test Results refer to Item 3.3
3.2.8. - compressive strength (cast sample)
Description - To prove compressive strength compliance requirement
Method/Description - certified lab test
Test frequency - 1 test (I test shall include 4 cored specimen, 3 tested and 1 spare) for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter
Conformance Criteria - Min. 35 MPa at 28 days
Constructor - W
CPS - R
Lab -
IOM -
Verifying Records - IANZ lab test report
3.2.9. - compressive strength (cored sample)
Description - To prove compressive strength compliance requirement
Method/Description - certified lab test
Test frequency - 1 test for every 50m3 of sprayed shotcrete
Conformance Criteria - Min. 20 MPa at 7 days Min. 35 MPa at 28 days Min. 35 MPa at 90 days
Constructor - W
CPS - R
Lab -
IOM -
Verifying Records - IANZ lab test report
3.2.10. - Residual Flexural Tensile Strength
Description - To prove compliance with flexural strength requirements
Method/Description - certified lab test
Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter
Conformance Criteria - Min. FR,1 of 1.25MPa and FR,4 at 1MPa
Constructor - W
CPS - R
Lab -
IOM -
Verifying Records - IANZ lab test report
3.2.11. - Drying Shrinkage Testing
Description - To prove compliance with shrinkage requirements
Method/Description - certified lab test
Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter
Conformance Criteria - Max 850 micro strain
Constructor - W
CPS - R
Lab -
IOM -
Verifying Records - IANZ lab test report
3.2.12. - Permeability testing
Description - to prove compliance with permeability requirements
Method/Description - certified lab test
Test frequency - 3 tests for the first 50m3 of shotcrete then 1 test every 1 month thereafter
Conformance Criteria - Maximum allowable penetration 25mm
Constructor - W
CPS - R
Lab -
IOM -
Verifying Records - IANZ lab test report
3.2.13. - Steel fibre content
Description - To prove compliance with fibre content test requirement
Method/Description - certified lab test
Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter
Conformance Criteria - Minimum 35kg/m3
Constructor - H
CPS - R
Lab -
IOM -
Verifying Records - IANZ lab test report
3.2.14. - Relative density
Description - To prove compliance with the relative density requirement
Method/Description - certified lab test
Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter
Conformance Criteria - Minimum 98% of the density measured from base mix
Constructor - H
CPS - R
Lab -
IOM -
Verifying Records - IANZ lab test report
3.2.15. - Layer thickness, Tunnel Lining Intrados, C-Line
Description - Provide control means to verify the thickness of final shotcrete layer
Method/Description - Survey scans, deep pins
Test frequency - As-builts shall be taken of EACH layer of shotcrete
Conformance Criteria - Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8130 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8119
Constructor - H
CPS - R
Lab -
IOM -
Verifying Records - As-built Report
3.2.16. - Construction joints
Description - Construction joints in the shotcrete lining top heading/bench shall be inspected by the Designer’s Representative as required by the Drawings.
Method/Description - Visual Inspection
Test frequency - Every Construction Joints
Conformance Criteria - Hold point released by CPS
Constructor - H
CPS - H
Lab -
IOM -
Verifying Records - Site Inspection Report Shotcrete Checklist
3.2.17. - Curing
Description - Curing to be carried out in accordance with the Specification
Method/Description -
Test frequency - Each Spray
Conformance Criteria -
Constructor - H
CPS - R
Lab -
IOM -
Verifying Records - Shotcrete Checklist
3.2.18. - Defects and Repair
Description - The final layer of shotcrete shall be inspected for any defects and repaired accordingly. At the completion of the lining, all core holes in the lining (resulting from testing or inspection) shall be backfilled with non-shrink mortar of an equivalent strength and fire resistance properties unless otherwise specified. The surface of the restored hole shall be similar to the surrounding surface in texture and colour.
Method/Description - Visual Inspection
Test frequency - Every defect on Every advance
Conformance Criteria - Crack CHAR(LESS)0.5mm ,Crack >0.5mm -Non corformance report
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Post spray inspection record
3.3.1. - Reinforcing mesh for primary lining
Description - To prove position, cover and overlap are achieved
Method/Description - Visual inspection and survey
Test frequency - Every advance
Conformance Criteria - Longitudinal and transverse overlap of 250mm ( one mesh square plus 50mm) Min. cover 65mm at the extrados and 85mm at the intrados
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Check sheet
3.4.1. - Drilling
Description - Bolts shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
Method/Description - Survey
Test frequency - Each bolt
Conformance Criteria - Rockbolts shall be installed perpendicular to the excavation face unless stated otherwise. Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular. Position Tolerence +150,-150mm No overdrill tolerance -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Drilling log
3.4.2. - Installation
Description - Record all information on installation (position, hole length and dianeterm length of the bolt…)
Method/Description - Review
Test frequency - Each bolt
Conformance Criteria - Rockbolts to be clean and free from rust or any other physical damage at the time of installation -Type of bolts, diameter, length, location, spacing and orientation according to detailed design -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Drilling log
3.4.3. - Grouting mixing
Description - To ensure correct practice
Method/Description - Review
Test frequency - Every batch prior to grouting
Conformance Criteria - Target w/c ratio as per MAR
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Grouting records
3.4.4. - Grout test
Description - Testing specimen to measure UCS
Method/Description - Compressive strength test
Test frequency - Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days)
Conformance Criteria - min 20MPa at 1 day min 40MPa at 28 days The average compressive strength determined from any group of cubes shall exceed the specified characterisitc strength by: 1MPa at 1 day 3MPa at 28 days
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Test results
3.4.5. - Resin
Description - To ensure correct practice and full encapsulation
Method/Description - Review
Test frequency - Each bolt
Conformance Criteria - Sufficient number of resin cartridges to be used with each rock reinforcement installation in accordance with the approved project specific procedure developed during the trials. daily records of all grouting works to be kept
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Grouting records
3.4.6. - Pull test
Description - Demonstrate that the installed rock reinforcements can provide at least the design working load capacity. .
Method/Description - Test
Test frequency - 1. First three installations of both rock bolts and rock dowels in each ground type as present in production. 2. 5% of the next 100 installations of rock bolts and rock dowels, proportionately throughout the ground types presenting. 3. 2.5% of the remaining bolts and dowels proportionately throughout the ground types presenting Note: 3 neighbouring installations of rock reinforcement surrounding a failed rock bolt or dowel test (and test frequency to revert back to 5% for the next 100 and 2.5% for the remaining installations)
Conformance Criteria - The bolt or dowel is deemed acceptable if, during the cycle, the displacement of the bolt or dowel head relative to the measuring datum (after allowing for any temperature changes) does not exceed the criteria for 100% of the working load, as set out in Table 6.4 of the specification. Failure criteria: 2% Maximum Permissible Displacement or failure to maintain specified loads or ongoing creep of the rock bolt or rock dowel
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Testing records
3.5.1. - Drilling
Description - Spiles shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
Method/Description - Survey
Test frequency - Each spile
Conformance Criteria - Positional tolerance of portal spile bars not to exceed 25mm in any direction -Setout angle shall be as per drawing. Max. angular tolerance not to exceed 1 in 60.
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Drilling record ,Survey Report
3.5.2. - Installation
Description - Record information on installation.
Method/Description - Review
Test frequency - Each bolt
Conformance Criteria - -Spiles shall be free of dirt, detrimental rust or any other deleterious substance. - Type of spile, diameter, length, location, spacing and orientation according to detailed design.
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Rock Bolt Installation Record
3.5.3. - Grouting mixing
Description - To ensure correct practice and w/c ratio check
Method/Description - Review
Test frequency - Every batch prior to grouting
Conformance Criteria - Target w/c ratio as per MAR
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Rock Bolt Installation Record
3.5.4. - Grout test
Description - Testing specimen to measure UCS
Method/Description - Compressive strength test
Test frequency - Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days)
Conformance Criteria - min 20MPa at 1 day min 40MPa at 28 days The average compressive strength determined from any group of cubes shall excess the specified characterisitc strength by: 1MPa at 1 day 3MPa at 28 days
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - IANZ lab test report
3.6.1. - Drilling
Description - Dowels shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
Method/Description - Survey
Test frequency - Each dowel
Conformance Criteria - Dowels shall be installed perpendicular to the excavation face unless stated otherwise. Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular. Position Tolerence +150,-150mm No overdrill tolerance -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Rock Bolt Installation Record/Check list /As built Survey
3.6.2. - Installation
Description - Dowels shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
Method/Description - Review
Test frequency - Each dowel
Conformance Criteria - dowels to be clean or any other physical damage at the time of installation -Type of bolts, diameter, length, location, spacing and orientation according to detailed design -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Rock Bolt Installation Record
3.6.3. - Grouting
Description - To ensure correct practice and w/c ratio check
Method/Description - Review
Test frequency - Every batch prior to grouting
Conformance Criteria - Target w/c ratio as per MAR
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Rock Bolt Installation Record
-
Description - Testing specimen to measure UCS
Method/Description - Compressive strength test
Test frequency - Every batch prior to grouting (three cubes at 1 day, three cubes at 28 days)
Conformance Criteria - min 20MPa at 1 day, and average to exceed specified strength by 1MPa min 40MPa at 28 days, and average to exceed specified strength
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - IANZ lab test report
3.7.1. - Drilling probe holes
Description - Record information during drilling Check the water inflow during and after drilling
Method/Description - Geological monitoring
Test frequency - Maintain minimum one probe at 20 m ahead of the face at all times
Conformance Criteria - -Hole diameter minimum 50 mm - Not less than three probe holes shall be maintained a minimum of 6m ahead of the excavation face at all times and with at least 1 probe hole maintained a minimum 20m ahead of the excavation face at all times
Constructor - H
CPS - W
Lab -
IOM -
Verifying Records - Probe holes record ,Survey As built report
3.8.1. - Tunnel convergency (Extensometer)
Description - Monitoring and reading records of the tunnel extensometer
Method/Description - Review
Test frequency - from excavation face >100m = Monthly 40m-100m = Weekly 15m - 40m = 2x weekly CHAR(LESS)15m = daily
Conformance Criteria -
Constructor - H
CPS - R
Lab -
IOM -
Verifying Records - Monitoring Report
3.8.2. - In-Tunnel Optical Survey Convergence
Description - Monitoring and reading records on the tunnel optical survey targets
Method/Description - Review
Test frequency - from excavation face >100m = Monthly 40m-100m = Weekly 15m - 40m = 2x weekly CHAR(LESS)15m = daily
Conformance Criteria -
Constructor - H
CPS - R
Lab -
IOM -
Verifying Records - Monitoring Report
3.9.1 - Strip drain installations
Description - Record location and ensure correct installation
Method/Description - Review
Test frequency -
Conformance Criteria - Location and quantity of the strip drains shall be as instructed on site by the Designer's representative
Constructor - H
CPS - R
Lab -
IOM -
Verifying Records - Excavation and shotcrete check sheet,Survey as built record
3.9.2 - Groundwater (rectification)
Description - Where the inflow into the tunnel exceeds the design criteria,appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative.
Method/Description - Visual Inspection
Test frequency - Ongoing
Conformance Criteria - Shall not be exceed 3L/m of length/day averaged over a 100m length of tunnel. Where exceeded, the post-installation groundwater methodology is to be followed.
Constructor - H
CPS - H
Lab -
IOM -
Verifying Records - Installation Checksheet