## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Strip Out |  |  |  |  | Yes | SYS - PT - Strip Out | 8147ab36-75dd-4e81-88db-1f8b64a5833f
checkpoint-status |  |  | checkpoint | Flush boxes cut as per plan
checkpoint-status |  |  | checkpoint | Fans cut as per plan
checkpoint-status |  |  | checkpoint | Lights cut as per plan
checkpoint-status |  |  | checkpoint | Exterior lights have been bought out centre / as per pre-wire
checkpoint-status |  |  | checkpoint | Cables stripped
checkpoint-status |  |  | checkpoint | Switching as per plan
checkpoint-status |  |  | checkpoint | Cables clearly labelled
checkpoint-status |  |  | checkpoint | Complete final walkthrough check
checkpoint-status |  |  | checkpoint | Damages and remidials documented
checkpoint-status |  |  | checkpoint | Photos
checklist-sectioned |  |  | checklist | Lake District - Second Fix - Laundry/Scullery |  |  |  |  | Yes | Lake District - Second Fix - Laundry/Scullery | 9d91683d-0c6f-4b15-b0eb-2f11ed0d11a1
checkpoint-group |  |  | section | Power outlets
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Switches
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Switching as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Fixtures
checkpoint-status |  |  | checkpoint | Correct fixtures installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Height as per plan
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-group |  |  | section | Fans
checkpoint-status |  |  | checkpoint | Interior grill installed
checkpoint-status |  |  | checkpoint | Exterior grill installed
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-group |  |  | section | Photos
checkpoint-status |  |  | checkpoint | Uploaded
checklist-sectioned |  |  | checklist | Lake District - First Fix - Bathrooms/Ensuite |  |  |  |  | Yes | Lake District - First Fix - Bathrooms/Ensuite | 9df3b481-2a68-46d6-8187-b00c42220446
checkpoint-group |  |  | section | Flush Boxes
checkpoint-status |  |  | checkpoint | Height as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Nogging installed for towel rail
checkpoint-status |  |  | checkpoint | Marked on floor
checkpoint-group |  |  | section | Cabling
checkpoint-status |  |  | checkpoint | Circuits clearly labelled
checkpoint-status |  |  | checkpoint | Cables secured
checkpoint-status |  |  | checkpoint | Separation between data and power
checkpoint-group |  |  | section | Lights
checkpoint-status |  |  | checkpoint | Cabling in correct location
checkpoint-status |  |  | checkpoint | Measurements recorded
checkpoint-status |  |  | checkpoint | Nogging installed
checkpoint-status |  |  | checkpoint | Marked on floor
checkpoint-group |  |  | section | Fans
checkpoint-status |  |  | checkpoint | Installed in accessible location
checkpoint-status |  |  | checkpoint | Surface socket fit-off and lead taped on (inline fan)
checkpoint-status |  |  | checkpoint | Ducts run flat and straight
checkpoint-status |  |  | checkpoint | Measurements recorded
checkpoint-status |  |  | checkpoint | Marked on floor
checkpoint-group |  |  | section | Photos
checkpoint-status |  |  | checkpoint | Uploaded
checklist-sectioned |  |  | checklist | Lake District - Mains Install |  |  |  |  | Yes | Lake District - Mains Install | ddcebcef-207f-4050-9def-de97e5133d9c
checkpoint-group |  |  | section | Electrical
checkpoint-status |  |  | checkpoint | Cable installed at minimum depth of 600mm
checkpoint-status |  |  | checkpoint | Protection mag slab installed
checkpoint-status |  |  | checkpoint | Warning signal tape installed
checkpoint-status |  |  | checkpoint | Cable installed through concrete slab
checkpoint-status |  |  | checkpoint | Cable bought up next to gyro / pole
checkpoint-status |  |  | checkpoint | Cable clearly labelled
checkpoint-status |  |  | checkpoint | Cable size and measurements recorded
checkpoint-status |  |  | checkpoint | Plan marked with as-built
checkpoint-status |  |  | checkpoint | Photos
checkpoint-group |  |  | section | Telecom / Fibre
checkpoint-status |  |  | checkpoint | Cable installed at minimum depth of 400mm
checkpoint-status |  |  | checkpoint | Approved exterior fibre cable used
checkpoint-status |  |  | checkpoint | Cable installed through concrete slab
checkpoint-status |  |  | checkpoint | Cable bought up next to gyro / pole
checkpoint-status |  |  | checkpoint | Cable measurements recorded
checkpoint-status |  |  | checkpoint | Plan marked with as-built
checkpoint-status |  |  | checkpoint | Photos
checklist-sectioned |  |  | checklist | Lake District - Second Fix - Kitchen |  |  |  |  | Yes | Lake District - Second Fix - Kitchen | c89153f8-78b3-4052-a6ea-dd865660ef73
checkpoint-group |  |  | section | Power outlets
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-status |  |  | checkpoint | Sink earth bond connected
checkpoint-group |  |  | section | Light Switches
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Switching as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Fixtures
checkpoint-status |  |  | checkpoint | Correct fixtures installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Height as per plan / client preference
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-group |  |  | section | Appliances
checkpoint-status |  |  | checkpoint | HOB installed and secured
checkpoint-status |  |  | checkpoint | Oven installed and secured
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-group |  |  | section | Photos
checkpoint-status |  |  | checkpoint | Uploaded
checklist-sectioned |  |  | checklist | Lake District - Second Fix - Living/Bedroom/Garage |  |  |  |  | Yes | Lake District - Second Fix - Living/Bedroom/Garage | 843bbd04-3cb7-42ba-9f69-40e7b1312923
checkpoint-group |  |  | section | Power outlets
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Switches
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Switching as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Fixtures
checkpoint-status |  |  | checkpoint | Correct fixtures installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Height as per plan / client preference
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-group |  |  | section | Photos
checkpoint-status |  |  | checkpoint | Uploaded
checklist-sectioned |  |  | checklist | Lake District - First Fix - Kitchen/Living/Photos/Bedrooms/Garage/Hallway |  |  |  |  | Yes | Lake District - First Fix - Kitchen/Living/Photos/Bedrooms/Garage/Hallway | 1ac9f44e-b23f-41d6-9417-029f0f927858
checkpoint-group |  |  | section | Flush Boxes
checkpoint-status |  |  | checkpoint | Height as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Marked on floor
checkpoint-group |  |  | section | Cabling
checkpoint-status |  |  | checkpoint | Circuits clearly labelled
checkpoint-status |  |  | checkpoint | Cables secured
checkpoint-status |  |  | checkpoint | Separation between data and power
checkpoint-group |  |  | section | Lights
checkpoint-status |  |  | checkpoint | Cabling in correct location
checkpoint-status |  |  | checkpoint | measurements recorded
checkpoint-status |  |  | checkpoint | Nogging installed
checkpoint-status |  |  | checkpoint | Marked on floor
checkpoint-group |  |  | section | Photos
checkpoint-status |  |  | checkpoint | Uploaded
checklist-flat |  |  | checklist | Walkthrough |  |  |  |  | Yes | Walkthrough Checklist | 98be94a7-2b0a-4227-bd53-6af012a093cb
checkpoint-status |  |  | checkpoint | Power outlet locations confirmed and marked
checkpoint-status |  |  | checkpoint | Light switch locations confirmed and marked
checkpoint-status |  |  | checkpoint | Switchboard locations confirmed and marked
checkpoint-status |  |  | checkpoint | Bathroom outlet locations confirmed and marked
checkpoint-status |  |  | checkpoint | Bathroom outlets vertical or horizontal
checkpoint-status |  |  | checkpoint | Towel rail locations confirmed and marked
checkpoint-status |  |  | checkpoint | Interior light locations confirmed
checkpoint-status |  |  | checkpoint | Exterior light locations confirmed and marked
checkpoint-status |  |  | checkpoint | Exterior fan grills soffit mount or wall mount
checkpoint-status |  |  | checkpoint | CCTV locations confirmed
checkpoint-status |  |  | checkpoint | CCTV soffit mount or wall mount
checkpoint-status |  |  | checkpoint | Aerial locations confirmed
checkpoint-status |  |  | checkpoint | Aerial cabling location confirmed and marked
checkpoint-status |  |  | checkpoint | Plans updated with changes
checklist-flat |  |  | checklist | Lake District - Strip Out |  |  |  |  | Yes | Lake District - Strip Out | 65a29de1-ff7c-41d1-9c5f-a4a3e999fedc
checkpoint-status |  |  | checkpoint | Flush boxes cut as per plan
checkpoint-status |  |  | checkpoint | Fans cut as per plan
checkpoint-status |  |  | checkpoint | Lights cut as per plan
checkpoint-status |  |  | checkpoint | Exterior lights have been bought out centre / as per pre-wire
checkpoint-status |  |  | checkpoint | Cables stripped
checkpoint-status |  |  | checkpoint | Switching as per plan
checkpoint-status |  |  | checkpoint | Cables clearly labelled
checkpoint-status |  |  | checkpoint | Complete final walkthrough check
checkpoint-status |  |  | checkpoint | Damages and remedials documented
checkpoint-status |  |  | checkpoint | Photos
checklist-sectioned |  |  | checklist | Lake District - First Fix - Switchboards |  |  |  |  | Yes | Lake District - First Fix - Switchboards | 1de958f4-2696-44df-99c1-3cd4e3ef0cc4
checkpoint-group |  |  | section | Electrical
checkpoint-status |  |  | checkpoint | Installed as per plan
checkpoint-status |  |  | checkpoint | Height as per plan
checkpoint-status |  |  | checkpoint | Cables clearly labelled
checkpoint-status |  |  | checkpoint | Check all cables have been bought into switchboard
checkpoint-status |  |  | checkpoint | Mains cable installed
checkpoint-status |  |  | checkpoint | Photos
checkpoint-group |  |  | section | Data
checkpoint-status |  |  | checkpoint | Installed as per plan
checkpoint-status |  |  | checkpoint | Height as per plan
checkpoint-status |  |  | checkpoint | Cables clearly labelled
checkpoint-status |  |  | checkpoint | Check all cables have been bought into board
checkpoint-status |  |  | checkpoint | Interior fibre cable installed
checkpoint-status |  |  | checkpoint | Photos
checklist-sectioned |  |  | checklist | Lake District - Second Fix - Switchboards |  |  |  |  | Yes | Lake District - Second Fix - Switchboards | e709e920-bd29-43fa-b4cf-e1185cbedb58
checkpoint-group |  |  | section | Electrical
checkpoint-status |  |  | checkpoint | Cables clearly labelled
checkpoint-status |  |  | checkpoint | Cables neatly dressed
checkpoint-status |  |  | checkpoint | Switchboard bonded
checkpoint-status |  |  | checkpoint | Neutrals and earths labelled
checkpoint-status |  |  | checkpoint | Terminations checked for tightness
checkpoint-status |  |  | checkpoint | Board is clean inside and outside
checkpoint-status |  |  | checkpoint | Masking blanks installed
checkpoint-status |  |  | checkpoint | Masking panel labelled with circuits
checkpoint-status |  |  | checkpoint | Photos
checkpoint-group |  |  | section | Data
checkpoint-status |  |  | checkpoint | Cables clearly labelled
checkpoint-status |  |  | checkpoint | Cables neatly dressed
checkpoint-status |  |  | checkpoint | Board bonded
checkpoint-status |  |  | checkpoint | Terminations checked for tightness
checkpoint-status |  |  | checkpoint | Board is clean inside and outside
checkpoint-status |  |  | checkpoint | Photos
checklist-sectioned |  |  | checklist | Lake District - Second Fix - Exterior |  |  |  |  | Yes | Lake District - Second Fix - Exterior | 3f0fb53a-48da-4a1a-ae23-1595fcc8b848
checkpoint-group |  |  | section | Power outlets
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-status |  |  | checkpoint | Danger sign installed
checkpoint-group |  |  | section | Light Switches
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Switching as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Fixtures
checkpoint-status |  |  | checkpoint | Correct fixtures installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Height as per plan
checkpoint-status |  |  | checkpoint | Settings adjusted (sensores + timers)
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-status |  |  | checkpoint | Landscape lighting (cable disconnected)
checkpoint-group |  |  | section | Fans
checkpoint-status |  |  | checkpoint | Exterior grill installed
checkpoint-status |  |  | checkpoint | Installed square
checkpoint-group |  |  | section | Photos
checkpoint-status |  |  | checkpoint | Uploaded
checklist-flat |  |  | checklist | Lake District - BTS Install |  |  |  |  | Yes | Lake District - BTS Install | 46340e19-3286-4505-8af8-1c6e2c182b1c
checkpoint-status |  |  | checkpoint | Location as per plan / discussion
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-status |  |  | checkpoint | Earth electrode installed
checkpoint-status |  |  | checkpoint | Earth tag installed
checkpoint-status |  |  | checkpoint | Earth clamp installed
checkpoint-status |  |  | checkpoint | Zinc spray applied
checkpoint-status |  |  | checkpoint | Earth toby installed and secured in place
checkpoint-status |  |  | checkpoint | Danger sign installed
checkpoint-status |  |  | checkpoint | Terminations checked for tightness
checkpoint-status |  |  | checkpoint | Cable installed at minimum depth of 600mm
checkpoint-status |  |  | checkpoint | Cable bought up next to gyro / pole
checkpoint-status |  |  | checkpoint | Test results recorded
checkpoint-status |  |  | checkpoint | COC complete
checkpoint-status |  |  | checkpoint | Photos
checklist-sectioned |  |  | checklist | Lake District - First Fix - Laundry/Scullery |  |  |  |  | Yes | Lake District - First Fix - Laundry/Scullery | 3be21705-536b-4213-ac5b-d34c6fdad2ee
checkpoint-group |  |  | section | Power outlets
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Switches
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Switching as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Fixtures
checkpoint-status |  |  | checkpoint | Correct fixtures installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Height as per plan
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-group |  |  | section | Fans
checkpoint-status |  |  | checkpoint | Interior grill installed
checkpoint-status |  |  | checkpoint | Exterior grill installed
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-group |  |  | section | Photos
checkpoint-status |  |  | checkpoint | Uploaded
checklist-sectioned |  |  | checklist | Exterior |  |  |  |  | Yes | SYS - PT - Exterior | ceb88086-4e4f-4326-8e84-4c52a62bbdd7
checkpoint-group |  |  | section | Power outlets
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-status |  |  | checkpoint | Danger sign installed
checkpoint-group |  |  | section | Light Switches
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Switching as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Fixtures
checkpoint-status |  |  | checkpoint | Correct fixtures installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Height as per plan
checkpoint-status |  |  | checkpoint | Settings adjusted (sensores + timers)
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-status |  |  | checkpoint | Landscape lighting (cable disconnected)
checkpoint-group |  |  | section | Fans
checkpoint-status |  |  | checkpoint | Exterior grill installed
checkpoint-status |  |  | checkpoint | Installed square
checkpoint-group |  |  | section | Photos
checkpoint-status |  |  | checkpoint | Uploaded
checkpoint-status |  |  | checkpoint | Flush boxes cut as per plan
checkpoint-status |  |  | checkpoint | Fans cut as per plan
checkpoint-status |  |  | checkpoint | Lights cut as per plan
checkpoint-status |  |  | checkpoint | Exterior lights have been bought out centre / as per pre-wire
checkpoint-status |  |  | checkpoint | Cables stripped
checkpoint-status |  |  | checkpoint | Switching as per plan
checkpoint-status |  |  | checkpoint | Cables clearly labelled
checkpoint-status |  |  | checkpoint | Complete final walkthrough check
checkpoint-status |  |  | checkpoint | Damages and remedials documented
checkpoint-status |  |  | checkpoint | Photos
checklist-sectioned |  |  | checklist | Lake District - Second Fix - Bathroom/Ensuite |  |  |  |  | Yes | Lake District - Second Fix - Bathroom/Ensuite | 2453cdbe-8430-4b61-a7ad-5e32c83267b1
checkpoint-group |  |  | section | Power outlets
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Switches
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Switching as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Fixtures
checkpoint-status |  |  | checkpoint | Correct fixtures installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Height as per plan
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-group |  |  | section | Fans
checkpoint-status |  |  | checkpoint | Interior grill installed
checkpoint-status |  |  | checkpoint | Exterior grill installed
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-group |  |  | section | Towel rail
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Height as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-group |  |  | section | Photos
checkpoint-status |  |  | checkpoint | Uploaded
checklist-sectioned |  |  | checklist | Lake District - First Fix - Exterior |  |  |  |  | Yes | Lake District - First Fix - Exterior | 7838edf3-2dc9-4be3-b650-fc4a0a5f878b
checkpoint-group |  |  | section | Cabling
checkpoint-status |  |  | checkpoint | Circuits clearly labelled
checkpoint-status |  |  | checkpoint | Cables secured
checkpoint-status |  |  | checkpoint | Separation between data and power
checkpoint-status |  |  | checkpoint | Dektite waterproofing seals installed
checkpoint-group |  |  | section | Lights
checkpoint-status |  |  | checkpoint | Cabling in correct location
checkpoint-status |  |  | checkpoint | measurements recorded
checkpoint-status |  |  | checkpoint | Nogging installed
checkpoint-status |  |  | checkpoint | Photos
checkpoint-group |  |  | section | Fans
checkpoint-status |  |  | checkpoint | measurements recorded
checkpoint-status |  |  | checkpoint | Grills installed
checkpoint-group |  |  | section | Earthing
checkpoint-status |  |  | checkpoint | Earth electrode installed
checkpoint-status |  |  | checkpoint | Earth tag installed
checkpoint-status |  |  | checkpoint | Earth clamp installed
checkpoint-status |  |  | checkpoint | Zinc spray applied
checkpoint-status |  |  | checkpoint | Earth toby installed and secured in place
checkpoint-group |  |  | section | Fibre
checkpoint-status |  |  | checkpoint | Interior fibre cable installed through trade seal
checkpoint-status |  |  | checkpoint | Exterior fibre cable installed through trade seal
checkpoint-group |  |  | section | Photos
checkpoint-status |  |  | checkpoint | Uploaded
checkpoint-group |  |  | section | Aerial
checkpoint-status |  |  | checkpoint | Pre-install photo
checkpoint-status |  |  | checkpoint | Coax cables clearly labelled
checkpoint-status |  |  | checkpoint | Aerial installed to roof
checkpoint-status |  |  | checkpoint | Aerial installed with correct orientation
checkpoint-status |  |  | checkpoint | Aerial installed level
checkpoint-status |  |  | checkpoint | Check tightness of fixings and fittings
checkpoint-status |  |  | checkpoint | Test signal levels
checkpoint-status |  |  | checkpoint | Clean roof area
checkpoint-status |  |  | checkpoint | Installed Splitter in cabinet if required
checkpoint-status |  |  | checkpoint | Photos
checklist-flat |  |  | checklist | Compliance |  |  |  |  | Yes | Compliance | 9c9583f4-28db-45e1-84fb-cfbeb1bdd711
checkpoint-status |  |  | checkpoint | COC complete eForms
checkpoint-status |  |  | checkpoint | ESC complete eForms
checkpoint-status |  |  | checkpoint | Test results complete eForms
checkpoint-status |  |  | checkpoint | Documents uploaded eForms
checklist-sectioned |  |  | checklist | Lake District - Second Fix - Hallway |  |  |  |  | Yes | Lake District - Second Fix - Hallway | 25362faf-4529-40a4-b188-e39ddf5261be
checkpoint-group |  |  | section | Power outlets
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Switches
checkpoint-status |  |  | checkpoint | Correct switchgear installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Switching as per plan
checkpoint-status |  |  | checkpoint | Installed level
checkpoint-group |  |  | section | Light Fixtures
checkpoint-status |  |  | checkpoint | Correct fixtures installed as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Height as per plan / client preference
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-group |  |  | section | Hot Water Cylinder
checkpoint-status |  |  | checkpoint | Connection kit installed
checkpoint-status |  |  | checkpoint | Earth bond tested
checkpoint-status |  |  | checkpoint | Load test completed
checkpoint-group |  |  | section | Photos
checkpoint-status |  |  | checkpoint | Uploaded
checklist-sectioned |  |  | checklist | Lakes District - Solar installation |  |  |  |  | Yes | Lakes District - Solar installation | ae2e56f5-67ca-4f65-8e18-8c36d7cc9cda
checkpoint-group |  |  | section | Switchboard
checkpoint-status |  |  | checkpoint | Cables clearly labelled
checkpoint-status |  |  | checkpoint | Cables neatly dressed
checkpoint-status |  |  | checkpoint | Correctly rated MCB installed
checkpoint-status |  |  | checkpoint | Neutrals and earths connected
checkpoint-status |  |  | checkpoint | Module rail earth bonding connected
checkpoint-status |  |  | checkpoint | Terminations checked for tightness
checkpoint-status |  |  | checkpoint | Board is clean inside and outside
checkpoint-status |  |  | checkpoint | Masking blanks installed
checkpoint-status |  |  | checkpoint | Masking panel labelled with circuits
checkpoint-status |  |  | checkpoint | PV Label kit installed
checkpoint-status |  |  | checkpoint | Photos
checkpoint-group |  |  | section | Inverter
checkpoint-status |  |  | checkpoint | Inverter location as per plan
checkpoint-status |  |  | checkpoint | Inverter installed level
checkpoint-status |  |  | checkpoint | Inverter installed as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | AC circuit installed
checkpoint-status |  |  | checkpoint | AC circuit clearly labelled
checkpoint-status |  |  | checkpoint | AC isolator installed level
checkpoint-status |  |  | checkpoint | AC isolator correctly rated
checkpoint-status |  |  | checkpoint | AC cable terminated and checked for tightness
checkpoint-status |  |  | checkpoint | DC circuit installed
checkpoint-status |  |  | checkpoint | DC circuit clearly labelled
checkpoint-status |  |  | checkpoint | DC isolator installed level
checkpoint-status |  |  | checkpoint | DC isolator correctly rated
checkpoint-status |  |  | checkpoint | DC inverter plug-ends connected
checkpoint-status |  |  | checkpoint | DC cable terminated and checked for tightness
checkpoint-status |  |  | checkpoint | Cat6 network cable connected
checkpoint-status |  |  | checkpoint | Separation between data and power
checkpoint-status |  |  | checkpoint | PV Label kit installed
checkpoint-status |  |  | checkpoint | Photos
checkpoint-group |  |  | section | Cable / conduit
checkpoint-status |  |  | checkpoint | Cable adequately supported
checkpoint-status |  |  | checkpoint | Cable adequately protected
checkpoint-status |  |  | checkpoint | Conduit installed in accessible areas
checkpoint-status |  |  | checkpoint | DC Conduit labelled every 600mm
checkpoint-status |  |  | checkpoint | Conduit is solar type
checkpoint-status |  |  | checkpoint | Earth bond installed per array
checkpoint-status |  |  | checkpoint | Earth bond installed between rails
checkpoint-status |  |  | checkpoint | Photos
checkpoint-group |  |  | section | Rails / modules
checkpoint-status |  |  | checkpoint | Correct support feet installed
checkpoint-status |  |  | checkpoint | Support feet installed into purlin
checkpoint-status |  |  | checkpoint | Rails installed straight
checkpoint-status |  |  | checkpoint | Rails adequately supported
checkpoint-status |  |  | checkpoint | Rail components checked for tightness
checkpoint-status |  |  | checkpoint | Module layout as per plan
checkpoint-status |  |  | checkpoint | Modules installed straight
checkpoint-status |  |  | checkpoint | Module cabling kept off roof
checkpoint-status |  |  | checkpoint | Module earth plates installed
checkpoint-status |  |  | checkpoint | Module components checked for tightness
checkpoint-status |  |  | checkpoint | Photos
checkpoint-group |  |  | section | Compliance
checkpoint-status |  |  | checkpoint | COC complete eForms
checkpoint-status |  |  | checkpoint | ESC complete eForms
checkpoint-status |  |  | checkpoint | Test results complete eForms
checkpoint-status |  |  | checkpoint | Commissioning sheet complete eForms
checkpoint-status |  |  | checkpoint | Documents uploaded eForms