## BTS Install
type | name | values
checklist-flat | BTS Install
checkpoint | Location as per plan / discussion
checkpoint | Installed level
checkpoint | Earth electrode installed
checkpoint | Earth tag installed
checkpoint | Earth clamp installed
checkpoint | Zinc spray applied
checkpoint | Earth toby installed and secured in place
checkpoint | Danger sign installed
checkpoint | Terminations checked for tightness
checkpoint | Cable installed at minimum depth of 600mm
checkpoint | Cable bought up next to gyro / pole
checkpoint | Test results recorded
checkpoint | COC complete
checkpoint | Photos

## Mains Install
type | name | values
checklist | Mains Install
section | Electrical
checkpoint | Cable installed at minimum depth of 600mm
checkpoint | Protection mag slab installed
checkpoint | Warning signal tape installed
checkpoint | Cable installed through concrete slab
checkpoint | Cable bought up next to gyro / pole
checkpoint | Cable clearly labelled
checkpoint | Cable size and measurments recorded
checkpoint | Plan marked with as-built
checkpoint | Photos
section | Telecom / Fibre
checkpoint | Cable installed at minimum depth of 400mm
checkpoint | Approved exterior fibre cable used
checkpoint | Cable installed through concrete slab
checkpoint | Cable bought up next to gyro / pole
checkpoint | Cable measurments recorded
checkpoint | Plan marked with as-built
checkpoint | Photos

## First Fix
type | name | values
checklist | First Fix - Switchboards
section | Electrical
checkpoint | Installed as per plan
checkpoint | Height as per plan
checkpoint | Cables clearly labelled
checkpoint | Check all cables have been bought into switchboard
checkpoint | Mains cable installed
checkpoint | Photos
section | Data
checkpoint | Installed as per plan
checkpoint | Height as per plan
checkpoint | Cables clearly labelled
checkpoint | Check all cables have been bought into board
checkpoint | Interior fibre cable installed
checkpoint | Photos
checklist | First Fix - Kitchen/Living/Photos/Bedrooms/Garage/Hallway
section | Flush Boxes
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Marked on floor
section | Cabling
checkpoint | Circuits clearly labelled
checkpoint | Cables secured
checkpoint | Seperation between data and power
section | Lights
checkpoint | Cabling in correct location
checkpoint | Measurments recorded
checkpoint | Nogging installed
checkpoint | Marked on floor
section | Photos
checkpoint | Uploaded
checklist | First Fix - Laundry/Scullery
section | Flush Boxes
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Marked on floor
section | Cabling
checkpoint | Circuits clearly labelled
checkpoint | Cables secured
checkpoint | Seperation between data and power
section | Lights
checkpoint | Cabling in correct location
checkpoint | Measurments recorded
checkpoint | Nogging installed
checkpoint | Marked on floor
section | Fans
checkpoint | Installed in accesible location
checkpoint | Power plug fit-off
checkpoint | Ducts run flat and straight
checkpoint | Measurments recorded
checkpoint | Marked on floor
section | Photos
checkpoint | Uploaded
checklist | First Fix - Bathrooms/Ensuite
section | Flush Boxes
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Nogging installed for towel rail
checkpoint | Marked on floor
section | Cabling
checkpoint | Circuits clearly labelled
checkpoint | Cables secured
checkpoint | Seperation between data and power
section | Lights
checkpoint | Cabling in correct location
checkpoint | Measurments recorded
checkpoint | Nogging installed
checkpoint | Marked on floor
section | Fans
checkpoint | Installed in accesible location
checkpoint | Surface socket fit-off and lead taped on (inline fan)
checkpoint | Ducts run flat and straight
checkpoint | Measurments recorded
checkpoint | Marked on floor
section | Photos
checkpoint | Uploaded
checklist | First Fix - Exterior
section | Cabling
checkpoint | Circuits clearly labelled
checkpoint | Cables secured
checkpoint | Seperation between data and power
checkpoint | Dektite waterproofing seals installed
section | Lights
checkpoint | Cabling in correct location
checkpoint | Measurments recorded
checkpoint | Nogging installed
checkpoint | Photos
section | Fans
checkpoint | Measurments recorded
checkpoint | Grills installed
section | Earthing
checkpoint | Earth electrode installed
checkpoint | Earth tag installed
checkpoint | Earth clamp installed
checkpoint | Zinc spray applied
checkpoint | Earth toby installed and secured in place
section | Fibre
checkpoint | Interior fibre cable installed through trade seal
checkpoint | Exterior fibre cable installed through trade seal
section | Photos
checkpoint | Uploaded
section | Aerial
checkpoint | Pre-install photo
checkpoint | Coax cables clearly labelled
checkpoint | Aerial installed to roof
checkpoint | Aerial installed with correct orientation
checkpoint | Aerial installed level
checkpoint | Check tightness of fixings and fittings
checkpoint | Test signal levels
checkpoint | Clean roof area
checkpoint | Installed Splitter in cabinet if required
checkpoint | Photos

## Strip Out
type | name | values
checklist-flat | Strip Out
checkpoint | Flush boxes cut as per plan
checkpoint | Fans cut as per plan
checkpoint | Lights cut as per plan
checkpoint | Exterior lights have been bought out centre / as per pre-wire
checkpoint | Cables stripped
checkpoint | Switching as per plan
checkpoint | Cables clearly labelled
checkpoint | Complete final walkthrough check
checkpoint | Damages and remidials documented
checkpoint | All remedial work sent to CM and PM
checkpoint | Remedial photos
checkpoint | Strip-out Photos

## Second Fix
type | name | values
checklist | Second Fix - Switchboards
section | Electrical
checkpoint | Cables clearly labelled
checkpoint | Cables neatly dressed
checkpoint | Switchboard bonded
checkpoint | Neutrals and earths labelled
checkpoint | Terminations checked for tightness
checkpoint | Board is clean inside and outside
checkpoint | Masking blanks installed
checkpoint | Masking panel labelled with circuits
checkpoint | Photos
section | Data
checkpoint | Cables clearly labelled
checkpoint | Cables neatly dressed
checkpoint | Board bonded
checkpoint | Terminations checked for tightness
checkpoint | Board is clean inside and outside
checkpoint | Photos
checklist | Second Fix - Kitchen
section | Power outlets
checkpoint | Correct switchgear installed as per plan
checkpoint | Location as per plan
checkpoint | Installed level
checkpoint | Sink earth bond connected
section | Light Switches
checkpoint | Correct switchgear installed as per plan
checkpoint | Location as per plan
checkpoint | Switching as per plan
checkpoint | Installed level
section | Light Fixtures
checkpoint | Correct fixtures installed as per plan
checkpoint | Location as per plan
checkpoint | Height as per plan / client preference
checkpoint | Tested for operation
section | Appliances
checkpoint | HOB installed and secured
checkpoint | Oven installed and secured
checkpoint | Tested for operation
section | Photos
checkpoint | Uploaded
checklist | Second Fix - Living/Bedroom/Garage
section | Power outlets
checkpoint | Correct switchgear installed as per plan
checkpoint | Location as per plan
checkpoint | Installed level
section | Light Switches
checkpoint | Correct switchgear installed as per plan
checkpoint | Location as per plan
checkpoint | Switching as per plan
checkpoint | Installed level
section | Light Fixtures
checkpoint | Correct fixtures installed as per plan
checkpoint | Location as per plan
checkpoint | Height as per plan / client preference
checkpoint | Tested for operation
section | Photos
checkpoint | Uploaded
checklist | Second Fix - Hallway
section | Power outlets
checkpoint | Correct switchgear installed as per plan
checkpoint | Location as per plan
checkpoint | Installed level
section | Light Switches
checkpoint | Correct switchgear installed as per plan
checkpoint | Location as per plan
checkpoint | Switching as per plan
checkpoint | Installed level
section | Light Fixtures
checkpoint | Correct fixtures installed as per plan
checkpoint | Location as per plan
checkpoint | Height as per plan / client preference
checkpoint | Tested for operation
section | Hot Water Cylinder
checkpoint | Connection kit installed
checkpoint | Earth bond tested
checkpoint | Load test completed
section | Photos
checkpoint | Uploaded
checklist | Second Fix - Bathroom/Ensuite
section | Power outlets
checkpoint | Correct switchgear installed as per plan
checkpoint | Location as per plan
checkpoint | Installed level
section | Light Switches
checkpoint | Correct switchgear installed as per plan
checkpoint | Location as per plan
checkpoint | Switching as per plan
checkpoint | Installed level
section | Light Fixtures
checkpoint | Correct fixtures installed as per plan
checkpoint | Location as per plan
checkpoint | Height as per plan
checkpoint | Tested for operation
section | Fans
checkpoint | Interior grill installed
checkpoint | Exterior grill installed
checkpoint | Tested for operation
section | Towel rail
checkpoint | Location as per plan
checkpoint | Height as per plan
checkpoint | Installed level
checkpoint | Tested for operation
section | Photos
checkpoint | Uploaded
checklist | Second Fix - Laundry/Scullery
section | Power outlets
checkpoint | Correct switchgear installed as per plan
checkpoint | Location as per plan
checkpoint | Installed level
section | Light Switches
checkpoint | Correct switchgear installed as per plan
checkpoint | Location as per plan
checkpoint | Switching as per plan
checkpoint | Installed level
section | Light Fixtures
checkpoint | Correct fixtures installed as per plan
checkpoint | Location as per plan
checkpoint | Height as per plan
checkpoint | Tested for operation
section | Fans
checkpoint | Interior grill installed
checkpoint | Exterior grill installed
checkpoint | Tested for operation
section | Photos
checkpoint | Uploaded
checklist | Second Fix - Exterior
section | Power outlets
checkpoint | Correct switchgear installed as per plan
checkpoint | Location as per plan
checkpoint | Installed level
checkpoint | Danger sign installed
section | Light Switches
checkpoint | Correct switchgear installed as per plan
checkpoint | Location as per plan
checkpoint | Switching as per plan
checkpoint | Installed level
section | Light Fixtures
checkpoint | Correct fixtures installed as per plan
checkpoint | Location as per plan
checkpoint | Height as per plan
checkpoint | Settings adjusted (sensores + timers)
checkpoint | Tested for operation
checkpoint | Landscape lighting (cable disconnected)
section | Fans
checkpoint | Exterior grill installed
checkpoint | Installed square
section | Photos
checkpoint | Uploaded
checklist | Second Fix - Remedials
checkpoint | Damages and remidials documented
checkpoint | All remedial work sent to CM and PM
checkpoint | Remedial photos

## Compliance
type | name | values
checklist-flat | Compliance
checkpoint | COC complete eForms
checkpoint | ESC complete eForms
checkpoint | Test results complete eForms
checkpoint | Documents uploaded eForms