## res_auckland
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Auckland - Strip Out |  |  |  |  | Yes | Auckland - Strip Out | a27a934a-8786-44fe-849e-ee603419d343
checkpoint-status | Flush boxes cut as per plan
checkpoint-status | Fans cut as per plan
checkpoint-status | Lights cut as per plan
checkpoint-status | Exterior lights have been bought out centre / as per pre-wire
checkpoint-status | Cables stripped
checkpoint-status | Switching as per plan
checkpoint-status | Cables clearly labelled
checkpoint-status | Complete final walkthrough check
checkpoint-status | Damages and remedials documented
checkpoint-status | All remedial work sent to CM and PM
checkpoint-status | Remedial photos
checkpoint-status | Strip-out Photos
checklist-sectioned | Auckland - First Fix - Laundry/Scullery |  |  |  |  | Yes | Auckland - First Fix - Laundry/Scullery | ab96726b-e79d-424d-a431-28df3235c64b
section | Flush Boxes
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Marked on floor
section | Cabling
checkpoint | Circuits clearly labelled
checkpoint | Cables secured
checkpoint | Seperation between data and power
section | Lights
checkpoint | Cabling in correct location
checkpoint | Measurments recorded
checkpoint | Nogging installed
checkpoint | Marked on floor
section | Fans
checkpoint | Installed in accesible location
checkpoint | Power plug fit-off
checkpoint | Ducts run flat and straight
checkpoint | Measurments recorded
checkpoint | Marked on floor
section | Photos
checkpoint | Uploaded
checklist-sectioned | Mains Install |  |  |  |  | Yes | SYS - PT - Mains Install | 627d4729-781c-4e41-b986-1e5b0e9c3d73
section | Electrical
checkpoint | Cable installed at minimum depth of 600mm
checkpoint | Protection mag slab installed
checkpoint | Warning signal tape installed
checkpoint | Cable installed through concrete slab
checkpoint | Cable bought up next to gyro / pole
checkpoint | Cable clearly labelled
checkpoint | Cable size and measurments recorded
checkpoint | Plan marked with as-built
checkpoint | Photos
section | Telecom / Fibre
checkpoint | Cable installed at minimum depth of 400mm
checkpoint | Approved exterior fibre cable used
checkpoint | Cable installed through concrete slab
checkpoint | Cable bought up next to gyro / pole
checkpoint | Cable measurments recorded
checkpoint | Plan marked with as-built
checkpoint | Photos
checklist-flat | Strip Out |  |  |  |  | Yes | SYS - PT - Strip Out | efbbe89b-6195-428a-ab02-937eec286938
checkpoint-status | Flush boxes cut as per plan
checkpoint-status | Fans cut as per plan
checkpoint-status | Lights cut as per plan
checkpoint-status | Exterior lights have been bought out centre / as per pre-wire
checkpoint-status | Cables stripped
checkpoint-status | Switching as per plan
checkpoint-status | Cables clearly labelled
checkpoint-status | Complete final walkthrough check
checkpoint-status | Damages and remedials documented
checkpoint-status | All remedial work sent to CM and PM
checkpoint-status | Remedial photos
checkpoint-status | Strip-out Photos
checklist-flat | Second Fix - Remedials | [5 empty] | Second Fix - Remedials
checkpoint | Damages and remidials documented
checkpoint | All remedial work sent to CM and PM
checkpoint | Remedial photos