## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) |  |  |  |  | Yes | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | 1c06b75c-d06d-4916-8631-a8a49cab656b
checkpoint-group |  |  | section | Defects
checkpoint-status |  |  | checkpoint | Major Defects (Send back to Aline)
label | 561e8b18-60df-555d-8eff-ce738e188c51 |  | note | Add photos/comments & Send back to Aline
button | e34e269d-2d00-5e73-81c7-bb6125f553a3 |  | button | Is the switchboard structurally sound | Yes, No
button | 907a7f74-52eb-57ea-9e2f-0a5b6e07b4bb |  | button | Does the main door close | Yes, No
checkpoint-status |  |  | checkpoint | Minor defects (Fix Onsite)
button | d3f7a75c-118f-5418-9d74-263cd66064ce |  | button | Is the main isolating switch identified | Yes, No
button | 26c61464-b5f0-5592-9aa6-60f4d6ffd982 |  | button | Are all C.B’s and R.C.D’s identified | Yes, No
button | 9829ab18-37e1-5962-86ad-0977ad26810e |  | button | Is 1.2m clearance signage in place | Yes, No
label | ab32beaa-142c-5d33-a2f3-2cca76b75d26 |  | note | Add Photo below
button | 17da13e9-1f7a-5997-8d98-de94ee979c47 |  | button | Is ‘Live Parts’ signage in place | Yes, No
label | 2f85cafd-6b9f-577a-8fb9-e6d859e11da3 |  | note | Add Photo below
checkpoint-group |  |  | section | Electrical
checkpoint-status |  |  | checkpoint | Do pole fillers cover all gaps
checkpoint-status |  |  | checkpoint | Are test points installed in the board
checkpoint-status |  |  | checkpoint | Are all holes in connection (J.Box) filled with screwed stops
checkpoint-status |  |  | checkpoint | Are Perspex covers in place
checkpoint-status |  |  | checkpoint | Do escutcheon plates have all screws fitted
checkpoint-status |  |  | checkpoint | Is insulated lead stand attached and insulation intact
checkpoint-status |  |  | checkpoint | Do the flap-lock and door-lock work
checkpoint-group |  |  | section | Replacement Parts
checkpoint-status |  |  | checkpoint | Replacement parts list - Pass=Required, N/A if not Required
label | c0772424-cd4f-547c-a391-4f204dc2204a |  | note | Complete this section and order from the office as required. Send report to office Top Right
label | 98337946-8bdd-50e8-afb7-ec4dccdaa284 |  | note | ----Please do not strip other boards for parts.----
checkpoint-status |  |  | checkpoint | Galvanised Style - Pass=Required, N/A if not Required
label | d17f0129-dffd-5ee8-80e5-23e8cd5b5d05 |  | note | Input quantities required below
text | 60fbef9d-4dfe-5b49-9ac1-bf4ee6f72be3 |  | textbox | 10 A DIN mounted GPO
text | eb17504d-112f-557e-95d3-4c62d17a4ea3 |  | textbox | 15 A DIN mounted GPO
text | 85e019bd-1fb8-5f7c-b0d2-9720cea4d1da |  | textbox | Line taps
text | 2905b317-c44c-5c66-89f1-1d15c6b8a43a |  | textbox | Hinges
text | af15f337-2cb8-5532-b3d0-7ab83632404c |  | textbox | Door
text | 31358e63-6016-57ba-a66a-ba9050dd270b |  | textbox | Door handle and tongue
text | b490a33f-04c3-5cfb-8a82-0030d40163b7 |  | textbox | Bottom connection box
text | d206182a-b1c5-5aa5-ae77-15c4e569ee5a |  | textbox | Bottom connection box cover
text | bc474545-84af-5288-81cb-758b852b20d2 |  | textbox | RCD cover lock 001
text | dd167c42-211f-562d-825f-e6552cd7b70f |  | textbox | RCD cover
text | a5200335-67c7-5427-900f-4fbfb84c512c |  | textbox | Pole fillers
text | 109a6354-c3a7-5673-b0a6-8aaa9992dfac |  | textbox | 63 A main switch
text | 42ee06f5-8c1c-5937-9dc0-1320ba12746d |  | textbox | 100 A main switch
text | 2938900f-f755-523d-b502-d5b15fc2c3b7 |  | textbox | 16 A RCBO 2 pole
text | 74d2dca9-4eae-5bd7-96df-2277839ee4ed |  | textbox | 20 A RCBO 2 pole
text | 1f3c72fe-35de-54cb-9285-038c7e4f69fa |  | textbox | 32 A 4 pole CB
text | ae44beaf-2cf0-5445-9dd3-732f13b9c149 |  | textbox | 40 A 4 pole CB
text | 252520af-c287-5c5c-b73e-99e7bc2a8222 |  | textbox | Set of legs
text | 154ef440-99fb-5653-8dce-78c5656f8398 |  | textbox | Set of feet
text | fb8974f7-aac9-5874-b135-bb8f14b4fd9a |  | textbox | Perspex cover for line tap
text | 03677d5f-f74e-560b-97c0-e710791b8729 |  | textbox | Lead stand
text | 1d47e736-9485-5582-8a30-8653e591579d |  | textbox | Escutcheon
text | b52ab48e-24aa-5970-9177-ec4812d1cb9a |  | textbox | Connectors
text | dd331969-4718-5944-9e51-82792c75e263 |  | textbox | RCD cover lock 001
checkpoint-status |  |  | checkpoint | New Green Style
label | 60421b63-1941-5303-9af8-4f1a5035a74e |  | note | Input quantities required below
text | f84b20e4-ae4d-5b3e-bf3e-38feb4727b8c |  | textbox | Door
text | 1f0d0930-8b92-5ec0-a65a-3f99d6ef7110 |  | textbox | Hinges
text | 1388db08-8472-5c14-a572-4253918b621c |  | textbox | Legs
text | 95309802-63f1-5822-8cfb-06caa44eeeac |  | textbox | Lead stand
text | df1393fb-03f4-54dc-816e-13adc4d6061c |  | textbox | Escutcheon
text | e672765f-c216-553b-afeb-84e90980a433 |  | textbox | Rcd cover
text | 368b7b87-ed0a-5f9e-b8c6-73c00c500679 |  | textbox | Rcd cover lock 001
text | a6bc0b1a-986c-5b06-8d2c-90c40b5556c1 |  | textbox | Door handle and tongue
text | 1ebcc7c3-57e1-53a9-9ec8-69ee28770b27 |  | textbox | 32 A 3 phase outlet
text | 887b5077-bdd6-5883-adee-df4db21a1708 |  | textbox | Connectors
text | ebc2494b-e35a-5489-8f61-2645e7e15ef2 |  | textbox | 15 A GPO
text | ad6c54bd-c423-5152-b487-0275082dbb5b |  | textbox | 10 A DGPO
text | 75ad3a2b-cd7e-55d0-8274-4a50e098089e |  | textbox | 63 A main switch
text | 6cf3f1de-af2d-55ed-a581-2a3f71d47200 |  | textbox | 100 A main switch
text | 6e7fc2f6-ec57-5ab0-a6c7-af38ac2c9b64 |  | textbox | 40 A 4 pole CB
text | 5657902e-46b0-5f40-9835-26d6bf113d41 |  | textbox | 32 A 4 pole CB
text | 709f6fe6-a535-5af9-93e1-919cb49a05fd |  | textbox | 16 A RCBO 1 pole
text | 1974807f-6494-5eb1-b4cd-2df0d4afc01a |  | textbox | 20 A RCBO 1 pole
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Temp Board completed to specification/drawings
label | ff8c52c2-ceee-5c7f-9c7c-f946e50fe3f5 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 852f9b98-a9a6-5251-890e-d217bbed2185 |  | note | Any Corrective Actions to be Photographed & Commented below
select | b9171723-f81d-51ee-a8fc-64de438b7ca7 |  | dropdown | Installed by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622, ADAM STRONG - AGrade: A38815 - Employee#: 2002, ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794, ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684, ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863, ALAN BIRCHALL - Agrade: A18981 - Employee#: 379, ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111, ALI HASAN - Agrade: A48087 - Employee#: 1654, ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015, ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957, ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972, ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309, BEN DARBY - Agrade: A53332 - Employee#: 1702, BEN FINDLAY - Agrade: A41429 - Employee#: 2006, BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933, BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733, BENJAMIN STEWART - Agrade: A50504 - Employee#: 1865, BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801, BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850, BRENTON HILL - Agrade: A47213 - Employee#: 1729, BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887, BROCK DOWNIE - Agrade: A53290 - Employee#: 1849, BROCK LLOYD - Agrade: A44808 - Employee#: 1680, CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644, DAMIEN CASEY - Agrade: A39744 - Employee#: 1193, DANIEL BENDINELLI - Agrade: A67728 - Employee# 2097, DANIEL MILLER - Agrade: A42685 - Employee#: 1909 , DANIEL SETTE - Agrade: A50502 - Employee#: 1812 , DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194 , DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937, DAVID OLSEN - Agrade: A42915 - Employee#: 1685, DEAN NGUYEN - Agrade: A48514 - Employee#: 1515, DEREK JACOBS - Agrade: A67318 - Employee#: 2078, DWAYNE KLOET - Agrade: A48278 - Employee#: 1239, ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782, EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895, FERGUS COATES - Agrade: A59054 - Employee#: 1774, FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679, HUY DO - Agrade: A40954 - Employee#: 873, IMMANUEL KAWITI - Agrade: - Employee#: 2023, JACKSON SHARPE - Agrade: A53801 - Employee#: 1540, JAMES MARASCO - Agrade: A55184 - Employee#: 1758, JAMES PLEASANT - Agrade: A62956 - Employee#: 1976, JAMES SPOKES - Agrade: A48756 - Employee#: 1770, JASON CRAMER - Agrade: A57832 - Employee#: 1673, JASON GARETTO - Agrade: A46469 - Employee#: 1896, JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756, JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719, JASON PERL - Agrade: A36692 - Employee#: 1868, JASON SALE - Agrade: A28662 - Employee#: 1615, JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029, JESS ZAHRA - Agrade: A52969 - Employee#: 1403, JOEL BASSETT - Agrade: A39498 - Employee#: 1958, JOEL COGHLAN - Agrade: A43339 - Employee#: 1220, JOHN BATTISTA - Agrade: A41810 - Employee#: 1908, JOHN GREEN - Agrade: A55589 - Employee#: 1734, JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682, JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720, KALE BLACKLER - Agrade: A39293 - Employee#: 1751, KAYNE WALKER - Agrade: A38805 - Employee#: 1718, KEVIN MURPHY - Agrade: A63544 - Employee#: 2022, KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698, LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834, MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308, MARK D_ANGELO - Agrade: A40610 - Employee#: 1832, MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352, MATTHEW COX - Agrade: A42092 - Employee#: 1704, MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894, MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915, MICHAEL BRASHER - Agrade: A29237 - Employee#: 954, NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748, PAT DOUBLE - Agrade: A46604 - Employee#: 1118, PAUL HARMAN - Agrade: A26306 - Employee#: 1728, PAUL RABAHI - Agrade: A52747 - Employee#: 1939, PAUL WAISTELL - Agrade: A41819 - Employee#: 1190, PETER LEWIS - Agrade: A53556 - Employee#: 1749, PHILIP BROWN - Agrade: A55466 - Employee#: 1940, PHILLIP CHOW - Agrade: A55466 - Employee#: 1612, ROB POLLARD - Agrade: A56906 - Employee#: 1754, ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132, RYAN DEPRADA - Agrade: A41361 - Employee#: 1848, SCOTT RYAN - Agrade: A59062 - Employee#: 2017, SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034, SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771, SIMON COLLARD - Agrade: A32749 - Employee#: 883, STEVEN THOM - Agrade: A48941 - Employee#: 1199, STUART MALVENAN - Agrade: A61071 - Employee#: 1829, TOM HAMILTON - Agrade: A48254 - Employee#: 1434, VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218, WILLIAM FISHER - Agrade: A20679 - Employee#: 859, Other (Specify below)
text | e831f02b-d7ea-5449-bce2-fb6ab45f08f1 |  | textbox | Other (Specify here)
select | 6e534487-7eff-5c2d-ac7e-203ab63881b8 |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622, ADAM STRONG - AGrade: A38815 - Employee#: 2002, ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794, ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684, ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863, ALAN BIRCHALL - Agrade: A18981 - Employee#: 379, ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111, ALI HASAN - Agrade: A48087 - Employee#: 1654, ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015, ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957, ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972, ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309, BEN DARBY - Agrade: A53332 - Employee#: 1702, BEN FINDLAY - Agrade: A41429 - Employee#: 2006, BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933, BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733, BENJAMIN STEWART - Agrade: A50504 - Employee#: 1865, BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801, BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850, BRENTON HILL - Agrade: A47213 - Employee#: 1729, BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887, BROCK DOWNIE - Agrade: A53290 - Employee#: 1849, BROCK LLOYD - Agrade: A44808 - Employee#: 1680, CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644, DAMIEN CASEY - Agrade: A39744 - Employee#: 1193, DANIEL BENDINELLI - Agrade: A67728 - Employee# 2097, DANIEL MILLER - Agrade: A42685 - Employee#: 1909 , DANIEL SETTE - Agrade: A50502 - Employee#: 1812 , DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194 , DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937, DAVID OLSEN - Agrade: A42915 - Employee#: 1685, DEAN NGUYEN - Agrade: A48514 - Employee#: 1515, DEREK JACOBS - Agrade: A67318 - Employee#: 2078, DWAYNE KLOET - Agrade: A48278 - Employee#: 1239, ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782, EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895, FERGUS COATES - Agrade: A59054 - Employee#: 1774, FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679, HUY DO - Agrade: A40954 - Employee#: 873, IMMANUEL KAWITI - Agrade: - Employee#: 2023, JACKSON SHARPE - Agrade: A53801 - Employee#: 1540, JAMES MARASCO - Agrade: A55184 - Employee#: 1758, JAMES PLEASANT - Agrade: A62956 - Employee#: 1976, JAMES SPOKES - Agrade: A48756 - Employee#: 1770, JASON CRAMER - Agrade: A57832 - Employee#: 1673, JASON GARETTO - Agrade: A46469 - Employee#: 1896, JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756, JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719, JASON PERL - Agrade: A36692 - Employee#: 1868, JASON SALE - Agrade: A28662 - Employee#: 1615, JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029, JESS ZAHRA - Agrade: A52969 - Employee#: 1403, JOEL BASSETT - Agrade: A39498 - Employee#: 1958, JOEL COGHLAN - Agrade: A43339 - Employee#: 1220, JOHN BATTISTA - Agrade: A41810 - Employee#: 1908, JOHN GREEN - Agrade: A55589 - Employee#: 1734, JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682, JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720, KALE BLACKLER - Agrade: A39293 - Employee#: 1751, KAYNE WALKER - Agrade: A38805 - Employee#: 1718, KEVIN MURPHY - Agrade: A63544 - Employee#: 2022, KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698, LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834, MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308, MARK D_ANGELO - Agrade: A40610 - Employee#: 1832, MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352, MATTHEW COX - Agrade: A42092 - Employee#: 1704, MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894, MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915, MICHAEL BRASHER - Agrade: A29237 - Employee#: 954, NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748, PAT DOUBLE - Agrade: A46604 - Employee#: 1118, PAUL HARMAN - Agrade: A26306 - Employee#: 1728, PAUL RABAHI - Agrade: A52747 - Employee#: 1939, PAUL WAISTELL - Agrade: A41819 - Employee#: 1190, PETER LEWIS - Agrade: A53556 - Employee#: 1749, PHILIP BROWN - Agrade: A55466 - Employee#: 1940, PHILLIP CHOW - Agrade: A55466 - Employee#: 1612, ROB POLLARD - Agrade: A56906 - Employee#: 1754, ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132, RYAN DEPRADA - Agrade: A41361 - Employee#: 1848, SCOTT RYAN - Agrade: A59062 - Employee#: 2017, SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034, SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771, SIMON COLLARD - Agrade: A32749 - Employee#: 883, STEVEN THOM - Agrade: A48941 - Employee#: 1199, STUART MALVENAN - Agrade: A61071 - Employee#: 1829, TOM HAMILTON - Agrade: A48254 - Employee#: 1434, VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218, WILLIAM FISHER - Agrade: A20679 - Employee#: 859, Other (Specify below)
text | 32ae67b3-ab5b-595b-95c0-2cc6cb218f7b |  | textbox | Other (Specify here)
label | 5f1314ce-8c08-561f-b3dc-c279c5beb6ed |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) |  |  |  |  | Yes | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | 41d65570-8180-45c8-9f58-7ad8b6db8bc7
checkpoint-group |  |  | section | Electrician Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | 3ebd0c91-7f76-5b09-aebb-22ba96709b41 |  | textbox | Equipment being Energised
select | 52c3f37d-88a2-5c14-a93d-54fae3ed4eee |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622, ADAM STRONG - AGrade: A38815 - Employee#: 2002, ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794, ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684, ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863, ALAN BIRCHALL - Agrade: A18981 - Employee#: 379, ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111, ALI HASAN - Agrade: A48087 - Employee#: 1654, ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015, ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957, ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972, ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309, BEN DARBY - Agrade: A53332 - Employee#: 1702, BEN FINDLAY - Agrade: A41429 - Employee#: 2006, BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933, BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733, BENJAMIN STEWART - Agrade: A50504 - Employee#: 1865, BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801, BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850, BRENTON HILL - Agrade: A47213 - Employee#: 1729, BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887, BROCK DOWNIE - Agrade: A53290 - Employee#: 1849, BROCK LLOYD - Agrade: A44808 - Employee#: 1680, CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644, DAMIEN CASEY - Agrade: A39744 - Employee#: 1193, DANIEL BENDINELLI - Agrade: A67728 - Employee# 2097, DANIEL MILLER - Agrade: A42685 - Employee#: 1909 , DANIEL SETTE - Agrade: A50502 - Employee#: 1812 , DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194 , DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937, DAVID OLSEN - Agrade: A42915 - Employee#: 1685, DEAN NGUYEN - Agrade: A48514 - Employee#: 1515, DEREK JACOBS - Agrade: A67318 - Employee#: 2078, DWAYNE KLOET - Agrade: A48278 - Employee#: 1239, ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782, EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895, FERGUS COATES - Agrade: A59054 - Employee#: 1774, FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679, HUY DO - Agrade: A40954 - Employee#: 873, IMMANUEL KAWITI - Agrade: - Employee#: 2023, JACKSON SHARPE - Agrade: A53801 - Employee#: 1540, JAMES MARASCO - Agrade: A55184 - Employee#: 1758, JAMES PLEASANT - Agrade: A62956 - Employee#: 1976, JAMES SPOKES - Agrade: A48756 - Employee#: 1770, JASON CRAMER - Agrade: A57832 - Employee#: 1673, JASON GARETTO - Agrade: A46469 - Employee#: 1896, JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756, JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719, JASON PERL - Agrade: A36692 - Employee#: 1868, JASON SALE - Agrade: A28662 - Employee#: 1615, JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029, JESS ZAHRA - Agrade: A52969 - Employee#: 1403, JOEL BASSETT - Agrade: A39498 - Employee#: 1958, JOEL COGHLAN - Agrade: A43339 - Employee#: 1220, JOHN BATTISTA - Agrade: A41810 - Employee#: 1908, JOHN GREEN - Agrade: A55589 - Employee#: 1734, JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682, JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720, KALE BLACKLER - Agrade: A39293 - Employee#: 1751, KAYNE WALKER - Agrade: A38805 - Employee#: 1718, KEVIN MURPHY - Agrade: A63544 - Employee#: 2022, KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698, LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834, MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308, MARK D_ANGELO - Agrade: A40610 - Employee#: 1832, MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352, MATTHEW COX - Agrade: A42092 - Employee#: 1704, MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894, MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915, MICHAEL BRASHER - Agrade: A29237 - Employee#: 954, NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748, PAT DOUBLE - Agrade: A46604 - Employee#: 1118, PAUL HARMAN - Agrade: A26306 - Employee#: 1728, PAUL RABAHI - Agrade: A52747 - Employee#: 1939, PAUL WAISTELL - Agrade: A41819 - Employee#: 1190, PETER LEWIS - Agrade: A53556 - Employee#: 1749, PHILIP BROWN - Agrade: A55466 - Employee#: 1940, PHILLIP CHOW - Agrade: A55466 - Employee#: 1612, ROB POLLARD - Agrade: A56906 - Employee#: 1754, ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132, RYAN DEPRADA - Agrade: A41361 - Employee#: 1848, SCOTT RYAN - Agrade: A59062 - Employee#: 2017, SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034, SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771, SIMON COLLARD - Agrade: A32749 - Employee#: 883, STEVEN THOM - Agrade: A48941 - Employee#: 1199, STUART MALVENAN - Agrade: A61071 - Employee#: 1829, TOM HAMILTON - Agrade: A48254 - Employee#: 1434, VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218, WILLIAM FISHER - Agrade: A20679 - Employee#: 859, Other (Specify below)
text | ff4f9120-d616-5493-8eb1-81fdb43fc8ae |  | textbox | Other (Specify here)
boolean | ea3fbdae-03e4-503d-b32e-a4df3967f6e5 |  | tickbox | Signature added below
checkpoint-group |  |  | section | Temporary Board Visual Inspection
checkpoint-status |  |  | checkpoint | All cables secured and protected appropriately
checkpoint-status |  |  | checkpoint | All cables identified with Construction Wiring tape
checkpoint-status |  |  | checkpoint | Switchboard is structurally sound
checkpoint-status |  |  | checkpoint | Appropriate signage in place
checkpoint-status |  |  | checkpoint | All holes filled with stops
checkpoint-group |  |  | section | Temporary lighting visual inspection
checkpoint-status |  |  | checkpoint | All cables secured and protected appropriately
checkpoint-status |  |  | checkpoint | All cables identified with Construction Wiring tape
checkpoint-status |  |  | checkpoint | Appropriate number of emergency lights installed
checkpoint-status |  |  | checkpoint | All lighting plug bases terminated
checkpoint-status |  |  | checkpoint | Light fittings in serviceable condition with wire-guards or plastic diffusers
checkpoint-group |  |  | section | Test Results
checkpoint-status |  |  | checkpoint | Test Results - Pass once complete
text | 15d11091-2780-5c6f-9270-7d47956ff6f1 |  | textbox | Insulation Resistance (Mega Ohms)
button | 712f82b7-402c-591f-983d-939aab4b0d0d |  | button | Result | Pass, Fail
label | a773e7bf-07f4-5813-adb6-c8eb39e7668c |  | note | .. ..
text | 6e4cdf1d-4eec-574e-b857-9bad3c0d7c59 |  | textbox | Earth Resistance & Continuity (Ohms)
button | 2f723019-cb6f-55c3-a21f-32373a148faa |  | button | Result | Pass, Fail
label | b858327d-92d4-5154-bfbc-3585f54d0976 |  | note | .. ..
text | 37d9016e-a519-5d8c-9ffc-56dfdaf3d81c |  | textbox | Polarity
text | 0754bb25-0f2c-5205-9070-4da13b0f8e4d |  | textbox | Earth loop impedance
button | b43a1453-cfdd-5751-bc7c-1e43865f48e5 |  | button | Result | Pass, Fail
checkpoint-status |  |  | checkpoint | RCD Time trip test completed
checkpoint-status |  |  | checkpoint | Correct circuit connection
checklist-sectioned |  |  | checklist | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) |  |  |  |  | Yes | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | 7c485932-6c2f-43e5-a141-aed76650f0e3
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | 9ffd14b3-6387-5bcb-9527-93e2bc9fe81b |  | textbox | Test Date
text | d25fbbfe-575b-5c92-841a-84249993aac9 |  | textbox | Switchboard No.
text | 30ee4e1f-743a-5c5d-a0c9-f5bd5593f64d |  | textbox | Tag No.
select | 41999c41-cf46-514f-a476-f8b153504b93 |  | dropdown | Tested by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622, ADAM STRONG - AGrade: A38815 - Employee#: 2002, ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794, ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684, ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863, ALAN BIRCHALL - Agrade: A18981 - Employee#: 379, ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111, ALI HASAN - Agrade: A48087 - Employee#: 1654, ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015, ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957, ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972, ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309, BEN DARBY - Agrade: A53332 - Employee#: 1702, BEN FINDLAY - Agrade: A41429 - Employee#: 2006, BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933, BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733, BENJAMIN STEWART - Agrade: A50504 - Employee#: 1865, BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801, BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850, BRENTON HILL - Agrade: A47213 - Employee#: 1729, BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887, BROCK DOWNIE - Agrade: A53290 - Employee#: 1849, BROCK LLOYD - Agrade: A44808 - Employee#: 1680, CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644, DAMIEN CASEY - Agrade: A39744 - Employee#: 1193, DANIEL BENDINELLI - Agrade: A67728 - Employee# 2097, DANIEL MILLER - Agrade: A42685 - Employee#: 1909 , DANIEL SETTE - Agrade: A50502 - Employee#: 1812 , DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194 , DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937, DAVID OLSEN - Agrade: A42915 - Employee#: 1685, DEAN NGUYEN - Agrade: A48514 - Employee#: 1515, DEREK JACOBS - Agrade: A67318 - Employee#: 2078, DWAYNE KLOET - Agrade: A48278 - Employee#: 1239, ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782, EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895, FERGUS COATES - Agrade: A59054 - Employee#: 1774, FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679, HUY DO - Agrade: A40954 - Employee#: 873, IMMANUEL KAWITI - Agrade: - Employee#: 2023, JACKSON SHARPE - Agrade: A53801 - Employee#: 1540, JAMES MARASCO - Agrade: A55184 - Employee#: 1758, JAMES PLEASANT - Agrade: A62956 - Employee#: 1976, JAMES SPOKES - Agrade: A48756 - Employee#: 1770, JASON CRAMER - Agrade: A57832 - Employee#: 1673, JASON GARETTO - Agrade: A46469 - Employee#: 1896, JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756, JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719, JASON PERL - Agrade: A36692 - Employee#: 1868, JASON SALE - Agrade: A28662 - Employee#: 1615, JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029, JESS ZAHRA - Agrade: A52969 - Employee#: 1403, JOEL BASSETT - Agrade: A39498 - Employee#: 1958, JOEL COGHLAN - Agrade: A43339 - Employee#: 1220, JOHN BATTISTA - Agrade: A41810 - Employee#: 1908, JOHN GREEN - Agrade: A55589 - Employee#: 1734, JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682, JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720, KALE BLACKLER - Agrade: A39293 - Employee#: 1751, KAYNE WALKER - Agrade: A38805 - Employee#: 1718, KEVIN MURPHY - Agrade: A63544 - Employee#: 2022, KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698, LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834, MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308, MARK D_ANGELO - Agrade: A40610 - Employee#: 1832, MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352, MATTHEW COX - Agrade: A42092 - Employee#: 1704, MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894, MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915, MICHAEL BRASHER - Agrade: A29237 - Employee#: 954, NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748, PAT DOUBLE - Agrade: A46604 - Employee#: 1118, PAUL HARMAN - Agrade: A26306 - Employee#: 1728, PAUL RABAHI - Agrade: A52747 - Employee#: 1939, PAUL WAISTELL - Agrade: A41819 - Employee#: 1190, PETER LEWIS - Agrade: A53556 - Employee#: 1749, PHILIP BROWN - Agrade: A55466 - Employee#: 1940, PHILLIP CHOW - Agrade: A55466 - Employee#: 1612, ROB POLLARD - Agrade: A56906 - Employee#: 1754, ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132, RYAN DEPRADA - Agrade: A41361 - Employee#: 1848, SCOTT RYAN - Agrade: A59062 - Employee#: 2017, SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034, SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771, SIMON COLLARD - Agrade: A32749 - Employee#: 883, STEVEN THOM - Agrade: A48941 - Employee#: 1199, STUART MALVENAN - Agrade: A61071 - Employee#: 1829, TOM HAMILTON - Agrade: A48254 - Employee#: 1434, VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218, WILLIAM FISHER - Agrade: A20679 - Employee#: 859, Other (Specify below)
text | cdacf9ad-fb5c-5950-a96d-c13dee1701e6 |  | textbox | Other (Specify here)
boolean | 386b4c21-c24b-5a4a-8116-c8409d4aa00b |  | tickbox | Signature attached below
checkpoint-group |  |  | section | RCD Test 1
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 0057ca27-1a23-5529-b89f-51449bf7096f |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | ec446358-36b7-5141-9cfe-0f74627383c3 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 00cd8ac5-1a8e-5478-98cb-93c424430221 |  | textbox | RCD No
text | 7c8e4366-b713-5a2f-8520-c6124ffd4ae3 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | c39536fb-5291-520a-ae9f-49c28108270e |  | textbox | 0.Deg (ms)
text | efad8750-3b82-58eb-b07e-843a052d54f9 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 15ea0688-101e-5e75-8556-d2e9dc494d05 |  | textbox | 0.Deg (ms)
text | 3db112fd-1dcc-58e6-a394-f551df5c69e3 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 615d5b23-07f7-58bd-ba7e-9a4aea1af6cb |  | textbox | 0.Deg (ms)
text | d3307bec-c966-5730-be7d-7d516a45b752 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 93fb5f89-badb-547b-ab13-c6dce3c7a299 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 2
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 7bff8ea2-7904-5b92-a57f-8529ac2f8bcf |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | a0233dbe-31ba-5e9b-af34-d3a90eddd94e |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 7c44cf52-6822-5391-9f0a-be0e09f79903 |  | textbox | RCD No
text | 64c9b317-80ec-56d7-a5ec-e3e22ba74322 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | e041c2a0-d3d2-5e57-9b91-61c74ec88eb2 |  | textbox | 0.Deg (ms)
text | 8c9dfef8-75e2-5e76-ba54-0229e33d5c95 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | ca3ae0ff-8ca0-5717-b81d-1151a9d688fd |  | textbox | 0.Deg (ms)
text | d2356246-6198-5987-b702-0ef3362084a3 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | d56c3817-0d23-5816-a43b-14c32fa68b8e |  | textbox | 0.Deg (ms)
text | 34e4032e-59a5-57ba-8f07-7183a9da9e97 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 24c81124-3127-5182-8e78-2f67e6cb28c0 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 3
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 7f6dddc3-85aa-5b37-8368-b47c34c33162 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | a55b7481-e145-50cd-b00c-799f063075ae |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 2495163e-29e3-5ee3-bd8b-2701a5b50bf2 |  | textbox | RCD No
text | 7c36147d-522e-5cfb-883f-710adc628784 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | c87f071d-a5c1-5c92-aeba-1240e244a1a1 |  | textbox | 0.Deg (ms)
text | 16904c0d-f434-5537-a593-ec0f6d3ac338 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | bf3291c1-4281-59de-9cf0-2ea345d22177 |  | textbox | 0.Deg (ms)
text | 81b05112-a46a-537f-af29-85f32fbd2b69 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 95756da5-d2d1-5f26-b6a9-7860bf3cfb91 |  | textbox | 0.Deg (ms)
text | cf1f211b-107a-5dc9-af1e-c1f27a33ed71 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 959a082f-37f0-59fc-a795-7654befb3a13 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 4
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 2f539192-8f77-55e1-801d-a0b8240fab09 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | f59524a9-c8ed-5e69-9dc6-7088f5a5c3b9 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 27817bc1-11af-5fcd-8041-17f859d3038d |  | textbox | RCD No
text | 01b6f2f7-5130-5ba2-8665-bf4862984aa9 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 3d2e1099-244c-5132-8f27-f83306b9916e |  | textbox | 0.Deg (ms)
text | 965fca8a-8f44-57c9-8bf6-e1e291a2629a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | c45eedfc-cb42-5688-9afd-1b1296464de1 |  | textbox | 0.Deg (ms)
text | 5bc8d036-3c3d-56b8-86f1-e5cbaf4541f9 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 7194f7c6-9f04-50b8-8ec1-63af86eb8367 |  | textbox | 0.Deg (ms)
text | 7da00f9c-d459-5000-900b-c155cc391eee |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | ccf0f279-9117-589d-87fc-f7dc9ad25130 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 5
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 0becfebc-6f3a-50f2-b572-c400ee8676b1 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | e59ee2bf-e6d3-5a22-91b5-f9db3f6c43e0 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | b2c32e03-e24f-5899-965b-d7884249043e |  | textbox | RCD No
text | 10a49a2d-1d9b-5b4a-8189-a1e23868212a |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | f7abd4d8-3106-5151-a3b2-b3420d6369dd |  | textbox | 0.Deg (ms)
text | 56c395b2-443f-55b5-96a5-5d875577b20c |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | afcfeb1f-076a-5c86-a6ec-fe66bd663268 |  | textbox | 0.Deg (ms)
text | aedb0568-0d8f-5d2c-a1e9-b2782b92b670 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 4f4e7359-d945-5408-afad-e666a106e747 |  | textbox | 0.Deg (ms)
text | 11143fad-b499-537d-afc9-d76a2b166f9a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | b49565df-f04c-5f3e-8918-ad5bdefd470c |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 6
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 0fe5e5f0-9e61-5281-b6e7-b51dac4c929a |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | e631d0dd-8f07-589b-840f-52eb604c7f6b |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 5e1d0656-3774-526b-943c-1c48aa95c175 |  | textbox | RCD No
text | 85fa8e70-be9d-52d4-874a-8a68c6a93496 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | d6ff318d-4177-5ea6-9176-b0a0a64fc53f |  | textbox | 0.Deg (ms)
text | 8195c4a1-2d02-5875-8ae0-8cdb17db49f9 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 7cbc889a-ade3-57d1-9663-b041319adcce |  | textbox | 0.Deg (ms)
text | 110f7ecb-82ee-5ded-8c95-52bd6b13f197 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | e792d1e3-9b8c-5a64-bd95-8baab1e537b0 |  | textbox | 0.Deg (ms)
text | a2ea54f8-9c4e-5415-8d47-f38fe5b52fdb |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 4ff5ec26-3e65-5677-b5a7-73f291a9d5ba |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 7
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | b15eccb8-670b-5414-95a6-8fb0750ee04b |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c41cc33e-b95c-52f8-98c9-9ee8db13e323 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 3f2ee580-d5f1-5e05-a0bf-34e9efe24fb1 |  | textbox | RCD No
text | 468f7480-131e-582a-8bf0-2ce131dea8c4 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 21916bd5-e74e-5c4b-be57-ac05b1bbc16b |  | textbox | 0.Deg (ms)
text | e97a54a2-7e55-50d2-b8dc-ed7b1507638c |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 176a7a8e-16ff-5123-9dda-8490706454e9 |  | textbox | 0.Deg (ms)
text | b41ac6af-564d-53c2-8474-bdef1626ce68 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | f7407048-a443-5aa9-af48-1c9eae411493 |  | textbox | 0.Deg (ms)
text | 01b8d5e7-0814-5f1a-a187-570d5b0152de |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | fd39e759-4daf-53f4-be2c-9e0bea6e7a00 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 8
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 6a3e4d1e-a5df-504c-999d-d27a5ff52fea |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 4fa9098d-0a6a-57c0-90e7-4c59390dd446 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 0384ba30-d1da-51bd-883d-386c65a86f01 |  | textbox | RCD No
text | ee8de02e-86b9-50c7-b75f-6ccffb9cf04b |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | e3e0f165-9f6b-55d1-b651-f1d7f9ef39dc |  | textbox | 0.Deg (ms)
text | 2d481cbc-3533-533f-be5c-64ed8e5c8703 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | ef66d146-d4ae-5abd-b37d-2ad16445156a |  | textbox | 0.Deg (ms)
text | d8f99337-8792-5677-80d9-d2ac00ebc6e1 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | fe63a83d-5c20-5189-bbb9-6e883f29fe57 |  | textbox | 0.Deg (ms)
text | 10e11c7f-7785-5138-8775-adad5aef9c77 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 5c47b0f2-c2ab-5ed4-867b-c5fede711944 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 9
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 54b83717-9b14-520b-a118-7044dac8e504 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | fb20c10a-35b9-5c45-bde7-5e32d3376b66 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | b23aacad-93c8-5f32-93ea-88f267f90ce6 |  | textbox | RCD No
text | f5c4b67f-58aa-57bc-a41c-66ff8047600a |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | d95d224f-4502-551c-9077-30596db4ebdc |  | textbox | 0.Deg (ms)
text | 1975d1d1-3aad-5e26-903a-aa103caec97f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | f2f58346-44cd-562a-af70-96f8d53605ab |  | textbox | 0.Deg (ms)
text | 5da7e8ce-8aca-587d-857b-d25930e584cd |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | f9c699e3-e021-56a3-92bb-8a6a45b28cad |  | textbox | 0.Deg (ms)
text | 65517df6-a1e3-5736-85e4-5e97d23d8a3d |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 4548a32a-dbcf-55fb-915a-ac6b74f251f9 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 10
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | ffa87b1a-9139-51f5-b38f-3bfec00eda41 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 75c932e2-1cd7-5334-9ec5-849f39b100b4 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 145f634f-4cb2-5491-a14d-1fcd2bf3de3d |  | textbox | RCD No
text | dda212f7-097a-5674-aede-b09897ea58b4 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 15802006-2949-59c4-8046-8ae1732268a7 |  | textbox | 0.Deg (ms)
text | 44482222-c688-5a05-ae1a-06f77dd9488c |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 5cdce234-6a02-5bca-ab60-17056c4cee0f |  | textbox | 0.Deg (ms)
text | 972338af-192e-5a4d-95f9-a5721a98fd61 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 2027dec0-3410-57c3-9514-8c95813ce7f1 |  | textbox | 0.Deg (ms)
text | a0e6e818-fb0a-56e8-9525-ad15e97d0173 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | c7b018df-e990-5ad6-9ec8-9ec54a047580 |  | textbox | Action taken