## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | ITP - Retaining Walls - Rev E | itp |  |  |  | Yes | ITP - Retaining Walls - Rev E | 6cec8363-521e-436f-9cd1-098d4f4cec3a
checkpoint-group | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint-status | 3.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 10 days prior to commencement of works
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 3.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Activity - H
label | By - SV
checkpoint-status | 3.01.03 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Activity - H
label | By - SE
checkpoint-status | 3.01.04 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Activity - H
label | By - SE
checkpoint-status | 3.01.05 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Activity - H
label | By - PE
checkpoint-status | 3.01.06 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Activity - H
label | By - PE
checkpoint-group | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
checkpoint-status | 4.01.01 - Stone Strong Block Molds
label | Acceptance / Conformance Criteria - Stonestrong blocks to be supplied by an approved supplier. The Contractor shall liaise with the Principal-appointed Cultural Artist to coordinate carving of the supplied blanks and the production of moulds & blocks
label | Standard / Specification - PS - 12
label | Verifying Document - Conforming Molds Post Carving
label | Frequency - Before Installation
label | Activity - H
label | By - PE
checkpoint-status | 4.01.02 - MSE retaining wall backfill and drainage Material
label | Acceptance / Conformance Criteria - Backfill is to comprise a well graded, granular material such as GAP65 or site won Hinuera Sand, which must be free of any deleterious material. Sand backfill shall have a fines content (less than 0.075mm diameter) of no more than 10%.
label | ○ Drainage metal to be 20/40 drainage aggregate or similar approved by engineer.
label | ○ Labratory MDD (x2 per material type) at standard compaction
label | Standard / Specification - GWS - 5.3.3
label | Verifying Document - Lab Results
label | Frequency - Prior to works
label | Activity - H
label | By - PE
checkpoint-status | 4.01.03 - Geogrid
label | Acceptance / Conformance Criteria - Geogrid to be Miragrid GX200/30 or similar approved
label | Standard / Specification - GWS - 5.3.1
label | Verifying Document - Datasheet
label | Frequency - Before Installation
label | Activity - H
label | By - PE
checkpoint-status | 4.01.04 - Para web
label | Acceptance / Conformance Criteria - Paraweb to be the correct grade: Paraweb 2D-50
label | Standard / Specification - GWS - 5.3.2
label | Verifying Document - Datasheet
label | Frequency - Before Installation
label | Activity - H
label | By - PE
checkpoint-status | 4.01.05 - Drainage Pipes
label | Acceptance / Conformance Criteria - Shall be 160mm diameter NZTA F/2 compliant smooth bore perforated corrugated pipe with filter sock
label | Standard / Specification - GWS - 5.3.4
label | Verifying Document - Datasheet
label | Frequency - Before Installation
label | Activity - H
label | By - PE
checkpoint-status | 4.01.06 - Geocomposite drainage board
label | Acceptance / Conformance Criteria - Shall be Bidim A39 geotextile or similar equivalent
label | Standard / Specification - SS - 12
label | Verifying Document - Datasheet
label | Frequency - Before Installation
label | Activity - H
label | By - PE
checkpoint-group | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
checkpoint-status | 5.01.01 - Excavation to subgrade
label | Acceptance / Conformance Criteria - The foundation materials are to comprise natural Hinuera sand material, stiff Hinuera Silt or imported clean sand and must achieve a minimum of 4 blows per 100mm when tested with a Scala penetrometer. Any exposed silts must have vane shear strengths greater than 70kPa.
label | Standard / Specification - GWS - 5.2
label | Verifying Document - Scala Results
label | Frequency - Every 10m
label | Activity - H
label | By - SE
checkpoint-status | 5.01.02 - Foundation Approval
label | Acceptance / Conformance Criteria - Results of the foundation material testing shall be supplied to the Engineer for approval and the prepared ground shall be inspected by the Engineer. Construction may not proceed until receiving Engineer’s approval.
label | Standard / Specification - GWS - 5.2
label | Verifying Document - Approval
label | Frequency - Prior to proceeding. Min 48h notice to Engineer
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.01.03 - Undercut subgrade
label | Acceptance / Conformance Criteria - Any unsuitable materials, such as uncontrolled fill, contaminated materials or any weak or organic materials, shall be undercut and replaced with compacted granular fill (WHAP65 or equivalent) or Hinuera Sand. Surveyor to capture extent of undercut (if any) to include in asbuilt.
label | Standard / Specification - GWS - 5.2
label | Verifying Document - Survey Record/ Photo record
label | Frequency - If required
label | Activity - I
label | By - SE
checkpoint-status | 5.01.04 - Undercut backfill compaction
label | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
label | Standard / Specification - GWS - Table 3
label | Verifying Document - NDM Results
label | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
label | Activity - H
label | By - SE
checkpoint-status | 5.01.05 - Geogrid Installation
label | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. Engineer to inspect 1 layer prior to backfill.
label | Standard / Specification - GWS - 4.1
label | Verifying Document - Photo record
label | Frequency - Each layer - 1 layer per abutment to be inspected
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.01.06 - Backfill Installation
label | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts and compacted to the following standards.
label | Standard / Specification - GWS - 5.3.3
label | Verifying Document - Photo record
label | Frequency - Each layer
label | Activity - I
label | By - SUP
checkpoint-status | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
label | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
label | Standard / Specification - GWS - Table 3
label | Verifying Document - NDM Results
label | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
label | Activity - H
label | By - SE
checkpoint-status | 5.01.08 - Clegg/Proofroll (Gap 65)
label | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test. Engineer to proofroll/inspect final layer of load transfer platform.
label | Standard / Specification - GWS - Table 3
label | Verifying Document - Clegg Result sheet
label | Frequency - Each layer - final layer to be inspected
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.01.09 - Scala Penetrometer (Hinuera Sand)
label | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
label | Standard / Specification - GWS - Table 3
label | Verifying Document - Scala Results
label | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
label | Activity - H
label | By - SE
checkpoint-status | 5.02.01 - Level founding platform
label | Acceptance / Conformance Criteria - The Contractor shall construct a 200 mm thick levelling pad on top of the load transfer platform to create a level founding platform to accept the MSE retaining wall.
label | Standard / Specification - PS - 12
label | Verifying Document - Site Photo / Checksheet
label | Frequency - Prior to Stone Strong block installation
label | Activity - I
label | By - SUP
checkpoint-status | 5.02.02 - Installation of blocks
label | Acceptance / Conformance Criteria - Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances.
label | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | Table 4: MSE Tolerances
label | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
label | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
label | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
label | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
label | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | Standard / Specification - GWS - 5.4
label | Verifying Document - Site Photo / Checksheet
label | Frequency - Each layer
label | Activity - I
label | By - SUP
checkpoint-status | 5.02.03 - Paraweb Installation
label | Acceptance / Conformance Criteria - The correct number of parawebs are to be installed as shown on the construction drawings.
label | ○ Para web is to be placed flat or with a 1% fall toward the rear of the wall. The Para web must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
label | ○ The Para web must be continuous over the design embedment length and no joins are permitted unless adequately lapped and spliced according to the Manufacturer’s instructions.
label | ○ 150mm of fill cover is required before construction equipment can travel over the area
label | Standard / Specification - GWS - 5.3.2
label | Verifying Document - Site Photo / Checksheet
label | Frequency - Each layer
label | Activity - I
label | By - SUP
checkpoint-status | 5.02.04 - Geotextile
label | Acceptance / Conformance Criteria - Geotextile to be placed against rear excavated face with a minimum overlap of 400mm between adjacent geotextile strips. Further Geotextile required to separate drainage aggeragate and MSE wall backfill, if sand is used. Short widths of geotextile to be placed across the internal open join area on the rear face of each Stonestrong block join to contain internal block void hardfill. Geotextile to be used to block paraweb voids within Stonestrong blocks that are not in use.
label | Standard / Specification - SS - 5
label | Verifying Document - Site Photo
label | Frequency - Each Layer
label | Activity - I
label | By - SUP
checkpoint-status | 5.02.05 - Drainage Outlet Installation
label | Acceptance / Conformance Criteria - Two x 160mm Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Transfer Platform.
label | ○ Drainage aggregate to be placed along external perimeter of Load Transfer Platform for each MSE wall layer backfill, forming a Chimney Drain. Chimney Drain to be a minimum width of 300mm and extend to the base of the Load Transfer Platform.
label | ○ Internal block void hardfill to be 20/40 drainage aggregate or similar approved by engineer.
label | ○ Additional Drainage pipe wrapped in 0.75m3/m run of drainage metal only required beneath wall embedment at toe of the outside of the wall if the slope doesn’t grade away from the toe of the wall.
label | ○ Drainage outlets shall be connected to the reticulated stormwater system or other approved outlet structure at the discretion of the design engineer
label | Standard / Specification - SS - 5
label | Verifying Document - Site Photo / Checksheet
label | Frequency - During Installation
label | Activity - I
label | By - SUP
checkpoint-status | 5.02.06 - Backfill Installation
label | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts adnd compacted to the following standards.
label | Standard / Specification - GWS - 5.3.3
label | Verifying Document - Site Photo / Checksheet
label | Frequency - Each layer
label | Activity - I
label | By - SUP
checkpoint-status | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
label | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
label | Standard / Specification - GWS - Table 3
label | Verifying Document - NDM Results
label | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
label | Activity - H
label | By - SE
checkpoint-status | 5.02.08 - Clegg/Proofroll (Gap 65)
label | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test.
label | Standard / Specification - GWS - Table 3
label | Verifying Document - Clegg Result sheet
label | Frequency - Each layer
label | Activity - H
label | By - SE
checkpoint-status | 5.02.09 - Scala Penetrometer (Hinuera Sand)
label | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
label | Standard / Specification - GWS - Table 3
label | Verifying Document - Scala Results
label | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
label | Activity - H
label | By - SE
checkpoint-status | 5.03.01 - Settlement Pins
label | Acceptance / Conformance Criteria - Settlement pins shall be installed within 24 hours of reaching design subgrade level. Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
label | Standard / Specification - GWS - 6.3
label | Verifying Document - Survey Results (in paper as well as electronic format)
label | Frequency - Weekly for the first month, then monthly
label | Activity - R
label | By - SV, ENG
checkpoint-status | 5.03.02 - Settlement Targets
label | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
label | ○ Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
label | Standard / Specification - GWS - 6.4
label | Verifying Document - Survey Results (in paper as well as electronic format)
label | Frequency - Weekly for the first month, then monthly
label | Activity - R
label | By - SV, ENG
checkpoint-status | 5.03.03 - Engineers Approval
label | Acceptance / Conformance Criteria - Geotechnical engineer assesment required before commencement of Pavement construction
label | Standard / Specification - BBO
label | Verifying Document - Written approval
label | Frequency - Prior to pavement construction
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint-status | 6.01.02 - Draft As-Builts
label | Acceptance / Conformance Criteria - Draft as-builts completed on the completion of MSE wall including red pen mark up to IFC drawing changes.
label | ○ The draft as-builts shall be provided on a continual basis throughout the project for verification by the Engineer, and as a minimum shall be provided in electronic form prior to application for Practical Completion.
label | Standard / Specification - PS 2.2.17
label | Verifying Document - Draft As-Builts Drawings
label | Frequency - Prior to PC
label | Activity - H
label | By - SV / PE