## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # CTN-ITP-001
[11 empty] | Revision : 0 | 2023-05-29
Client: |  | Hobart International Airport Pty Ltd |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Project Mercury Early Works At Hobart International Airport |  | Removal of Existing Structures |  | Name: | Dave Hart/Mileva Savic | Name: |  | David Ewers | Name:
Contract No: |  | MER-EW-001 |  | Specifications: AS2601-1991 Demolition of structures. AS2436-1981 (noise control)
|  |  |  | Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Hobart International Airport |  | Date : | 29/05/2023 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Design and Planning
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Lift Planning |  | Prior to commencing any activity | Lift plan review compelted | Work Procedure Lift Plan HSMP | Verify | This ITP signed Lift Plan | HP* | Fulton Hogan | N/A |  | N/A
1.4 | Permiting |  | Prior to commencing any activity | Verify approval of all permits and approval processes for removal of structure | Work Procedure HSMP | Verify | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.5 | Transport Plan |  | Prior to commencing any activity | Transport route and plan complete, sight and review any transport documentaion | Work Procedure | Verify | This ITP signed Rout Map | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.6 | Asbestos |  | Prior to commencing any activity | Identify and verify removal of any asbestos material | Work Procedure | Verify | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.7 | Exisiting Services |  | Prior to commencing any activity | Verify the disconnection of any existing services to structure | Work Procedure | Verify | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Structure Removal
2.1 | Exclusion Zones |  | Prior to demolition | Identify and establish any no go and exclusion zones required for demolition | Work Procedure | Inspect | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Demolition of Incidental Strutures |  | Prior to concrete pour | Identify and remove any incidental structures relating to the main structure | Work Procedure Drawings | Inspect | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Relocation Route |  | Prior to Removal | Ensure relocation route is prepped and clear for relocation | Work Procedure | Inspect | This ITP signed Route Map | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.4 | Removal of Struture |  | Prior to Removal | Ensure removal of structure is undertaken per approved documentation | Work Procedure | Verify | This ITP signed Lift Plan | HP* | Fulton Hogan Engineer | N/A |  | N/A
3 | Structure Laydown
3.1 | Laydown Area |  | Prior to Removal | Verify laydown area is ready to receive structure | Work Procedure | Verify | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
3.2 | Storage |  | Prior to Removal | Structures are stored in such a way as to prevent damage if required | Work Procedure | Verify | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
3.3 | Photos |  | Prior to Removal | Photos of stored materials | Work Procedure | Verify | Photos | HP* | Fulton Hogan Engineer | N/A |  | N/A
4 | Closeout
4.1 | NCR |  | Prior to lot closure | Details of any NCRs to be recorded in CL01E (if applicable) | CL 01E | Verify | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
4.2 | Permits |  | Prior to lot closure | Close out applicable permits | Work Procedure | Verify | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on K18: Rodrigo Anchico: Write "N/A" to disable the cell.