## ITP - Subsurface drains
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # CTN-ITP-004
[11 empty] | Revision : 0 | Date : 06/06/2023
Client: |  | Hobart International Airport Pty Ltd |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Project Mercury Early Works At Hobart International Airport |  | Subsurface Drainage |  | Name: | Zac Buick | Name: |  |  | Name:
Contract No: |  | MER-EW-001 |  | Specifications: Hobart Airport Project Mercury Early Works Civil Specification
|  |  |  | Structure / Component: Drainage |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Hobart International Airport |  | Date : | 2023-06-06 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Independent QA Verifier | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Site Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TGS, SWMS, WP | Visual Inspection | This ITP signed | HP* | Site Engineer | N/A |  | N/A
1.3 | Material Classification |  | Each Lot | Pipes supplied shall be of the category and diameter shown on the drawings Material shall be as indicated on the project drawings and / or shall conform to the following:- uPVC slotted spigot and socket sub-soil drainage pipes. Fibre reinforced cement slotted spigot and socket sub-soil drainage pipes. Perforated corrugated polyethylene continuous tubes. Geo textile must be of A34 | DWG EW-CE-DRW-526-001 C.6 | Verify | , This ITP signed off | IP | Site Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | This ITP Signed | HP* | Site Engineer | N/A |  | N/A
2.2 | Outlets |  | Each lot | Superintendent inspection of proposed underground outlet location. Outlets shall be installed through walls of pits, provided inverts are not below the top level of the outfall drain. | C.6.2 | Visual Inspection | This ITP Signed | HP | QAV | N/A
2.3 | Excavation of Trench |  | Specification for trenching | Excavations for sub-soil drains shall conform to the requirements specified for excavation for services subject to the following specific requirements and modifications: • Trench depth and width shall be as shown on the Drawings. • Trench bases shall be uniformly graded to an even fall as necessary to suit whichever of the following is applicable: • Parallel with pavement or kerb and channel formation grade. • Parallel with overall grade of stepped footings. • Not less than 1:250. If it is not possible to conform to any of the above requirements, the Contractor shall notify the Superintendent and await direction before continuing with the affected part of the work. | C.6.1 | Visual Inspection | This ITP signed | HP | QAV | N/A |  | N/A
2.4 | Bedding |  | Each Lot | The bottom of the trench shall be well compacted and evenly graded suitable material, 25mm minimum depth of 20mm Class 3 FCR If rock excavation was necessary and if the bottom of the trench is uneven, all low and rough areas shall be filled, and solid rock outcrops covered with bedding material to a compacted thickness of not less than 25 mm. | C.6.6 | Visual Inspection | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.5 | Placing pipes |  | Each Lot | Sub-Soil drain to be 100mm Dia. PVC Class 1000 Agricultural drain. The pipes shall be laid true to line and gradient on the graded compacted bedding. Pipes shall be jointed to fit tightly by pushing the spigots firmly into the sockets. For pipes without sockets, special end jointing fittings shall be used. Fittings shall be compatible with pipe material. | DWG EW-CE-DRW-526-001 C.6.4 | Visual Inspection | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.6 | Backfilling |  | Each Lot | Superintendant inspection of Subsoil drain backfill prior to covering Backfill needs to to encase subsoil drain and cover upto 150mm over to allow for sediment collection. Backfill to be 14mm screenings to subgrade. | C.6.5 | Visual Inspection | This ITP signed | HP | QAV | N/A
2.6 | Backfilling |  | Each Lot | At full depth pavement joints 100ø class 1000 pvc pipe sub-surface drain type 2 with filter fabric around trench (150mm Overlap) with "no fines" concrete filter Material (with 4% cement & compacted). | DWG EW-CE-DRW-416-001 C.6.5 | Visual Inspection | This ITP signed | HP | QAV | N/A
2.8 | Access Points and Flushouts |  | Each Lot | A flush out riser is to be located at the Back of kerb (BOK), comprsing of 100mm UPVC PIPE, capped. Minimum 200m intervals along road alignments, a single flushout points at high point or at locations within WSUD/Raingardens. | C.6.5 | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
5 | Finishing and Commissioning
5.1 | As-Constructed survey and documentation |  | Each Lot | The survey shall include pickup of location and depth of installed sub-soil drainage and location of any inlet/outlet/flush out points. Lot Maps shall be completed to show the extent of works for each lot. |  | Review | This ITP Signed | HP* | Site Engineer / Superintendent | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Fulton Hogan | Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent