## ITP - Asphalt
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # CTN-ITP-005
[11 empty] | Revision : 0 | Date : 31/05/2023
Client: |  | Hobart International Airport Pty Ltd |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Project Mercury Early Works At Hobart International Airport |  | Asphalt Placement |  | Name: | Zac Buick | Name: |  |  | Name:
Contract No: |  | MER-EW-001 |  | Specifications: Hobart Airport Project Mercury Early Works Civil Specification
|  |  |  | Structure / Component: Pavement |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Hobart International Airport |  | Date : | 28/06/2023 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | QAV | Fulton Hogan | Asphalt Supervisor | Date
1 | Construction Works
1.1 | Submission of Mix Design |  | Prior to commencing paving | No Asphalt shall be supplied until the mix has been registered and the superintendant approves the mix for use. Only use mixes that are registered by State Growth as 'General Mixes' | Cl 407.06 | Verify | Mix registration & correspondence | HP | FH Engineer/ Asphalt Supervisor / QAV |  |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | HP* | FH Engineer | N/A |  | N/A
1.3 | Site Inspection and Base Condition |  | Prior to commencing paving | Base condition is acceptable for placement of asphaltic concrete. | Work Procedure | Visual Inspection | This ITP signed off | IP | FH Engineer / Asphalt Supervisor | N/A |  | N/A
1.4 | Ambient Conditions for Placing |  | Prior to commencing paving | The temperature of the pavement to be surfaced shall have a temperature greater than 10 degrees and no rain shall fall during placement of the mix and the surface shall be dry. Primer seal - no primer sealing shall be applied whilst the pavement surface temperature is less than 20 degrees or during wet, windy or rainy conditions, or when adverse weather conditions may prevail at any time during the work. | C.9.13 | Verify | This ITP Signed off | IP | FH Engineer / Asphalt Supervisor | N/A
2 | Asphalt Placement works
2.1 | Tack Coat |  | Prior to commencing paving | The tack coat shall consist of a diluted rapid-setting Anionic bitumen emulsion as specified. Application shall take place not less than 30 minutes nor more than 2 hours before placing asphaltic concrete. The tack coat application rate shall achieve a residual bitumen of 0.1 to 0.2 litres per square metre. The actual rate of application will be selected by the Superintendant to suit the class of material. Any pools of tack coat which may have formed in surface depressions shall be brushed out | EW-CE-DRW-406-001 EW-CE-DRW-416-001 C.9.12 | Visual Inspection | This ITP Signed off | WP | FH Engineer/ Asphalt Supervisor | N/A
2.2 | Prime Coat |  | Prior to commencing paving final layer | Prime coat to be applied at 1.0L per square meter Primer sealing shall be carried out under favourable weather conditions and the prepared base course shall be sufficiently dry to permit adherence to and penetration of the base course by the bitumen. Before primer sealing, the pavement shall be broomed free of all loose material and dust and any defects are to be made good. Should conditions require it, the surface shall be lightly watered immediately prior to the application of the primer. The primed surface shall be covered with 5mm diorite screenings at the rate of 80 square metres coverage to one cubic metre of screenings and rolled with a 6 - 8 tonne roller until screenings are firmly embedded in the primer. | EW-CE-DRW-406-001 EW-CE-DRW-416-001 C.9.12 | Visual Inspection | This ITP Signed off | WP | FH Engineer/ Asphalt Supervisor | N/A
2.3 | Commencement of Placing |  | Prior to commencing Paving | The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Superintendent | Work Procedure | Visual Inspection | Hold Point Release | HP* | FH Engineer / QAV |  |  | N/A
2.4 | Delivery of Mix |  | Each load | The asphaltic concrete mix shall be placed at a minimum temperature of 140 degrees Celsius immediately on delivery to the spreader | C.9.13 | Visual Inspection | Delivery Docket /Asphalt Traceability Sheet | IP | FH Foreman / Asphalt Supervisor | N/A
2.5 | Layer Thickness and Level Control |  | Regularly during paving | Thickness of asphalt layer conforms to asphalt thickness on drawings. The asphaltic concrete shall be placed in one layer by an approved self-propelled machine spreader, conforming to AS 2150, Section 12. | EW-CE-DRW-416-001 EW-CE-DRW-406-001 | Verify | Dips using ruler or dip stick | IP | FH Foreman / Asphalt Supervisor | N/A
2.6 | Asphalt Placement works |  | Each Load | The temperature of the asphaltic concrete at the time of initial rolling must not fall below 120 degrees Celsius. | C.9.13 | Verify | Thermometer | TP | FH Foreman / Asphalt Supervisor | N/A
2.7 | Surface Finish of Wearing Course |  | During paving and after final roll | Joints shall be in accordance with AS 2150 Section 12.6. Form any joints necessary and ensure that the finished profile is smooth and even over the joints without ridges or depressions. Joints shall be waterproof. If the asphaltic concrete begins to shove or crack, in no circumstances continue with rolling until the cause has been determined and corrective measures taken. Keep drums and wheels of rollers wet with water and clean during all rolling operations. | C.9.13 | Visual Inspection | This ITP signed off | IP | FH Foreman / Asphalt Supervisor | N/A
2.8 | Kerb and Channel |  | During paving and after final roll | Where asphalt is placed against kerb and channel, The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel | Work Procedure | Visual Inspection | This ITP signed off | IP | FH Foreman / Asphalt Supervisor | N/A
3 | Testing and Conformance
3.1 | Compaction |  | As Requested | The density of the compacted concrete shall be not less than 97% of the Marshall maximum density. | C.9.13 | Verify | Test Report | HP | FH Engineer/ Lab Technician | N/A
3.2 | As-constructed survey and conformance documentation |  | Each Lot ( 1 per day) | Lot Maps shall be completed to show the extent of works for each lot. Lot Maps shall include layer depth and finished levels at 20m intervals and conformation of ponding checks per lot. Tolerances Width of prime: + 150mm or - 0mm Width of primer seal: + 150mm or - 0mm Thickness: + 5mm or - 0mm Finished level: + 10mm or - 10mm | C.7.2 (5.) C.7.4 (Table 6) | Verify | Visual match existing / This ITP signed off | SCP | FH Engineer/ Surveyor | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which may be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent