## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP021-2 – Reinstallation of Secondary Cable | itp |  |  |  | Yes | ITP021-2 – Reinstallation of Secondary Cable | 1cfb7361-a366-4c0e-9e8b-c7d8bdaa7ec3
checkpoint-group |  |  | section | 1. Installation of New Secondary Cable in Existing Shallow Base Canister
checkpoint-status |  |  | checkpoint | 1.1 - Mark and cut
label | c9ce93bd-32e5-5f01-bd8d-97141d69681b |  | note | Frequency - Each Lot
label | 172c1f4c-5c6c-5e78-a572-0a40c418ff28 |  | note | Acceptance Criteria - Slots marked out and cut from to light base.
label | c2d8f07a-4621-5e36-8465-818866d08379 |  | note | Reference Documents - Drawing sets:
label | b3d52a34-773a-5777-8f00-4ea58f706f49 |  | note | • 60692389- SHT-01_1-10
label | 3bf9a24d-56f8-5aef-a9dd-4f0709295422 |  | note | • 60692389- SHT-01_2-10
label | e31705a1-94bc-5c4e-87c8-01075816544a |  | note | Inspection/ Test Method - Verify
label | 9dd02238-7d01-5371-9ea4-33ab5ae7b545 |  | note | Record of conformity - This ITP Signed / Avionics CL002
label | 48028c4b-8ff2-5355-a286-c9cc1ebb5e35 |  | note | HP*
label | a6c2e4e2-f9b9-58db-9a98-ee27c226b5e3 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.2 - Cabling
label | ddc9bfb0-b3fa-58e8-8b18-2800ae758d7b |  | note | Frequency - Each Lot
label | 8724c8a9-2991-5ae2-b484-f2812687ba2d |  | note | Acceptance Criteria - Cables ran and connected from existing base via joints/slots/conduits to SIT pit.
label | a5e3595d-9a84-5ab3-920a-26c555bb9161 |  | note | Reference Documents - Drawing sets:
label | bcb241a5-faac-5338-8767-4950358bcc71 |  | note | • 60692389- SHT-01_1-10
label | f384c5d9-67c4-51fe-94b3-5446f230bcb6 |  | note | • 60692389- SHT-01_2-10
label | 967e7192-55e6-5fab-8164-9110ef701258 |  | note | Inspection/ Test Method - Verify
label | f06df35c-37d0-560b-ab68-955c58b7211d |  | note | Record of conformity - This ITP Signed / Avionics CP002
label | 9364342e-9b6d-51f3-9c2f-f1223a6e7f9a |  | note | IP
label | 79ec13e7-c19b-586c-8dc2-9695826a7d9d |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.3 - Sealing
label | bcb93093-ad5b-582e-b027-5f2f590e16fe |  | note | Frequency - Each Lot
label | a252292e-9f29-5b34-9bd4-082c38f7f5e8 |  | note | Acceptance Criteria - Once cables installed, backing rod placed and expansion joints sealed with approved product.
label | c0095fc4-f3c5-5c43-8b17-04433a49a4d3 |  | note | Reference Documents - Drawing sets:
label | 2cba519e-86ee-52f4-96a8-862b6b8e0a5b |  | note | • 60692389- SHT-01_1-10
label | 49901a61-1077-59c0-ab01-0b729cdd0852 |  | note | • 60692389- SHT-01_2-10
label | 1db8b096-aafa-5753-9f7b-f35bf747285a |  | note | Inspection/ Test Method - Verify
label | fbdad067-8d36-50b5-bf33-8beb15f69e41 |  | note | Record of conformity - This ITP Signed / CL002
label | eea10b64-57e7-5e9f-9ab9-93471b2aa673 |  | note | IP
label | a905c71e-ab24-5cfb-80d4-d12aa2980bbc |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.6 - Finishing, Testing, Demobilisation
label | d1aacb6a-e58f-55a9-bfa5-4321b9490333 |  | note | Frequency - Each Lot
label | bb2692db-c28c-55a9-8754-2200d04c27b9 |  | note | Acceptance Criteria - Gasket positioned on light top, light plugged and positioned to current orientation. Light tested and area cleaned before demobilisation.
label | 5647c4e6-6c78-5ea0-90a4-862c81e30fe0 |  | note | Reference Documents - Drawing sets:
label | 1fe85205-ed49-5399-b116-86deaad472ec |  | note | • 60692389- SHT-01_1-10
label | 476a4b48-9184-56b3-9ca0-f98edc7bbd28 |  | note | • 60692389- SHT-01_2-10
label | d883cbbd-0e28-5490-bff4-809c61f8ed01 |  | note | Inspection/ Test Method - Verify
label | a659c63b-8bc2-5ecd-bb1f-9d080b858ee5 |  | note | Record of conformity - This ITP Signed / Avionics CL002
label | b2e4ab8a-ed78-5969-b2f3-508556c15900 |  | note | IP
label | 1108fd0c-e44b-5144-9d3c-96bc4288f1fc |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | Final Inspection
label | d8ae4fd7-cd40-5a1d-b213-6a1ab7133ed3 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 3a4254a6-7855-55a8-812f-9a57d4afee56 |  | textbox | Name:
text | e39b3e56-dfff-5cc3-98bf-cfc0ad96c0c1 |  | textbox | Position:
text | 9a513d9d-f6d0-580b-9237-250b4864b054 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP001 – Demolition and Service Location | itp |  |  |  | Yes | ITP001 – Demolition and Service Location | 4126bb83-2a4c-4cdd-803a-64e600bee7ff
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - The current revision of drawings are being used including subcontractors copy.
label | e451fa2a-bf7a-5311-bae7-0b261bd9e103 |  | note | Frequency - Prior to commencing works
label | c52621fc-8a80-5d03-aadf-8140d8e698b8 |  | note | Acceptance Criteria - Current revision drawings are being used, including the subcontractors copy. Current revision to be obtained via Aconex
label | 6eef650b-6ce2-59d0-9e87-0080bd0ab51f |  | note | Reference Documents - Current Revision Drawings in Aconex
label | a56bcad9-9f6b-5681-ba9e-f09cddb2e98e |  | note | Inspection/ Test Method - Visual Inspection
label | 5a881b14-b6e5-546f-9179-d6387cdc5ec7 |  | note | Record of conformity - This ITP signed
label | ca83b3d3-a2de-5969-87e2-3f6d880fca04 |  | note | HP*
label | a944e7db-7d6a-5e41-9c12-818db97a77af |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Dilapidation Report
label | 5ce6a6f3-3a9a-5654-9e78-65439ce98201 |  | note | Frequency - Prior to commencing works
label | 963323c9-c3c3-529b-be80-bcbe4c7c598d |  | note | Acceptance Criteria - Prior to the Works, the Contractor must provide the Contract Administrator and Principal’s Design Consultant with a fully detailed dilapidation survey recording the current condition of aircraft pavements, aircraft pavement surface features, underground services, roads, drives, footpaths and adjoining premises.
label | e7c26a3c-89a4-5ea5-8e53-2972a6eeddd5 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl1.23.1
label | 1d92130c-9ceb-5e38-9696-692220aa23c7 |  | note | Inspection/ Test Method - Verify
label | 4913e422-961a-57d4-a0b0-87ad09e119d7 |  | note | Record of conformity - Aconex Correspondence
label | 64ee6ce5-c0c8-5541-8951-5eea4f12363b |  | note | HP
label | c53aaf24-6e9b-5941-8d00-bf5c37bc3145 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Service Location and Detection Methodology
label | e90a3039-1e71-54f4-97d9-821ca3ab356f |  | note | Frequency - Prior to commencing works
label | 9af3d57e-cbd7-515c-b7ee-0118b617559a |  | note | Acceptance Criteria - The Contractor must submit a methodology of service detection to the Contract Administrator for review.
label | eb4ab646-b3f5-53ac-89b2-ae66d8ebe08a |  | note | • Within 20m of intrusive works the Contractor must locate and mark the ground position of all underground services and structures.
label | 5514b730-423d-558d-8d36-818fd8c1c85a |  | note | • Services located within the works area must be exposed using hand tools or specialist sensitive excavation techniques (NDD).
label | 499aa3fa-69b6-5d26-b153-018be7217f77 |  | note | • This methodology is contained within the work procedure for demolition.
label | dd731314-fe0f-5983-9bf1-ed21e9489d2b |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl3.2.1 & AECOM – MAP MP 2.0 Spec. Cl3.2.2
label | be60e866-7601-55c3-8068-978389eca1c3 |  | note | • FH-DP1PM-WP001 Section 3.2
label | 4bb4c060-5878-5250-ab3c-444e2d7d1617 |  | note | Inspection/ Test Method - Verify
label | 23a35fc7-eb6b-5697-8739-3c093c7f97b2 |  | note | Record of conformity - This ITP signed
label | fcc1c18a-eec5-5ff4-a987-21937a8c83ae |  | note | WP
label | 39b5a662-39e0-501d-8a1f-9b37e582e602 |  | note | Responsibility - FH Project Engineer Contract Administrator
checkpoint-status |  |  | checkpoint | 1.4 - Demolition Work Plan
label | 4fd5e26f-d17e-512f-a72d-4c887e6f2db3 |  | note | Frequency - Prior to commencing works
label | 6c0978f7-03c7-524c-96ac-a24df2eeed17 |  | note | Acceptance Criteria - The Contractor must prepare a Demolition Work Plan and shall submit this plan to the Contract Administrator at least ten (10) business days prior to the works commencing for approval.
label | 3ad95fbd-4265-509f-9ffe-f701602bf94c |  | note | • The Contractor must maintain pavements surrounding the demolition site in a clean condition that is free from debris and saw and core cuttings, slurry etc
label | 567494d0-deb2-5ae4-94eb-e51344c05deb |  | note | • Precautions to protect the existing remaining pavement from damage must be undertaken where tracked equipment are required to traverse or operate on existing pavement.
label | dee362ba-0ed9-5c1d-8f43-d89323b881e1 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl4.5 & AECOM – MAP MP 2.0 Spec. Cl4.6.3
label | 3820e23a-f39e-533a-a083-44fd7ea0421f |  | note | Inspection/ Test Method - Verify
label | b92cd670-f161-51cd-8d90-496f342093d2 |  | note | Record of conformity - This ITP signed
label | dbd2e819-061c-5536-83bf-fb9282317efa |  | note | HP
label | 8d30254a-663a-5764-89ad-78053f197b07 |  | note | Responsibility - FH Project Engineer Contract Administrator
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Obtain approvals to start works
label | e354c684-42ab-5450-b061-334fbbabb57c |  | note | Frequency - Prior to commencing works
label | 85ce99f6-295c-5f3f-bdb1-a12636c6f41e |  | note | Acceptance Criteria - The Contractor needs to obtain all required works approval from the Principal as required. This must include excavations, hot works, electrical isolation permits and crane access. Evidence of permits being obtained by the Contractor must be submitted to the Contract Administrator prior to works commencing.
label | 466e523f-8c6c-5ce3-b36e-34558fd44f75 |  | note | • Fulton Hogan Excavation permit issued to plant operators.
label | e554df67-6da7-522e-a049-99fc26249bff |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl4.4
label | d56c0406-5f05-54b6-aa77-a6ea803f685e |  | note | Inspection/ Test Method - Verify
label | 7696d8e3-09a9-56b8-864b-2874d6c453d7 |  | note | Record of conformity - This ITP signed
label | d32d235f-459b-5f41-b6b4-12cffa6af0a7 |  | note | HP
label | a25071ba-1f84-5abf-a4ac-1847d9949ac1 |  | note | Responsibility - FH Project Engineer Contract Administrator
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Implementation of all measures and controls
label | 78525fc0-b343-5724-832b-ab985d5edcce |  | note | Frequency - Prior to commencing works
label | 43bf98c3-a6ad-5087-8ada-cadeba1448af |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 5a91760f-12e3-53b0-a795-ad547753ee70 |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | 6e892edc-ac91-54c9-832b-a744d2412a2d |  | note | Inspection/ Test Method - Visual Inspection
label | f404247d-c887-5d11-8e7b-099885f4decb |  | note | Record of conformity - This ITP signed
label | e32b9ec4-0eb1-55a8-b690-3cf4da4c4da9 |  | note | HP*
label | a2da9781-bcef-5de3-b0c6-ac827ea40447 |  | note | Responsibility - FH Project Engineer / Site Supervisor
checkpoint-group |  |  | section | 2. Demolition Works
checkpoint-status |  |  | checkpoint | 2.1 - Services Detection
label | 1b660b5e-4e36-5b70-97df-5d1e3990b79b |  | note | Frequency - Each Lot
label | 2ae8213c-d4f0-5260-b5c2-d4bb9c0b4264 |  | note | Acceptance Criteria - Confirmation that Services Detection has been Completed for the Works area(s)
label | 90737bb8-a522-5edf-8c63-a781fe9a2d92 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl3.3.1
label | 1fb3479b-0015-5794-b62f-67909d873052 |  | note | Inspection/ Test Method - Visual Inspection
label | c1da686a-90e5-5561-a911-d802b00deabd |  | note | Record of conformity - This ITP signed
label | 54287634-139b-5bfb-a94f-e736befc7095 |  | note | HP
label | 4f40739f-11ce-546f-b341-1a8142905b4d |  | note | Responsibility - FH Project Engineer / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Discovery of Contaminated Materials
label | b275801d-e1e8-5d0b-b202-55ffa61ebd80 |  | note | Frequency - Each Lot
label | ceafb911-9098-5277-92d6-f3a343f6506f |  | note | Acceptance Criteria - If contaminated or hazardous materials are found, immediate notice is to be given to the Principal’s Representative. These include the following;
label | 62afce4a-859c-568a-b266-fdc782169eef |  | note | • Asbestos or material containing asbestos;
label | a3a7db0c-4c2a-5621-8240-245e23e24d96 |  | note | • Flammable or explosive liquids or gases;
label | 34f5220f-9e7f-560f-a047-0a8b8f800d7a |  | note | • Toxic, infective or contaminated materials;
label | 21961daa-d9b5-5358-be91-88c825caf57c |  | note | • Radiation or radioactive materials;
label | 33766565-94c0-5ce0-9225-0a3debe3514a |  | note | • Noxious or explosive chemicals; and
label | 615d5aed-9918-5754-a8fe-9d958c24f0f7 |  | note | • Tanks or other containers which have been used for storage of explosive, toxic, infective or contaminated substances.
label | 3869b836-7cd3-516f-a9e8-707536159340 |  | note | ○ A proposal for the procedure to remove contaminated or hazardous materials from the site to be agreed between FH, APAM and AECOM in accordance with all statutory and contractual requirements to approved locations.
label | 63b1c77e-4ceb-5364-9651-262595b24922 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl1.19
label | f9783270-b99a-5ce6-9a07-a076383e2a9e |  | note | • FH-DP1PM-WP001 Section 3.3.7.
label | 64d31025-da8d-537d-995e-1663bd59385c |  | note | Inspection/ Test Method - Verify
label | e6b8a0c5-9ced-5c5a-a8d5-77613e4fcd87 |  | note | Record of conformity - This ITP signed
label | 14f307bd-391f-59e3-af7e-138c7bfdf3c2 |  | note | HP*
label | 264a18d9-6447-54e7-98ea-97a188dbc396 |  | note | Responsibility - FH Project Engineer / Contract Administrator
checkpoint-status |  |  | checkpoint | 2.3 - Disposal of Demolished Materials
label | e4f64fb8-a33f-5fbb-afd3-3f3ba9d6f392 |  | note | Frequency - Each Lot
label | 63daef29-7b0e-55f1-90e0-946d0baf2b64 |  | note | Acceptance Criteria - The disposal of demolished materials is to be managed under the approved Construction Environmental Management Plan (CEMP).
label | 19d0096f-ebd2-51a0-9e23-4c2e6b401b32 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl4.6.5
label | f5052e03-03f8-518d-9561-e4747afc5922 |  | note | Inspection/ Test Method - Verify
label | fde1eaf0-4726-5622-af2a-3516769a9e10 |  | note | Record of conformity - This ITP signed
label | 7e66fe75-ff60-5ee2-bf2e-bab4304e3b17 |  | note | HP*
label | add96f63-5270-543a-bf82-38b717d8f343 |  | note | Responsibility - FH Project Engineer / Foreman
checkpoint-status |  |  | checkpoint | 2.4 - Completion
label | a8d501ff-5c3b-5239-8e70-ef7b279912e8 |  | note | Frequency - Each Lot
label | 46d81abd-0266-5a89-a775-dc7fe607a15b |  | note | Acceptance Criteria - The Contractor to make the area safe and clean post completion of works. Any temporary supports are to be removed at completion of demolition.
label | 209d3bdd-787f-5983-a9b0-169853ce0927 |  | note | Reference Documents - FH-DP1PM-WP001 Section 3.3.14
label | de87db96-f05c-568f-bd84-57adc63304ab |  | note | Inspection/ Test Method - Inspection
label | dc4f8a50-a0ae-5687-994f-a4da22b4b19f |  | note | Record of conformity - This ITP signed
label | ef0aec62-1520-54dd-a51d-3958d6f48f63 |  | note | HP*
label | c1a0ca52-3f5f-5ffe-a3b0-093bedb3ee31 |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 88f6e925-9f70-5997-abd1-0a63557faabc |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | d29489dc-31c6-5878-a2ea-15d6c6699b00 |  | textbox | Name:
text | 05b0406e-962e-58b1-a9e4-d01002915775 |  | textbox | Position:
text | e37fe8b5-98aa-5054-8c3d-bdb014c9b9fd |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | FH-DP1-PM-ITP008 - Minor Asphalt Works |  |  |  |  | Yes | ITP008 – Subsoil Drainage | 6a3a8108-fdea-4b27-b7b6-8f56ff1e63d8
checkpoint-group |  |  | section | 1. Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 8f268b77-edc8-559c-853d-6b1fbacc8545 |  | note | Frequency - Prior to commenc ing any activity
label | 44850c9f-7f88-5222-896f-a3ac58e287ec |  | note | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex
label | fb7bd970-1d09-5c80-b080-92a06e930a8c |  | note | Reference Documents - Drawings and drawing registers on Aconex
label | 9cdf7216-b75e-5449-b282-3f37f77f5faa |  | note | Inspection/ Test Method - Visual inspection
label | 34b38ecf-7efd-53a7-8891-9dacfad9ff19 |  | note | Record of conformity - This ITP signed
label | d08e489f-6373-5fe2-8b8a-ba7cc3340a58 |  | note | HP*
label | 67038ed8-460b-5cc6-97db-d3f8976f8bae |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | add06799-dc56-58ee-92d3-898ce4b37d01 |  | note | Frequency - Prior to commenc ing any activity
label | 79b883c3-21cf-549a-ad51-604ebbc3fdc9 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 9cf10057-e1ac-523f-8d4b-f772c238f695 |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | 7523015a-29cc-541e-855e-53a7ea3922d8 |  | note | Inspection/ Test Method - Visual Inspection
label | feda99c4-8f88-5f0a-92e6-68d71ec96bd8 |  | note | Record of conformity - This ITP signed
label | 708363b5-9bd0-5a26-89f8-fb45f697b165 |  | note | HP*
label | b10ae669-02a8-51ad-871a-bfdd132d45ea |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.3 - Definition of the work area
label | 76fd599f-6143-58f3-b15d-077302dff450 |  | note | Frequency - Prior to commenc ing any activity
label | e9241b5a-bad1-5588-94c2-fb8b6ae96151 |  | note | Acceptance Criteria - Work area has been cleared and surveyed (marked on site). Limits of excavation clearly defined.
label | 7a91de06-e0f3-5ee0-b19d-ef7fb93798db |  | note | Reference Documents - Drawings
label | d2b079c3-74a3-52af-b89a-fac750f92994 |  | note | Inspection/ Test Method - Visual Inspection
label | abaa4c0d-bfc1-5a5e-bd46-f3f3ff3212ad |  | note | Record of conformity - This ITP signed
label | 6e037040-19b8-5d4a-a76f-426c312fcdbd |  | note | HP*
label | 12fb8905-d8ec-59bb-9c91-7dada119ac11 |  | note | Responsibility - Project Engineer
checkpoint-group |  |  | section | 2. Subsoil Material
checkpoint-status |  |  | checkpoint | 2.1 - Subsurface Drainage Pipes
label | 5b1925f7-85ad-56c6-b35d-3d2c73ebe5a3 |  | note | Frequency - Prior to Start
label | 7effdd2e-fb98-5819-9cd8-f90802a82890 |  | note | Acceptance Criteria - Subsoil Pipe material to be 150mm slotted agi class 1000 SN20, or approved alternative.
label | e515e9a4-cd2a-559d-9f85-9d094d83f037 |  | note | Reference Documents - Drawings
label | 09a2fbdb-cd77-54dd-8a25-b080147ed8ee |  | note | Inspection/ Test Method - Verify
label | cfa7f4a6-7190-5860-982b-fb28a2517e97 |  | note | Record of conformity - This ITP signed
label | 7f6b8c54-112b-587d-8148-b478d5af2921 |  | note | HP*
label | dec25b73-495c-5caa-a981-640f287b550b |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Bedding & Backfill Material
label | 62ed14ae-6013-589f-a5dc-b3e9a78cac3a |  | note | Frequency - Each Lot
label | 58b4dd78-db35-5bf6-b304-7190bdd4f441 |  | note | Acceptance Criteria - Backfill filter material - approved alternative, complying with VicRoads Section 702.
label | aa077d17-d9c5-5567-a42c-142505863e41 |  | note | Reference Documents - AECOM- MAPMP 2.0 Spec. Cl 8.4.2 Design Drawings
label | 25682e3a-a455-596d-b60b-dbf4b69f28c3 |  | note | Inspection/ Test Method - Verify
label | 7244b799-1c2e-59e6-96b5-8ee27eed68bf |  | note | Record of conformity - This ITP signed
label | 0b03a671-847d-55ad-8f00-768ef060c72e |  | note | HP*
label | c16df0f7-a77e-5bfa-a2c0-6e13618c115b |  | note | Responsibility - Project Engineer
checkpoint-group |  |  | section | 3. Excavation and Installation
checkpoint-status |  |  | checkpoint | 3.1 - Trench Excavation
label | 23194073-219c-564e-964f-6448fb697248 |  | note | Frequency - Each Lot
label | b3c07443-e9c5-501c-8031-b74ebf24a8b1 |  | note | Acceptance Criteria - Trenches excavated to dimensions and grades shown on design drawings. Excavation to allow for 100mm bedding material. The base of the trench shall be inspected to verify compliance with the requirements in this clause prior to placing bedding in completed excavations. Excavated material disposed per approved CEMP.
label | d1944bcf-28e3-5dfb-94f0-b5753780ff7c |  | note | HP: Base of trench inspected prior to placing bedding material
label | 59a87ee4-ef43-5f53-95a4-16c9c7562ef5 |  | note | Reference Documents - Drawings & AECOM – "MAPMP 2.0
label | 8b422297-646c-5036-ba32-d6b7e2b76b23 |  | note | Spec. Cl 8.5.3, 8.5.4, 8.5.5 & 8.5.7"
label | 9aec0526-a4fb-5872-876e-ded8cd8280af |  | note | Vic Roads 702.08
label | 12dfeb7e-fe71-5700-b880-5ee83b91eb9c |  | note | Inspection/ Test Method - Verify
label | 4338d00e-102a-568a-ad17-414863d53984 |  | note | Record of conformity - This ITP Signed
label | 6e83994b-a128-59df-a423-14efdfcc3d72 |  | note | HP
label | 6595edd1-ce7b-5dbd-8bf6-1b417e8c4a58 |  | note | Responsibility - Project Engineer / Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Bedding, Laying Pipes & Backfill
label | d2ed11b4-d7be-58eb-b425-66cf6ff2d059 |  | note | Frequency - Each Lot
label | d9540ec8-8a4b-5c65-858c-751b44f8132c |  | note | Acceptance Criteria - In accordance to the dimensions outlined in the drawings. Tolerances: +/- 50mm from specified line +/- 25mm from specified level Minimum Grade 1 in 250, unless approved or designed otherwise. Bedding to be tamped and screeded or graded to level.
label | 1b565ae0-2542-5f73-bd78-5d470666811d |  | note | Reference Documents - Drawings & AECOM – MAPMP 2.0 Spec. Cl 8.5.4 & 8.5.5 Vic Roads 702.03, 702.09
label | 336325ab-803a-50a9-91c6-d7dbd5c5d19b |  | note | Inspection/ Test Method - Visual Inspection
label | 48ec3f4b-e2a4-5c47-99c3-a14b1c24203b |  | note | Record of conformity - This ITP Signed
label | 21b735ef-7f7d-5eee-8f78-dffa3516fdac |  | note | HP
label | 88bc3b59-c230-58f2-8714-3e0499e5da10 |  | note | Responsibility - Project Engineer / Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Laying and Jointing of Pipes
label | 6d4f86ce-de6a-5360-b858-2317f3eefa2f |  | note | Frequency - Each Lot
label | bb96d8f9-4bf8-5e84-b204-9ddb5e725324 |  | note | Acceptance Criteria - Pipes laid at the depths and lines indicated on drawings.
label | 7367ed3a-2fae-50e1-9007-627997583b55 |  | note | Reference Documents - Drawings
label | 1850a5a0-4369-5c8e-996c-0321dfefd88e |  | note | Inspection/ Test Method - Visual Inspection
label | a6b7bf54-587a-586d-9468-71847a7457af |  | note | Record of conformity - This ITP Signed
label | fb6f9ed6-62cd-5e9c-a094-81af3d87929c |  | note | HP*
label | 1e94b7c5-bfb8-52b9-9488-7c1726ed382e |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Subsoil Drain Outlet
label | db97bb79-82cc-58f9-b541-43f958caa2f0 |  | note | Frequency - Each lot
label | f8c8b260-7666-50e0-9422-ee411b23ddb5 |  | note | Acceptance Criteria - Outlets from subsoil drains shall be constructed to discharge into stormwater drainage system.
label | 2a3b7cd8-896c-522d-8005-29bf0cd36bae |  | note | Reference Documents - AECOM – MAPMP 2.0 Spec. Cl 8.5.6
label | 7cda3f4f-dac1-5fe7-a6ea-772590689dd1 |  | note | Inspection/ Test Method - Verify
label | dcfa8aa1-bf50-5039-b62c-8c81b2cd43ee |  | note | Record of conformity - This ITP Signed
label | 2b0397c8-2e90-51ed-b003-276d2600e77c |  | note | HP*
label | 8531e4db-5e90-5a82-90d4-566bdcf8ce1e |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 3.5 - Flush out risers
label | c085b5e2-cda3-53a6-8375-13ac5d21808b |  | note | Frequency - Each Lot
label | 7e17ee1f-082f-5df2-9223-c7e0142de366 |  | note | Acceptance Criteria - To be the same diameter as the subsoil pipe and be installed in locations indicated on the drawings.
label | 71a25b99-0e42-57f2-aace-0d0303ef0396 |  | note | Reference Documents - Drawings & Vic Roads 702.10
label | 47f6d33e-bf99-5243-abee-1dc950f03749 |  | note | Inspection/ Test Method - Visual Inspection
label | a4a60bd6-1095-5f6c-9e1c-f76389380ee6 |  | note | Record of conformity - This ITP Signed
label | 2826828f-7a03-576e-9c2f-84dfa7d62647 |  | note | HP*
label | 2ede5a57-3f10-5db4-a648-3a2e925e9ad5 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Flushing Test
label | 86194e5d-fa26-52dd-9432-9b70ea8e25e6 |  | note | Frequency - Each Lot
label | 8d1ee07c-02ea-53c6-a536-4e105934a014 |  | note | Acceptance Criteria - A flushing test shall be carried out on each subsurface drainage line after completion of subsurface drains, flushers and outlets. The test shall be witnessed by the Principal’s representative.
label | 479a4cf2-95ac-5cec-9e28-fbe14683478d |  | note | Reference Documents - Drawings & Vic Roads 702.09
label | 5682edbb-896b-511a-b604-c8bf17ff8dd3 |  | note | Inspection/ Test Method - Visual Inspection
label | 689412b3-5d1b-5839-9101-c1e4a640d89c |  | note | Record of conformity - This ITP Signed
label | 375a87ba-fe71-529e-8bea-796531e8a69c |  | note | WP
label | b4c6cfd4-f065-5216-9a78-114d2541da1a |  | note | Responsibility - Project Engineer / Principal’s Representative
checkpoint-group |  |  | section | 4. Post Construction
checkpoint-status |  |  | checkpoint | 4.1 - Records
label | 7f46220c-2c64-558d-94a7-b03efcae8388 |  | note | Frequency - Each Lot
label | 1d97d353-2260-567d-8336-7f28071d72cd |  | note | Acceptance Criteria - Levels and alignment recorded in as built documentation and provided to superintendent.
label | 064bb156-4185-582b-8f00-e6779bceee8d |  | note | Reference Documents - Vic Roads 702.03
label | b1f8dd07-f351-55cf-97a0-718b65b4c569 |  | note | Inspection/ Test Method - Inspection
label | 32cf3a7e-c3b4-5c55-8ff8-131dac998d06 |  | note | Record of conformity - Aconex Correspond ence
label | 849d96ba-3a9a-5caf-ae07-88b456ae7b60 |  | note | SCP
label | 6fa0c136-8058-58d5-8169-77b48c050265 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 48abf1b3-2720-5940-a07e-c4d48607bc98 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8a527336-437b-50d4-b052-40d71833d66b |  | textbox | Name:
text | 92fad45b-70e9-5976-bb60-6274d2634f41 |  | textbox | Position:
text | 05abea65-5051-55e5-bc9a-b875c8d49e5d |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP021-4B – New Foundation Works – Installation | itp |  |  |  | Yes | ITP021-4B – New Foundation Works – Installation | 834406bf-1910-458d-9a5a-d996ac4e7161
checkpoint-group |  |  | section | 1. Re-installs
checkpoint-status |  |  | checkpoint | 1.1 - Preparation for the works to be undertaken
label | 9ec0508b-7a26-5460-91ec-90bc0a8979b7 |  | note | Frequency - Prior to Start
label | 494e8445-50f3-592a-96ad-eaa2cd19fc71 |  | note | Acceptance Criteria - Resurvey light position and aiming points.
label | 02ba1458-bcb8-556e-9351-bce7c17ac4d1 |  | note | Reference Documents - Drawing sets:
label | e661beaf-29b3-5e86-a0ee-e6a5704c8199 |  | note | • 60692389- SHT-01_1-10
label | 0b6460ec-f272-58ac-9c5d-49a3e48608a4 |  | note | • 60692389- SHT-01_2-10
label | 1d87aeed-50b3-5e95-9b14-9255d0754e93 |  | note | • Specification: 60692389-PS-01-AV-0001
label | 8a956f82-d778-5c4b-9743-3d385f3ac5bd |  | note | Inspection/ Test Method - Verify
label | aef3b3d3-15ff-5cb3-9c44-ea363f6d0ec2 |  | note | Record of conformity - This ITP Signed / Avionics CL004B
label | 4e6135d0-b57d-5722-b8cf-3769b8368ac5 |  | note | HP*
label | bf37f103-654b-58fa-ab15-26126d40a566 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.2 - Core and inspect
label | d7b5541e-6fa4-53ec-968c-d472a101e918 |  | note | Frequency - Each Lot
label | a4827a9d-461b-5cd7-b062-1569b7b8249d |  | note | Acceptance Criteria - Core to depth of new foundation.
label | 681eaf66-7e60-5f1b-a572-5a2e473252bb |  | note | Reference Documents - Drawing sets:
label | 90569a6d-7348-5df2-b48d-59690309151b |  | note | • 60692389- SHT-01_1-10
label | 0562a0f6-13cd-5daa-a1fe-87c4d5835094 |  | note | • 60692389- SHT-01_2-10
label | eb5ea336-4650-552c-822d-3ff786f7fa7f |  | note | • Specification: 60692389-PS-01-AV-0001
label | 1107928e-b25e-53c5-9ccc-5136a26c41e8 |  | note | Inspection/ Test Method - Verify
label | 76c17acc-6184-5a50-bd6a-05218e80fdd1 |  | note | Record of conformity - This ITP Signed / Avionics CL004B
label | 64644ce1-006c-5597-b7e5-4e602f0c0e7f |  | note | IP
label | ba168a4d-1ab6-5f6b-9faf-21b0b263cfc6 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.3 - Installation of new can
label | 5427e444-7fa2-5599-a2e2-8e4528eee0a6 |  | note | Frequency - Each Lot
label | e503d7d8-0e62-55d4-81ff-d96474c0451b |  | note | Acceptance Criteria - New can mounted on positioning jig. Jig/can positioned, levelled, aligned. Spacers positioned and conduits checked for clearance. Epoxy poured.
label | c0bdbe2f-de2b-5dbe-b4f9-c9746f0fb35f |  | note | Reference Documents - Drawing sets:
label | a5c82c3f-c42c-5769-ade2-dc092b25c633 |  | note | • 60692389- SHT-01_1-10
label | 7435a913-8cf8-521e-a7c5-9dddfaccf5c9 |  | note | • 60692389- SHT-01_2-10
label | ab80029c-d466-5669-a91b-f542a7e17899 |  | note | • Specification: 60692389-PS-01-AV-0001
label | 76c4303e-9938-5656-97b1-d6643f64be2b |  | note | Inspection/ Test Method - Verify
label | 750317bc-93db-5bd2-880e-1b1a4c9b1065 |  | note | Record of conformity - This ITP Signed / Avionics CL004B
label | b41385f3-60c5-5435-a205-854873640fa9 |  | note | IP
label | 503e5da8-0444-562a-bf2a-05b9eeb6418a |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.4 - Reinstallation of light
label | fa9967fa-3403-50f6-87be-41960adbcc91 |  | note | Frequency - Each Lot
label | 9ceddfba-ce89-5152-a773-c87703028e89 |  | note | Acceptance Criteria - Foundation hole cleaned and existing light to be positioned, identified.
label | a61437cd-90f4-5c91-81db-297327054be9 |  | note | • Light plugged back in and positioned. New bolts installed with required torque.
label | f01cc9c7-ff7b-520d-b6cf-08eb891a0c15 |  | note | Reference Documents - Drawing sets:
label | 91eeb0ec-88ba-5e29-b69b-9443f1a93958 |  | note | • 60692389- SHT-01_1-10
label | 978ae198-b43e-59ba-990e-7dde196d9584 |  | note | • 60692389- SHT-01_2-10
label | eec53f6f-8145-5d70-93b4-3bbf6c9a0f86 |  | note | • Specification: 60692389-PS-01-AV-0001
label | 96abb3e5-b166-56b6-b23d-7c19f41203d1 |  | note | Inspection/ Test Method - Verify
label | 55495033-06e3-56e7-ba96-d36f1afa6cb4 |  | note | Record of conformity - This ITP Signed / Avionics CL004B
label | 7c1a0127-7c45-5a46-9b9d-d95e6f26dba8 |  | note | IP
label | fe02ab65-2b36-51af-8fca-1e3101ace399 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.5 - Finishing, demobilisation and testing
label | 72c64959-5b86-5789-bd38-143888e825ca |  | note | Frequency - Each Lot
label | f8287440-7aa6-5fbd-97ee-40fb2b9ab1e3 |  | note | Acceptance Criteria - Pavement area cleaned and equipment packed away. Work crews demobilised and FOD walk undertaken. Light tested once circuit re-energised.
label | 4cf420d7-e683-59f7-a6a9-ea1103470dea |  | note | Reference Documents - Drawing sets:
label | 90d79c87-ede9-595c-a337-4223b00c9ac9 |  | note | • 60692389- SHT-01_1-10
label | 140a84ae-5f3c-57f5-a8ee-90fbf7632c12 |  | note | • 60692389- SHT-01_2-10
label | e279e7ad-ed54-5cca-855a-11717fef5034 |  | note | • Specification: 60692389-PS-01-AV-0001
label | 4a7dcc8f-c998-5dcc-8a62-69a18d884716 |  | note | Inspection/ Test Method - Verify
label | 97ba94fe-7272-5f59-bf40-f0b9903601d9 |  | note | Record of conformity - This ITP Signed / Avionics CL004B
label | f13a4eaa-7354-5741-ad71-2101025e7694 |  | note | IP
label | 9dc68024-1985-5de5-a4e4-1f22aabeab0b |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | Final Inspection
label | 3cfae073-e1f4-54cf-af43-5f67f1247029 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 0d7f55a4-5fc9-5b1a-a198-2fe56bbe5a80 |  | textbox | Name:
text | a7e72102-a916-5e60-9396-91218f635a29 |  | textbox | Position:
text | 664f4287-dffb-5ded-8b99-18dfaf836adf |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP002B - Crushed Rock Basecourse | itp |  |  |  | Yes | ITP002B - Crushed Rock Basecourse | 9a969d26-55ea-4497-b049-3a251fc088b0
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | 75763acd-c41a-54b1-b6d5-892feea78101 |  | note | Frequency - Prior to works
label | 585abae7-04b3-52f8-bae2-29c2ba277b2d |  | note | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Principal’s Representative
label | 21f9a8a8-13aa-5c73-b076-e34edaa67766 |  | note | Reference Documents - ACONEX
label | cad0e7cb-050b-52e4-a680-dbb753ae30ad |  | note | Inspection/ Test Method - Visual Inspection
label | f7fd0195-3722-591a-898e-c180b9ce23e6 |  | note | Record of conformity - Current drawings
label | 331feced-7d42-5128-82e4-a31ea83792f5 |  | note | HP*
label | d365fd3c-8f41-56a4-a003-5b17f0cec1a2 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Material Submission & Approval
label | defc7e58-ec5a-5d4a-a79c-bd187f78bba8 |  | note | Frequency - Prior to commencing works
label | d1133443-2663-5106-8fd3-84494068a9ee |  | note | Acceptance Criteria - At least seven (7) working days prior to the delivery of the Class 1 Crushed Rock the Contractor is to provide the following for review and approval;
label | 9ecad806-7e67-54c5-b500-5750ffb336b7 |  | note | • Grading Curve
label | ab36aa1b-846c-5de4-848c-0f3217a307d4 |  | note | • Atterbergs Limits
label | 0d317ced-974e-5024-8be5-5f329acfe1a9 |  | note | • CBR
label | ea17c212-3e9b-5a83-a135-f15d1df26a31 |  | note | • MDD
label | d484bd19-5e59-5240-85a2-628bb66ef407 |  | note | ○ Once approval has been received the Contractor is to obtain one reference sample weighing 50kg and which is to be kept on site.
label | bd226843-d188-5641-aeae-46eb1bcafc3e |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.4.1.2 & Cl.6.4.1.3
label | b7b61ad6-fd7f-5464-8847-dbcab51313da |  | note | Inspection/ Test Method - Verify
label | 3487fae2-a82c-5b14-b329-a6c4507799ac |  | note | Record of conformity - Aconex Reference
label | 75657c04-197a-566f-a162-7eeedc4d2f7b |  | note | HP
label | 67c5c409-091f-5bd6-a657-a152d0725530 |  | note | Responsibility - Project Engineer, AECOM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Production Testing
label | 4ee517fd-ae4a-5adf-8259-7c2f40848c6b |  | note | Frequency - Prior to commencing works
label | 6d56c227-7259-5eea-94b4-d23a3a68d292 |  | note | Acceptance Criteria - Supply information with respect to production testing, to requirements in VicRoads Section 812.
label | 97e2a503-8fff-532f-bf1c-b27948f40d3f |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.6.1 & VicRoads section 812
label | d7c1cd76-eb09-5b65-9f53-86da3897ed5f |  | note | Inspection/ Test Method - Verify
label | e1a0600e-e0f2-58a2-bf99-e879dfa2c0e1 |  | note | Record of conformity - Approved production testing results
label | 968b63b2-d78c-57c8-ba32-31b44ee147bc |  | note | TP
label | 0c94a056-94c1-5ddf-9515-7f82d4578c50 |  | note | Responsibility - Project Engineer, Principal’s Design Representative
checkpoint-status |  |  | checkpoint | 1.4 - Implementation of all measures and controls.
label | 67e71f01-0366-5cec-bf56-677e25492d7b |  | note | Frequency - Prior to commencing works
label | 6065ef5b-16e1-5854-98a5-65faeae3ddae |  | note | Acceptance Criteria - All necessary measures and controls are being implemented including: PSP, EMP, TMP, SWMS and WP.
label | 37c78d8d-6b77-5ddf-8bed-7d1beb4d1852 |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | 73084a8d-edc2-51b2-aaf7-8055808b0f05 |  | note | Inspection/ Test Method - Visual inspection
label | 0226c1cd-c079-5a45-a7bd-3e84b81aee5b |  | note | Record of conformity - Site inspection
label | 372c84cb-82d8-559d-95df-888944f3e8e8 |  | note | HP*
label | 01ac9c94-3be8-5b0e-b4e4-bbf3c0b1a159 |  | note | Responsibility - Project Engineer
checkpoint-group |  |  | section | 2. Construction
checkpoint-status |  |  | checkpoint | 2.1 - Placing Crushed Rock
label | 0e84a207-335f-5843-addb-82e10c12f3b8 |  | note | Frequency - Each Lot
label | 69389381-2781-50eb-9d7d-145407be393c |  | note | Acceptance Criteria - The crushed rock base course is to be placed in 2 equal layers. The Contractor shall supply survey reports prior to the placement of prime coat or primerseal.
label | 9f736218-4a4b-510a-9529-72ba7531f29a |  | note | • The levels must be checked in a 5m square grid on the finished surface level and shall not deviate more than +0,10mm.
label | 5a9a0d27-423d-59f9-b0c7-c90f3a9a87b6 |  | note | • The levels shall be recorded in a .TXT format with the relevant points displayed in a PDF file.
label | 6a4fdc7a-0845-5c80-9c77-bfca0598098f |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.5.2.1 & Cl.6.5.2.5
label | 0268be74-b467-56f6-95b9-b214fafd6748 |  | note | Inspection/ Test Method - Visual Inspection
label | e3a3d8e5-5c32-5248-9367-e4abc291784c |  | note | Record of conformity - Survey Report and Visual Inspection
label | 1a22a5c1-4a90-5b89-a057-137851d6efad |  | note | HP*
label | e0e5957f-5b8d-50bd-856e-c9f37c547f3b |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Proof Rolling
label | 0a5f6c2e-55c0-5ec7-b45c-45fb2b45e2e7 |  | note | Frequency - Each Lot
label | 8c75e84a-f6a5-5222-9400-c7ff7b429cab |  | note | Acceptance Criteria - Proof rolling will occur upon the completion of compaction.
label | c49d7020-d561-556c-9324-13141b5655e6 |  | note | • The proof roll will be conducted in a systematic manner such that the entire area is covered uniformly.
label | fbe65308-1375-52c5-b8ec-ec70fc863e3b |  | note | • Only the top layer of the crushed rock basecourse is subject to proof rolling. Proof rolling to be undertaken with a multi wheel roller.
label | f066e6fd-b9ae-55c6-93ee-d559dee65dc3 |  | note | • The plant must travel at a speed no greater than 6km/hr.
label | 11ef8c6c-720f-5155-88b4-efeff58b9c4a |  | note | • Contractor shall notify the Principal’s Design Consultant so that they are present for the entire duration of proof rolling.
label | c8b698ca-a117-517d-9bfc-531b9f523198 |  | note | • Proof rolling shall be undertaken with the pneumatic tyred roller or watercart.
label | 021fd9e4-8fff-5164-84d0-104cf778a073 |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.5.1.2.1
label | a2ec46e0-af1c-5fa8-a2af-a0bcdff0ae4d |  | note | Inspection/ Test Method - Visual Inspection
label | 725447a7-e751-55c7-a553-6d088bfcbd21 |  | note | Record of conformity - This ITP Signed
label | 0e43e075-d5b0-536d-855e-50b332dbd56d |  | note | WP
label | 35b62db2-c758-56d6-aecc-efdd2e2595a1 |  | note | Responsibility - Project Engineer, Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 2.3 - Identification and treatment of unsuitable areas.
label | a07c03a3-8729-5538-83f8-49e7cdd4cad4 |  | note | Frequency - Each Lot
label | 3e38fe69-5279-5406-b0fc-47992ef4ccce |  | note | Acceptance Criteria - Should any area of crushed rock be disturbed or become unstable during proof rolling, the Principal’s Representative should be advised immediately and proof rolling of the area ceased.
label | b9609656-eb2e-55e0-a3a9-ea1753ebe38b |  | note | • Any areas of crushed rock layer that rut, yield or become unstable under the proof rolling must be investigated in the presence of the Principal’s Representative.
label | f24b425d-e6f4-57b3-ab26-a566ca670674 |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.5.1.2.1
label | 4a0e55d7-5a0c-5a14-9671-38e729a1efb9 |  | note | Inspection/ Test Method - Visual Inspection
label | 28dd6a1a-6fc9-58c1-b273-1b14d40bdc21 |  | note | Record of conformity - Visual Inspection
label | 9402bf04-91e0-5d30-8582-b928bb79a16c |  | note | HP*
label | 0147e11f-6eb4-52f8-a534-f2b77367a62f |  | note | Responsibility - Project Engineer, Principals Design Representative
checkpoint-status |  |  | checkpoint | 2.4 - Submission of Proof Roll Report
label | 49de4434-a802-54fe-8c37-84f31d0e6407 |  | note | Frequency - Each Lot
label | 3adddda7-a5e7-598c-8ae6-8ee3d6c47e70 |  | note | Acceptance Criteria - A Proof roll report must be submitted to the Contract Administrator and Principal’s Design Consultant for review.
label | a7fcfe94-0255-588e-bb5f-d54b4a99923b |  | note | • The hold point is released by the Contract Administrator or Principal’s Design Consultant after review and written approval of the proof rolling report.
label | b454af40-594e-5c08-937d-b057e1ff56cd |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.5.1.2.3
label | 8157e084-91ea-5a29-85dd-9a797eba8c85 |  | note | Inspection/ Test Method - Proof Roll Report
label | 75b87d67-f03e-5764-8521-148ae017364e |  | note | Record of conformity - Aconex
label | 264bb03c-0c3f-5d9d-ac9c-838e146653e4 |  | note | HP
label | 679fb2bb-a72f-5bdc-924a-d81138e84045 |  | note | Responsibility - Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Compaction Testing Report
label | 265b8e12-0925-5826-8b7a-e9c01259a2cb |  | note | Frequency - Each Lot
label | ce000869-dfa9-56b7-a63e-4409b459a7e7 |  | note | Acceptance Criteria - Submission of the compaction report shall be submitted to the Contract Administrator for review. The report is to include:
label | 8d751f55-ea23-5a16-94a9-527781e4e700 |  | note | • Details of the Lot being tested
label | 3a168984-199a-5f95-90bb-54f4b3148540 |  | note | • Test certificates (field density, MMDD)
label | 0f5a9c3b-646d-58f1-8ecd-ca472de0a141 |  | note | • Dry density ratio (characteristic and average)
label | 3355a456-0079-597d-a051-6a5fa307cfa2 |  | note | • Compliance or non-complaince of the lot
label | 77ae1673-6f8b-5336-83a5-844b3438b0b3 |  | note | • Rectification actions and outcome in case of non-conforming compaction
label | 869f064b-13aa-5f5c-a56c-5cb45b3f61da |  | note | ○ When minimum field density testing frequency is 6 per lot or greater:
label | 2d0037be-ab4d-5dcf-a576-e18cd91003bc |  | note | • Character dry density ratio ≥98% modified compaction
label | e6d3c2da-49e4-5fdc-a342-4d31cc78b19e |  | note | ○ When minimum field density testing frequency is less than 6 per lot:
label | 2590243c-5518-558b-bd17-5810150a0bec |  | note | • Average dry density ratio ≥98% modified compaction
label | 1f4d4d98-44c1-5994-922e-238a86a80a92 |  | note | Testing Frequency:
label | 61be3ed3-8c2a-5e4e-911a-a80422d312b3 |  | note | • Up to 800 m2 Min 4
label | f25171aa-fd83-51c3-8b05-5647f706f64c |  | note | • 801 m2 to 3,000 m2 Min 6
label | 71e498c7-4e20-5ba6-9199-f807d8d8a804 |  | note | • More than 3000 m2 Minimum of one (1) test per 500 m2 or part thereof
label | 9bafd915-5f28-5d06-9a32-9b84f607d0d4 |  | note | ○ Hold point released after review and written confirmation of the compaction report being received.
label | 2742baa5-b1d2-5b8d-a54d-5dd7e926b9fe |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.6.2.5
label | e64d1e39-22f5-50a7-8ced-9afd932fde46 |  | note | Inspection/ Test Method - Testing
label | b1cba137-7f3f-5e2e-89eb-689d331e52cc |  | note | Record of conformity - Compaction Testing Report & This signed ITP
label | e9b52d9c-b2e5-5c37-9c4e-e2adea1a244c |  | note | HP
label | 480e0998-8340-5b20-8534-1a62050f6e17 |  | note | Responsibility - Project Engineer, Contract Administrator
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Smoothness Testing
label | ec74f112-7090-57af-82e4-ac2cc2f1749b |  | note | Frequency - Each Lot
label | 97ad973d-f20b-5d00-b14d-c3ee1584f852 |  | note | Acceptance Criteria - Submission of the smoothness testing report is to be submitted to the contractor within seven (7) days of completion of the crushed rock lot.
label | 8a7f00b3-efa0-5a87-a35c-2c5e39693d47 |  | note | • Surface smoothness shall be undertaken using 3.5m straight edge that is either hand held or mobile.
label | 799668c5-f3e3-5100-b004-812439fe6cda |  | note | ○ The straight edge shall be operated along:
label | 4b7e0702-a709-5def-a911-7a9801236a84 |  | note | • A set of parallel lines not more than 10m apart covering the whole surface and on another set of parallel lines not more than 10m apart that are perpendicular to the first set. The surface of the crushed rock basecourse shall not deviate from the 3.5m long straight edge by more than 7mm, except in directions of where a grade change occurs.
label | 30eb9d3e-5eef-5ee7-a000-1358ed6cfe8c |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.5.2.2
label | 84dcd019-b194-5d0e-8b1d-607cecccf126 |  | note | Inspection/ Test Method - Visual Inspection
label | 2fc9bcfa-54a2-5393-afa6-d7a4bdf86f48 |  | note | Record of conformity - Straight Edge Report & This signed ITP
label | 0ac608f3-1c51-5ff4-9691-fb5ddbb8ca1e |  | note | HP
label | 76361d58-0af4-5c5e-ae04-b7fb805fd014 |  | note | Responsibility - Project Engineer, Contract Administrator
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 645fe97d-0889-54c1-a217-314437c9085b |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
text | beecdfb9-cbd1-5c64-9631-c1a2fb74f2fa |  | textbox | Name:
text | 52c10e39-e2b3-5db9-b6df-5702370743d2 |  | textbox | Position:
text | 55c7da03-58e6-5aca-856d-f1b48e5a7e6e |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP021-1 – Demolition and Isolation | itp |  |  |  | Yes | ITP021-1 – Demolition and Isolation | ad9ef77d-baf6-4d27-835c-3a013c84c866
checkpoint-group |  |  | section | 1. Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Preparation for the Works to be Undertaken
label | 387f5a41-384a-55fc-be1a-e3ce4b0e8026 |  | note | Frequency - Prior to Start
label | 8512ab75-c139-5341-bcf2-8e7ace95075d |  | note | Acceptance Criteria - Notify the Airport’s Engineering personnel at least two days prior to removing the works area from service and prior to returning the works area to service.
label | 80f8342a-7b3d-594a-9147-0de2f970883d |  | note | Reference Documents - Drawing sets:
label | 40e412b0-790d-5db4-becd-042640509244 |  | note | • 60692389- SHT-01_1-10
label | 7a3e38d2-c75a-5b29-af80-c413408a5171 |  | note | • 60692389- SHT-01_2-10
label | 2139891d-9120-5f9e-b6d1-00a07623efbb |  | note | Inspection/ Test Method - Verify
label | bbbf0585-5d6d-5c94-84ec-2577da0673a9 |  | note | Record of conformity - This ITP Signed / Aconex
label | 4a0f0c5f-64c4-5f19-bb57-5d2ee857c290 |  | note | HP*
label | 993ee621-5492-5dd8-9138-5e3d39ccf0cd |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - AGL Continuity of Service
label | ed4a47af-06fc-569f-8977-956e229e6e36 |  | note | Frequency - Prior to Start
label | 0046a875-b91f-5a28-b00e-1e0c9841187e |  | note | Acceptance Criteria - Ensure the continuity of service of the AGL facilities is maintained while undertaking the works.
label | 347ce85f-f10d-5435-9fbe-3480c96b6af6 |  | note | • No outages of any facilities shall be permitted unless prior approval has been received by the Contractor from the Contract Administrator.
label | 2d9ce5e0-2274-5683-bf7d-4e4e2501de21 |  | note | Reference Documents - Drawing sets:
label | cf56df2e-f037-5017-a3c9-012f401ef467 |  | note | • 60692389- SHT-01_1-10
label | 6f1b834a-afc3-51dd-ab9c-fc09258f906e |  | note | • 60692389- SHT-01_2-10
label | a73861ab-8563-5ed7-8a67-c887b174a620 |  | note | Inspection/ Test Method - Verify
label | 324c4b3d-5889-5f36-920f-71263cb4e889 |  | note | Record of conformity - This ITP Signed
label | a6d06324-f6bf-55fb-b3cb-3065d9dfb551 |  | note | HP*
label | 6b6ca3d7-2292-5d94-87f5-60b35474100e |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.3 - Check for correct documentation
label | 93ff5929-c854-56e1-b92d-99db66ac99b6 |  | note | Frequency - Prior to commencing any activity
label | 74d7bcf0-5bba-5acf-8a54-48e6ffeed14b |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | e970d41f-5510-5217-a4c8-12f5c9defb18 |  | note | Reference Documents - IFC Drawings
label | b875be50-7c25-52e2-8f8e-8154ff5b67e5 |  | note | Inspection/ Test Method - Verify
label | 1716ff81-14c3-5ff3-bb3b-69a494fdf722 |  | note | Record of conformity - This ITP Signed
label | 44cfebec-5d91-5b9d-9cd1-3140d13c2bdc |  | note | HP*
label | 95d882dc-a439-593c-88a7-823ac3d7fc1e |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.4 - Implementation of all measures and controls
label | 93320373-3053-58b4-b7b6-932f8e0e2173 |  | note | Frequency - Prior to commencing any activities
label | 931c29a9-fde6-59e0-97ef-62f243e900ae |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | 193aa33d-13a4-5d10-867a-34ae5e4b1774 |  | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | 82c03cec-33d1-5ae5-86a5-0a0518776d30 |  | note | Inspection/ Test Method - Verify
label | b1fa07dd-a009-5271-b51c-f9f3068831aa |  | note | Record of conformity - Site and Office Inspection
label | 8f84808d-c8b1-512b-9dfa-c6263facf7c5 |  | note | HP*
label | fc52f2e2-a658-58d3-8375-90c47fb2048e |  | note | Responsibility - Project Engineer / Site Supervisor
checkpoint-group |  |  | section | 2. Demolition and Isolation Works
checkpoint-status |  |  | checkpoint | 2.1 - Investigation, Location, Identification, Protection, Modification, Isolation, Extension or Relocation of Existing Features
label | b1eb78d0-dff1-57ad-9088-8d9906e26c5d |  | note | Frequency - Prior to commencing demolition works
label | 9a6bd9d3-6963-5b1f-a54a-0768985d39d7 |  | note | Acceptance Criteria - The Contractor must:
label | ebac65cb-3188-551e-b666-a2f4068851b4 |  | note | a. investigate and locate both above ground level features and below ground services that may be affected during the performance of the Work under the Contract;
label | 685737d1-e400-5ed4-94a5-72b050f3d30f |  | note | b. identify, protect, modify, extend or relocate existing features, services or facilities as necessary for the performance of the Work under the Contract to the satisfaction of the Principal and other relevant authorities;
label | a84bee71-4452-5ed4-b280-67a7d983f064 |  | note | Reference Documents - IFC Drawings
label | 5ba7f1ef-a92c-585a-82f8-702329625c18 |  | note | Inspection/ Test Method - Verify
label | 18053d84-9635-5308-95b3-f309aa98aeff |  | note | Record of conformity - This ITP signed / Avionics CL001-1, CL001-2, CL001-3
label | 05e58540-f88b-5b34-bfce-8982338c80ee |  | note | IP
label | 133e8b70-d4c7-55d9-b3f4-4e35d5b530af |  | note | Responsibility - Project Engineer/Avion ics
checkpoint-status |  |  | checkpoint | 2.2 - Demolition and/or removal of AGL
label | c35b39df-3789-5d50-85f9-5fbbc2db6628 |  | note | Frequency - Each Lot
label | 06d92eb4-1cb2-5c8d-bc52-00f82b2a5ff1 |  | note | Acceptance Criteria - Prior to any pavement overlay works, all light fittings and shallow bases impacted by the pavement reconstruction works shall be removed. The shallow bases shall be removed by neatly saw cutting a hole in the pavement slightly larger than the outside diameter of the light base.
label | 05e104f0-e338-5110-8dbc-d920f3c219d9 |  | note | Reference Documents - IFC Drawings
label | 774a92bc-1d9d-5999-aa23-7d746de8953c |  | note | Inspection/ Test Method - Verify
label | a8e450c5-74cc-5e36-9d0e-3d7f924e4302 |  | note | Record of conformity - This ITP signed / Avionics CL001-1, CL001-2, CL001-3
label | 5c92fb0e-c1ec-5845-92fa-5f0da2d3e4bc |  | note | IP
label | 5a9221fb-c981-59c4-93ac-ce61f3623ca3 |  | note | Responsibility - Project Engineer/Avion ics
checkpoint-status |  |  | checkpoint | Final Inspection
label | 99f7c5a1-9460-5a19-9ac9-61819a22e1c8 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 1debd9ab-681f-5d73-8ed2-43b7a25e4f40 |  | textbox | Name:
text | 2ead918a-3f3a-56b3-a048-df204623898b |  | textbox | Position:
text | fd8076fa-8729-55ce-8738-0b4c5df766f9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP021-4A – New Foundation Works – Removal | itp |  |  |  | Yes | ITP021-4A – New Foundation Works – Removal | bac453aa-ef9f-402a-86bf-44cd5f8d0f69
checkpoint-group |  |  | section | 1. Removals
checkpoint-status |  |  | checkpoint | 1.1 - Preparation for the works to be undertaken
label | 9b1f094a-6484-5512-b42c-c2b7b50bff28 |  | note | Frequency - Prior to Start
label | 22057c2d-63a2-5b7b-a3bc-c2d28b8eb753 |  | note | Acceptance Criteria - Ensure survey set out is undergone, excavation permit obtained and (if required) services in work(s) area isolated. Dilapidation survey.
label | d847bf86-7517-51ca-8b02-ac3e6fa855c3 |  | note | Reference Documents - Drawing sets:
label | 2d349ecd-f7ca-55ff-8a75-dadf91ff1f89 |  | note | • 60692389- SHT-01_1- 10
label | 1dff0fea-91a3-5abc-8955-b31de1d8992e |  | note | • 60692389- SHT-01_2- 10
label | aebb0b5a-d5bb-5b3a-90aa-0109e2971db5 |  | note | • Specification: 60692389-PS-01-AV-0001
label | 9a8f9a9e-8964-5559-8655-3823634e264a |  | note | Inspection/ Test Method - Verify
label | 99119b03-59ae-5eee-9d80-15c9e535b26b |  | note | Record of conformity - This ITP Signed / Avionics CL004A
label | dca9d378-3226-511c-9706-5cd069b46506 |  | note | HP*
label | f4235298-f73b-5c71-b5fa-dd2bc7060946 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.2 - Core and inspect
label | 6058dccd-794d-5c76-bd23-23ce7d8d31fb |  | note | Frequency - Each Lot
label | 93c69a91-5537-5109-819b-0bfe18dc6c45 |  | note | Acceptance Criteria - Light base cored into pavement and slot from base cut to pavement edge/expansion joint. Based removed and cleaned. Inspection to determine works method.
label | 5a57110a-c99f-54c3-bfbe-98c06e952686 |  | note | Reference Documents - Drawing sets:
label | 32383ddb-fdc8-5cd0-ba3a-d97cdb287dd2 |  | note | • 60692389- SHT-01_1-10
label | 48b7218c-8e0c-5e4f-a7c9-6888ffeffc6a |  | note | • 60692389- SHT-01_2-10
label | 4fe265a0-b7a1-5dc9-87bc-886e0382a6ba |  | note | • Specification: 60692389-PS-01-AV-0001
label | aaa1c9b3-5811-5984-94e2-ca90a7e86fbd |  | note | Inspection/ Test Method - Verify
label | 08511548-5618-5a12-82f9-6a87e5d8fbca |  | note | Record of conformity - This ITP Signed / Avionics CL004A
label | c8089bcd-055c-5082-af2c-9d78325cdc93 |  | note | IP
label | 9b378fad-2946-5a1e-a750-2b9da2716bf2 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.3 - ‘Method 2’ installation (SP1 only)
label | dfd55abe-ded0-538c-8fc7-e52f306682a0 |  | note | Frequency - Each Lot
label | 58ec732b-e859-5c48-bd51-bfdf982858f3 |  | note | Acceptance Criteria - Continue core to depth of basecourse.
label | d00afeda-c4fc-54dc-9773-207aeb40fc39 |  | note | • Reconnect conduits.
label | 22e95486-f6b0-5645-8233-426ecc157b9e |  | note | • Concrete poured to correct level and cover.
label | a35f7a55-0390-59dc-a4f4-4a853a68196e |  | note | • Spacers positioned and conduits/cabled cleaned.
label | 5bf81276-cbe2-5286-bd7a-813a9af3fb9f |  | note | • Mesh laid and rapid-set concrete poured.
label | da2abcd2-ad02-5ba8-a323-c7b189ffc6b4 |  | note | Reference Documents - Drawing sets:
label | 07d4b284-808a-5e1d-b2f7-65629672d57c |  | note | • 60692389- SHT-01_1- 10
label | ed8be1ff-9705-526d-a855-37fae3fdbca5 |  | note | • Specification: 60692389- PS-01-AV- 0001
label | 92794d88-2a8c-5e36-b3c5-1c02f08bbf0e |  | note | Inspection/ Test Method - Verify
label | ce10312d-2871-5b72-a152-bce9a29031e8 |  | note | Record of conformity - This ITP Signed / Avionics CL004A
label | 7d26e48b-a214-5a76-886a-7b3c89fffdf8 |  | note | IP
label | 20b03156-b758-58ff-97eb-8408232f686e |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.4 - Finishing and demobilisation
label | 2e772fbb-54d0-5021-a186-a5baf3e5522f |  | note | Frequency - Each Lot
label | d02200a4-5da6-5728-998d-5c548d305041 |  | note | Acceptance Criteria - Pavement area cleaned and equipment packed away. Work crews demobilised and FOD walk undertaken.
label | bce22c31-9749-580a-87f7-e0a236fdd304 |  | note | Reference Documents - Drawing sets:
label | ffd423f9-eb0c-55b6-906b-39b63a87c9ca |  | note | • 60692389- SHT-01_1-10
label | 2afb55e9-ea9e-50a5-b035-364383819dac |  | note | • 60692389- SHT-01_2-10
label | 33fbc54d-74db-5a07-92ba-c3b50c8a9776 |  | note | • Specification: 60692389-PS-01-AV-0001
label | 70a6c7dc-8feb-5452-9b32-f60ebcb0cdc1 |  | note | Inspection/ Test Method - Verify
label | c011ea6d-2553-580c-9312-1d9accc04191 |  | note | Record of conformity - This ITP Signed / Avionics CL004A
label | e06c53de-21f1-5001-9e01-9884734768e6 |  | note | IP
label | 36f74c54-d0ae-57f9-b9ba-df857abc1348 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | Final Inspection
label | fffaa5b7-89c2-5149-9ff9-be150cd20f32 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 465a37ac-532e-5248-8fe7-c067b296c1cc |  | textbox | Name:
text | 84b6d98e-d33c-5537-a093-355212f89ad5 |  | textbox | Position:
text | e8346b50-6a54-5b3d-bd77-bb329218c2bc |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP022 – Native Grass Protection |  |  |  |  | Yes | ITP022 – Native Grass Protection | bee085c5-ea93-43a1-80dd-a3e7f7dcecc7
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 97a5077d-1543-5714-b6d8-fe7d285c8a47 |  | note | Frequency - Prior to site establishment
label | 07900bea-ee78-50ea-8b27-5e033d9007b2 |  | note | Acceptance Criteria - Review whether a preliminary report has been completed for the project which will outline where the Significant native grasses are and what protection has been specified.
label | a83d0e72-23d5-57e1-b64b-1ef276cb719f |  | note | Reference Documents - Consultant reports
label | 2633dbae-6842-555b-b148-d5b68900c4e8 |  | note | Inspection/ Test Method - Visual inspection
label | 605a4a9b-4eae-5a3f-8f24-a9df901dcb15 |  | note | Record of conformity - This Signed ITP
label | 0cf75c13-b335-5146-bbd6-9dba0347d4b3 |  | note | HP*
label | d3376edf-d6d5-51ef-8a11-751a1841ecec |  | note | Responsibility - FH Project Engineer
label | 3ee6d271-1927-534d-bccb-515962c2b977 |  | note | Checked By
text | 104a7a08-16bb-5cc6-a6f9-ae6ffd73ff4b |  | textbox | Name
text | 292f60e4-046a-50c0-84db-04917ee3ad9d |  | textbox | Position
text | 7537d677-ddb1-5c8d-8283-00862dcee57d |  | textbox | Date
checkpoint-status |  |  | checkpoint | 1.2 - Check the Google Earth Mapping
label | 0c52afe2-1015-5eae-a74d-beb1efd09914 |  | note | Frequency - During site establishment
label | 9b2812b2-d002-5587-a28d-8247b328c9e7 |  | note | Acceptance Criteria - Review the Google Earth mapping which outlines the boundary of the native grasses at the time they were mapped.
label | 52bbb6b0-d7dc-52e9-85c5-47e684efcc15 |  | note | Reference Documents - Google Earth Mapping
label | bff35185-70ad-5d1e-813c-6c717c9e9e7a |  | note | Inspection/ Test Method - Visual inspection
label | 7c924f7a-330b-58ae-8607-5047bf331a52 |  | note | Record of conformity - This Signed ITP
label | dfbbccf8-448b-5071-9747-798658616f3c |  | note | HP*
label | 54475a94-532f-53ca-8ed7-3a4e758d1dc1 |  | note | Responsibility - FH Project Engineer
label | 73678c61-a0eb-51fe-b4b9-74de734f890b |  | note | Checked By
text | 7f2db4f6-71d3-5df8-9696-cf642447f6d1 |  | textbox | Name
text | 5870e086-ef0d-5088-b88d-4393a838866e |  | textbox | Position
text | cad23399-5222-5b97-865d-8ef8e60fed76 |  | textbox | Date
checkpoint-group |  |  | section | 3. Implementation of Controls to Protect the Native Grasses
checkpoint-status |  |  | checkpoint | 3.1 - Mark out the exact Significant Native Grass Boundary area
label | cad67f38-b0c5-56bd-9ca5-79539c289fad |  | note | Frequency - Prior to commencing any activity
label | 6df58813-4677-5544-a37f-426a50266bf1 |  | note | Acceptance Criteria - Work with the surveyor to mark out the Significant Native grass boundary. FH Project Engineer must verify the set out survey data file matches the ECP. Signage will be placed onto the bollards stating ‘Native Grass Boundary Area.’ NTGVVP Nationally Significant Grasses to protect within this area.
label | 2bdd86c0-705b-5967-a0a6-9feadba81641 |  | note | Reference Documents - CEMP & ECP
label | c1e2613f-408a-5bac-998a-09733ac1226e |  | note | Inspection/ Test Method - Inspect
label | 557c8d9d-cb38-5a96-a8fc-a019e71c05e3 |  | note | Record of conformity - This Signed ITP
label | 9dfd0a68-a3e0-5b7a-8cd8-e08a02ba5c62 |  | note | HP*
label | a533efbb-aaf6-5b19-9582-8196307e9fab |  | note | Responsibility - FH Project Engineer
label | 14f8c1b1-b43e-5ed2-a119-af3d073ec3e7 |  | note | Checked By
text | 2a9799f7-c5a1-5dfe-bb5f-ffa196183d7a |  | textbox | Name
text | 5e4fe02c-40d6-5a3a-a493-0db09100f466 |  | textbox | Position
text | 1fccc880-f7e5-594c-9ef3-e87f2b5021a1 |  | textbox | Date
checkpoint-status |  |  | checkpoint | 3.2 - Use temporary fencing and signage to block access to the Significant native grasses where we are working in close proximity.
label | 402a7e03-1ada-51fa-a19f-cc599cc2fc95 |  | note | Frequency - Prior to commencing any activity
label | 54f9a3cc-55d5-514e-b4be-280539a6ff37 |  | note | Acceptance Criteria - For works in close proximity to the native grasses, delineate the native grass boundary using temporary fencing or t-top bollards with signage stating, “Vegetation Protection – No Go Zone.” Where possible this fencing will be installed at a distance away from the actual native grass boundary to act as a ‘buffer zone’.
label | feb7c8a2-bb26-5788-a76f-6b58b681e8cc |  | note | Reference Documents - CEMP & ECP
label | 877326f5-590c-522e-b22e-6f4b1b86e942 |  | note | Inspection/ Test Method - Inspect
label | 77642930-b12d-5741-a462-4e2597d60101 |  | note | Record of conformity - This Signed ITP
label | bf7bc1d0-9ddd-5987-98cb-b5a77a8e17d7 |  | note | HP*
label | abbddda1-5441-5e46-8227-163635c06630 |  | note | Responsibility - FH Project Engineer
label | 12940442-87e3-5da2-821b-9977401e6a04 |  | note | Checked By
text | 47de9c16-ee36-5c1d-b78a-cbd2baeae213 |  | textbox | Name
text | c672030c-3a10-5351-b18f-a645385a7c2e |  | textbox | Position
text | fa4f8ae6-4b7d-58a7-8e5f-da098959bdd6 |  | textbox | Date
checkpoint-status |  |  | checkpoint | 3.3 - Implementation of control measures required to protect the significant native grasses around our project area
label | d8587498-b935-5adf-a4a6-052dea72e5de |  | note | Frequency - Prior to commencing any activity
label | 02a853ee-bf64-52a0-84f7-8ab88e75bb56 |  | note | Acceptance Criteria - Project Engineer and Superintendent / Foreman to confirm the ECP requirements of native grass delineation have been met; and verify the delineation has been set up correctly using a GPS Rover.
label | b58c14e2-7c11-504b-8347-bddc87bc70dd |  | note | Reference Documents - CEMP & EMP
label | ac312a57-c49c-52d2-ae6e-6c2af4b0c432 |  | note | Inspection/ Test Method - Inspect
label | d7de184b-a5e4-53b2-b7c4-52ce75de9922 |  | note | Record of conformity - This signed ITP
label | 2545beab-33e9-5b63-8154-f9115b97fe25 |  | note | HP
label | 5582e6eb-21ea-5781-a463-bf962aaa363f |  | note | Responsibility - FH Project Engineer
label | 705e8d28-701e-5481-852f-83ef000cd273 |  | note | Checked By
text | 8dc47b1c-62f7-5b5e-85fd-f4a1e3a3bad8 |  | textbox | Name
text | 4ef76219-73bd-5e92-9747-f1337acc2ae4 |  | textbox | Position
text | abee31b2-fab1-59d1-8ec7-6aed144d180e |  | textbox | Date
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Implementation of control measures required to protect the significant native grasses around our project area
label | e71c5b37-8d23-5843-85da-5a753a2cccd4 |  | note | Frequency - Prior to commencing any activity
label | 5e658ff3-9e5d-56d3-92ad-3bf7e9d55784 |  | note | Reference Documents - CEMP & EMP
label | 57a14d08-493a-5616-bb9c-befe5e249be7 |  | note | Inspection/ Test Method - Inspect
label | c068ce28-1000-59e8-bb5d-c10a644dc496 |  | note | Record of conformity - This signed ITP
label | 2b6b532f-77cf-5daa-aae7-701203ec2c55 |  | note | HP
label | 4940bb04-68dd-5f9e-b340-ee979eb6e38d |  | note | Responsibility - Superintendent / Foreman
label | c8c023c0-2e08-503e-8cda-d611860b02f5 |  | note | Checked By
text | 21595c30-dd2e-515f-ab6f-481f77f9c67f |  | textbox | Name
text | ae022b2c-1d92-58c8-b9a9-5b0379ba3445 |  | textbox | Position
text | f0c8cedc-4314-586e-a571-3fa3df4bd8e8 |  | textbox | Date
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | 4. APAM Hold Point Release - Second Inspection
checkpoint-status |  |  | checkpoint | 4.1 - Release of Hold Point for Native grass Protection
label | 09bf67c7-6ef4-5b24-a209-5b24bc588072 |  | note | Frequency - Prior to commencing construction
label | d033f7bb-eb5f-50ec-b879-ab8348e7d63a |  | note | Acceptance Criteria - Arrange an APAM inspection to confirm that the native grasses are protected with the required temporary fencing or bollards and correct signage where required. All parties are to sign off on this Hold Point Release document
label | 70203a1d-25d4-5b0d-bfb5-118ad7e25306 |  | note | Reference Documents - CEMP and ECP
label | 2d23acaf-5f9c-504d-9113-5cf1b3c46364 |  | note | Inspection/ Test Method - Visual
label | 4be8b80d-2d41-509e-b055-a98fc65b1618 |  | note | Record of conformity - This Signed ITP
label | 81087161-28f4-5372-9cfc-743448975d13 |  | note | HP
label | cc81507c-68a1-51d6-b176-6c13f0a35326 |  | note | Responsibility - APAM Fulton Hogan Environmental Manager or Project Manager
label | 1e9068e1-ec65-5913-b662-c8bb64daa910 |  | note | Checked By
text | baa74f55-8e61-554c-8793-0df345478405 |  | textbox | FH Name
text | d2fe5c16-666c-518b-9193-df8b847dc406 |  | textbox | Position
text | d554d2f2-33fa-50fb-8fde-84079cd6a9ef |  | textbox | Date
label | 7bce95d3-9a68-54fa-9cf6-716562e74236 |  | note | Checked By
text | cc05224d-d160-5ad7-81f0-03ddf828ee38 |  | textbox | APAM Name
text | 02831059-8bce-5bc6-b7d6-6dfd7ea70cec |  | textbox | Position
text | 856af1c4-2f3b-57c3-a3ac-c4d1616523fe |  | textbox | Date
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | b5f14223-83af-5988-bce0-d2787254b3cb |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed above have been reviewed and implemented in accordance with the Construction Environmental Management Plan and conform in all respects with the requirements of the Contract.
label | 5667f712-4d35-5f56-91af-9cb8bd315874 |  | note | FH Environmental Team
label | cb65dbfa-783e-502d-a5cd-37d4090117d1 |  | note | Name: Tirrell Slaney
label | 06cd603c-7231-524f-8a38-6facc10e3546 |  | note | Position: Environment and Sustainability Advisor
text | 7806662f-c172-53cc-ac4c-d4c3352005b3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7a0ecfb6-d6b4-55e1-ad9b-901c3b4be952 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed above have been reviewed and implemented in accordance with the Construction Environmental Management Plan and conform in all respects with the requirements of the Contract.
label | 11c383dd-47f0-53c0-9b48-eca5100071be |  | note | FH Environmental Team
label | 35255392-be4a-5269-9652-39a895f1334d |  | note | Name: Kevin Gatt
label | cde55f7d-26bc-5612-9275-cf00f9193c77 |  | note | Position: Project Manager
text | 4b6b9a95-0e7f-5210-b797-c28f85fe6836 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP021-3 – Reinstallation of Shallow Base Canister | itp |  |  |  | Yes | ITP021-3 – Reinstallation of Shallow Base Canister | feabcd3f-5409-406b-a4dd-590a79fc3119
checkpoint-group |  |  | section | 1. Installation of Shallow Base Canister
checkpoint-status |  |  | checkpoint | 1.1 - Preparation for the Works to be Undertaken
label | 4907c43f-3f77-5a82-838a-de7f57acb114 |  | note | Frequency - Prior to Start
label | 561e1a6a-433d-585d-969a-9767a439b515 |  | note | Acceptance Criteria - Ensure survey set out is undergone, excavation permit obtained and (if required) services in work(s) area isolated. Lights, slot cuts, and aiming points marked out.
label | 0a5242c1-947c-59b7-8632-5e415d724536 |  | note | Reference Documents - Drawing sets:
label | 262ea9b3-5371-5ca2-b8af-d38c344819ec |  | note | • 60692389- SHT-01_1-10
label | 820881fb-f86a-5af6-afb7-800e5e5d2580 |  | note | • 60692389- SHT-01_2-10
label | 194695d0-13a4-50e9-883d-534544320317 |  | note | Inspection/ Test Method - Verify
label | 36f2f895-4ffc-5817-b1e4-ad9888817bd3 |  | note | Record of conformity - This ITP Signed / Avionics CL003
label | e44f46f7-4e3c-54af-bbb5-57a8ab630b1f |  | note | HP*
label | 1cc682c4-e1b1-57de-b34c-5c1f73ad448d |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.2 - Core and Cut
label | e7b522f2-d6e7-5e65-a0d3-9e407dbacc30 |  | note | Frequency - Each Lot
label | 97364cd0-56eb-568e-9f03-62079e31a43c |  | note | Acceptance Criteria - Light base cored into pavement and slot from base cut to pavement edge/expansion joint
label | 39ec9bfc-a073-53b4-9f62-19a6f4b49ba2 |  | note | Reference Documents - Drawing sets:
label | cfbf2990-0724-593f-9c80-b4ae336ec5a2 |  | note | • 60692389- SHT-01_1-10
label | ca075061-8e8e-5f5c-bdf6-c9615a56dad9 |  | note | • 60692389- SHT-01_2-10
label | 883313c6-0148-5dab-82e1-0a70096010f8 |  | note | Inspection/ Test Method - Verify
label | f928b76b-a498-5077-bdb6-95816329ef9c |  | note | Record of conformity - This ITP Signed / Avionics CL003
label | a7ccb6e0-b506-53c8-9255-9226ae1ad93f |  | note | IP
label | f14d3e05-9f8b-59b9-89c1-a7eafbb56018 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.3 - Base positioning
label | c964830c-e6e9-5978-bdb6-eda110caafe6 |  | note | Frequency - Each Lot
label | 6217fd18-2e7a-57a5-b82e-cacf239f7d15 |  | note | Acceptance Criteria - Light base positioned and epoxy poured to secure. Installation of jig.
label | 4bdf2dcd-8eff-5f18-88e6-5df976845e71 |  | note | Reference Documents - Drawing sets:
label | 6693bde4-0969-5c83-aafe-daa2efe0061c |  | note | • 60692389- SHT-01_1- 10
label | cfcec325-2c74-58bd-8ba6-b05271454c66 |  | note | • 60692389- SHT-01_2- 10
label | def57218-157c-5a3b-a225-853c8c4f533c |  | note | Inspection/ Test Method - Verify
label | e008d92b-5386-525d-b3c8-2470b46d212c |  | note | Record of conformity - This ITP Signed / Avionics CL003
label | a6efac68-fabc-5909-95a3-5d6a2da9b8de |  | note | IP
label | 1f6eb286-9989-5b2d-bb02-64f82cb53871 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.4 - Cabling
label | ce7216bf-7d10-56cb-8dc5-e21ba27ce016 |  | note | Frequency - Each Lot
label | cf0712b9-fc7f-563b-a937-878179e1a599 |  | note | Acceptance Criteria - Cables ran and connected from new base via joints/slots/conduits to SIT pit.
label | f9cda923-2679-52ba-8c9a-275682ac5ad9 |  | note | Reference Documents - Drawing sets:
label | 2cc6f89e-5cce-51d3-8163-c7f1b10b68bf |  | note | • 60692389- SHT-01_1-10
label | cfc9202d-2ec4-5e29-a370-ed7d9dc14431 |  | note | • 60692389- SHT-01_2-10
label | 04b29a9d-4297-5143-8aa3-21713bcd8bff |  | note | Inspection/ Test Method - Verify
label | 463160bd-c785-56f7-b304-3877fa310cba |  | note | Record of conformity - This ITP Signed / Avionics CL003
label | 0a08da2e-b411-5132-8233-a4108be149a4 |  | note | IP
label | 4c1e2f85-3ef3-5736-82e9-5f53da08dc6c |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.5 - Sealing
label | 45f8e260-fa8c-537d-8c74-dc78abcc2f54 |  | note | Frequency - Each Lot
label | 4d5e2928-cac8-596f-a5c6-7d9784605c3d |  | note | Acceptance Criteria - Once cables installed, backing rod placed and expansion joints sealed with approved product.
label | bcf4ffe0-3001-573c-8bb8-c6c92baec0ff |  | note | Reference Documents - Drawing sets:
label | 64bf2db7-df8d-5242-a827-ea19e54d590c |  | note | • 60692389- SHT-01_1-10
label | f9d29101-fbd5-505b-b799-df063364e6ae |  | note | • 60692389- SHT-01_2-10
label | e8eb90cc-3ff0-5950-9960-d023b871a272 |  | note | Inspection/ Test Method - Verify
label | fd8da8cb-a927-5a93-81fa-136de870059d |  | note | Record of conformity - This ITP Signed / Avionics CL003
label | 60e0f6b8-7501-53a1-a010-0c2c872f7784 |  | note | IP
label | d9ab2582-177a-513d-af8d-3d787f4403bc |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.6 - Finishing, Testing, Demobilisation
label | 71dcccae-c1c3-5adc-b7a4-92a6f2866adf |  | note | Frequency - Each Lot
label | 32ba47cf-0e31-5c37-97db-e5f8cee925cd |  | note | Acceptance Criteria - Gasket positioned on light top, light plugged and positioned to current orientation. Light tested and area cleaned before demobilisation.
label | db2686ac-06ec-5157-869b-d218cf73434f |  | note | Reference Documents - Drawing sets:
label | 82dc948c-0eba-54df-958f-3c3b83d728b0 |  | note | • 60692389- SHT-01_1-10
label | 50d41268-8af7-5fbf-b2b4-7f83a283d693 |  | note | • 60692389- SHT-01_2-10
label | 543bee0b-3ac8-5bfe-b2cd-de51915ba494 |  | note | Inspection/ Test Method - Verify
label | cee19f35-f6c4-55b6-9953-9c912a3664cc |  | note | Record of conformity - This ITP Signed / Avionics CL003
label | 131e1fd6-b636-504c-91e2-9a067d008c78 |  | note | IP
label | ef849b5d-ac6e-56d4-a098-fc5bf517c9ee |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | Final Inspection
label | 4e7a1d7f-b14a-5c76-b9b8-e460f999d611 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 9f62b790-a3d9-5fcb-8683-c4c0821040f9 |  | textbox | Name:
text | 0bfe2038-7295-5750-b649-824aa128ee1f |  | textbox | Position:
text | 9e97f880-2f10-5c02-9360-174a08581030 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP003 - Plant Mixed Foamed Bitumen Stabilised Pavements | itp |  |  |  | Yes | ITP003 - Plant Mixed Foamed Bitumen Stabilised Pavements | fed39c4a-7156-44be-bc9c-89ef599284e3
checkpoint-group |  |  | section | 1.0 Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | 64454f23-3da8-5612-8aa6-62f829d87698 |  | note | Frequency - Prior to commencing works
label | eb547904-0c73-5c92-b306-ad385c55810d |  | note | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current revision to be obtained via Aconex
label | e9e29e0a-6e3d-5d9e-a1a1-656f6b451edc |  | note | Reference Documents - Aconex
label | adf58cfb-d47f-5e23-ad5f-29570694701f |  | note | Inspection / Test Method - Verify
label | 5a338c15-26bd-5502-bdf8-3fee131f8fb6 |  | note | Record of Conformity - This signed ITP
label | 927b8642-c936-55fd-b3f1-133a2278e107 |  | note | HP*
label | 1c1bb7ec-af9c-5be6-863c-52096ff57893 |  | note | Responsibility - Fulton Hogan
checkpoint-status |  |  | checkpoint | 1.2 - Work Method Statement
label | 99ed5ad0-d85f-5322-988b-3906dbcb54c1 |  | note | Frequency - Prior to commencing works
label | d20eb9b1-0a0b-509e-8488-c435178b9173 |  | note | Acceptance Criteria - No stabilisation works shall be commenced until the construction procedure for the stabilisation works including all required compliance test results is acceptable to, and approved by, the Administrator.
label | 954538e7-993f-53fb-855a-d259f65a4228 |  | note | Reference Documents - MRTS09 cl.5.2
label | b0fbe795-cb0e-509d-8b2c-6915bfdb9519 |  | note | Inspection / Test Method - Verify
label | edd8537b-7914-540c-b21d-47eb5fa3ba8f |  | note | Record of Conformity - Approved Work Method Statement
label | 17da4e9a-91f3-54de-9365-9d64f374afd5 |  | note | HP
label | e0fc586d-5122-5d59-a6d6-77438b500605 |  | note | Responsibility - Fulton Hogan / AECOM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Material Compliance
label | 0120ffa5-9ecf-5a21-a7ea-7d6d40abcce6 |  | note | Frequency - Prior to commencing works
label | cf40ea59-4cfa-5bab-a31a-2a2094b2a498 |  | note | Acceptance Criteria - No material shall be incorporated into the works unless it has been demonstrated to the Administrator’s satisfaction that all the material to be used comply with all the requirements of the Technical Specification. Compliant test results noted below to be submitted to contract administrator: • Aggregates [Class 2 Crushed Rock (ex Fulton Hogan Tylden Quarry), Class 1 Crushed Rock (ex Holcim Oaklands Junction Quarry) and RAP (ex Melbourne Airport)] – Compliant with VicRoads Section 812. Coarse Aggregate compliant with 10-1 and fine aggregate compliant with 10-2.
label | ba68cb21-4563-53c4-b9c0-205d1800b05c |  | note | Reclaimed Asphalt Pavement (RAP) – Use of up to 15% by mass of the aggregate
label | 5827d761-c5f5-5b62-ab9e-d461bbba53f9 |  | note | Primary Binder – Class 170 bitumen and penetration grade 70/100 complying with AS 2008. Minimum content is 2.5% of the dry mass density. Compliant with Table 10-3: o Expansion Ratio ≥10 o Half Life ≥20 seconds
label | 61d81f63-62f4-5aa3-9612-c31cc45db969 |  | note | Secondary Binder – GP Cement compliant with AS3972. Maximum cement content in is 2% by mass of dry mix Foaming Agent – Compliant with MRTS09 Water – Compliant with 10.5.6: o Total Soluble Salts ≤1,000mg/l o Chloride Ion ≤600mg/l o ≤ 400 parts per million of sulphate ion o ≤1% by mass of undissolved solids
label | 70552646-ee6c-57e3-9e80-4a0abc43e147 |  | note | Reference Documents - MRTS09 cl.7.1 & AECOM - MAP MP2.0 Spec. cl. 10.5
label | 69d9774a-6189-5437-a178-f2eafc9b698a |  | note | Inspection / Test Method - Verify / Test Results
label | 00a48823-24aa-5610-bc25-d83e9bc44ad7 |  | note | Record of Conformity - Approved materials and material sources
label | 9d403660-51d9-5a16-8ebf-0aa5d1206bd3 |  | note | HP
label | d3ee759e-0098-5a53-b768-5a676826d2e9 |  | note | Responsibility - Fulton Hogan / AECOM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Production Testing
label | 99b5c02c-5b84-5d88-8078-9d83051738b2 |  | note | Frequency - Prior to commencing works
label | a557e6d8-3382-5cde-ae42-78224c27ea5f |  | note | Acceptance Criteria - Supply information with respect to production testing of the unbound granular material utilised for the FBB mix.
label | a5de88dd-ee5b-53d9-9d47-748e6cca42ae |  | note | Reference Documents - Cl.4 VicRoads Section 812 & AECOM - MAP MP2.0 Spec. cl. 10.5.1
label | d2c503ed-88b2-5307-8f62-7d073b226fbd |  | note | Inspection / Test Method - TP
label | 920f3df5-d25a-51b7-9ab3-e869c5a1c399 |  | note | Record of Conformity - Approved Production Testing Results
label | 19af4d67-24dc-5575-b83e-f4720179166d |  | note | TP
label | e2b45095-1007-5844-8893-a3380200f888 |  | note | Responsibility - Fulton Hogan / AECOM
checkpoint-status |  |  | checkpoint | 1.5 - Mix Compliance
label | ee693e57-11cc-5c89-9516-e69aff18f975 |  | note | Frequency - Prior to commencing works
label | 1a0f8c65-88f8-5371-88db-57616ca1d36c |  | note | Acceptance Criteria - The mix design report must be submitted to the Contract Administrator at least 7 days prior to the plant production trials for review. Approval of the mix design report prior to commencing the production trial is a HOLD POINT. The mix design report must include the requirements stated in cl 10.6.2 of the AECOM specification.
label | 545c3832-e475-5cb5-9384-4f29532fff4b |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.6.2
label | 85e32735-3670-58a4-8857-e1c71b7510bf |  | note | Inspection / Test Method - Verify / Test Results
label | e4ed6037-5862-5bbf-9a60-3813bb24c0a7 |  | note | Record of Conformity - Approved mixed design
label | 5bd3dc7a-0bf4-541c-8f54-13d4333f548b |  | note | HP
label | a278ec1c-83c2-5b2b-af51-bd3c52c55f4f |  | note | Responsibility - Fulton Hogan / AECOM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Plant Production Trials
label | 3e17108b-1631-503e-8b8d-76b36527b76f |  | note | Frequency - Prior to commencing works
label | 04f1de27-c2ea-5253-bbe4-462f488bebae |  | note | Acceptance Criteria - The Contractor must undertake a production trial at their mixing plant to validate the approved Laboratory Design Mixture and to confirm the mix meets the requirements of the Specifications detailed in Table 10-5. The Contractor must issue an updated mix design report with the details of the Job Mixture (Laboratory Design Mixture modified) within 3 working days after completion of the production trial. Resilient Modulus: 1 test per mix design for plant production – Table 10-5 Requirements:
label | a4b5f7b3-8580-5406-8550-f45306e5c615 |  | note | • 3-day-curing Resilient Modulus ≥1,000 • Soaked after 7-day curing Resilient Modulus ≥1,500 • Soaked after 14-day curing Resilient Modulus ≥1,800
label | b403d995-812e-5a25-af81-f377db2bc802 |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.6.1 Table 10-5 & 10.6.3
label | db0d0e2a-b8d3-574d-8a5e-af9a77c4422f |  | note | Inspection / Test Method - Verify / Test Results
label | b0435833-62ea-590c-a63a-2e7f265ecfa3 |  | note | Record of Conformity - Approved mixed design
label | bcbf2a26-7677-5a7c-96f7-3c214b5f96e9 |  | note | HP
label | 91df4def-fc5e-5798-b8ad-bdd45134f17b |  | note | Responsibility - Fulton Hogan / AECOM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Construction Trial
label | 4ec0dbe8-7d2e-5c9e-b605-9dccf250b71d |  | note | Frequency - Prior to commencing works
label | d1b4b8c6-f6b3-5c26-8a0f-318a8b2a9622 |  | note | Acceptance Criteria - A trial section shall be constructed using the same construction plant, processes and methodology that it is proposed to be used for the remainder of the works. The trial section must be compliant with all testing requirements within the specification.
label | 35dfff1c-a848-5c45-839e-aa01500cb92e |  | note | Reference Documents - MRTS09 cl.8.1.2.4 & cl.8.7.2.1
label | 6bc759df-6a39-54a1-8df6-dca386d1bfd3 |  | note | Inspection / Test Method - Verify / Test Results
label | f6b6d8f7-5492-5a4d-b0aa-b1fcaf05dfb6 |  | note | Record of Conformity - This signed ITP
label | a435aa63-9e64-5aa7-bf45-0ae2fa4b2548 |  | note | HP
label | f4f0c031-a2a8-5468-bd57-fa8fd23db9e7 |  | note | Responsibility - Fulton Hogan / AECOM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Foamed Bitumen Properties
label | c3132ed3-7731-54ca-bf50-211c9c083af2 |  | note | Frequency - Prior to commencing works
label | ef886adf-25a7-5270-9a1c-3a0a86a08a1e |  | note | Acceptance Criteria - The bituminous stabilising agent shall not be incorporated into the material to be stabilised where the foaming properties of it do not comply with the requirements of the technical specification. The bitumen is to be tested at the start of each bitumen tanker and every 400T of production for the following parameters: Expansion ratio greater than 10 Half-Life greater than 20 seconds
label | 94921cdf-6baa-51a3-a3dd-bf975e604ad0 |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.5.3 & MRTS09 cl.8.8.5 Table 5.4
label | a9886c6f-3203-5a6a-94c3-290360059e35 |  | note | Inspection / Test Method - Verify / Test Results
label | ab586d5d-2095-5d72-b79f-f13915f06ea5 |  | note | Record of Conformity - Test Results
label | ffca5f3b-97e5-5652-8744-950eef2fe5d9 |  | note | HP
label | e66af499-3f7e-5f85-b0e7-3be3b3fdc0d1 |  | note | Responsibility - Fulton Hogan / AECOM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.9 - Stockpiling of Materials
label | de3604bf-54d2-50e9-8183-ca37d2321fca |  | note | Acceptance Criteria - Stockpiles shall be located on clear, even, firm, well drained ground and in a location where they can be clearly identified. All stockpiles shall be separated from other stockpiles by at least two metres and shall not be more than four metres high. The feedstock lot size is defined as 2500T.
label | 25d2c48d-f71f-54c9-9320-a3104e249d90 |  | note | The Contractor can delineate individual stock piles by either of the following methods: A.) Separate stock pile formed for each lot B.) Material of the same mix to be added to a single stockpile incrementally. Prior to adding the next portion of material, the initial/existing stockpile must be compliant with the specifications No stockpile that, in the opinion of the Administrator, is excessively wet shall be used in the stabilisation works.
label | 60f8e42a-7228-5d6e-9201-23d281d836ac |  | note | Reference Documents - MRTS09 cl. 6.6 & MRTS05 cl. 7.7
label | 319444ef-8189-575f-9d51-6f607c1b6023 |  | note | Inspection / Test Method - Verify
label | cdce000e-395b-50cc-a338-01c18ac4ecb7 |  | note | Record of Conformity - This ITP signed
label | 4c70221e-a14a-550b-b7d0-e505b681b5a3 |  | note | WP
label | 1c49698f-9597-5acd-b026-f588c0ffc326 |  | note | Responsibility - Fulton Hogan / AECOM
checkpoint-status |  |  | checkpoint | 1.10' - Feed Stockpile Testing
label | ee33f3ae-791b-51ba-b7ef-ff7b40a61e75 |  | note | Frequency - Prior to commencing works
label | 459a84d7-6cf2-5ec8-9370-4e0c2487843c |  | note | Acceptance Criteria - The following items must be tested for in the feed stockpile: Relative Moisture Ratio of Feed Stockpile: 4 tests per feedstock lot. Particle size distribution: 1 test per 1250T and a minimum of 2 tests per feedstock lot Fines Ratio: 1 test per 1250T and a minimum of 2 tests per feedstock lot Liquid Limit: 1 test per 1250T and a minimum of 2 tests per feedstock lot Linear Shrinkage: 1 test per 1250T and a minimum of 2 tests per feedstock lot Sulfate Content (water): 1 test per water source
label | 2dc3cc75-4750-5b1a-a40b-1bbdbee9b6e8 |  | note | Reference Documents - MRTS09 Cl. 8.8.6 & Table A2(c) & A3 AECOM - MAP MP2.0 Spec. cl. 10.5.6
label | 0a6b9917-3fdc-5a79-8264-e8f85eab3028 |  | note | Inspection / Test Method - Verify / Test Results
label | 6a7d3619-b313-58c5-b64e-bb963c859347 |  | note | Record of Conformity - Test Results
label | fafb294f-f945-5011-ad2b-c5b6af164cd0 |  | note | TP
label | 4182f1e0-0163-5fe7-ba10-31a028f9faf5 |  | note | Responsibility - Fulton Hogan / AECOM
checkpoint-group |  |  | section | 2.0 Construction Process
checkpoint-status |  |  | checkpoint | 2.1 - Testing of FBB Material for Stabilising Agent Contents and Resilient Modulus
label | 3088f96c-505a-5c07-97b1-e877d02407e1 |  | note | Frequency - Each Lot
label | 513e025c-cf39-51da-b630-4416bc41af1f |  | note | Acceptance Criteria - Bituminous stabilising agent content: Recorded at least once per 100T with a minimum if one recording in any production shift. Secondary stabilising agent: Recorded once per 100T with a minimum of one recording in any production shift. Resilient Modulus: 0 to 5000T: 1 Test 5000 to 15000T: 1 Test 15000 to 30000T: 1 Test Beyond 30000T: 1 Test per 20000T
label | bb7112cc-116e-55f6-91c0-395e59237b54 |  | note | Reference Documents - MRTS09 Table A3
label | 6ab60d3b-6881-54eb-82b0-53e3c94f42ef |  | note | Inspection / Test Method - Verify / Test Results
label | 77c7befb-d57e-51cc-afcf-7f15d1b5c94f |  | note | Record of Conformity - Test Results
label | 92e0ee48-30a0-531c-ad57-e027ad3a76f6 |  | note | TP
label | ee2d18a7-a3d6-5986-9e58-ed662d2eb655 |  | note | Responsibility - Fulton Hogan / AECOM
checkpoint-status |  |  | checkpoint | 2.2 - Surface Preparation
label | cb95e7fd-ad05-5053-96ba-504f029b81c4 |  | note | Frequency - Each Lot
label | 63b7b9ed-67fd-5250-8ca0-1cc7b4ad22bd |  | note | Acceptance Criteria - For all surfaces, preparation shall include the removal of all foreign and loose material. The Contractor shall ensure the surface onto which a stabilised layer is to be constructed is well compacted, trimmed and prepared before material for the overlying stabilised layer is placed.
label | c34eee8d-94d6-55d6-816e-322cb9d68fe8 |  | note | Reference Documents - MRTS09 cl. 8.8.9.1 & 8.8.9.3
label | 5417054c-840f-5b28-8a3c-2eb7d69a2f58 |  | note | Inspection / Test Method - Verify
label | ae865458-3f5f-5290-903c-475c0b13dd23 |  | note | Record of Conformity - This ITP signed
label | 61250ffc-2902-50a6-a854-67173b016a16 |  | note | WP
label | cb50ff48-9880-5e7f-85b5-28a7bcb494ab |  | note | Responsibility - Fulton Hogan / AECOM
checkpoint-status |  |  | checkpoint | 2.3 - Placement of FBB
label | aab920aa-237b-548a-aab5-05d0842a1294 |  | note | Frequency - Each Lot
label | 78573e7c-ef95-5673-a859-b2adbd302c0a |  | note | Acceptance Criteria - The FBB is to be placed in a single layer. The maximum compacted thickness of an individual layer is 300mm. The minimum compacted thickness should be equal to the design thickness stated on the drawings. The surface level at the topmost FBB layer shall not deviate from design level at the specified points by 0mm,-10mm. Surface Levels to be picked up following profiling, and prior to placement of Asphalt.
label | 07578853-4afa-5d6b-96a2-5157cf2dd00a |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.7 & Table 6-3 MRTS09 cl. 8.9.5.2.2 & 8.9.5.3.1
label | 7a1116ed-4a5b-578d-b973-f9b656c699bd |  | note | Inspection / Test Method - Visual Inspection
label | 13d4d6a7-d50a-54e8-a2d8-62b34c774bcc |  | note | Record of Conformity - Survey Report and Visual Inspection
label | 0466b8d0-a767-55dd-bec7-6a7e929a5b1b |  | note | HP*
label | 8dbb297c-e531-5114-affb-f0437fbd9d9c |  | note | Responsibility - Fulton Hogan
checkpoint-status |  |  | checkpoint | 2.4 - Proof Rolling
label | 41aa90da-ee8f-5cf9-9b94-4ccc9da4661c |  | note | Frequency - Each Lot
label | a75efb0b-6f5c-5488-8255-0d6a5fc321fb |  | note | Acceptance Criteria - Proof rolling of the completed layer must be undertaken at least 24 hours after the completion of the bitumen stabilised layer. The area must be uniformly covered with a minimum of 8 passes with either a pneumatic tyred roller or water cart not exceeding 6km/h.
label | a8f1bc6e-aab4-5cfe-9449-99ba42e6218e |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.8.3
label | 703d3a78-8fb7-524a-a77f-e23b0f4b0eb4 |  | note | Inspection / Test Method - Verify
label | 795a8eb0-1aa7-5e5d-96e8-eeb5e79f3870 |  | note | Record of Conformity - This ITP signed
label | b5d2d25c-be92-5640-adda-0f83a15ede50 |  | note | WP
label | a96795da-65ac-5e62-b039-1fcc0fbf7f3d |  | note | Responsibility - Fulton Hogan / AECOM
checkpoint-status |  |  | checkpoint | 2.5 - Proof Rolling Report
label | 45d0b942-e79b-5e66-9bb9-cb038e48ba04 |  | note | Frequency - Each Lot
label | c4bf2725-c590-55a8-bb75-8823876c3b18 |  | note | Acceptance Criteria - Proof roll report must be submitted to the Contract Administrator and Principal’s Design Consultant as soon as practical after completion of proof rolling.
label | 9054c34c-04bd-5973-94b0-26c8b22658df |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.8.7.2
label | 7a351e93-002c-5064-882b-735bb943ce6c |  | note | Inspection / Test Method - Verify / Proof Rolling Report
label | 250eecd9-fe20-5bba-86b9-cdc247f9a8ea |  | note | Record of Conformity - Aconex
label | fa179187-800a-518c-a4f4-5b39097c4489 |  | note | HP
label | 07f71408-3cec-5516-9b62-462067178a59 |  | note | Responsibility - Fulton Hogan / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Proof Roll Failure
label | f60b0e32-7fd3-5cba-af02-0fca547d3ebc |  | note | Frequency - Each Lot
label | 8dd1f2bd-5c21-5e56-a851-de2f95a60f17 |  | note | Acceptance Criteria - In the event of a failed proof roll the contractor must rectify the stabilised material to the extent and methodology identified in the proof rolling report. Area and depth of replacement to be agreed with CA prior to replacing.
label | ca472317-7617-57f9-8ff6-60b742ec4b33 |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.8.7.3
label | fd091ded-523c-585d-a93a-f793396e70ed |  | note | Inspection / Test Method - Verify
label | 039a7f56-e489-5cad-af6d-33d7f0d2c606 |  | note | Record of Conformity - This signed ITP
label | ae1ad443-2814-5002-86ab-ece576df77bc |  | note | HP*
label | 0d4d30bd-bcb7-5d91-9f46-59de0ffb9055 |  | note | Responsibility - Fulton Hogan
checkpoint-status |  |  | checkpoint | 2.7 - Testing Requirements
label | 07b04610-2db0-56cc-8277-705cb31b020f |  | note | Frequency - Each Lot
label | f3817d06-bd79-5696-8b5c-154d38775b54 |  | note | Acceptance Criteria - The foamed bitumen basecourse must be compacted to characteristic dry density ratio ≥98% modified compaction and a minimum of 4 test points per lot must be undertaken. Lots that contain in-situ material that failed the proof roll at subgrade level must be compaction tested in the location of the failed proof roll.
label | a78b9512-b8e8-53ff-99a0-5aa701a5b4d5 |  | note | Characteristic Construction Moisture Content to be within the limits of 60 – 80% and a minimum of 4 test points per lot must be undertaken.
label | 106dfb49-6edb-5bfe-8a7c-b89904a817d8 |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 5.10.3.2, 10.8.3, 10.8.4 & MRTS09 Table A3
label | 7fa23245-3a0d-5e0d-8cb7-1abaac9ae5a9 |  | note | Inspection / Test Method - Verify / Test Results
label | 4dcae702-72a4-57b3-9ee6-9de614c7ca0b |  | note | Record of Conformity - This ITP signed
label | f3409ffe-86de-5994-8919-287a6b26d7b6 |  | note | TP
label | 39e9db59-98cc-56f2-8478-622f4df28fec |  | note | Responsibility - Fulton Hogan
checkpoint-status |  |  | checkpoint | Final Inspection
label | 2f37ae5f-1513-519c-82f0-c85775281321 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 2dd1505b-7eef-589a-91d3-625530856022 |  | textbox | Name:
text | c48350af-d506-5bd3-baf6-d70e74b111fc |  | textbox | Position:
text | 1485ce09-6a28-542a-8933-5fb9e58ff24b |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP