## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CTN-ITP-001 - Removal of Existing Structures | itp |  |  |  | Yes | CTN-ITP-001 - Removal of Existing Structures
section | 1 - Design and Planning
checkpoint | 1.1 - Check for correct documentation
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents: Drawings and drawing registers
label | Inspection / Test Method: Visual inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.3 - Lift Planning
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Lift plan review compelted
label | Reference Documents: Work Procedure, Lift Plan, HSMP
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed, Lift Plan
label | HP*
label | Responsibility: Fulton Hogan
text | Date Completed:
checkpoint | 1.4 - Permiting
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Verify approval of all permits and approval processes for removal of structure
label | Reference Documents: Work Procedure, HSMP
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.5 - Transport Plan
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Transport route and plan complete, sight and review any transport documentaion
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed, Route Map
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.6 - Asbestos
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Identify and verify removal of any asbestos material
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.7 - Exisiting Services
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Verify the disconnection of any existing services to structure
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
section | 2 - Structure Removal
checkpoint | 2.1 - Exclusion Zones
label | Frequency: Prior to demolition
label | Acceptance Criteria: Identify and establish any no go and exclusion zones required for demolition
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Inspect
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.2 - Demolition of Incidental Strutures
label | Frequency: Prior to concrete pour
label | Acceptance Criteria: Identify and remove any incidental structures relating to the main structure
label | Reference Documents: Work Procedure Drawings
label | Inspection / Test Method: Inspect
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.3 - Relocation Route
label | Frequency: Prior to Removal
label | Acceptance Criteria: Ensure relocation route is prepped and clear for relocation
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Inspect
label | Record of conformity: This ITP signed, Route Map
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.4 - Removal of Structure
label | Frequency: Prior to Removal
label | Acceptance Criteria: Ensure removal of structure is undertaken per approved documentation
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed, Lift Plan
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
section | 3 - Structure Laydown
checkpoint | 3.1 - Laydown Area
label | Frequency: Prior to Removal
label | Acceptance Criteria: Verify laydown area is ready to receive structure
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 3.2 - Storage
label | Frequency: Prior to Removal
label | Acceptance Criteria: Structures are stored in such a way as to prevent damage if required
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 3.3 - Photos
label | Frequency: Prior to Removal
label | Acceptance Criteria: Photos of stored materials
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: Photos
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
section | 4 - Closeout
checkpoint | 4.1 - NCR
label | Frequency: Prior to lot closure
label | Acceptance Criteria: Details of any NCRs to be recorded in CL01E (if applicable)
label | Reference Documents: CL 01E
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 4.2 - Permits
label | Frequency: Prior to lot closure
label | Acceptance Criteria: Close out applicable permits
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Sign ITP