## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CTN-ITP-004 - Subsurface drains | itp |  |  |  | Yes | CTN-ITP-004 - Subsurface drains Rev2
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents: Drawings and drawing registers
label | Inspection / Test Method: Visual inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | Reference Documents: PSP, EMP, TGS, SWMS, WP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.3 - Material Classification
label | Frequency: Each Lot
label | Acceptance Criteria: Pipes supplied shall be of the category and diameter shown on the drawings
label | ○ Material shall be as indicated on the project drawings and / or shall conform to the following:-
label | • uPVC slotted spigot and socket sub-soil drainage pipes.
label | • Fibre reinforced cement slotted spigot and socket sub-soil drainage pipes.
label | • Perforated corrugated polyethylene continuous tubes.
label | • Geo textile must be of A34
label | Reference Documents: DWG EW-CE-DRW-526-001 C.6
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed off
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | Frequency: Each lot
label | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing.
label | • Plant and equipment shall be appropriate for the task.
label | • Excavation operations shall not disturb areas outside the limit of excavation
label | Reference Documents: Excavation permit
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.2 - Outlets
label | Frequency: Each lot
label | Acceptance Criteria: Superintendent inspection of proposed underground outlet location. Outlets shall be installed through walls of pits, provided inverts are not below the top level of the outfall drain.
label | Reference Documents: C.6.2
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed
label | HP
label | Responsibility: QAV
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Excavation of Trench
label | Frequency: Specification for trenching
label | Acceptance Criteria: Excavations for sub-soil drains shall conform to the requirements specified for excavation for services subject to the following specific requirements and modifications:
label | • Trench depth and width shall be as shown on the Drawings.
label | • Trench bases shall be uniformly graded to an even fall as necessary to suit whichever of the following is applicable:
label | • Parallel with pavement or kerb and channel formation grade.
label | • Parallel with overall grade of stepped footings.
label | • Not less than 1:250.
label | ○ If it is not possible to conform to any of the above requirements, the Contractor shall notify the Superintendent and await direction before continuing with the affected part of the work.
label | Reference Documents: C.6.1
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP
label | Responsibility: QAV
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Bedding
label | Frequency: Each Lot
label | Acceptance Criteria: The bottom of the trench shall be well compacted and evenly graded suitable material, 25mm minimum depth of 20mm Class 3 FCR
label | • If rock excavation was necessary and if the bottom of the trench is uneven, all low and rough areas shall be filled, and solid rock outcrops covered with bedding material to a compacted thickness of not less than 25 mm.
label | Reference Documents: C.6.6
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.5 - Placing pipes
label | Frequency: Each Lot
label | Acceptance Criteria: Sub-Soil drain to be 100mm Dia. PVC Class 1000 Agricultural drain.
label | • The pipes shall be laid true to line and gradient on the graded compacted bedding.
label | • Pipes shall be jointed to fit tightly by pushing the spigots firmly into the sockets. For pipes without sockets, special end jointing fittings shall be used.
label | • Fittings shall be compatible with pipe material.
label | Reference Documents: DWG EW-CE-DRW-526-001 C.6.4
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.6 - Backfilling
label | Frequency: Each Lot
label | Acceptance Criteria: Superintendant inspection of Subsoil drain backfill prior to covering
label | • Backfill needs to to encase subsoil drain and cover upto 150mm over to allow for sediment collection.
label | • Backfill to be 14mm screenings to subgrade.
label | Reference Documents: C.6.5
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP
label | Responsibility: QAV
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Backfilling
label | Frequency: Each Lot
label | Acceptance Criteria: At full depth pavement joints 100ø class 1000 pvc pipe sub-surface drain type 2 with filter fabric around trench (150mm Overlap) with "no fines" concrete filter
label | • Material (with 4% cement & compacted).
label | Reference Documents: DWG EW-CE-DRW-416-001 C.6.5
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP
label | Responsibility: QAV
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Access Points and Flushouts
label | Frequency: Each Lot
label | Acceptance Criteria: A flush out riser is to be located at the Back of kerb (BOK), comprsing of 100mm UPVC PIPE, capped.
label | • Minimum 200m intervals along road alignments, a single flushout points at high point or at locations within WSUD/Raingardens.
label | Reference Documents: C.6.5
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 5 - Finishing and Commissioning
checkpoint | 5.1 - As-Constructed survey and documentation
label | Frequency: Each Lot
label | Acceptance Criteria: The survey shall include pickup of location and depth of installed sub-soil drainage and location of any inlet/outlet/flush out points.
label | • Lot Maps shall be completed to show the extent of works for each lot.
label | Inspection / Test Method: Review
label | Record of conformity: This ITP Signed
label | HP*
label | Responsibility: Site Engineer / Superintendent
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Sign ITP