## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CTN-ITP-005 - Asphalt Placement | itp |  |  |  | Yes | CTN-ITP-005 - Asphalt Placement
section | 1 - Construction Works
checkpoint | 1.1 - Submission of Mix Design
label | Frequency: Prior to commencing paving
label | Acceptance Criteria: No Asphalt shall be supplied until the mix has been registered and the superintendant approves the mix for use. Only use mixes that are registered by State Growth as 'General Mixes'
label | Reference Documents: Cl 407.06
label | Inspection / Test Method: Verify
label | Record of conformity: Mix registration & correspondence
label | HP
label | Responsibility: FH Engineer/ Asphalt Supervisor / QAV
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed off
label | HP*
label | Responsibility: FH Engineer
text | Date Completed:
checkpoint | 1.3 - Site Inspection and Base Condition
label | Frequency: Prior to commencing paving
label | Acceptance Criteria: Base condition is acceptable for placement of asphaltic concrete.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed off
label | IP
label | Responsibility: FH Engineer / Asphalt Supervisor
text | Date Completed:
checkpoint | 1.4 - Ambient Conditions for Placing
label | Frequency: Prior to commencing paving
label | Acceptance Criteria: The temperature of the pavement to be surfaced shall have a temperature greater than 10 degrees and no rain shall fall during placement of the mix and the surface shall be dry.
label | • Primer seal - no primer sealing shall be applied whilst the pavement surface temperature is less than 20 degrees or during wet, windy or rainy conditions, or when adverse weather conditions may prevail at any time during the work.
label | Reference Documents: C.9.13
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed off
label | IP
label | Responsibility: FH Engineer / Asphalt Supervisor
text | Date Completed:
section | 2 - Asphalt Placement works
checkpoint | 2.1 - Tack Coat
label | Frequency: Prior to commencing paving
label | Acceptance Criteria: The tack coat shall consist of a diluted rapid-setting Anionic bitumen emulsion as specified. Application shall take place not less than 30 minutes nor more than 2 hours before placing asphaltic concrete.
label | • The tack coat application rate shall achieve a residual bitumen of 0.1 to 0.2 litres per square metre. The actual rate of application will be selected by the Superintendant to suit the class of material.
label | • Any pools of tack coat which may have formed in surface depressions shall be brushed out
label | Reference Documents: EW-CE-DRW-406-001 EW-CE-DRW-416-001 C.9.12
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed off
label | WP
label | Responsibility: FH Engineer/ Asphalt Supervisor
text | Date Completed:
checkpoint | 2.2 - Prime Coat
label | Frequency: Prior to commencing paving final layer
label | Acceptance Criteria: Prime coat to be applied at 1.0L per square meter
label | • Primer sealing shall be carried out under favourable weather conditions and the prepared base course shall be sufficiently dry to permit adherence to and penetration of the base course by the bitumen.
label | • Before primer sealing, the pavement shall be broomed free of all loose material and dust and any defects are to be made good. Should conditions require it, the surface shall be lightly watered immediately prior to the application of the primer.
label | • The primed surface shall be covered with 5mm diorite screenings at the rate of 80 square metres coverage to one cubic metre of screenings and rolled with a 6 - 8 tonne roller until screenings are firmly embedded in the primer.
label | Reference Documents: EW-CE-DRW-406-001 EW-CE-DRW-416-001 C.9.12
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed off
label | WP
label | Responsibility: FH Engineer/ Asphalt Supervisor
text | Date Completed:
checkpoint | 2.3 - Commencement of Placing
label | Frequency: Prior to commencing Paving
label | Acceptance Criteria: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Superintendent
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: Hold Point Release
label | HP*
label | Responsibility: FH Engineer / QAV
text | Date Completed:
checkpoint | 2.4 - Delivery of Mix
label | Frequency: Each load
label | Acceptance Criteria: The asphaltic concrete mix shall be placed at a minimum temperature of 140 degrees Celsius immediately on delivery to the spreader
label | Reference Documents: C.9.13
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: Delivery Docket /Asphalt Traceability Sheet
label | IP
label | Responsibility: FH Foreman / Asphalt Supervisor
text | Date Completed:
checkpoint | 2.5 - Layer Thickness and Level Control
label | Frequency: Regularly during paving
label | Acceptance Criteria: Thickness of asphalt layer conforms to asphalt thickness on drawings.
label | • The asphaltic concrete shall be placed in one layer by an approved self-propelled machine spreader, conforming to AS 2150, Section 12.
label | Reference Documents: EW-CE-DRW-416-001, EW-CE-DRW-406-001
label | Inspection / Test Method: Verify
label | Record of conformity: Dips using ruler or dip stick
label | IP
label | Responsibility: FH Foreman / Asphalt Supervisor
text | Date Completed:
checkpoint | 2.6 - Asphalt Placement works
label | Frequency: Each Load
label | Acceptance Criteria: The temperature of the asphaltic concrete at the time of initial rolling must not fall below 120 degrees Celsius.
label | Reference Documents: C.9.13
label | Inspection / Test Method: Verify
label | Record of conformity: Thermometer
label | TP
label | Responsibility: FH Foreman / Asphalt Supervisor
text | Date Completed:
checkpoint | 2.7 - Surface Finish of Wearing Course
label | Frequency: During paving and after final roll
label | Acceptance Criteria: Joints shall be in accordance with AS 2150 Section 12.6.
label | • Form any joints necessary and ensure that the finished profile is smooth and even over the joints without ridges or depressions.
label | • Joints shall be waterproof.
label | • If the asphaltic concrete begins to shove or crack, in no circumstances continue with rolling until the cause has been determined and corrective measures taken. Keep drums and wheels of rollers wet with water and clean during all rolling operations.
label | Reference Documents: C.9.13
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed off
label | IP
label | Responsibility: FH Foreman / Asphalt Supervisor
text | Date Completed:
checkpoint | 2.8 - Kerb and Channel
label | Frequency: During paving and after final roll
label | Acceptance Criteria: Where asphalt is placed against kerb and channel, The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed off
label | IP
label | Responsibility: FH Foreman / Asphalt Supervisor
text | Date Completed:
section | 3 - Testing and Conformance
checkpoint | 3.1 - Compaction
label | Frequency: As Requested
label | Acceptance Criteria: The density of the compacted concrete shall be not less than 97% of the Marshall maximum density.
label | Reference Documents: C.9.13
label | Inspection / Test Method: Verify
label | Record of conformity: Test Report
label | HP
label | Responsibility: FH Engineer/ Lab Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - As-constructed survey and conformance documentation
label | Frequency: Each Lot (1 per day)
label | Acceptance Criteria: Lot Maps shall be completed to show the extent of works for each lot.
label | • Lot Maps shall include layer depth and finished levels at 20m intervals and conformation of ponding checks per lot.
label | ○ Tolerances
label | • Width of prime: + 150mm or - 0mm
label | • Width of primer seal: + 150mm or - 0mm
label | • Thickness: + 5mm or - 0mm
label | • Finished level: + 10mm or - 10mm
label | Reference Documents: C.7.2 (5.), C.7.4 (Table 6)
label | Inspection / Test Method: Verify
label | Record of conformity: Visual match existing / This ITP signed off
label | SCP
label | Responsibility: FH Engineer/ Surveyor
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Sign ITP