## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CTN-ITP-006 - Concrete - Kerbs | itp |  |  |  | Yes | CTN-ITP-006 - Concrete - Kerbs
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents: Drawings and drawing registers
label | Inspection / Test Method: Visual inspection
label | Record of conformity: ITP Signed
label | HP*
label | Responsibility: Site Engineer/ Site Foreman
text | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents: PSP, EMP, TMP, SWMS, WP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: ITP Signed
label | HP*
label | Responsibility: Site Engineer/ Site Foreman
text | Date Completed:
checkpoint | 1.3 - Submission & Approval of Concrete Mix Design
label | Frequency: Prior to first concrete pour
label | Acceptance Criteria: Supplied concrete pre-mixture for kerbs, needs to be in accordance with the supplied Early Works Civil Drawings.
label | • Unless specified, then concrete used in this construction shall conform to AS 3600 and be provided by an approved pre-mixed concrete supplier, conforming with AS 1379.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed, Mix design approval
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | Frequency: Prior to start
label | Acceptance Criteria: Set out work in accordance with drawings. The Engineer and Supervisor will review and confirm set out with surveyor.
label | • No survey/level pegs to be removed by any persons until completion of works.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.2 - Excavation Permit
label | Frequency: Each lot
label | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing.
label | • Plant and equipment shall be appropriate for the task.
label | • Excavation operations shall not disturb areas outside the limit of excavation
label | Reference Documents: Excavation permit
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.3 - Excavation
label | Frequency: Each Lot
label | Acceptance Criteria: Excavation completed to required depth to allow placement of the bedding layer
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.4 - Concrete Placement
label | Frequency: Each Lot
label | Acceptance Criteria: All kerbing shall be constructed from 32 MPa 28 day cylinder test compressive strength concrete manufactured in accordance with AS 3600 for 10mm aggregate. Slump tolernaces to be in accordance with a 50mm slump.
label | • Kerbs to roads shall be constructed of extruded concrete kerbing. Kerbing to smaller radii than can be placed with the extrusion machine used shall be cast insitu to the same cross section as that of the extruded kerbing, except that the cast insitu kerb shall be 100mm deeper than the extruded kerbing and shall be embedded firmly in the road surface to the extra depth. The outward appearance of the extruded and cast insitu kerbing shall be identical.
label | • Where required match all new kerbs to existing level neatly, ensuring minimum 1 in 250 grade, saw cutting and reinstating pavement in front of kerb to fall to new kerb level.
label | Reference Documents: DWG EW-CE-DRW-406-001 C.10.15 C.10.16
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer/ Site Foreman
text | Date Completed:
checkpoint | 2.5 - Pram Crossings
label | Frequency: Each Lot
label | Acceptance Criteria: Ensure that pram crossings are constructed in accordance with requirements for access and mobility and with dimansions as specified on DWG-416-001.
label | • For pram crossings within concrete kerb refer to Figure 24A of AS 1428.1
label | • Kerb ramp allignment in accordance with Clause 7.7.1 of AS1428.1
label | Reference Documents: Figure 24A AS1428.1 DWG-416-001 Clause 7.7.1 of AS1428.1
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer/ Site Foreman
text | Date Completed:
checkpoint | 2.6 - Joints
label | Frequency: Each Joint
label | Acceptance Criteria: Contraction joints shall be constructed at 2.0m intervals, at sides of entry pits and at tangent point of sweeps by complete separation of adjoining sections of the kerb immediately after extrusion.
label | • Joints shall be 3mm wide, clean cut and made vertically through the concrete at right-angles to the direction of the work.
label | • Where kerbing is laid by machine, joints shall be formed in a manner which doe s not cause damage to the adjoining concrete during cutting and to a depth which will prevent cracking elsewhere. In general it can be expected that the cut should extend to at least one-quarter of the depth of the section.
label | • Where kerbing is cast against fixed forms, contraction joints shall be formed by means of a 3mm thick steel plate cut to profile which shall be withdrawn before final finishing.
label | • Expansion Joints shall be constructed at every third contraction joint not less than 24 hours after placing. The expansion joints shall be formed by the sawing of a 10mm gap that completely severs the adjoining sections of the kerb. The gap shall be filled with approved joint filler after the Superintendant and the Local Authority have inspected and approved the cut joints.
label | • All existing pavement adjacent to proposed kerb or proposed joints shall be saw cut in a neat line to the satisfaction of the supervising engineer, and to have 300mm overlap.
label | Reference Documents: EW-CE-DRW-007-001 C.10.17 C.10.18, EW-CE-DRW-406-001
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer/ Site Foreman/Superintendant
text | Date Completed:
checkpoint | 2.7 - Protection of concrete
label | Frequency: Each Lot
label | Acceptance Criteria: Kerbs shall be always protected from bitumen overspray by adequately covering the kerbs with polythene sheeting or similar approved material
label | Reference Documents: C.10.20
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Foreman
text | Date Completed:
checkpoint | 2.8 - Curing - Kerb
label | Frequency: Each Lot
label | Acceptance Criteria: Within two hours of surface finishing, all exposed faces of the completed kerb shall be protected against loss of moisture for a period of not less than 96 hours after placing by shrouding with plastic sheeting or by spraying with a curing compound complying with AS 3799.
label | Reference Documents: C.10.19
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | HP
label | Responsibility: Site Engineer/ Site Foreman
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Completion
checkpoint | 3.1 - Carry out sampling of concrete - strength and consistency
label | Frequency: Each 50m3
label | Acceptance Criteria: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Checklist
label | Record of conformity: ITP Signed/Test Records
label | TP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 3.2 - Tolerances
label | Frequency: Each Lot
label | Acceptance Criteria: Tolerances
label | • Surface: + or - 5mm when tested with a 3m straight edge
label | • Level: + or - 5mm
label | • Line: + or - 10mm
label | Reference Documents: C.7.4 Table 6 (9.)
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer/ Site Foreman
text | Date Completed:
checkpoint | 3.3 - Backfilling
label | Frequency: Each Lot
label | Acceptance Criteria: The backfilling to kerbing shall be placed as shown on the drawings after the curing and acceptance of the kerbing. The backfill material to be a similar material to the locally occurring topsoil, free from debris and compacted adequately to accommodate the driving of rubber tyred domestic vehicles.
label | • After curing, no earlier than 3 days, backfilling shall be completed as per the below:
label | – Topsoil compacted in layers < 150mm
label | – Width ≥ 300mm behind edging to top of edging
label | Reference Documents: C.10.21 Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Foreman
text | Date Completed:
checkpoint | 3.4 - As-constructed survey and conformance documentation
label | Frequency: Each Lot (1 per day)
label | Acceptance Criteria: Lot Maps shall be completed to show the extent of works for each lot.
label | • Lot Maps shall include Width between kerb at 20m intervals, contraction joints, expansion joints and Curing Certification per lot
label | Reference Documents: C.7.2 (7.)
label | Inspection / Test Method: Verify
label | Record of conformity: Visual match existing / This ITP signed off
label | SCP
label | Responsibility: FH Engineer/ Surveyor
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Sign ITP