## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CTN-ITP-007 - Concrete - Footpaths & Islands | itp |  |  |  | Yes | CTN-ITP-007 - Concrete - Footpaths & Islands
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents: Drawings and drawing registers
label | Inspection / Test Method: Visual inspection
label | Record of conformity: ITP Signed
label | HP*
label | Responsibility: Site Engineer/ Site Foreman
text | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents: PSP, EMP, TMP, SWMS, WP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: ITP Signed
label | HP*
label | Responsibility: Site Engineer/ Site Foreman
text | Date Completed:
checkpoint | 1.3 - Concrete Mix Design
label | Frequency: Prior to first concrete pour
label | Acceptance Criteria: Supplied concrete pre-mixture for footpaths, needs to be in accordance with the supplied Early Works Civil Drawings.
label | • Unless specified, then concrete used in this construction shall conform to AS 3600 and be provided by an approved pre-mixed concrete supplier, conforming with AS 1379.
label | Reference Documents: C.11.2 Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed, Mix design approval
label | HP*
label | Responsibility: Site Engineer/ Superintendent
text | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | Frequency: Prior to start
label | Acceptance Criteria: Set out work in accordance with drawings.
label | • The Engineer and Supervisor will review and confirm set out with the surveyor.
label | • No survey/level pegs to be removed by any persons until completion of works.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | HP*
label | Responsibility: Site Engineer/ Superintendent
text | Date Completed:
checkpoint | 2.2 - Excavation Permit
label | Frequency: Each lot
label | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing.
label | • Plant and equipment shall be appropriate for the task.
label | • Excavation operations shall not disturb areas outside the limit of excavation
label | Reference Documents: Excavation permit
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.3 - Excavation
label | Frequency: Each Lot
label | Acceptance Criteria: Excavation completed to required depth to allow placement of the bedding layer
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.4 - Formwork
label | Frequency: Each Lot
label | Acceptance Criteria: Formwork shall comply with the requirements of AS 3610
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.5 - Reinforcement
label | Frequency: Each Lot
label | Acceptance Criteria: Reinforcement must comply with the requirements of AS/NZS 4671.
label | • Concrete Infill pavement reinforcement to be SL82 mesh central.
label | • Concrete Footpath Pavement reinforcement to be SL72 central reinforcement.If required to be stopped or cut either side of expansion joint (EJ)
label | Reference Documents: DWG EW-CE-DRW-406-001, Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.6 - Concrete Placement
label | Frequency: Each Lot
label | Acceptance Criteria: The concrete, when placed, must be well tamped to remove all voids and to work fines to the surface for trowelling.
label | • Concrete Infill pavement to be 150mm depth N25 concrete
label | • Concrete Footpath Pavement to be 100mm depth N25 concrete
label | • Concrete shall be of 25 MPa 28-day cylinder test compressive strength.
label | • The maximum aggregate size shall be 20mm.
label | • The slump shall not exceed 65mm or be less than 25mm
label | Reference Documents: DWG EW-CE-DRW-406-001 C.11.2
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer/ Site Foreman
text | Date Completed:
checkpoint | 2.7 - Surface Finish
label | Frequency: Each Lot
label | Acceptance Criteria: A brushed finish shall be provided to the surface of the slab with joints and edges polished smooth for 80mm width with jointing and edging tools.
label | • The alignment of the edge of the path is to be straight and true to line.
label | • Deviations from alignment or from specified width will not be accepted.
label | Reference Documents: C.11.5
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.8 - Joints
label | Frequency: Each Joint
label | Acceptance Criteria: Expansion Joint
label | • A 19mm expansion joint shall be provided whenever rigid pavements abut fixed structures or at max. 15m centres to footpaths.
label | • An approved joint sealer shall be inserted in the joint and finished flush with the surface of the path.
label | • Contraction Joints in footpaths and cycleways shall be constructed at 2.0 metre centres for footpaths.
label | • Concrete Infill Pavements to have Sawcut/tool joint at every 1200mm (DWG 406)
label | Reference Documents: EW-CE-DRW-007-001 C.11.3 C.11.4 EW-CE-DRW-406-001
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer/ Site Foreman
text | Date Completed:
checkpoint | 2.9 - Protection of concrete
label | Frequency: Each Lot
label | Acceptance Criteria: The finished path shall be protected from damage by passers-by and with polythene film for 24 hours after completion if rainfall during this period is apparent.
label | • Barricade, warning signs and lights shall be erected to prevent damage of the footpath from vehicles and pedestrians for not less than 24 hours after completion.
label | Reference Documents: C.11.5 C.11.7
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Foreman
text | Date Completed:
checkpoint | 2.10 - Curing - Pedestrian Footpaths
label | Frequency: Each Lot
label | Acceptance Criteria: The entire footpath shall be protected against loss of moisture for a period of not less than 72 hours after placing by shrouding with polythene sheeting or by spraying with a curing compound complying with AS 3799.
label | Reference Documents: C.11.6
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | HP
label | Responsibility: Site Engineer/ Site Foreman
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Completion
checkpoint | 3.1 - Carry out sampling of concrete - strength and consistency
label | Frequency: Each 50m3
label | Acceptance Criteria: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Checklist
label | Record of conformity: ITP Signed/Test Records
label | TP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 3.2 - Backfilling
label | Frequency: Each Lot
label | Acceptance Criteria: Contractor is reasonable to ensure the site is made safe and clean, this includes All cement droppings, slurry, etc. and surplus materials to be removed from site, cleaning of surrounding strcutres from conrere splats.
label | All formwork, pegs, stakes, etc. shall be removed after the curing of the path has been completed.
label | Reference Documents: C.11.8
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Foreman
text | Date Completed:
checkpoint | 3.3 - As-constructed survey and conformance documentation
label | Frequency: Each Lot (1 per day)
label | Acceptance Criteria: Lot Maps shall be completed to show the extent of works for each lot.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: Visual match existing / This ITP signed off
label | SCP
label | Responsibility: FH Engineer/ Surveyor
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Sign ITP