## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CTN-ITP-008 - Cast In-Situ Pits | itp |  |  |  | Yes | CTN-ITP-008 - Cast In-Situ Pits
section | 1 - Preliminary Works
checkpoint | 1.1 - Check that current revision drawings are being used
label | Frequency: Prior to Commencing Work
label | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | Reference Documents: IFC Project Drawings/ Drawing Register
label | Inspection / Test Method: Document review
label | Record of conformity: Latest revision IFC drawings, ITP signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents: OHSMP, EMP, TMS, SWMS, WP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
section | 2 - Material Conformance
checkpoint | 2.1 - Materials & source Approval - In-Situ Pits
label | Frequency: Prior to works commencing, 1 per delivery
label | Acceptance Criteria: In-situ Pit resources including bedding, reinforcing steel and formwork shall be as specified or as shown on the Drawings.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: Receival inspection checklist
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.2 - Materials & source Approval - Pit Covers
label | Frequency: Prior to works commencing, 1 per delivery
label | Acceptance Criteria: Pit covers shall be either cast iron, precast concrete covers or gratings as per drawings and shall be constructed and fixed to pits in accordance with relevant Tasmanian Standard Drawings
label | Reference Documents: EW-CE-DRW-526-001 - Pit Schedule C.5.16
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: Receival inspection checklist
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.3 - Materials & source Approval - Step Irons
label | Frequency: Prior to works commencing, 1 per delivery
label | Acceptance Criteria: For pit depths greater than 1200mm, provide 24mm galvanized hot dipped step irons or approved equivalent at 300mm centres measured from top of cover to invert level of the base as detailed on the drawings and in accordance with AS 1657-1992.
label | Reference Documents: EW-CE-DRW-526-001 C.5.17
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: Receival inspection checklist
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.4 - Source In-situ Pit Material
label | Frequency: Each Lot
label | Acceptance Criteria: Concrete shall be at minimum 28-day strength, F’c of 32 MPa and when placed shall be well rammed to ensure thorough consolidation.
label | Reference Documents: C.5.15
label | Inspection / Test Method: Verify
label | Record of conformity: Mix Design
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 3 - Construction \ Erection of Formwork
checkpoint | 3.1 - Pouring Concrete
label | Frequency: Each Lot
label | Acceptance Criteria: Excavation depth shall be as per specified or as shown on Drawings to accommodate structure including blinding layer / bedding.
label | • Excavations for pits shall be trimmed neatly to size so as to give the exact thickness of walls as required.
label | Reference Documents: EW-CE-DRW-526-001 - Pit Schedule C.5.15
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 3.2 - Bedding
label | Frequency: Each Lot
label | Acceptance Criteria: Pit base to be poured on 75mm min. depth of 75mm Class 3 FCR.
label | Reference Documents: EW-CE-DRW-526-001 C.5.15
label | Inspection / Test Method: Inspection
label | Record of conformity: This ITP signed
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Formwork
label | Frequency: Each Lot
label | Acceptance Criteria: Formwork shall conform to shapes, lines, levels and dimensions of the concrete shown or indicated on the Drawings.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 3.4 - Subsurface Drainage Accomodation
label | Frequency: Each Lot
label | Acceptance Criteria: Form holes in walls to accommodate subsurface drains as directed.
label | Reference Documents: EW-CE-DRW-526-001
label | Inspection / Test Method: Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 4 - Reinforcement
checkpoint | 4.1 - Steel Fixing
label | Frequency: Each Lot
label | Acceptance Criteria: Reinforcement type and design to be in accordance with reinforcement schedule on DRW-526-001 with a 300 min. lap
label | • Reinforcing steel shall be bent and placed in accordance with AS 4671 and sufficient bar chairs shall be installed to ensure reinforcement is in the correct position.
label | Reference Documents: EW-CE-DRW-526-001 Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 4.2 - Reinforcement Installation
label | Frequency: Each Lot
label | Acceptance Criteria: Pre-pour Checklist Completed:
label | – Position and spacing check and recorded
label | – Cover checked and recorded
label | – Reinforcing supports checked and recorded
label | – Laps at required length
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 5 - Inspections
checkpoint | 5.1 - Pre-pour Inspection - Pit Base and Pit Walls
label | Frequency: Each Lot
label | Acceptance Criteria: Concrete shall not be placed until:
label | (i) the evidence that the forms, reinforcement, any stressing materials and embedments conforming to the requirements of this specification and the drawings, has been reviewed by the Superintendent
label | (ii) all foreign material has been completely removed from the forms
label | • Superintendent requires 48 HR notice for inspection.
label | Reference Documents: C.5.15
label | Inspection / Test Method: Inspection
label | Record of conformity: Pre Pour Inspection Checklist Completed
label | HP
label | Responsibility: Site Engineer/ Superintendant
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 6 - Placing and Finishing Concrete
checkpoint | 6.1 - Pour in-situ Pits
label | Frequency: Each Lot
label | Acceptance Criteria: Pits shall be constructed to the detail shown on the drawings
label | Reference Documents: EW-CE-DRW-526-001
label | Inspection / Test Method: Inspection
label | Record of conformity: Concrete pour record and delivery docket
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 6.2 - Finishing
label | Frequency: Each Lot
label | Acceptance Criteria: Concrete to be vibrated to ensure compaction and air voids removed. Screed finish required on exposed surfaces
label | • Concrete surface finishes to meet Class 4 requirements as per table 3.2.3 and 3.3.5.1 of AS 3610. (Attached Below)
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: Completion of prepour inspection checklist
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 6.3 - Installation of Pit Cover
label | Frequency: Each Lot
label | Acceptance Criteria: Precast concrete cover or cast iron concrete infill SEP cover to be installed as scheduled
label | Reference Documents: EW-CE-DRW-526-001
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 6.4 - Concrete Testing
label | Frequency: Each Lot
label | Acceptance Criteria: Concrete Testing to be carried out as per specifications. In AS 1379
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: Test Results
label | TP
label | Responsibility: Site Engineer
text | Date Completed:
section | 7 - Post Pour Details and Inspections
checkpoint | 7.1 - Concrete Curing
label | Frequency: Each Lot
label | Acceptance Criteria: Concrete to be cured as per project specifications
label | Reference Documents: EW-CE-SPC-000001
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 7.1 - Removal of Formwork
label | Frequency: Each Lot
label | Acceptance Criteria: Stripping of vertical faces in accordance with AS 3610 as per Table C2. See Table C2 Below.
label | – – – – – – – – – – – – – – – – –
label | Table C2 Vertical Face Formwork Minimum Stripping Times After Casting
label | Classification ¦¦ Average temperature (Greater than 20°C \ Between 12°C and 20°C \ Between 5°C and 12°C)
label | – – – – – – – – – – – – – – – – –
label | Class 1, Class 2 or Class 3 (see Note 1) ¦¦ 1 d \ 2 d \ 3d
label | Class 4 or Class 5 ¦¦ 9 h \ 12 h \ 18 h
label | All ¦¦ A minimum of 1 d applies to the stripping of vertical faces where frost damage is likely
label | – – – – – – – – – – – – – – – – –
label | Reference Documents: AS 3610
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 7.2 - Allowable Tolerances Level & Alignment
label | Frequency: Each Lot
label | Acceptance Criteria: The horizontal deviation of any piped or box culverted drain shall not exceed 25mm from the true alignment. There shall be no obvious sharp changes of direction.
label | • The maximum deviation from grade shall not exceed + or - 10mm for grades flatter than 1 in 500 and + or - 20mm for grades steeper than 1 in 500.
label | • The grade of any piped, box culverted, or open drain shall not exceed + or - 5% for grades flatter than 1 in 500 and + or - 10% for grades steeper than 1 in 500.
label | • Invert levels at structures shall not exceed + or - 10mm from the design invert.
label | • As-built survey completed for lot
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | SCP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 7.3 - Post-pour Checklist
label | Frequency: Each Lot
label | Acceptance Criteria: Completion of Pre Pour checklist quality checks.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Inspection
label | Record of conformity: Pre Pour Inspection Checklist Completed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 7.4 - Backfilling Around Pits
label | Frequency: Each Lot
label | Acceptance Criteria: Backfilling to match pavement design and to occur min. 72 hours post concrete pour.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Inspection
label | Record of conformity: This ITP Signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Sign ITP