## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | a21ef0af-51d3-4fb3-ab40-73ff10f2bf79 |  | checklist | Standard Wall Lining Checklist |  |  |  |  | Yes | QA - Standard Wall Lining Checklist | 0f617939-35aa-4b7b-9b23-93f4aff78bf5
checkpoint-status | 53413b9d-e493-40cc-b9b8-add79c2baefd |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 474e9605-7417-417c-9473-559ee9186fdb |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 4e7457b7-5acb-48e2-b600-620f545d210b |  | checkpoint | Correct Standard Wall lining used as per spec
checkpoint-status | 882d1474-0e70-430c-9844-703a55386bd2 |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | 86b8df23-a338-4671-bae1-d51cf1179a30 |  | checkpoint | Gaps and joints acceptable
checkpoint-status | 0ea0d2f5-a109-4519-a257-f2fef7feb837 |  | checkpoint | All screws installed to correct depth
checkpoint-status | 4e264fcd-6bc5-4c48-b585-9310c933fcb2 |  | checkpoint | No overcut service penetrations
checkpoint-status | af31a40c-5e62-4807-9957-1a1e35ffe766 |  | checkpoint | Correct sealant used
checkpoint-status | 5fbfb616-1a46-48c6-a890-7d5fe0651b2f |  | checkpoint | Standard Wall Lining completed, checked and Supervisor sign off
checkpoint-status | 553b2846-a6b2-4142-8568-4b676e09edbc |  | checkpoint | Area left clean & tidy
checklist-flat | e92919b7-db01-4629-b450-0b726d3e1246 |  | checklist | IT Walls / Fire Rated Lining Checklist |  |  |  |  | Yes | QA - IT Walls / Fire Rated Lining Checklist | 157da02b-162c-4d3b-8f0f-509ec20fd12e
checkpoint-status | 85982a5a-b460-491c-86af-017f1a416b16 |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 236073d4-eb82-4273-9622-249f98a72394 |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 39531a49-53ad-42b9-99df-22e39bdd7823 |  | checkpoint | Correct IT Walls / Fire Rated lining used as per spec
checkpoint-status | 5dcd2a6c-0594-4ad8-8bc7-f8ce12f965a0 |  | checkpoint | First layer fitted as per GIB spec & ready for inspection
checkpoint-status | 2ffcf64e-8de1-44b4-87e2-d7809756e208 |  | checkpoint | Second layer fitted as per GIB spec & ready for inspection
checkpoint-status | ed28c79a-c02f-4fed-81d5-bd148a666338 |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | 45b6112d-c46c-4e8a-8b40-a05cb1bf5783 |  | checkpoint | Gaps and joints acceptable
checkpoint-status | defbb826-c85f-4383-88f8-e2dd3eac2b0c |  | checkpoint | All screws installed to correct depth
checkpoint-status | 3c3e9510-c9b0-460a-a679-d491763c0ef5 |  | checkpoint | No overcut service penetrations
checkpoint-status | 03ff505b-9375-48b9-88bf-1c6ed20b2ef1 |  | checkpoint | Correct sealant used
checkpoint-status | 7000c9ba-58ea-4e0d-95dd-aa894a5fcedf |  | checkpoint | IT Walls / Fire Rated Lining completed, checked and Supervisor sign off
checkpoint-status | d6213630-b5ba-4257-9481-ac2276d8c91d |  | checkpoint | Area left clean & tidy
checklist-flat | 9b75fb9d-1c69-4c5d-aac8-29458de86882 |  | checklist | Acoustic Lining Checklist |  |  |  |  | Yes | QA - Acoustic Lining Checklist | 1ae80975-39ad-423a-a905-fece5f871a93
checkpoint-status | 46256415-8ebe-4e9f-ab4b-4c0d5439da90 |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 95f73969-839e-4038-b71b-6fa7337dfec2 |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 1698d94e-46ea-412d-8387-3c39b47918a8 |  | checkpoint | Correct Acoustic lining used as per spec
checkpoint-status | 8eed9369-5ae5-4ddc-b35d-afa3cc9f96e3 |  | checkpoint | First layer fitted as per GIB spec & ready for inspection
checkpoint-status | 70121760-36f5-4eb3-b5fe-91e278bd9a94 |  | checkpoint | Second layer fitted as per GIB spec & ready for inspection
checkpoint-status | ffc11b3a-59a8-4c8e-8016-4e9752066d78 |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | 86a3d8ed-5385-4330-b7a8-6a5d71d882f2 |  | checkpoint | Gaps and joints acceptable
checkpoint-status | 360a5441-3739-4c77-acf8-4a1ca97ffe60 |  | checkpoint | All screws installed to correct depth
checkpoint-status | aa172397-fa5b-4e3a-a959-37ab32224d65 |  | checkpoint | No overcut service penetrations
checkpoint-status | 095de529-4bd6-4535-b8e7-f62ceeba8d9a |  | checkpoint | Correct sealant used
checkpoint-status | 354846ab-893d-4d48-a583-60b04f7f659b |  | checkpoint | Acoustic Lining completed, checked and Supervisor sign off
checkpoint-status | 606dea8f-f9ec-4ace-839e-f5a848c5e008 |  | checkpoint | Area left clean & tidy
checklist-flat | 164ec8ed-637a-4cda-8fe6-07253a6a16f8 |  | checklist | Toolbox Safety Meeting Minutes |  |  |  |  | Yes | Add Toolbox Safety Meeting Minutes | 1ce4b78d-08cf-4b45-9bd2-c68de9967321
checkpoint-status | dcc4fa11-d5cc-4277-9f16-d52a5c1b0743 |  | checkpoint | Toolbox Safety Meeting Minutes:
text | 581da611-017a-51d5-89fb-6b37b1ed84e3 |  | textbox | Project/Site:
text | 8f51f5c9-bc0c-5a3f-8c72-b65d11f0880d |  | textbox | Main Contractor
text | 0d94939a-c296-55fd-b84c-d60b7f6b3269 |  | textbox | Foreman/Supervisor
checkpoint-status | e64d013c-ed15-406e-887c-d84528cf12d7 |  | checkpoint | Attendees, photo of team
checkpoint-status | b44270a7-52be-41d3-be9f-526853e614a7 |  | checkpoint | Site Activity/Safe Work Practices/Accident/Incident Investigations Discussed:
checkpoint-status | 230011be-0aad-44dc-a649-5b703909378e |  | checkpoint | Toolbox Topics
boolean | 4a305552-f6bb-5eed-82ef-606e2688a2f0 |  | tickbox | Trip Hazards
boolean | ef784964-1e36-5827-a916-13094beac9cf |  | tickbox | Moving Plant and Machinery
boolean | 365064a0-d0fc-5d86-a225-ab8477fdf88b |  | tickbox | Low Hung Scaffolding/Protruding Objects
boolean | af78b090-2d6a-51df-81f7-6ec291fd8693 |  | tickbox | PPE
boolean | d381c159-ebdd-56ad-951e-ec856a787edb |  | tickbox | Dust
boolean | ada8abb1-869a-5ee1-bd9e-01ca08222a15 |  | tickbox | Signing In/Out
boolean | 4d193c93-a007-5ece-a734-4a0b71e61dd3 |  | tickbox | Covid Protocols
boolean | 2dd4cfe3-2efd-598c-bcfc-c14d74c29ced |  | tickbox | Exclusion Zones
boolean | b32f7f20-6e95-504c-b9d3-bba109bb0032 |  | tickbox | Weather/Slippery Surfaces
text | 74c0650f-5d12-5791-965d-67533a2b3fd6 |  | textbox | Others please list:
checkpoint-status | 461c67ab-d8d3-4564-a2af-a0e79910fdae |  | checkpoint | Employee Issues Raised:
boolean | 9985a37d-98e0-54b8-976c-7585325f40d5 |  | tickbox | Asked, no concerns
boolean | 79a91242-4660-5821-8913-8158b23856b1 |  | tickbox | Concerns as below
text | e9847920-b860-5883-a721-e7509957e999 |  | textbox | Concerns:
checkpoint-status | 5d0236cf-4f29-4193-ae81-6f496f90c27f |  | checkpoint | All present site inducted?
label | b3fa2d92-eac7-5df7-b771-25a8e3d8a03d |  | note | MUST SELECT PASS OR FAIL!
text | 522ec596-e9a2-5a3a-a4ae-275a3e56a5f7 |  | textbox | Action:
checkpoint-status | 27cb7a75-2c54-4900-b192-b7780a153934 |  | checkpoint | SSSP Onsite/Up to Date
label | 98e72b5e-b086-5228-a210-539361cc3035 |  | note | MUST SELECT PASS OR FAIL!
boolean | 0c5600ef-7b4c-5a4a-84e7-974117aa6747 |  | tickbox | Everyone on Competency Register
boolean | a33c08ad-23a5-5899-8bd5-88affba7e51c |  | tickbox | Everyone read/signed Task Analysis
text | be1e0636-3d07-5d4e-8ebe-d6f276a76490 |  | textbox | Action:
checkpoint-status | 9ff1d678-c7dd-4ea2-b324-5022737ba24d |  | checkpoint | PPE Gear
label | e37c2732-8e19-5fcf-b18a-85471ffe9642 |  | note | MUST SELECT PASS OR FAIL!
boolean | 5456fc7e-426e-5e5e-a488-751d17cb5d5d |  | tickbox | Hard Hat
boolean | dc6cac00-1c17-52c2-90cc-e8cfc2bab4de |  | tickbox | Hi Vis shirt/jacket
boolean | 24ca0681-ecfc-5fa7-88ea-aba723cda279 |  | tickbox | Steel cap boots
boolean | 6d8d3ff7-c41b-5db3-9a94-af8cf38f37a6 |  | tickbox | Eye protection
boolean | 287e94ff-a38e-5007-a52a-f79e1d079eae |  | tickbox | Mask - minimum P1 (no surgical masks)
boolean | acf492ae-c0a3-5be5-8af2-b774718540a2 |  | tickbox | Gloves
text | 5a910561-5b3d-58d5-8782-a47490f7a21f |  | textbox | Action:
checkpoint-status | 27070eb5-28c3-4829-a42f-5ff94c4bca66 |  | checkpoint | Site safe registered
label | 46db7b79-ca3b-556c-bba3-93ea3034cfed |  | note | MUST SELECT PASS OR FAIL!
text | ddde4b8c-084d-5cb0-9201-e2ffad5c2127 |  | textbox | Action:
checkpoint-status | 018e016c-fcc7-4668-964f-2d9b48fe8d44 |  | checkpoint | Safe Equipment/Equipment Tagged
checkpoint-status | 343e9eb8-dc26-4f96-984f-4b6196da9fec |  | checkpoint | Environmental
boolean | 8de0210f-74a2-57aa-bffa-8ebebdaf2893 |  | tickbox | Skip bin onsite
boolean | 4b55d394-ead9-527b-b201-99cdb89e4779 |  | tickbox | Wash out facility onsite
boolean | 1a77cf8a-6129-5ba3-b444-b7fdfd805966 |  | tickbox | Site clean and ready to start
text | 56322da7-d6cf-5f5a-a76c-d9537f8c1175 |  | textbox | Action:
checkpoint-status | e11d3b86-29ba-4bba-8936-1c20db621993 |  | checkpoint | Ladders/Scaffolding/EWP
boolean | 2d6942cf-063a-589e-88be-6b17f8f4ada7 |  | tickbox | Scaffold checked/green tag
boolean | 2f316d7d-41c6-579c-be86-4e91e0ad0c26 |  | tickbox | Ladders Platform/A Frame
boolean | d09c7f5e-308d-50b2-adb3-e8acabd92350 |  | tickbox | Ladders in good order - check stays
boolean | d934af1f-8da9-5ac7-9275-56a5ed1411e0 |  | tickbox | Operator of EWP has current/valid licence
boolean | 447b724e-e81a-5222-acc3-8c7b13114413 |  | tickbox | Log Book
text | b973a276-57dc-5843-8492-52586c5b717a |  | textbox | Action:
checkpoint-status | 17da309f-13ea-4fea-946a-2d5b4e7ab695 |  | checkpoint | Areas of concern:
text | d62bdab2-0f4c-598c-8d59-8f7df87e024d |  | textbox | List Concerns:
checklist-flat | 0628ce08-feaa-444f-b2bc-e15f2367aaf6 |  | checklist | Speedwall Checklist |  |  |  |  | Yes | QA - Speedwall Checklist | 50a66660-93b6-474a-bd4f-a5f0f1298aa3
checkpoint-status | 4ee7ebc8-2f42-4a95-8f10-3e05982b757e |  | checkpoint | Work area ready and approval to progress
checkpoint-status | b5fb519e-6ca0-4d2e-83bc-8b593d84efec |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 3baaddbb-4c38-4099-9eaf-f724c4529f84 |  | checkpoint | Bottom track correctly installed (size, location and fixings)
checkpoint-status | 061e30cb-bc00-443b-83ed-aa038d3651db |  | checkpoint | Top track correctly installed (size, location and fixings)
checkpoint-status | 798a329e-28b9-465d-b816-41f6fca273b6 |  | checkpoint | 30mm minimum gap at head
checkpoint-status | 0020b2b1-1e66-438a-acb1-30801468edb2 |  | checkpoint | Fixings installed as per spec
checkpoint-status | 14de590f-6fc7-4250-af2d-892fb1850786 |  | checkpoint | Fire sealant installed correctly and photographed
checkpoint-status | 7e7ee48c-1693-47ae-a015-889204bbdd55 |  | checkpoint | All joints sealed correctly as per specification
checkpoint-status | 7f382fc8-1ce2-4fcd-80d8-f7bfc3179afb |  | checkpoint | Openings installed for services as per drawings
checkpoint-status | 9bc1f990-1c6c-4c1d-bf0d-6610a16dc596 |  | checkpoint | Speedwall completed, checked and Supervisor sign off
checkpoint-status | c613cc52-a1f9-4c83-ab64-6eae45ee2ba9 |  | checkpoint | Area left clean & tidy
checklist-flat | f1ba624f-5aa5-40c5-a4ca-bcc8bd3ed2ae |  | checklist | Stopping Checklist |  |  |  |  | Yes | QA - Stopping Checklist | 6e80855f-9e42-4350-83fa-b4a2808041ca
checkpoint-status | ce1c59ef-21fc-4b1d-bbe3-367da6d0fa93 |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 8087a51c-2991-4cb5-a843-addd604ef0bd |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 2331fb60-2eee-4988-9951-34202ff33edd |  | checkpoint | Appropriate preparation to substrate & area (dust control, dropsheets etc)
checkpoint-status | fcc1f8d5-a8e0-4cc0-8955-90110af6b768 |  | checkpoint | Correct stopping product and applied correctly to FRR walls or ceilings to Level 3 finish
checkpoint-status | 140351c4-d837-4e5f-b28d-6895e95c470b |  | checkpoint | Correct stopping product and applied correctly to Level 4 finish
checkpoint-status | 58c2ca0d-5ba3-4fb5-85a8-0fc39aeda85d |  | checkpoint | Square stopping, coving, slimlines and joints checked and acceptable
checkpoint-status | 4eaa875b-b647-4273-9807-f5436d5714a4 |  | checkpoint | Adequate drying time between applications & no visible bubbling
checkpoint-status | 10ba69b3-7714-48f5-851a-781b1d5d488b |  | checkpoint | All sanding completed as required
checkpoint-status | b7eff325-159a-4bb8-b9db-305564dbb6b8 |  | checkpoint | All Stopping completed, checked and Supervisor sign off
checkpoint-status | 37982684-68d9-45e7-a1ce-4f1a0353caf6 |  | checkpoint | Area left clean & tidy
checklist-flat | 4c9c391a-6f77-4216-b89c-1299f9bd8460 |  | checklist | Metal Ceiling Grid Checklist |  |  |  |  | Yes | QA - Metal Ceiling Grid Checklist | 79a1c112-0e05-42e7-9755-6e9488824d9e
checkpoint-status | 7d1ffe2e-dffc-48fe-82bd-0f17efed6815 |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 768398fe-87ae-475f-8432-ae4dfa69b877 |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 0b549052-e887-490d-81fb-3ad226c27e52 |  | checkpoint | Installed level and to correct heights
checkpoint-status | 086a89a9-c2b2-4b2e-88a0-62ca229d2d82 |  | checkpoint | Correct fixings and clips installed
checkpoint-status | c12e7326-3a86-4d6e-ac58-26875158afea |  | checkpoint | Member centres correct
checkpoint-status | ce8616bf-8f36-4501-b751-b4fc9dc5afb9 |  | checkpoint | Earth strap installed
checkpoint-status | a6bacba5-650d-4db6-8063-5d47ee3179c2 |  | checkpoint | Hatches openings trimmed out and installed
checkpoint-status | 3ac7d830-3bbc-4017-b219-31977f6929dc |  | checkpoint | Bulkheads installed plumb/level/square
checkpoint-status | ecccd27f-d253-4090-84a1-14bd28f92463 |  | checkpoint | Metal ceiling grid completed, checked and Supervisor sign off
checkpoint-status | 1b89044e-0be7-40eb-b7c4-cde87df29aaa |  | checkpoint | Area left clean & tidy
checklist-flat | 32ecc0fb-bb6c-4f2b-9bbc-fc39530a8870 |  | checklist | Painting Checklist |  |  |  |  | Yes | QA - Painting Checklist | 83be5527-03b3-4c1d-9b79-1a563aebf668
checkpoint-status | 1cf1ec68-e438-4c09-96af-b6b5ade7903b |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 8c77aa6f-9639-40d5-a89e-7016f1c8316e |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 0c9191fc-828d-48d7-9e41-be2977ec1378 |  | checkpoint | Sealer primer coat applied
checkpoint-status | f51b5bf2-ac6e-4910-ae54-86cc589d9f08 |  | checkpoint | Light check performed and passed, failed areas addressed
checkpoint-status | 2be79c79-2b2f-4951-a19c-8c8020ff4e1b |  | checkpoint | Top coat 1 applied
checkpoint-status | d273bcf6-5c10-4779-a1ea-274e71b2343c |  | checkpoint | Top coat 2 applied
checkpoint-status | 8b73510e-6d3b-479f-8160-96da8c2b5fdc |  | checkpoint | Painting completed correctly, checked and Supervisor sign off
checkpoint-status | 3a348896-c716-414e-b57f-f24f2ca99ece |  | checkpoint | Area left clean & tidy
checklist-flat | 465bb3f9-e33b-4e1d-85a0-d3103e790d6c |  | checklist | Standard Ceiling Lining Checklist |  |  |  |  | Yes | QA - Standard Ceiling Lining Checklist | a128245d-9bcf-4031-a3a3-e1afcb84f832
checkpoint-status | 347d58cd-ab3f-4343-a773-6382d837d140 |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 1923f03c-aed2-44fd-8195-9034bc19a78b |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 120ac85e-2b07-4a83-b8c0-ff7ccb033cc3 |  | checkpoint | Correct Ceiling lining used as per spec
checkpoint-status | ef5d60f7-d306-4c1f-b56c-d64a36f62ca8 |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | adaf3f8c-c43f-43c9-9c4c-a66e0cf69b46 |  | checkpoint | Gaps and joints acceptable
checkpoint-status | 1ae51660-e5fc-49a0-acf7-1a325f243d60 |  | checkpoint | All screws installed to correct depth
checkpoint-status | 1472bcd5-9b8c-4ba3-8b52-b5a00af8e6cb |  | checkpoint | No overcut service penetrations
checkpoint-status | 7cfc0bc0-5b0b-4bcc-b9a9-d85ad9fedf65 |  | checkpoint | Correct sealant used
checkpoint-status | d8700419-3fec-40fb-870f-931f6a350640 |  | checkpoint | Standard Ceiling Lining completed, checked and Supervisor sign off
checkpoint-status | 053dec1e-c9a7-4c6e-9d98-7ed61492f0cd |  | checkpoint | Area left clean & tidy
checklist-flat | 53cbcf50-48fa-48fa-a09a-70e0ebf3c046 |  | checklist | Korok Riser Panel |  |  |  |  | Yes | QA - Korok Riser Panel | a96b35cd-0e26-4261-99eb-9ef341edced6
checkpoint-status | a680460b-8b11-4e78-be72-ad8a31f337c0 |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 2c6a1ebc-371f-4244-a66f-a2f4439872f8 |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | ceab3c32-473c-4d61-a6e8-47bc58173a80 |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status | dc63ac54-2a9b-4219-8942-cfba4c6bfb8f |  | checkpoint | C - Track installed to perimeter checked and correct with sealant
checkpoint-status | 7a2d6c50-13c4-42a0-948b-15a3f7c51cdb |  | checkpoint | C- Track fixings correct
checkpoint-status | 43a0f6e4-b078-4b3c-a2b0-6987e3c0f523 |  | checkpoint | Korok Panels installed horizontally correctly
checkpoint-status | 71fe6b6d-d4f9-4a0d-a7db-c0f676f1fa3e |  | checkpoint | Sealant applied to perimeter of walls and screwed off correctly
checkpoint-status | 142673b7-b5ab-43af-87ee-6167b55b5759 |  | checkpoint | Plastic Film removed
checkpoint-status | 647dd91b-03a6-4114-9dbe-4c609124204f |  | checkpoint | All Korok Panels completed correctly, checked & Supervisor sign off
checkpoint-status | 1c8573a8-3ff4-4123-ae71-38e1b948a56e |  | checkpoint | Area left clean & tidy
checklist-flat | 8e94f1fa-59b8-4d67-b80d-ccce25223dcd |  | checklist | Insulation Checklist |  |  |  |  | Yes | QA - Insulation Checklist | b27cf796-2f83-4635-ab1b-5dabc4565b34
checkpoint-status | e876176e-a0c2-4da4-b62e-fc4f904339a0 |  | checkpoint | Walls dry and ready for installation
checkpoint-status | 9f7af6e7-ff88-445f-b051-699d595ea704 |  | checkpoint | Correct product and R values installed
checkpoint-status | ee8fcc17-8d8f-4e79-9fe0-5326171e1f54 |  | checkpoint | Installed correctly with no gaps or bunching
checkpoint-status | 273dc24e-f140-43c8-a335-217d6cc449a6 |  | checkpoint | Installed correctly around services
checkpoint-status | e248e798-9ded-41af-a69b-f69c37c56080 |  | checkpoint | Insulation completed correctly, checked and Supervisor sign off
checkpoint-status | 1aa7df30-363c-45cf-a526-b80a2922b229 |  | checkpoint | Area left clean & tidy
checklist-flat | 07199c1d-0b4d-40e7-a376-d076c282bba3 |  | checklist | Add Variation Checklist |  |  |  |  | Yes | Add Variation Checklist | b564b1ff-0e65-4fc3-940f-7d95a31bfb74
checkpoint-status | dec4eaa0-2d8f-41c2-a986-70ac757789e5 |  | checkpoint | Details entered below or photographed
checkpoint-status | f9315263-27c1-4b60-aede-a3dc76823e34 |  | checkpoint | Variation Approved
checkpoint-status | 01710171-aea1-4ddd-899f-5312dfa34f43 |  | checkpoint | Variation Completed
checklist-flat | f8630331-30a5-4901-9186-bc2768884784 |  | checklist | Finishing Lines Checklist |  |  |  |  | Yes | QA - Finishing Lines Checklist | d6b3bc3a-b465-42f2-a172-9b26930a6cd3
checkpoint-status | 7f806b91-b66d-4e01-95b2-13ca571c324b |  | checkpoint | Work area ready and approval to progress
checkpoint-status | b26342f8-1712-4ed4-82f0-6b051352dac4 |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | d6a84279-1930-4d7a-89e3-9af49d9721b6 |  | checkpoint | Timber skirtings installed correctly and checked
checkpoint-status | 72310f9d-ca58-474e-88f8-3c210b6ff1fa |  | checkpoint | Timber architraves installed correctly and checked
checkpoint-status | 5e853c00-ed19-4092-b42f-67ecd65950a6 |  | checkpoint | Timber Finishing Lines completed correctly, checked & Supervisor sign off
checkpoint-status | 101266e1-986f-42f0-92e9-bd0f984a312d |  | checkpoint | Area left clean & tidy
checklist-flat | 34bc6c9c-88e1-4ac1-b263-32b950a62acd |  | checklist | Site Safety Checklist |  |  |  |  | Yes | Add Site Safety Checklist | e00e564f-97f2-43a7-9661-07fe295a7ee1
checkpoint-status | 026ac7be-1470-485f-8479-695c2127c176 |  | checkpoint | Work area clean and tidy
checkpoint-status | 5bafcb24-49cb-49ff-9cad-781464e07ab6 |  | checkpoint | P.P.E. safety gear in use
checkpoint-status | 1e3921f4-53f5-48c5-8925-db9ceacf774a |  | checkpoint | First aid kit available
checkpoint-status | 56aa49be-e7f8-4726-8c5f-41304a74ff08 |  | checkpoint | Stock material stored safely
checkpoint-status | bc4dfc96-b7b1-41ad-948f-4511e7630397 |  | checkpoint | Hazchem products stored correctly
checkpoint-status | 926048a6-715a-4151-ab1e-8e2f98b01b0a |  | checkpoint | Electrical equipment fit for purpose, tagged and used safely
checkpoint-status | b904f320-40c1-4045-9565-3c926ed949a0 |  | checkpoint | Ladders fit for purpose and site approved
checkpoint-status | dc5c4b0c-6e7c-40bf-8b1a-bed206bf63a9 |  | checkpoint | Fixed scaffold is safe and being used correctly
checkpoint-status | 2e4f1420-1129-4f1e-984a-dd6c198b8a93 |  | checkpoint | Portable scaffold is safe and being used correctly
checkpoint-status | 09ecd2d0-bd13-4e06-9486-603f090c6ed5 |  | checkpoint | All fall hazards have suitable fall protection in place or barricades
checkpoint-status | 018d8aa6-3b1c-4378-b57e-73bdd9cb2f94 |  | checkpoint | Toolbox meetings being held
checkpoint-status | 4637d730-0b14-4ac5-a678-e50e131c7e1e |  | checkpoint | Covid 19 Protocols
checklist-flat | 241ff53b-98e5-45cb-9317-161f73b29674 |  | checklist | Steel Stud and Wall Strapping Checklist |  |  |  |  | Yes | QA - Steel Stud and Wall Strapping Checklist | e6977fe5-0aa8-495b-a75f-1baa0e70b149
checkpoint-status | d2b50053-5a5e-4736-835d-e21064e382d9 |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 67bf0737-fd9f-4f04-9b7d-0380774fbc33 |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | f9a7eb4e-535b-4367-8b71-1afacae25c88 |  | checkpoint | Set out is correct & signed off
checkpoint-status | b4ea11eb-9f3d-4cda-b99c-0c6773ad5917 |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status | e4556081-9d8c-4dc0-ac91-dd9d07b488b7 |  | checkpoint | All frames are square & plumb
checkpoint-status | 88825d5c-d5e6-4bcc-9373-0494d3ad9b1e |  | checkpoint | Deflection head track installed and correct
checkpoint-status | 44f8a806-f537-469a-ac0c-775750c813e3 |  | checkpoint | Trackloks installed and in the correct locations
checkpoint-status | d40cd3b7-0f20-4206-9a3f-b4fd9edc2e18 |  | checkpoint | Nogging track is installed and in correct location
checkpoint-status | e67dda1c-c601-49ed-9a6f-d0b44c909264 |  | checkpoint | Steel studs are correct size installed at correct centres
checkpoint-status | 0aa3724c-fb26-44c6-8ff6-6978f2c64a64 |  | checkpoint | Studs are fixed at bottom track but nothing in deflection head track
checkpoint-status | 50b010f2-f072-47ec-b3d9-99497bd3fb2b |  | checkpoint | Strapping brackets installed with Thermal Break at correct centres
checkpoint-status | 41456207-ea30-4956-bb4d-10e4b56ca1e6 |  | checkpoint | Door & window openings are in correct location and correct size
checkpoint-status | 6d4c37b0-c7c8-4867-9f94-76387c8598e6 |  | checkpoint | All Steel Stud and Wall Strapping completed correctly, checked & Supervisor sign off
checkpoint-status | 092c22ee-10eb-44ca-be67-0ad4c5d49983 |  | checkpoint | Area left clean & tidy
checklist-flat | c01bab61-1289-4835-b246-b060c2a85816 |  | checklist | Barrierline Checklist |  |  |  |  | Yes | QA - Barrierline Checklist | f244955b-b792-4da3-b6ef-c369a9fb6c39
checkpoint-status | dd01876f-34a8-4eb9-a86a-214547c4cdf7 |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 32861258-2131-4ade-9a79-9431e81a1f9b |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 0b39012a-fab2-4aab-9734-d52b1b0352bd |  | checkpoint | Correct Barrierline used as per spec
checkpoint-status | dbb5dd97-1355-4ac7-b470-00e13eee6090 |  | checkpoint | Perimeter channel to bottom plate installed flush with framing ends and 25-40mm gap
checkpoint-status | d10ed6db-68fd-4850-af34-ee41c295c999 |  | checkpoint | Correct fire sealant used between bottom channel and floor
checkpoint-status | 20566c63-a994-41f5-b005-9ae04c48f6a6 |  | checkpoint | Wall clips installed at each H stud with 16x10 drill points
checkpoint-status | f4405055-9600-48a7-a6b6-2dbc912d3bb1 |  | checkpoint | Each layer has perimeter channel at sides, bottom and top
checkpoint-status | 8f111bc1-bac8-4cc2-b80f-9bf4fc101485 |  | checkpoint | Gaps and joints acceptable
checkpoint-status | a26ab00b-18a3-420e-b32c-99b164b98ada |  | checkpoint | All screws installed to correct depth
checkpoint-status | 6dc92159-d560-49d1-b069-ab1438f5800f |  | checkpoint | Barrierline completed, checked and Supervisor sign off
checkpoint-status | 76124fe5-c5b4-4a75-b4d0-9a2020c39df8 |  | checkpoint | Area left clean & tidy