## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-0003 - Stormwater Drainage Line Record | itp |  |  |  |  | DN1210-0003 - Stormwater Drainage Line Record
section | SET OUT
checkpoint | 1 - Confirm Stormwater alignment is as per latest Drawing revision and does not clash with other Services.
label | Comments: Design Engineer to approve if the location needs to be moved.
textbox | NCR/OFI/RFI No:
checkpoint | 2 - Check Survey Set out and mark out completed.
label | Comments: Max. 10m interval
checkpoint | 3 - Confirm correct location of Manholes or Chambers, Catchpits.
textbox | Comments: Refer to Dwg:
section | TRENCH EXCAVATION
checkpoint | 4 - Ensure permits are in place.
checkpoint | 5 - Pothole existing services data in place.
checkpoint | 6 - Confined Space Permit required?
label | Comments: Trench depth > 1.5m must be shored or battered.
checkpoint | 7 - Foundation test conducted.
label | Granular Material: Scala 3 blows/100mm 5% CBR
label | Cohesive Material: Shear Vane Strength 70kPa
checkpoint | 8 - Undercut required?
label | Comments:
textbox | Undercut depth:
textbox | Metal:
section | STORMWATER PIPE INSTALLATION, BACKFILL AND TESTING
checkpoint | 9 - Check actual horizontal and vertical alignment achieved
checkpoint | 10 - Ensure pipe is checked & cleaned before being laid into the trench.
label | Comments: No vandalism, surface damage or deterioration. No install if found defective.
checkpoint | 11 - Line, level, and grade conformance checked
checkpoint | 12 - Ensure Bedding, surround & backfill materials are well-compacted and tested.
label | GAP20 - NDM- minimum 95%
label | LRAP65 - NDM- minimum 95%
label | Comments: At every 200mm compacted lift
checkpoint | 13 - Ensure installed pipeline has CCTV completed
label | Comments: No internal surface cracks. Clean from debris and contaminants.
section | ACCEPTANCE
checkpoint | Inspection By: Downer
textbox | Name:
date | Date:
holdpoint | Signature
checklist | DN1210-0004 - Manhole and Catchpit Record | itp |  |  |  |  | DN1210-0004 - Manhole and Catchpit Record
section | SET OUT
checkpoint | 1 - Confirm Stormwater alignment is as per latest Drawing revision and does not clash with other Services.
label | Comments: Design Engineer to approve if the location needs to be moved.
textbox | NCR/OFI/RFI No:
checkpoint | 2 - Check Survey Set out and mark out completed.
label | Comments: Centre point of MH
checkpoint | 3 - Confirm correct location of Manholes or Chambers, Catchpits.
textbox | Comments: Refer to Dwg:
section | TRENCH EXCAVATION
checkpoint | 4 - Ensure permits are in place.
checkpoint | 5 - Pothole existing services data in place.
checkpoint | 6 - Confined Space Permit required?
label | Comments: Trench depth > 1.5m must be shored or battered.
checkpoint | 7 - Foundation test conducted.
label | Granular Material: Scala 3 blows/100mm 5% CBR
label | Cohesive Material: Shear Vane Strength 70kPa
checkpoint | 8 - Undercut required?
label | Comments:
textbox | Undercut depth:
textbox | Metal:
section | STRUCTURE INSTALLATION, BACKFILL AND TESTING
checkpoint | 9 - Installation of Precast Base Unit on Bedding
checkpoint | 10 - Installation of Precast Risers to Lid Level
checkpoint | 11 - Installation of Manhole/Catchpit Furniture, Steps / clamps
textbox | Comments: If N/A- why?
checkpoint | 12 - Haunching around pipe connection and benching of MH base.
checkpoint | 13 - Installation of Precast Lid
label | Comments: 300mm above pipe or per IFC drawing
checkpoint | 14 - Epoxy- Joints exterior and Interior.
checkpoint | 15 - Backfill around Manhole/Catchpit – testing as per below:
label | GAP20 - NDM – minimum - 95%
label | LRAP65 - NDM – minimum - 95%
checkpoint | 16 - Installation of Cast Iron Frame A Cover Lid Level – set with contour
section | ACCEPTANCE
checkpoint | Inspection By: Downer Engineer
textbox | Name:
date | Date:
holdpoint | Signature