## ITP-02a
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-024
[11 empty] | Revision : 00 | Date : 07/12/2023
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Direct Buried Overhead Pole Installation |  | Name: | Samuel Johnson | Name: | Charles Bate |  | Name: Shaun Kent
Contract No: |  |  |  | Specifications: Tram Overhead Construction Specification Yarra Trams, Design Drawings
|  |  |  | Structure / Component: Overhead pole |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : 07/12/2023 |  | Date : 07/12/2023 |  |  | Date : 07/12/2023
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | YT | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Approval of OHP Layout and Rake |  | Prior to commencing any activity | Check that layout designs satisfy the requirements of the Principal, and drawings are approved for construction. Confirm pole rake bearing and grade. | Plan Approved for Construction | Verify | This ITP signed off | IP | Fulton Hogan Engineer / Yarra Trams |  |  | N/A
1.2 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Ensure Safety and Environmental Measures |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP. | PSP, EMP, TMP, JSEA, SWMS, WP | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Services |  | Prior to commencing any activity | Check DBYD records for any known existing services in the area. Service proving is required to ensure all service locations are known. | DBYD Records and Inspection | Visual Inspection | This ITP signed Receival and Inspection Checklist | WP | Fulton Hogan Engineer | N/A |  | N/A
1.5 | Lift Plan |  | Prior to pole erection | Ensure a lift plan has been prepared for the lift to mitigate against the risk of lifting the overhead poles near a live overhead power line. | WP 02 Cl 3.7 | Veify | This ITP signed off | IP | Fulton Hogan Engineer | N/A
1.6 | Pole Type and Quality Conformance |  | Each Pole | Principal Supplied Poles and Rag Bolts shall be examined for any damage, corrosion and rust. The materials shall be check for conformance to requirements. Ensure that draw rope is installed prior to pole erection if required and galvanising tags are removed. | Contract Drawings, YT Tram Overhead Construction Specification 2013 | Verify | This ITP signed off Recivable Inspection Checklist | IP | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Hole Excavation |  | Each Pole | Each hole shall first include a bored hole of uniform diameter throughout the entire depth, 200mm lower than the embedment depth specified on contract drawing. Boring direction shall be in line with specified new pole rake Diameter of the hole shall always be at minimum 100mm greater than the diameter of the pole. | Contract Drawings, YT Tram Overhead Construction Specification 2013 | Inspection/Verify | This ITP signed off | WP* | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Pole Setting |  | Each Pole | Ensure that poles are set as per IFC drawings. | Contract Drawings, YT Tram Overhead Construction Specification 2013 | Visual Inspection | This ITP signed off | WP | Fulton Hogan Foreman | N/A |  | N/A
2.3 | Pole Rake |  | Each Pole | Ensure that poles are set to rake as per IFC drawings. | Contract Drawings, YT Tram Overhead Construction Specification 2013 | Visual Inspection | This ITP signed off | IP | Fulton Hogan Foreman | N/A |  | N/A
3 | Testing
3.1 | Visual Inspection |  | Each pole | Surface of each pole shall be visually inspected for any damage, corrosion or rust before and after erection | Contract Drawings, YT Tram Overhead Construction Specification 2013 | verify | Visual inspection | IP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent