## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP020 - Prime Coat | itp |  |  |  |  | FH-ZU2-QU-ITP020 - Prime Coat - Rev 0
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision of drawings, technical specifications, permits as required for excavation and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ○ Current revisions of these documents to be obtained via Aconex or ACC.
label | Reference Documents - Current Revisions in Aconex or ACC
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS
label | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.3 - Plant & Equipment Check
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Contractor shall provide equipment for heating and uniformly applying the bituminous material and blotter material.
label | ○ The bitumen distributor shall comply with the requirements of NAS 70: ‘Bitumen Sprayers’
label | Reference Documents - Beca Spec 002 - 7.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.4 - Weather Conditions
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Prime coat shall not be applied on a wet surface, or when the surface temperature is below 10°C, or when the weather conditions would prevent the proper application or adhesion of the prime coat
label | Reference Documents - Beca Spec 002 - 7.9
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 2.0 - Materials
checkpoint | 2.1 - Cut-back Bitumen
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Cut-back bitumen for prime coat shall comply with AS 2157 and shall be class AMC0, AMC00 or AMC1.
label | Reference Documents - Beca Spec 002 – 7.4.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.2 - Cutter
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The cutter for use in cutback bitumen shall be a suitable petroleum-based material complying with the requirement of AS 3569.
label | Reference Documents - Beca Spec 002 – 7.4.4
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.3 - Bitumen Emulsion
label | Frequency - Prior to commencing works
label | Acceptance Criteria - If directed by the Principal’s Representative, bitumen emulsion complying to AS 1160 shall be used as a prime coat.
label | Reference Documents - Beca Spec 002 – 7.4.2
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.4 - Blinding Sand
label | Frequency - Prior to commencing works
label | Acceptance Criteria - If required, blinding sand to be used for absorbing excess primer shall comply with the following PSD.
label | – – – – – – – – –
label | AS Sieve Size (mm) ¦¦ Percent Passing Sieve by Mass
label | – – – – – – – – –
label | 6.7 ¦¦ 100
label | 4.75 ¦¦ 85-100
label | 1.18 ¦¦ 40-100
label | 0.425 ¦¦ 10-50
label | 0.075 ¦¦ 0-5
label | – – – – – – – – –
label | Reference Documents - Beca Spec 002 – 7.4.5
label | Inspection/Test Method - Verify
label | Record of conformity - Test Report
label | TP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.5 - Test Certificates
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Contractor shall submit a Test Certificate for each material proposed for use in the Works indicating compliance of those materials with the properties or requirements specified.
label | Reference Documents - Beca Spec 002 – 7.11.2
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Construction
checkpoint | 3.1 - Trial Application
label | Frequency - Prior to commencing works
label | Acceptance Criteria - A trial application, to be conducted as part of permanent works, shall be conducted on an area of the Works agreed and witnessed by the Principal’s Representative
label | Reference Documents - Beca Spec 002 – 7.5
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 3.2 - Surface Preparation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Immediately before applying the prime coat, the full width of the surface to be primed shall be swept to removal all loose dirt and material. The prepared surface is to be inspected by the Principal’s Representative.
label | Reference Documents - Beca Spec 002 – 7.6
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Application of Bituminous Material
label | Frequency - During works
label | Acceptance Criteria - The prime coat shall be applied at a uniform rate and shall be between 1.0 and 1.4 litres/m². The depth of penetration shall be a minimum of 6mm and maximum of 10mm
label | Reference Documents - Beca Spec 002 - 7.7.1
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 3.5 - Job Samples
label | Frequency - During works
label | Acceptance Criteria - Samples of each bituminous material shall be obtained from the delivery vehicle at not less than one sample per 10,000 litres of bituminous material sprayed.
label | Reference Documents - Beca Spec 002 – 7.11.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 3.6 - Spray Rates
label | Frequency - During works
label | Acceptance Criteria - The Contractor shall submit records of spray application rates at completion of each mobilisation
label | Reference Documents - Beca Spec 002 - 7.11.4
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality\System Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: