## Checklists
type | name | values
checklist | Delivery / Installation Day Checklist | values
section | HOLD POINT - Confirmation of slab strength
checkpoint | Has the slab reached the minimum strength required (UPLOAD copy of concrete slab test result)
label | 12MPa for cast-in anchors and 20MPa for post installed anchors
section | Prestart / Start-up
checkpoint | Date of Installation
checkpoint | Exclusion Zone is set up (PHOTO REQUIRED of the exclusion zone)
checkpoint | Plant & Equipment prestart/logbooks filled out (PHOTO REQUIRED of logbooks)
checkpoint | Toolbox Talk / Pre-Start has been completed (PHOTO REQUIRED of talk)
checkpoint | Element details
dropdown | Number of elements installed (COMMENT below if number of elements installed doesn't match the Load Lists in the Safe Load Declarations) | Drop down selection to show 1 through to 40
section | Element Install & Grouting
checkpoint | Bedding grout placed and finished as per project requirements
tickbox | Bedding grout (trowellable) used is as per project specification (PHOTO REQUIRED of the grout bag)
tickbox | Grout mixed in line with manufacturers recommendations
tickbox | Grout bed sufficient to ensure full coverage (PHOTO REQUIRED of grout bed prior to landing element)
checkpoint | Element installed to (PHOTO REQUIRED to show survey pins and spirit level bubble):
tickbox | Survey Pins
tickbox | Within 5mm of vertical plumb
tickbox | Face alignment within 5mm
checkpoint | Element propped as per Euro Precast PEDS (PHOTO REQUIRED of element propped)
tickbox | Prop bolts installed with tool to ensure locking mechanism can't be removed by hand (upload photo)
checkpoint | Dowel tube (flowable) grout placed and finished as per project requirements
tickbox | Dowel tube grout used is as per project specification (PHOTO REQUIRED of the grout bag)
tickbox | Grout mixed in line with manufacturers recommendations
tickbox | Dowel tubes filled to top of tubes
checkpoint | Were there any delays or Site Instructions given. If yes, please comment below and have builder sign | Yes, No
checkpoint | Is there any transport or erection damage that needs to be fixed (PHOTO REQUIRED of damaged area) | Yes, No
checkpoint | Area has been cleaned from grout and rubbish (PHOTO REQUIRED of the area before leaving)
section | Element Caulking
checkpoint | Element caulked as per project requirements
tickbox | Caulking product used as per element/project requirements (PHOTO REQUIRED of caulking product used)
tickbox | Open or closed cell backing rod used? (SPECIFY in comments section below)
tickbox | Caulking installed and checked (PHOTO REQUIRED of caulked joint/s)
section | HOLD POINT - Confirmation that Props can be removed
checkpoint | Has the Builder given us written confirmation that props can be removed (UPLOAD copy of correspondence)
checkpoint | PHOTO REQUIRED of element after the props have been removed
section | Basic Patch
checkpoint | Have the lifting anchors been patching as per project requirements
checkpoint | Have the prop points been patching as per project requirements
checkpoint | Have the grout tubes been patching as per project requirements
section | Final Finish
checkpoint | Has all outstanding patching been completed (PHOTO REQUIRED of all visible faces of element)
checkpoint | Has the builder signed off on the element? (ATTACH signature box below)
checklist-flat | Safe Load Declaration Checklist
checkpoint | Details complete
textbox | Date:
textbox | Time truck arrived at Factory:
textbox | Time truck departed Factory:
textbox | Project Name:
textbox | Delivery Address:
textbox | Transport Company:
textbox | Truck Registration #
textbox | Trailer Registration
dropdown | Trailer Type: | Drop Deck, Drop Deck No Frame, Flat Top, Layover, Super Layover, Commission
checkpoint | Upload photo of Load List used for load
checkpoint | Upload photos of both sides of loaded truck (after being chained down)
Checkpoint | Load Declaration
label | In signing below, you agree and acknowledge that:
label | You are not permitted to leave the Euro Precast factory unless a Safe Load Declaration has been completed
label | You have been provided with a copy of the load list that indicates individual element weights and total approximate load weight (excluding trailer/frame weight)
label | You have chained down all units/elements in a safe and secure manner and in accordance with the latest published government/industry best practice guidance material
label | You will abide by all safety rules, PPE requirements and client instructions on the project site at all times.
label | You as an individual, the truck, the trailer and load comply with the latest requirements of the Heavy Vehicle National Law and Regulations (HVNL)
signoff | Driver Signature (must include Company)