## Sheet1
type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist | TPO Concrete Checklist |  |  |  | 0 | Yes | Roofing QA - TPO Concrete Checklist | 229cceb4-6fd4-43b1-96ec-46014e42ced5
section | Substrate Check
checkpoint | Concrete substrate has been allowed to fully cure - at least 28 days from pour
text | Concrete Pour date:
checkpoint | Fill hallows or holes with a cement plaster, or FLC
checkpoint | Surface smooth, clean, dry and free of debris or release agents
checkpoint | Substrate venting installed as required
checkpoint | All drains and outlets are membrane compatible. Refer to your Allco Representative prior to installation if unsure.
checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
section | TPO Horizontal & Vertical Application
checkpoint | Conducted test weld on an off cut of membrane prior to installation?
checkpoint | Ensure even coating of approved adhesive used on JM sheet as well as substrate
checkpoint | Ensure 40mm minimum sheet laps
checkpoint | Ensure all weld areas thoroughly cleaned with JMCLEAN membrane cleaner
checkpoint | Test all welds with a seam probe
checkpoint | Attach application photos (1 photo per 20m2)
section | TPO Detailing (Gutters, Corners, Overflows)
checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
button | Ensure the correct JM accessories are used? | Yes, No, N/A
bool | Attach Photos (1 photo per drain/outlet )
checkpoint | Penetrations - appropriate detailing techniques used
button | Ensure JM Single ply caulking is applied on appropriate areas? | Yes, No, N/A
button | Ensure 200mm upstand extension over pipe penetrations, and 150 mm for vent and square post (deck) penetrations | Yes, No, N/A
bool | Attach Photo (1 photo per penetration)
checkpoint | Transitions - appropriate detailing techniques used
button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
bool | Application photos of transitions
checkpoint | External & Internal Corners - appropriate detailing techniques used
button | Ensure appropriate JM corners accessories are used? | Yes, No, N/A
button | Ensure appropriate detailing techniques used? | Yes, No, N/A
button | Ensure 40mm wield length on all sides and corner fully welded | Yes, No, N/A
bool | Application photos of corners ( 1 per corner)
section | TPO Concrete Termination
checkpoint | Ensure appropriate detailing used for termination?
checkpoint | Ensure 40mm hot weld between TPO and steel folded flashing (if appropriate)
checkpoint | Application photos of terminations (1 photo per termination)
checklist | Torch-On Concrete Checklist |  |  |  | 0 | Yes | Roofing QA - Torch-On Concrete Checklist | 23dc0d9b-8267-41d1-acc8-7bda484bfd97
section | Substrate Check
checkpoint | Concrete substrate has been allowed to fully cure - at least 28 days from pour
text | Concrete Pour date:
checkpoint | Fill hallows or holes with a cement plaster, or FLC
checkpoint | Surface smooth, clean, dry and free of debris or release agents
checkpoint | Substrate venting installed as required
checkpoint | Minimum 20mm triangular fillets at the base of upstands
checkpoint | All drains and outlets are membrane compatible. Refer to your Allco Representative prior to installation if unsure.
checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
section | Torch-On Horizontal & Vertical Application
checkpoint | Check sheets are correctly aligned, unrolled completely and positioning them
checkpoint | Ensure side laps are at least 100mm and at head laps should be 150mm
checkpoint | Ensure dermaprimer is used appropriately on the substrate
checkpoint | The second layer fully bonded on to the first layer, staggering the side overlaps by 500mm and the head overlaps by half a roll
checkpoint | Ensure 150mm upstand height of membrane
checkpoint | Attach application photos (1 photo per 20m2)
section | Torch-On Detailing (Drains, Gutters, Joints, Overflows, Penetrations)
checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
bool | Attach Photos (1 photo per drain/outlet )
checkpoint | Penetrations - appropriate detailing techniques used
button | Ensure 100mm extension from edge of penetration in all sides | Yes, No, N/A
button | Ensure 100mm upstand extension over pipe | Yes, No, N/A
bool | Attach Photo (1 photo per penetration)
checkpoint | Transitions - appropriate detailing techniques used
button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
bool | Application photos of transitions
checkpoint | Joints - appropriate detailing techniques used
button | For expansion joints, ensure there is 150mm extension cover over the joint | Yes, No, N/A
bool | Application photos (1 photo per joint)
section | Torch-On Terminations
checkpoint | Ensure appropriate 100mm laps at transitions
checkpoint | Ensure appropriate detailing is used on terminations
checkpoint | Application photos (1 photo per termination)
checklist-flat | Protection & Backfill for Area: |  |  |  | 0 | Yes | Waterproofing QA - Protection & Backfill Checklist | 3daf804b-83ee-4c00-b0b3-e5d7b9f5e222
checkpoint | Checklist named with location or text box below or marked up drawing attached
text | Description, grid sections, etc:
checkpoint | Allguard has been installed as per Allco specifications?
checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm?
text | Backfill date
checklist | TPO Plywood Checklist |  |  |  | 0 | Yes | Roofing QA - TPO Plywood Checklist | 4977edce-bf65-47a9-a2a7-16456949fe8d
section | Substrate Check
checkpoint | Framing supports at 400mm centres for 17.5m ply (in one direction). All plywood edges must also be supported.
checkpoint | Tongue and groove plywood NOT used
checkpoint | Framing supports at 600mm centres for 19.5m ply (in one direction). All plywood edges must also be supported.
checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
checkpoint | Minimum CD grade with the sanded C face upwards
checkpoint | Plywood to be laid at right angles (90 degrees) to supporting timber.
checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
checkpoint | Chamfer all external edges with a minimum radius of 5mm.
checkpoint | Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood to be at no more than 18%moisture content.
checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. - 1 vent for the first 40m2 and one for every 50m2 thereafter. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
checkpoint | All drains and outlets are membrane compatible. Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
section | TPO Horizontal & Vertical Application
checkpoint | Conducted test weld on an off cut of membrane prior to installation?
checkpoint | Ensure even coating of approved adhesive used on JM sheet as well as substrate
checkpoint | Ensure 40mm minimum sheet laps
checkpoint | Ensure all weld areas thoroughly cleaned with JMCLEAN membrane cleaner
checkpoint | Test all welds with a seam probe
checkpoint | Attach application photos (1 photo per 20m2)
section | TPO Detailing (Gutters, Corners, Overflows)
checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
button | Ensure the correct JM accessories are used? | Yes, No, N/A
bool | Attach Photos (1 photo per drain/outlet )
checkpoint | Penetrations - appropriate detailing techniques used
button | Ensure JM Single ply caulking is applied on appropriate areas? | Yes, No, N/A
button | Ensure 200mm upstand extension over pipe penetrations, and 150 mm for vent and square post (deck) penetrations | Yes, No, N/A
bool | Attach Photo (1 photo per penetration)
checkpoint | Transitions - appropriate detailing techniques used
button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
bool | Application photos of transitions
checkpoint | External & Internal Corners - appropriate detailing techniques used
button | Ensure appropriate JM corners accessories are used? | Yes, No, N/A
button | Ensure appropriate detailing techniques used? | Yes, No, N/A
button | Ensure 40mm wield length on all sides and corner fully welded | Yes, No, N/A
bool | Application photos of corners ( 1 per corner)
section | TPO Plywood Termination
checkpoint | Ensure appropriate detailing used for termination?
checkpoint | Ensure 40mm hot weld between TPO and steel folded flashing (if appropriate)
checkpoint | Application photos of terminations (1 photo per termination)
checklist | Voltex for Area: |  |  |  | 0 | Yes | Waterproofing QA - Voltex Checklist | 8b9ce594-0b11-4628-9f0f-df5e4410ca2f
section | Voltex Area of Installation
checkpoint | Checklist named with location or text box below or marked up drawing attached
text | Description, grid sections, etc:
section | Voltex Site & Substrate Prep
checkpoint | Appropriate site conditions for installation
checkpoint | Appropriate water control in place
text | Concrete pour date
checkpoint | Substrate photos taken
section | Voltex Walls, Underslab and Footings
checkpoint | Membrane appropriately laid on substrate with dark grey (woven) side up
checkpoint | 100 mm overlap between each sheet, and stagger sheets end at a minimum of 300mm
checkpoint | Appropriate detailing done to external/internal corners
section | Voltex Penetrations
checkpoint | Penetrations detailed as per Allcos recommendations
section | Voltex Backfill & Protection
checkpoint | Allguard has been installed as per Allco specifications
checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm
text | Backfill date
checklist | Sweltite for Area: |  |  |  | 0 | Yes | Waterproofing QA - Sweltite Checklist | 907624a7-d76b-4a6d-a4cf-bd89e14731c0
section | Sweltite Area of Installation
checkpoint | Checklist named with location or text box below or marked up drawing attached
text | Description, grid sections, etc:
section | Sweltite Site & Substrate Prep
checkpoint | Appropriate site conditions for installation
checkpoint | Appropriate water control in place
checkpoint | Substrate photos taken
section | Sweltite - Foundation walls
checkpoint | Appropriate detailing done as per Allco specifications
checkpoint | Ensure 100mm laps between membrane
checkpoint | All laps seam taped horizontally & vertically using Allco seam tape
checkpoint | Sweltite exceeds 150mm past F.F.L
checkpoint | Drainage coil has been placed 100mm from the floor/wall joint
section | Sweltite Penetrations
checkpoint | Penetrations detailed appropriately using appropriate accessory Volclay products
section | Sweltite Termination
checkpoint | Termination bar used on vertical & horizonal edges
checkpoint | Cetcoat applied at appropriate areas
checkpoint | Termination sealed off correctly (i.e. M2000, Cetseal)
section | Sweltite Backfill & Protection
checkpoint | Allguard has been installed as per Allco specifications
checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm
text | Backfill date
checklist | Hydrotech for Area: |  |  |  | 0 | Yes | Waterproofing QA - Hydrotech Checklist | a4b6f218-fa60-4c2d-a99e-72caa291fb6a
section | Hydrotech Area of Installation
checkpoint | Checklist named with location or text box below or marked up drawing attached
text | Description, grid sections, etc:
section | Hydrotech Site & Substrate Prep
checkpoint | Wind uplift has been considered prior to installation
checkpoint | Ensure all drains and outlets are membrane compatible. Confirm with Allco rep if required
checkpoint | Concrete substrate has been allowed to fully cure with a minimum wood float finish
checkpoint | Substrate clean, dry and free of debris or release agents
checkpoint | Substrate photos taken
section | Hydrotech Horizontal & Vertical Application
checkpoint | Test conducted to ensure membrane creates a mechanical bond to the substrate
label | Attach application photo (1 photo per 20m2 or separate area)
checkpoint | First membrane layer applied at 3mm thickness
label | Attach application photos (1 photo per 20m2)
checkpoint | Top coat of Hydrotech applied at 3mm thickness
label | Attach application photos (1 photo per 20m2)
checkpoint | Photo proving total thickness of membrane system is 9mm (including protection layer)
checkpoint | Photo of complete installation
section | Hydrotech Detailing
checkpoint | All penetrations have detailed as per Allco specifications
section | Hydrotech Terminations
checkpoint | Ensure the approved sealant or tape is used for termination
checklist-flat | Site Visit date: |  |  |  | 1 | Yes | TA - Site Visit | dd59b423-ae69-446e-9eb6-b96a3791a994
checkpoint | Site Details
text | Project Name/Address:
text | Contractor Name:
text | Applicator Name:
button | System Warranty | Yes, No
checkpoint | Product(s) Used
bool | Voltex
bool | Voltex DS
bool | Voltex SWR
bool | Sweltite
bool | Rx Waterstop 101
bool | Rx Waterstop 102
bool | Aquadrain
bool | Corflute
bool | Accessories
text | Other
checkpoint | Site Visit complete and NO REPAIRS REQUESTED
button | Substrate acceptable | Yes, No
text | Location or Grid Lines:
text | Inspection Notes
checklist | Waterstop-RX for Area: |  |  |  | 0 | Yes | Waterproofing QA - Waterstop-RX Checklist | e4376826-6dee-4e85-9b40-9d186f264134
section | Waterstop-RX Area of Installation
checkpoint | Checklist named with location or text box below or marked up drawing attached
text | Description, grid sections, etc:
section | Waterstop-RX Site & Substrate Prep
checkpoint | Substrate is acceptable
checkpoint | Confirm appropriate Waterstop-RX is going to be used in relation to concrete thickness
text | Concrete pour date
checkpoint | Substrate photos taken
section | Waterstop-RX Installation
checkpoint | Waterstop-RX has been installed as per Allco specifications
checkpoint | All parties aware of Waterstop-RX requirements with exposure to climatic conditions
checklist | Torch-On Plywood Checklist |  |  |  | 0 | Yes | Roofing QA - Torch-On Plywood Checklist | f31a796c-a097-4633-9780-0e1b4e2ca536
section | Substrate Check
checkpoint | Framing supports at 400mm centres for 17.5m ply (in one direction). All plywood edges must also be supported.
checkpoint | Framing supports at 600mm centres for 19.5m ply (in one direction). All edges must also be supported.
checkpoint | Minimum 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
checkpoint | Plywood screw-fixed with 10g x 50mm SS counter sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
checkpoint | Plywood laid with face grain at right angles to supports.
checkpoint | Plywood is to be laid with staggered joints in a brick-bond pattern with a continuous bead of suitable construction adhesive on top of timber supports. Sheet edges to be carefully glued with a continuous bead of suitable construction adhesive (no spot gluing) and tight butt-jointed. Once sheets have been placed together remove any excess adhesive by scraping the joint with a chisel. Ensure joints and sheets are not walked on within 2 hours of application. When fully cured remove excess and sand off joints.
checkpoint | Provide min. 20mm timber fillets at the base of all upstands.
checkpoint | Chamfer all external edges with a minimum radius of 5mm.
checkpoint | Plywood is to be laid with staggered joints in a brick-bond pattern with a continuous bead of suitable construction adhesive on top of timber supports. Sheet edges to be carefully glued with a continuous bead of suitable construction adhesive (no spot gluing) and tight butt-jointed. Once sheets have been placed together remove any excess adhesive by scraping the joint with a chisel.
checkpoint | Ensure joints and sheets are not walked on within 2 hours of application. When fully cured remove excess and sand off joints
checkpoint | Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18% moisture content.
checkpoint | Leave a 5mm minimum expansion gap around the perimeter of the plane. The fixing specification allows for a maximum 50m2 without expansion joints (dependant on design). 5mm expansion joints should be used on areas over 50m2 . For further information regarding placement of expansion joints for your design, please contact your Allco Representative .
checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
checkpoint | All drains and outlets are membrane compatible. Refer to your Allco Representative prior to installation if unsure.
section | Torch-On Horizontal & Vertical Application
checkpoint | Check sheets are correctly aligned, unrolled completely and positioning them
checkpoint | Ensure side laps are at least 100mm and at head laps should be 150mm
checkpoint | Ensure dermaprimer is used appropriately on the substrate
checkpoint | The second layer fully bonded on to the first layer, staggering the side overlaps by 500mm and the head overlaps by half a roll
checkpoint | Ensure 150mm upstand height of membrane
checkpoint | Attach application photos (1 photo per 20m2)
section | Torch-On Detailing (Drains, Gutters, Joints, Overflows, Penetrations)
checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
bool | Attach Photos (1 photo per drain/outlet )
checkpoint | Penetrations - appropriate detailing techniques used
button | Ensure 100mm extension from edge of penetration in all sides | Yes, No, N/A
button | Ensure 100mm upstand extension over pipe | Yes, No, N/A
bool | Attach Photo (1 photo per penetration)
checkpoint | Transitions - appropriate detailing techniques used
button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
bool | Application photos of transitions
checkpoint | Joints - appropriate detailing techniques used
button | For expansion joints, ensure there is 150mm extension cover over the joint | Yes, No, N/A
bool | Application photos (1 photo per joint)
section | Torch-On Terminations
checkpoint | Areas of installation input
text | Description, grid sections, etc
checkpoint | Ensure appropriate 100mm laps at transitions
checkpoint | Ensure appropriate detailing is used on terminations
checkpoint | Application photos (1 photo per termination)