## Project Structure
Folder Structure |  |  | Checklists
Site QA
| Prelim Activities | To Contain Preliminary Checklist | Preliminary Activities and Materials Approval
| Whiteman Park | To Contain Viaduct Checklist | Ability to Add Viaduct Checklists

## Resources
type | name | values
checklist-sectioned | Preliminary Activities and Materials Approval
section | Preliminary Activities (Approved by Client)
checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint | Permacast Project Quality Management Plan
checkpoint | Inspection & Test Plan
checkpoint | MDR Index
checkpoint | Work Method Statement (WMS) - Prestress
checkpoint | Work Method Statement (WMS) - Curing
checkpoint | Concrete Repair Methodology
checkpoint | Shop Drawings
checkpoint | Test Panel Prepared and Inspected by Client
checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
section | Concrete
checkpoint | S65 Concrete Mix Design Approved by Client
section | Steel Reinforcement
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
section | Prestressing Tendons
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Ensure that all Coil Numbers are recorded
checkpoint | Stressing Calculations Submitted and Approved by Client for Works
checkpoint | Stressing Jack Calibration Certificates
section | Post-Tensioning Materials
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
section | Lifting Anchors
checkpoint | Lifting Design Approved by Client
checkpoint | Lifting Devices Approved by Client
checkpoint | Inspection of Delivery for Completeness and Quality
section | Cast-in Items and Ferrules
checkpoint | All Cast in Materials Approved
checkpoint | Inspection of Delivery for Completeness and Quality
checklist-sectioned | Viaduct Checklist
section | Pre-Pour Checklist
text | Cast Number | 1
text | Viaduct Number | 3
text | Viaduct Number | 4
checkpoint | Shop Drawings approved for Works
checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Mould Surface Checked
label | Cleaned
label | Sealed
label | Rubbers in Place
label | Oiled
label | Chamfers in Place
checkpoint | Reinforcement in Accordance with Drawings
label | Reinforcement size
label | Lap Length
label | Splicing
label | Bar Chairs
checkpoint | Cover maintained and within tolerance
checkpoint | All Ferrules are installed in accordance with Drawings
text | Ferrules Type A (External Cladding)
text | Ferrules Type B (Cable Tray)
text | Ferrules Type C (Ceiling Under the Rail)
text | Ferrules Type D (Ceiling Under the Platform)
text | Ferrules Type E (Steel Angle)
text | Ferrules (Expansion Joint)
text | Ferrules (Balustrade)
text | Ferrules (Temporary Works)
text | Ferrules (Other type, specify)
checkpoint | All Stainless Items are installed in accordance with Drawings
text | Canopy
text | Support Beams
text | OLE Mast
text | Handrail Lifters
text | Other type, specify
checkpoint | All Blockout Conduits are installed in accordance with Drawings
text | Temporary Works
text | Transport Holes
text | Bearings
text | Stainless Item (i.e. Canopy, Support Beam)
checkpoint | All Lifting Inserts are installed in accordance with Drawings
text | VSL Bars
text | Locknut
text | Plate
checkpoint | All Couplers are installed in accordance with Drawings
checkpoint | Earthing and Bonding is installed in accordance with Drawings
text | Earthing Terminals (FDB-16)
text | 100mm 6mm fillet welds between bars
text | <20 mOhm across cage Length
text | Checklist Completed (Viaduct 1) (attach results)
text | Checklist Completed (Viaduct 2) (attach results)
checkpoint | Post-Tensioning Equipment is installed in accordance with Drawings
text | Tendon Ducts 105mm OD for 19 strand
text | Tendon Ducts 115mm OD for 22/24 strand tendons
text | Trumplate 1906
text | Trumplate 2206
text | Trumplate 2406
text | Breathing Tubes and Grout Vents
text | Temporary blockouts in Tendons
checkpoint | Prestressing Strands
text | Enter Coil Number Used for this Cast
label | Sag Load all Strand
label | Mutli-Stress as per Pre-stressing Procedures
checkpoint | Prepare Stressing Records and Submit to Client for Review (HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint | All Temperature Loggers are installed as per Approved WMS
text | Ensure All temperature Loggers are Working (Check Maturix)
checkpoint | QA Engineer Check Completed by
checkpoint | Client Inspector (if present)
section | Supervisor Release
checkpoint | Supervisor Release to Engineering Team
section | Casting Checklist
checkpoint | Casting Information
text | Cast Date | 2
checkpoint | Concrete Delivery Dockets
text | Concrete Delivery Docket (list all)
checkpoint | Total Concrete Volume
text | Volume (m3) | 6
checkpoint | Mix Design Verified
text | Specify mix used | 5
checkpoint | Ambient Temperature within Limits
label | max 38°C
checkpoint | Concrete Temperature
label | max 32°C
checkpoint | Slump within Allowable Tolerance
text | Slump (list all) | 7
checkpoint | Truck Tested for strength
text | Test Report Reference Number (list all)
checkpoint | Time Lag Between Trucks is not exceeded
checkpoint | Concrete Placed within allowable time from Batching Plant
checkpoint | No Free Fall During Pour
checkpoint | Required Finish Applied as per Drawings
checkpoint | Concrete Covered Overnight
checkpoint | Cylinders Stored next to Bed
section | Stripping Checklist
checkpoint | Date Stripped
text | Enter Date
checkpoint | Concrete Cylinders Crushed and Submitted to Client (HOLD POINT FOR CLIENT TO SIGN OFF)
text | Stripping Strength | 8
label | Strength = Reading / 7.851
checkpoint | Lifting Strength Achieved
checkpoint | Lifted and Handled as per Drawings
checkpoint | Product Clearly Labelled
checkpoint | Storage as per Approved Temporary Works Drawings
checkpoint | Secondary Curing as per Approved Methodology
label | Temperature 5 degrees past its peak
label | Differential between Core and Ambient within 30 degrees
label | Differential between Core and Cover within 20 degrees
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Specified Finish Achieved
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
text | Ferrules
text | Couplers
text | Stainless Items
text | Lifters
text | Blockouts
text | Earthing and Bonding
text | Post-Tensioning Equipment
checkpoint | Post-Pour Works Completed (As Required)
text | Strands are Cut Flush and Epoxied
text | Couplers are Cleaned and Capped
text | Roughened Surfaces are Greencut
text | Water Removed out of Cooling Pipes
text | All Miscellaneous Items are Completed
checkpoint | Survey Hog of Beams (Dumpy)
text | First Reading (Once Stripped)
text | Second Reading (if required)
text | Final Reading (Prior to Delivery)
checkpoint | Temperature Logging Completed and Conforming. Attach Results
section | Any Defect Identified
checkpoint | Punchlisting Completed
checkpoint | Repairs Required (if applicable)
checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint | Crack Map Completed
checkpoint | Any NCR Required (if applicable)
checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
section | As-Built Drawings
checkpoint | As-Built Drawings Completed, Stamped and Attached
section | Concrete Strength Test Report
checkpoint | Concrete Strength Test Report Received
text | Concrete Test Report | 9
text | 7 Day Strength (List all) | 10
text | 28 Day Strength (List all) | 11
section | Transportation Requirements
checkpoint | Certificate of Conformance
checkpoint | Inspection Release Certificate
checkpoint | Delivery Notes
checkpoint | Delivery Docket
section | Final Acceptance
checkpoint | Completed by
checkpoint | Reviewed by
checkpoint | Client Representative (if applicable)