## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Precast Beams |  |  |  |  | Yes | Precast Beams | ac9c1df8-0e90-44e9-b6e6-d9945aede9c4
checkpoint-group |  |  | section | Pre-Pour Checklist
checkpoint-no-status |  |  | checkpoint | Pre-Pour Checklist
text | 10b1b0f8-4441-5893-8ec8-945fc4db1fd9 |  | textbox | Cast Number
text | d43b7649-fa1d-57b2-aa68-1fe14d16d577 |  | textbox | Beam Number
checkpoint-status |  |  | checkpoint | Shop Drawings approved for Works
checkpoint-status |  |  | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | d8402d59-0028-53ba-8382-87bdb93009a4 |  | note | Length
label | d1aa86c4-5e36-5367-b0d2-9b6372946938 |  | note | Width
label | 75338a9f-c7ee-5135-a601-ebf0fad3af90 |  | note | Height
label | 86cb490d-5f96-567c-bb88-5847d89b9532 |  | note | Straightness
label | 181c57db-72c2-5763-81c5-285833de5632 |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Mould Surface Checked
label | 59835085-076e-5046-a629-7e6dd268ad49 |  | note | Cleaned
label | c6314187-2ba3-5575-b034-b30294639910 |  | note | Sealed
label | b0d378fa-5222-53ba-ba6b-18a52021965e |  | note | Rubbers in Place
label | 03fbf50c-3789-5512-9249-8d303fe23697 |  | note | Oiled
label | 9b2e4d0c-bcdb-58a6-aa16-ec20a6388349 |  | note | Chamfers in Place
checkpoint-status |  |  | checkpoint | Reinforcement in Accordance with Drawings
label | fd587fe6-f98d-58a0-adbc-489a6eb87301 |  | note | Reinforcement size
label | b6a07d71-a469-5ad1-988e-7f28879f1a80 |  | note | Lap Length
label | 6bfab525-e234-52d3-afb9-a183d34b4933 |  | note | Splicing
label | 4c722478-dfb6-5513-b5e5-f0c19be882dc |  | note | Bar Chairs
checkpoint-status |  |  | checkpoint | Cover maintained and within tolerance
checkpoint-status |  |  | checkpoint | All Cast-in Items are installed in accordance with Drawings
label | a670bf67-a534-5121-af88-ea6e00e1a8cd |  | note | Cast-in Items
label | a885f3fa-5c0b-51f4-9ce6-86039535d027 |  | note | Fittings
label | 0f357c4b-c72b-5867-92a6-3f4093bac55d |  | note | Lifters Position and Type
checkpoint-status |  |  | checkpoint | Prestressing Strands
text | 275edb46-37bc-533a-a75c-cf6e5e644bd8 |  | textbox | Enter Coil Number Used for this Cast
label | 2c31c790-c34d-50ba-a699-eb626aef6d33 |  | note | Sag Load all Strand
label | be3b6c4b-7192-501f-9fd8-2bd21380d150 |  | note | Multi-Stress as per Pre-stressing Procedures
checkpoint-status |  |  | checkpoint | All Temperature Loggers are installed as per Approved WMS
label | 93ec96df-4fa2-5082-922e-73b267cb47f3 |  | note | Every 25m
label | c2536eaf-fca5-52f6-bb4d-1f7aea03121d |  | note | 1 x End Block Mid-Diaphragm
label | c30f4604-96e7-52fd-83e5-2d1cbc50fc56 |  | note | 1 x Within Cover Zone
label | 1cbefcdd-ab1a-575d-80fa-25e722bcb79f |  | note | 1 x Within Tent/Tarp Enclosure (Outside concrete)
label | 37500688-77e7-539d-83e7-975e1497159d |  | note | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
checkpoint-status |  |  | checkpoint | Ensure All temperature Loggers are Working (Check App)
checkpoint-status |  |  | checkpoint | Prepare Stressing Records and Submit to Client for Review (HOLD POINT FOR CLIENT TO SIGN OFF)
holdpoint |  |  | signoff | CLIENT HOLD POINT
checkpoint-status |  |  | checkpoint | Electrical Conductivity Check Completed (if required)
checkpoint-status |  |  | checkpoint | QA Engineer Check Completed by
checkpoint-status |  |  | checkpoint | Client Inspector (if present)
checkpoint-group |  |  | section | Supervisor Release
checkpoint-status |  |  | checkpoint | Supervisor Release to Engineering Team
checkpoint-group |  |  | section | Casting Checklist
checkpoint-status |  |  | checkpoint | Casting Information
text | 6731687b-f5dc-54cf-ac34-08336c6afe2d |  | textbox | Cast Date
checkpoint-status |  |  | checkpoint | Concrete Delivery Dockets
text | 1c642a4f-3040-59b3-bdfb-4336c54e4ace |  | textbox | Concrete Delivery Docket (list all)
checkpoint-status |  |  | checkpoint | Total Concrete Volume
text | 36a44398-6ae5-512d-b310-66c9ec60ff6b |  | textbox | Volume (m3)
checkpoint-status |  |  | checkpoint | Mix Design Verified (BH1447 - S50)
checkpoint-status |  |  | checkpoint | Ambient Temperature within Limits
label | 61222b4c-fbf6-5c42-bc83-e17a2e4bfeb3 |  | note | 5 - 38°C
checkpoint-status |  |  | checkpoint | Concrete Temperature
label | 0c598eb5-7347-5b09-89e7-1f77f60b95f4 |  | note | max 32°C
checkpoint-status |  |  | checkpoint | Slump within Allowable Tolerance
text | 491cc1dd-44a0-57a9-86df-034b87af202a |  | textbox | Slump
label | 788263f9-1d63-509c-b5a5-437f2d2aaaf4 |  | note | 200 ± 40mm
checkpoint-status |  |  | checkpoint | Truck Tested for strength
text | a791a7d2-5973-5c0c-8877-09b205304fd1 |  | textbox | Test Report Reference Number
checkpoint-status |  |  | checkpoint | Time Lag Between Trucks (< 20min)
checkpoint-status |  |  | checkpoint | Concrete Placed within 90min from Batching Plant
checkpoint-status |  |  | checkpoint | No Free Fall During Pour (< 2m)
checkpoint-status |  |  | checkpoint | Required Finish Applied as per Drawings
checkpoint-status |  |  | checkpoint | Concrete Covered Overnight
checkpoint-status |  |  | checkpoint | Cylinders Stored next to Bed
checkpoint-group |  |  | section | Stripping Checklist
checkpoint-status |  |  | checkpoint | Date Stripped
text | 13639524-b9e9-5efe-a3dd-e40efb92b48e |  | textbox | Enter Date
checkpoint-status |  |  | checkpoint | Concrete Cylinders Crushed and Submitted to Client (HOLD POINT FOR CLIENT TO SIGN OFF)
text | de70bf0d-68b3-5010-99e9-701985ff3604 |  | textbox | Stripping Strength
label | 88da78a6-3f96-57c5-975d-1097e47ab446 |  | note | Strength = Reading / 7.851
holdpoint |  |  | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
checkpoint-status |  |  | checkpoint | Lifting Strength Achieved
checkpoint-status |  |  | checkpoint | Product Clearly Labelled
checkpoint-status |  |  | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | 30a0dfbc-7b3c-505e-bbec-c7de03d27ab0 |  | note | Length
label | 1273a51c-1672-5d7e-86eb-c4a3f53bd4a1 |  | note | Width
label | 7085954f-ff59-5e22-9fe3-26817343f431 |  | note | Height
label | 80cb9830-dbc1-59e0-a231-07fa725cf8a7 |  | note | Straightness
label | e72c671f-e730-56ce-ac53-5060650daf1c |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Specified Finish Achieved
checkpoint-status |  |  | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
label | 6830a97c-8195-5013-b22a-efe011e6cb78 |  | note | Cast-in Items
label | 63204ff8-121a-5175-b501-8a0f63adec38 |  | note | Fittings
label | bc4b9efa-d648-5d1b-bb9d-c5ee4380ca5e |  | note | Lifters Position and Type
checkpoint-status |  |  | checkpoint | Lifted and Handled as per Drawings
checkpoint-status |  |  | checkpoint | Storage/Stacking as per Approved Plan
checkpoint-status |  |  | checkpoint | Curing as per Approved Methodology
checkpoint-status |  |  | checkpoint | Post-Pour Works Completed (As Required)
text | 9f39603e-787c-5f04-89cf-271e2fb6c238 |  | textbox | Strands are Cut Flush
text | adfc24c4-e26a-58b3-b3b9-fb8cddadfa56 |  | textbox | Strands Bulbs as per Drawing
text | 740dc2d0-6d17-524e-b329-697b223f83cb |  | textbox | Starter Bars are Bent as Required
text | 7fd1cdfd-826a-5aa7-8a37-8e4e607efba6 |  | textbox | All Drain Holes are Clean
text | b0e05323-dc4d-5358-bec4-50433468cfa1 |  | textbox | All Miscellaneous Items are Completed
checkpoint-status |  |  | checkpoint | Survey Hog of Beams (Dumpy)
text | b1bc6fce-f1e3-5eca-86f1-4f283a8c54ba |  | textbox | First Reading (Once Stripped)
text | 7ecf0e2a-d9b4-50d3-a8c4-935e68edddf2 |  | textbox | Second Reading (if required)
text | 62b742ce-11aa-5447-bb36-09880673ca54 |  | textbox | Final Reading (Prior to Delivery)
checkpoint-status |  |  | checkpoint | Temperature Logging Completed and Conforming. Attach Results
checkpoint-group |  |  | section | Any Defect Identified
checkpoint-status |  |  | checkpoint | Punchlisting Completed
checkpoint-status |  |  | checkpoint | Repairs Required (if applicable)
checkpoint-status |  |  | checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint-status |  |  | checkpoint | Any NCR Required (if applicable)
checkpoint-status |  |  | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
checkpoint-group |  |  | section | As-Built Drawings
checkpoint-status |  |  | checkpoint | As-Built Drawings Completed, Stamped and Attached
checkpoint-group |  |  | section | Concrete Strength Test Report
checkpoint-status |  |  | checkpoint | Concrete Strength Test Report Received
text | 511165da-424b-5eb3-a53e-54882a72727f |  | textbox | Concrete Test Report Number 1
text | fe85a692-83cf-56db-b375-c198dda4cb18 |  | textbox | 7 Day Strength (1)
text | ef3f6d09-cff5-5792-9786-4feb38611afd |  | textbox | 28 Day Strength (1)
text | 9c4b945e-9625-5c0e-bc14-5a0fcf683407 |  | textbox | 28 Day Strength (2)
checkpoint-group |  |  | section | Final Acceptance (Conforming to all Requirements and is Ready for Transport)
checkpoint-status |  |  | checkpoint | Completed by
checkpoint-status |  |  | checkpoint | Reviewed by (INTERNAL HOLD POINT)
holdpoint |  |  | signoff | INTERNAL HOLD POINT
checkpoint-status |  |  | checkpoint | Client Representative (if applicable)
checklist-sectioned |  |  | checklist | Preliminary Activities and Materials Approval |  |  |  |  | Yes | Preliminary Activities and Materials Approval | bd08c19d-daca-4203-b63f-5dbc97bb21ed
checkpoint-group |  |  | section | Preliminary Activities (Approved by Client)
checkpoint-status |  |  | checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint-status |  |  | checkpoint | Permacast Project Quality Management Plan
checkpoint-status |  |  | checkpoint | Inspection & Test Plan
checkpoint-status |  |  | checkpoint | MDR Index
checkpoint-status |  |  | checkpoint | Work Method Statement (WMS) - Prestress
checkpoint-status |  |  | checkpoint | Work Method Statement (WMS) - Curing
checkpoint-status |  |  | checkpoint | Concrete Repair Methodology
checkpoint-status |  |  | checkpoint | Shop Drawings
checkpoint-status |  |  | checkpoint | Test Panel Prepared and Inspected by Client
checkpoint-status |  |  | checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
checkpoint-group |  |  | section | Concrete
checkpoint-status |  |  | checkpoint | S50 Concrete Mix Design Approved by Client
label | 3c0701d5-8f94-5ba6-8932-ad5ffae62a33 |  | note | Supplier : WA Premix
label | 93cdb902-fe1c-5597-abb6-13b2882c4cb6 |  | note | Mix Code: BH1447 (S50/14/200)
label | 926e2512-934c-5715-8b51-838a05846ac7 |  | note | Slump : 200 ± 40
checkpoint-group |  |  | section | Steel Reinforcement
checkpoint-status |  |  | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint-status |  |  | checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
checkpoint-group |  |  | section | Prestressing Tendons
checkpoint-status |  |  | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint-status |  |  | checkpoint | Ensure that all Coil Numbers are recorded
checkpoint-status |  |  | checkpoint | Stressing Calculations Submitted and Approved by Client for Works
checkpoint-status |  |  | checkpoint | Stressing Jack Calibration Certificates
checkpoint-group |  |  | section | Lifting Anchors
checkpoint-status |  |  | checkpoint | Lifting Design Approved by Client
checkpoint-status |  |  | checkpoint | Lifting Devices Approved by Client
checkpoint-status |  |  | checkpoint | Inspection of Delivery for Completeness and Quality
checkpoint-group |  |  | section | Cast-in Items and Ferrules
checkpoint-status |  |  | checkpoint | All Cast in Materials Approved
checkpoint-status |  |  | checkpoint | Inspection of Delivery for Completeness and Quality