## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Concrete Planning and Pour |  |  |  |  | Yes | ITP - R - Concrete - Planning and Pour (per townhouse block) | 2fd582e2-0c3c-46d3-af6a-c547067c4dbc
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | a566bafd-d8d5-5924-8c1b-18bebc9f8ca9 |  | textbox | Date of pour
text | 7a6d99a1-3423-5b59-9e58-84dfa3ac1e08 |  | textbox | Specified concrete strength:
text | 3cacc034-5dbf-50e4-af5e-e30943362526 |  | textbox | Concrete strength ordered:
text | efcbbbe0-f4ee-5425-aca3-bec378f10bf0 |  | textbox | Concrete quantity ordered:
text | 6f530bfc-72bd-5efc-9cf0-c10ed7217234 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Request to pour received and approved
button | e49e18c0-1f0f-5d55-97a7-225987e945f9 |  | button | Reinforcing meets specification | Yes, Reworked, N/A
button | 219c4d9f-601b-5d05-a5dc-6a2bbe9ba902 |  | button | Service penetrations present and correct | Yes, Reworked, N/A
button | 136fe8a8-f346-5359-9200-c15f91cc1972 |  | button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | 6a7010f5-8edd-5aa2-ad8e-fdf2749d52b4 |  | button | Couples present and correct | Yes, Reworked, N/A
button | 5783fa31-8dfe-525b-8996-24ec71381f8a |  | button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | a4c39795-223b-51a0-b54a-ff01fb46dc4e |  | button | Note remedial work needed | None, Minor, Major
text | 3b1508ed-e658-54a6-8413-967f24504f75 |  | textbox | Inspected by and date:
checklist-flat |  |  | checklist | Unit Benchmarking |  |  |  |  | Yes | ITP - R - Unit Benchmarking (Use at stage level) | 4f2ff27a-58cc-47b9-bd2e-eca3e2c4761c
checkpoint-status |  |  | checkpoint | Benchmark standard agreed as per Quality Management Plan
button | 2553b7b3-2fb6-5973-801c-5ee2275abbb6 |  | button | Project Manager or delegate present | Yes, No, N/A
button | a65cfbe6-5c9e-5eed-a0eb-bd94b0bf4303 |  | button | Sales representative or delegate present | Yes, No, N/A
button | 69ad3f81-c370-599e-8bb0-d5e36fa87dc3 |  | button | QA Advisor or delegate present | Yes, No, N/A
button | 56d86e50-7eec-5a03-a920-198b8e464a20 |  | button | Design representative or delegate present | Yes, No, N/A
text | 5633aa33-52a8-5724-90a1-3c34910da53e |  | textbox | Benchmark details (e.g. apartment number or explanation)
text | 7ae21135-e3ac-5e5e-8a92-c823303f735e |  | textbox | Record benchmark date
checklist-flat |  |  | checklist | Project Manager Handover to Operations |  |  |  |  | Yes | ITP - R - Project Manager Handover to Operations (per townhouse unit) | 6495bbaf-0148-4b3b-827f-0b780d042d7c
checkpoint-status |  |  | checkpoint | No outstanding defects/snag list items
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Chattels confirmed as operational
checkpoint-status |  |  | checkpoint | Chattel manuals provided.
checkpoint-status |  |  | checkpoint | Unit meets benchmark standards and expectations
checkpoint-status |  |  | checkpoint | Resident "Welcome Letter" completed by PM and left in property.
checkpoint-status |  |  | checkpoint | Formal handover to Sales/Operations conducted by PM.
checklist-flat |  |  | checklist | Punch Windows Frames (unglazed) |  |  |  |  | Yes | FC - R - Punch Windows Frames (unglazed) | a982193a-38dd-4fa6-ad7a-d89612bf58dd
checkpoint-no-status |  |  | checkpoint | Window # / Elevation / Level
text | 12f06f9d-851f-586f-b79f-934e897cacb0 |  | textbox | Window # / Elevation / Level
checkpoint-status |  |  | checkpoint | Installation (By others) completed as per detail Y/N
checkpoint-status |  |  | checkpoint | Check the joinery is free from damage
checkpoint-status |  |  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Check Frame number PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
checkpoint-status |  |  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
checkpoint-status |  |  | checkpoint | Glass Stickers removed
checkpoint-status |  |  | checkpoint | Trade Clean
checkpoint-status |  |  | checkpoint | Final Inspection PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Glazing complete for handover to Ryman Healthcare
holdpoint |  |  | signoff | Raise Remedial
checklist-flat |  |  | checklist | On Grade Slab Pre-Pour |  |  |  |  | Yes | ITP - R - On Grade Slab Pre-Pour (per townhouse block) | bfff35c9-603b-44ad-895a-add4d4bee63d
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Survey set out (height, location, setout) - confirmation attached.
checkpoint-status |  |  | checkpoint | Underground services installation completed
checkpoint-status |  |  | checkpoint | Backfilling completed
checkpoint-status |  |  | checkpoint | Waterproofing completed
checkpoint-status |  |  | checkpoint | DPM overlapping/taping with no tears or perforations. Council requirement
checkpoint-status |  |  | checkpoint | Reinforcing completed
checkpoint-status |  |  | checkpoint | Engineer sign off completed and approved for pour
button | 85efbc53-74fa-52a0-b06a-4d6ad661b420 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council inspection completed and approved for pour
button | 5a633978-fb98-5e51-8422-5f39bf626ea4 |  | button | Note remedial work needed | None, Minor, Major
text | 48106bbd-593e-51c0-9924-269c3c999bba |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | Fitout |  |  |  |  | Yes | ITP - R - Fitout (per townhouse unit) | d1c8a907-8caa-4c21-ac2b-752f96c0667a
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Finishing completed, meets benchmark standard. Refer separate checklist. Full response to the items below needed.
button | 90b59940-b9c7-5fd7-8a3e-0bced6739f38 |  | button | Hardware/Fittings | Yes, Reworked, N/A
button | 4bbc2670-6e28-53f5-ae59-8348ee82bdbb |  | button | Plumbing completed and acceptable | Yes, Reworked, N/A
button | f7916c64-81a3-58fd-a229-2c1272924308 |  | button | Electrical completed and acceptable | Yes, Reworked, N/A
button | 7e7a5a4a-7606-55e3-a327-ad6c429ff17e |  | button | Joinery/Doors completed and acceptable | Yes, Reworked, N/A
button | 4820c93c-e60f-5840-aa10-e4800a08310e |  | button | Decorating completed and acceptable | Yes, Reworked, N/A
button | 76aad3c5-12f2-578e-a88a-27c5acc855d4 |  | button | Flooring completed and acceptable | Yes, Reworked, N/A
button | 29049e71-86e9-5fa0-b76d-b772a27d7430 |  | button | Other works completed (inc. client extras) and acceptable, state below. | Yes, Reworked, N/A
text | a334a3eb-1b7f-59fc-9794-c9b9a4102b9e |  | textbox | Details:
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | Contractor Allocation |  |  |  |  | Yes | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage) | daafce47-e688-4e21-9903-a94721c702e6
checkpoint-group |  |  | section | Contractor Allocation
checkpoint-no-status |  |  | checkpoint | Contractor Allocation
text | 3f7fcc69-7d1c-530a-b1b4-7c54eadbb72e |  | textbox | Record Subcontractor Company Name
text | 6502520b-cad7-5862-a4ad-e634ad9371b4 |  | textbox | Record scope of works
checkpoint-status |  |  | checkpoint | Specifications confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | Programme milestones confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | All subcontractor ITPs (inspection test plans) attached and agreed.
checkpoint-status |  |  | checkpoint | Quality expectations and requirements discussed and confirmed as understood.
text | cecc99b1-2f97-50e5-a936-78285bd60b1c |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
holdpoint |  |  | signoff | Escalate concerns to QA Advisor
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | e702780c-401c-5509-a8a1-849c13e5fc80 |  | button | Note remedial work needed | None, Minor, Major
checklist-sectioned |  |  | checklist | Townhouse Block Build |  |  |  |  | Yes | ITP - R - Townhouse Block Build (per townhouse block) | efee36d2-c198-4a5c-acaf-5a59d8457993
checkpoint-group |  |  | section | Structure/Framing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Timber Framing installed
checkpoint-status |  |  | checkpoint | Council pre-clad inspection completed and approved. Note date of inspection in comments
button | d36c2053-3b4c-5d42-b8b3-3c1dc01cc805 |  | button | Note remedial work needed | None, Minor, Major
text | 734b5056-4aa5-5c7a-9d86-33267fb303de |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Roofing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Verify materials supplied to site (material and fixings) are as specified or approved samples
checkpoint-status |  |  | checkpoint | Construction complies with specifications
checkpoint-status |  |  | checkpoint | Obtain and upload all performance and authority certificates as required by specification or statutory regulations.
checkpoint-status |  |  | checkpoint | Council Pre-Roof Inspection completed and passed
button | 43618b40-f0bd-505e-b7e4-2e3edc044cf6 |  | button | Note remedial work needed | None, Minor, Major
text | 025df47e-66d6-5bf5-a607-00fb36e46ad6 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
button | b4f81066-3f6d-5559-8b5c-e9238b4a341c |  | button | Ecoply Board installed | Yes, Reworked, N/A
button | f1f5e14f-c94f-572b-a5c3-f91ce0be96e1 |  | button | Lintels installed | Yes, Reworked, N/A
button | 81579ca4-4558-5fcd-b3b8-6d3060817aec |  | button | Tapes and VaproShield installed. | Yes, Reworked, N/A
button | e75d1cae-2e6b-545a-89c8-ecafc6822593 |  | button | Windows and Sliders installed | Yes, Reworked, N/A
button | acbf913e-0c18-5f03-a6de-2e5e56ff7130 |  | button | Flashing installed | Yes, Reworked, N/A
button | 508bac90-ccff-5438-a400-37f7d3549364 |  | button | Envelope Penetrations completed | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 24084087-afdc-5fbf-8ac4-3336206bb111 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | f01676a5-c1b0-5876-ab68-18c01dfae556 |  | button | Note remedial work needed | None, Minor, Major
text | 8e6a1b1c-ec67-575c-a530-8dbf369e6a51 |  | textbox | Describe cladding type:
button | 1d0569d5-651d-51f5-a201-329f54d8d695 |  | button | Brick Works completed | Yes, Reworked, N/A
button | 738768b2-37d6-52f1-a535-b6993e4cc638 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
text | 2f09208f-5e7b-5aff-98ef-e9d9e950c4be |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Pre-line completed
button | 0e42350e-b3fd-5e06-b721-26bc704d08f0 |  | button | Timber frame installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Nogs Installed as below and comply
button | c40eb259-4a56-58de-9d09-3f877a517c2e |  | button | Steel Stud frame installation completed and acceptable | Yes, Reworked, N/A
button | 69ba2c2c-d640-5da3-9f49-f4d9bb73f1e6 |  | button | Electrical First Fix completed and acceptable | Yes, Reworked, N/A
button | c51ca6be-a615-5214-adf8-8165d072c256 |  | button | Plumbing First Fix completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
button | 0d0b968c-7ab2-583e-b9b0-3807df5e89de |  | button | HVAC First Fix completed and acceptable | Yes, Reworked, N/A
button | 19224e2c-bbc0-59f6-b7fd-44243f08a279 |  | button | Fire Security First Fix completed and acceptable | Yes, Reworked, N/A
button | 5d156462-8165-5107-b2ab-07c166fed994 |  | button | Underfloor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable | Yes, Reworked, N/A
button | 69292ca5-fa21-5b36-b6a4-8c60af6caf65 |  | button | Kitchen extract First Fix completed and acceptable | Yes, Reworked, N/A
button | daa078a6-ab97-5492-8d3d-1ceb1f5f7ddf |  | button | Passive fire installation completed and acceptable | Yes, Reworked, N/A
button | fb59201e-c353-5e2c-93fc-a7ec48328c4d |  | button | Suspended ceiling grids installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | 82976e74-c562-51a3-9f6d-2a6bd04f03be |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | 856b9346-be85-55a7-b2fb-c417c357d46b |  | button | Note remedial work needed | None, Minor, Major
text | 8d0d30e2-2ebe-5db9-91d8-66d0130663e4 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 7f0e7218-84ae-5457-97e0-28f4ea69b1ca |  | button | Note remedial work needed | None, Minor, Major