## Subsoil Drainage
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | C1503B - Mautaua Underslip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Master ITP |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: 1 |  |  |  | Corresponding Work Instruction: |  | C1503B - Mautaua Under Slip - SH2 RS562 RP13.287 Construction Approval |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS592 RP12.41
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Confirm Solution is Appropriate for the Site | H | Confirm the applicability of the solution for the site | Prior to commencement of construction | Visual inspection | To be confirmed by the CPS Engineer/Geotechnical Engineer | Photos, COR | Site Engineer | CPS Engineer
2 | Topsoil Strip | W | Once all ESC controls have been installed & the Tree Felling & Vegetation Clearance has been carried out | Prior to commencement | Document Review |  | Photos, log | Site Engineer
3 | Topsoil Strip | H | Confirm buttress extents and rock armouring toe extents | At completion of topsoil strip, before Toe construction | Inspection by the Geotechnical Design Manager | Buttress dimensions to be confirmed by CPS Engineer, including toe dimensions and placement. | Photos, log/sketch, COR | Site Engineer | CPS Engineer
4 | Topsoil Strip | H | Confirm Buttress foundation to be on suitable natural ground | At completion of site clearing and foundation excavation | Inspection by the CPS Engineer | Foundation to be suitable natural ground | Photo's, Scala, COR | Site Engineer | CPS Engineer
5 | Topsoil Strip | H | Confirm Slope face is 2H:1V if its required to be as steep as 1.5H:1V CPS Engineer approval is required | At completion of clearing and foundation excavation | Inspection by the CPS Engineer | Slope 2H:1V - proceed Slope >2H:1V CPS Engineer Approval required | Photo's and COR | Site Engineer | CPS Engineer
6 | Materials | H | Bulk fill to be approved by the Engineer | Prior to commencement | Lab Testing | Rock of GAP65, 100, or 150 grading. Broken faces | CS-4020 Bulk Fill Earthworks Record Check Sheet, material receipt | Site Engineer | CPS Engineer
7 | Materials | H | Rock Armour to be approved by the Engineer | Prior to commencement | Lab Testing | Rock armour shall be hard, durable, crushed, quarried or natural stone free from dust, clay, organic matter and other deleterious material. the stone shall be free from laminations and cleavages and shall not disintegrate on exposure to weathering. Rock to be SG 2,350kg with a D50 of 450mm Rock size to be A. Gradation D85/15 = 1.9 B. D85 max 690 (max) and 590 (min) C. D15 390 (max) and 275 (min) | Lab Test Report | Site Engineer | CPS Engineer
8 | Mega Flow Strip Drain or Drainage Blanket | W | If seepage is present in the slip scarp mega flow strip drain or a drainage blanket is required. | Prior to commencement | Visual inspection | Ensure Bidim complies with specification | Photos | Site Engineer
9 | Geofabric | W | Lay Bidim A39 geofabric over the slip between the existing ground and the bulk fill. Lay Bidim A49 between the bulk fill and the rock armouring . | Prior to commencement | Visual inspection | Ensure Bidim complies with specification | Photos | Site Engineer
10 | Geofabric | M | Check that the geofabric have been installed in accordance with the manufacturers specification - overlaps and pin centres | On completion of geofabric installation before fill is placed | Visual Inspection | Manufacturers specification | Photo's and Site Diary | Site Engineer
11 | Geofabric | M | Use of the correct geotextile at back and base of cut - Check information on the delivery docket against the requirements indicated on the Drawings. | Prior to commencement | Visual Inspection | Delivery dockets with roll details Class D placed at back and base of cut | Delivery docket | Site Engineer
12 | Filling Operation | W | Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately | Daily | Visual inspection | Fully drained conditions | Photos | Site Engineer
13 | Filling Operation | W | Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge | Daily visual survey check | Visual inspection | Line and level to be worked through with CPS throughout layer installation | Photos, Site log | Site Engineer
14 | Filling Testing Requirements | W | Fill placed in horizontal layers no greater than 300mm and compacted. Site Engineer to instruct lab when and where to carry out testing | testing low middle and top of buttress | Visual inspection and NDM Testing | Fill shall be compacted in accordance with NZ4431: 2022 | NDM testing report | Site Engineer
15 | Filling Testing Requirements | M | Use of the correct geotextile at back and base of cut - Check information on the delivery docket against the requirements indicated on the Drawings. | Prior to commencement | Visual Inspection | Delivery dockets with roll details Class D placed at back and base of cut | Delivery docket | Site Engineer
16 | Filling Testing Requirements | M | Check that the geofabric have been installed in accordance with the manufacturers specification - overlaps and pin centres | On completion of geofabric installation before fill is placed | Visual Inspection | Manufacturers specification | Photo's and Site Diary | Site Engineer
17 | Filling Testing Requirements | M | Use of the correct geogrid between slope face and rock armour- Check information on the delivery docket against the requirements indicated on the Drawings. | Prior to commencement | Visual Inspection | Delivery dockets with roll details Bidim A49 placed between rock armour and slope face | Delivery docket | Site Engineer
18 | Riprap Placement | W | Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material | Daily visual check | Visual inspection | Specification | Photo's | Site Engineer
19 | Trenching | H | CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works. |  | Visual Inspection | CPS Engineer to instruct action | RFI | Site Engineer | CPS Engineer
20 | Trenching | H | Location to be determined by CPS Engineer | Prior to install | Visual Inspection | Trenching location and direction to be confirmed by CPS Engineer | Photos, Log TBD | Site Engineer | CPS Engineer
21 | Drainage | W | Ensure drainage outlet from pavement connects to buttress fill if required | Prior to pavement commencement | Visual inspection | Confirm drainage connection if required | Photos, Log TBD | Site Engineer
22 | Road reinstatement | W | Refer to Pavement and Surfacing ITP's |  |  |  | Pavement and Surfacing ITP
23 | Survey As Built | H | Ensure all subsoil drainage lines comply with design prior to carrying on with next construction process | At completion of sub soil drainage line | Survey |  | Survey receipt | Site Engineer
24 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
25 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments: |  | F
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager |  |  |  |  | Signature: |  |  | Date: