## Bridge Deck Repair
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | C3001 Mangaturanga Bridge Repair |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Bridge Deck Repair |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | Robert Loomes |  | Quality Eng.
Lot No: C3001 |  |  |  | Corresponding Work Instruction: |  | C3001 MANGATURANGA BRIDGE REPAIR TREC Construction .docx |  | Compliance with Work Instructions and Specifications
Detailed Location: S.H.02 R.P. 562/5.62
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Dimensions and Setting Out | H | Dimensions of concrete breakout on bridge deck must be agreed with the CPS Engineer | Prior to commencement | Visual Inspection | Dimensions at top deck and deck soffit agreed upon | Photos | Site Engineer | CPS Engineer
2 | Materials | H | Contractor must provide a list of all proposed repair construction materials with any technical data sheets available for each material for CPS Engineer approval. | Prior to commencement | Submission | List of all materials and technical data sheets | Materials list, Data sheets | Site Engineer | CPS Engineer
3 | Concrete break out | H | CPS Engineer to inspect the areas broken out to inspect surface edge preparation | During construction | Visual Inspection | 45° taper cut on all 4 edges, no damage to existing reinforcement and shear cleat. | Photos, Site visit record | Site Engineer | CPS Engineer
4 | Concrete break out | H | Exposed and accessible (top and bottom) reinforcing steel must be power tool cleaned to SSPC SP3 standard. Other areas cleaned to SSPC SP2 standard | During construction | Visual Inspection | SSPC SP3 and SP2 standard. | Photos | Site Engineer | CPS Engineer
5 | Reinforcing bars | M | HD10 longitudinal bars to comply to design | During construction | Visual Inspection | Ensure all new and existing reinforcement bars are coated with a cement-based polymer modified coating material containing silica fume. Ensure all surfaces are fully coated | Photos | Site Engineer
6 | Reinforcing bars | M | Straight bars | During construction | Visual Inspection | HD10 hooked straight bars, crs 150mm, to form closed loop with hooked bent bar, embedded minimum 150mm, distance between 45° breakout face to be between 20-30mm | Photos | Site Engineer
7 | Reinforcing bars | M | Bent bars | During construction | Visual Inspection | HD10 hooked bent bars, crs 150mm, to form closed loop with hooked straight bar, embedded minimum 150mm with chemset, distance between 45° breakout face to be between 20-30mm | Photos | Site Engineer
8 | Reinforcing bars | H | CPS Engineer to inspect placement of reinforcing steel after it is fixed in position | During construction | Visual Inspection | Hooked bars tied with 2mm wire as per construction drawings | CS-4040 Concrete Insecption Record & Photos | Site Engineer | CPS Engineer
9 | Concrete casting | H | CPS Engineer to inspect formwork before casting | During Construction | Visual Inspection | Forms must have sufficient rigidity and strength to prevent distortion due to pressure from the concrete. Formwork to remain in place until concrete reaches a compressive strength of 30MPa | CS-4040 Concrete Insecption Record & Photos | Site Engineer | CPS Engineer
10 | Concrete casting | H | CPS Pre-pour inspection | During construction | Visual Inspection | Ensure exposed concrete edges are free from dust and loose particles | Concrete pre-pour checklist Photos | Site Engineer | CPS Engineer
11 | Concrete casting | W | Site Engineer to witness casting of concrete deck repair | During construction | Visual Inspection | All concrete used in deck repair must be in compliance with T-CES 101. Surface finish in accordance with NZS 3114. Deck top surface - U3. Exposed soffit of deck - F5. | Concrete pre-pour checklist Photos | Site Engineer
12 | Concrete casting | W | Contractor to provide minimum of 9 concrete cubes for laboratory material compressive testing | During construction | Lab Testing | Minimum compressive strength of: 30MPa (3 days) 50MPa (28 days) Patchroc C (Fosroc) or equivalent should be used. All concrete supplied shall comply with NZS 3109 | Lab Test Report | Site Engineer | CPS Engineer
13 | Concrete curing | H | Curing | During construction | Submission | Contractor to provide details of the proposed measures intended to protect the concrete during curing | Proposed Methods | Site Engineer | CPS Engineer
14 | Concrete curing | H | Prior to resurfacing, CPS Engineer to inspect the newly cast deck repair and make the decision whether crack injection is required | During construction | Visual Inspection | Crack injection required if crack between newly cast concrete and existing deck exceeds 0.3mm | Photos | Site Engineer | CPS Engineer
15 | Reinstate surfacing | H | Road surfacing reinstated to be consistent with rest of deck surfacing (Grade 3/5 racked in Chipseal). Contractor to provide methodology for resurfacing | During construction | Submission |  | Methodology, Photos | Site Engineer | CPS Engineer
16 | Completion Sign-off | H | Upon completion of works, Site Engineer to inspect works to confirm it is completed to required standard for sign off | At completion of works | Visual Inspection | Signatures from Site and CPS Engineers | Signatures | Site Engineer | CPS Engineer
17 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
18 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
| QA Compiled By : |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager:
[5 empty] | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date: