## Network Drainage
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | G1202B - Waikare Riverbend SH38 |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Network Drainage |  | Name / Signature | Name / Signature | Site Engineer
[7 empty] | Robert Loomes |  | Quality Eng.
Inspection & Test Plan / Checklist
Lot No: G1202B |  |  |  | Corresponding Work Instruction: |  | G1202B - Waikare Riverbend Recovery SH38 RP8 - TREC Quick Wins |  | Compliance with Work Instructions and Specifications
Detailed Location: SH38 at RS 161 RP 8.25-8.28
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Locate existing services by hand digging/hydro excavation | W | Ensure all services conflicting with the line of trench has been exposed by hand digging/ hydro excavation | Prior to commencement | Potholing | All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services | As-built Drawings Doc. Review | Site Engineer
2 | Trenching and Excavation | W | Inspect trench profile and ensure it is correct to minimum drainage standards | Daily | Visual/Inspection | Line and level is correct | CS-4025 Drainage Line Record Check Sheet | Site Engineer
3 | Trenching and Excavation | W | Ensure trench width is sufficient to provide enough space on either side of the pipe | Daily | Visual/Inspection | D/6 or 150mm whichever is greater on either side of the pipe | CS-4025 Drainage Line Record Check Sheet | Site Engineer
4 | Foundation Compliance | H | Test formation level on completion of excavation to check if undercut required | One test per 20 linear metres | Scala Penetrometer | If CBR is less than 50kPa , advise Engineer | Scala Record | Site Engineer | CPS Engineer
6 | Pipe Bedding Material Compliance | H | Material to meet specifications dependant on material type selected | Each material used | Document Review | Bedding material | Lab Test Report | Site Engineer | CPS Engineer
7 | Bedding | W | Bedding - Ensure correct thickness of bedding is placed and compacted | Daily | Visual/Inspection | 150 mm thick bedding for all mm dia pipe | CS-4025 Drainage Line Record Check Sheet | Site Engineer
8 | Pipes and Precast Units | W | Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition. | Per pipe | Visual/Inspection | Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc. | Photos | Site Engineer
9 | Pipe Laying | W | Pipe Laying - as only replacing section on outlet of existing pipe, grade is to follow existing levels | Prior to backfilling | Visual/Inspection | Invert level following pre-existing grade | Photos | Site Engineer
10 | Pipe Laying | H | Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness | Prior to backfilling | Visual/Inspection | No defects/ gaps / pipes are aligned correctly | Photos | Site Engineer | CPS Engineer
11 | Pipe Backfill Compliance | H | Material to meet specifications dependant on material type selected | Each material used | Document Review | Compliance with requirements from Specifications | CS-4025 Drainage Line Record Check Sheet | Site Engineer | CPS Engineer
12 | Pipe Backfill Compliance | W | Backfill Construction Material | 1 test per 50m | Lab Testing | CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65 | Lab Test Report | Site Engineer
13 | Backfilling | W | Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material. | 1 test per 20 m length of trench per 300mm lift | Testing | 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent | Clegg or NDM Test Results | Site Engineer
14 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
15 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: