## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - C1503B - Mautaua Under Slip - Master ITP | itp |  |  |  |  | ITP - C1503B - Mautaua Under Slip - Master ITP
section | Details
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Confirm Solution is Appropriate for the Site
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm the applicability of the solution for the site
label | Frequency - Prior to commencement of construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - To be confirmed by the CPS Engineer/Geotechnical Engineer
label | Records - Photos, COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Topsoil Strip
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Once all ESC controls have been installed & the Tree Felling & Vegetation Clearance has been carried out
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Photos, log
checkpoint | 3 - Topsoil Strip
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm buttress extents and rock armouring toe extents
label | Frequency - At completion of topsoil strip, before Toe construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | Conformance Criteria - Buttress dimensions to be confirmed by CPS Engineer, including toe dimensions and placement.
label | Records - Photos, log/sketch, COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Topsoil Strip
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm Buttress foundation to be on suitable natural ground
label | Frequency - At completion of site clearing and foundation excavation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the CPS Engineer
label | Conformance Criteria - Foundation to be suitable natural ground
label | Records - Photo's, Scala, COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Topsoil Strip
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm Slope face is 2H:1V if its required to be as steep as 1.5H:1V CPS Engineer approval is required
label | Frequency - At completion of clearing and foundation excavation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the CPS Engineer
label | Conformance Criteria - Slope 2H:1V - proceed
label | ○ Slope >2H:1V CPS Engineer Approval required
label | Records - Photo's and COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Materials
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Bulk fill to be approved by the Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Rock of GAP65, 100, or 150 grading. Broken faces.
label | Records - CS-4020 Bulk Fill Earthworks Record Check Sheet, material receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Materials
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Armour to be approved by the Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Rock armour shall be hard, durable, crushed, quarried or natural stone free from dust, clay, organic matter and other deleterious material. the stone shall be free from laminations and cleavages and shall not disintegrate on exposure to weathering.
label | ○ Rock to be SG 2,350kg with a D50 of 450mm
label | Rock size to be:
label | A. Gradation D85/15 = 1.9
label | B. D85 max 690 (max) and 590 (min)
label | C. D15 390 (max) and 275 (min)
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Mega Flow Strip Drain or Drainage Blanket
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - If seepage is present in the slip scarp mega flow strip drain or a drainage blanket is required.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure Bidim complies with specification
label | Records - Photos
checkpoint | 9 - Geofabric
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Lay Bidim A39 geofabric over the slip between the existing ground and the bulk fill. Lay Bidim A49 between the bulk fill and the rock armouring.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure Bidim complies with specification
label | Records - Photos
checkpoint | 10 - Geofabric
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check that the geofabric have been installed in accordance with the manufacturers specification - overlaps and pin centres
label | Frequency - On completion of geofabric installation before fill is placed
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Manufacturers specification
label | Records - Photo's and Site Diary
checkpoint | 11 - Geofabric
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Use of the correct geotextile at back and base of cut - Check information on the delivery docket against the requirements indicated on the Drawings.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Delivery dockets with roll details. Class D placed at back and base of cut.
label | Records - Delivery docket
checkpoint | 12 - Filling Operation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Fully drained conditions
label | Records - Photos
checkpoint | 13 - Filling Operation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge
label | Frequency - Daily visual survey check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Line and level to be worked through with CPS throughout layer installation
label | Records - Photos, Site log
checkpoint | 14 - Filling Testing Requirements
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill placed in horizontal layers no greater than 300mm and compacted. Site Engineer to instruct lab when and where to carry out testing
label | Frequency - testing low middle and top of buttress
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and NDM Testing
label | Conformance Criteria - Fill shall be compacted in accordance with NZ4431: 2022
label | Records - NDM testing report
checkpoint | 15 - Filling Testing Requirements
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Use of the correct geotextile at back and base of cut - Check information on the delivery docket against the requirements indicated on the Drawings.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Delivery dockets with roll details. Class D placed at back and base of cut.
label | Records - Delivery docket
checkpoint | 16 - Filling Testing Requirements
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check that the geofabric have been installed in accordance with the manufacturers specification - overlaps and pin centres
label | Frequency - On completion of geofabric installation before fill is placed
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Manufacturers specification
label | Records - Photo's and Site Diary
checkpoint | 17 - Filling Testing Requirements
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Use of the correct geogrid between slope face and rock armour- Check information on the delivery docket against the requirements indicated on the Drawings.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Delivery dockets with roll details. Bidim A49 placed between rock armour and slope face.
label | Records - Delivery docket
checkpoint | 18 - Riprap Placement
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photo's
checkpoint | 19 - Trenching
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS Engineer to instruct action
label | Records - RFI
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - Trenching
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location to be determined by CPS Engineer
label | Frequency - Prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Trenching location and direction to be confirmed by CPS Engineer
label | Records - Photos, Log TBD
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 21 - Drainage
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure drainage outlet from pavement connects to buttress fill if required
label | Frequency - Prior to pavement commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Confirm drainage connection if required
label | Records - Photos, Log TBD
checkpoint | 22 - Road reinstatement
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Refer to Pavement and Surfacing ITP's
label | Records - Pavement and Surfacing ITP
checkpoint | 23 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure all subsoil drainage lines comply with design prior to carrying on with next construction process
label | Frequency - At completion of sub soil drainage line
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 24 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 25 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT