## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - C3001 - Mangaturanga Bridge Repair - Bridge Deck Repair | itp |  |  |  |  | ITP - C3001 - Mangaturanga Bridge Repair - Bridge Deck Repair
section | Details
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Dimensions and Setting Out
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Dimensions of concrete breakout on bridge deck must be agreed with the CPS Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Dimensions at top deck and deck soffit agreed upon
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Materials
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Contractor must provide a list of all proposed repair construction materials with any technical data sheets available for each material for CPS Engineer approval.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - List of all materials and technical data sheets
label | Records - Materials list, Data sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Concrete break out
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Engineer to inspect the areas broken out to inspect surface edge preparation
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - 45° taper cut on all 4 edges, no damage to existing reinforcement and shear cleat.
label | Records - Photos, Site visit record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Concrete break out
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Exposed and accessible (top and bottom) reinforcing steel must be power tool cleaned to SSPC SP3 standard. Other areas cleaned to SSPC SP2 standard.
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - SSPC SP3 and SP2 standard.
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Reinforcing bars
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - HD10 longitudinal bars to comply to design
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Ensure all new and existing reinforcement bars are coated with a cement-based polymer modified coating material containing silica fume. Ensure all surfaces are fully coated
label | Records - Photos
checkpoint | 6 - Reinforcing bars
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Straight bars
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - HD10 hooked straight bars, crs 150mm, to form closed loop with hooked bent bar, embedded minimum 150mm, distance between 45° breakout face to be between 20-30mm
label | Records - Photos
checkpoint | 7 - Reinforcing bars
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Bent bars
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - HD10 hooked bent bars, crs 150mm, to form closed loop with hooked straight bar, embedded minimum 150mm with chemset, distance between 45° breakout face to be between 20-30mm
label | Records - Photos
checkpoint | 8 - Reinforcing bars
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Engineer to inspect placement of reinforcing steel after it is fixed in position
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Hooked bars tied with 2mm wire as per construction drawings
label | Records - CS-4040 Concrete Insecption Record & Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Concrete casting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Engineer to inspect formwork before casting
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Forms must have sufficient rigidity and strength to prevent distortion due to pressure from the concrete. Formwork to remain in place until concrete reaches a compressive strength of 30MPa
label | Records - CS-4040 Concrete Insecption Record & Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Concrete casting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Pre-pour inspection
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Ensure exposed concrete edges are free from dust and loose particles
label | Records - Concrete pre-pour checklist, Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Concrete casting
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Site Engineer to witness casting of concrete deck repair
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - All concrete used in deck repair must be in compliance with T-CES 101. Surface finish in accordance with NZS 3114. Deck top surface - U3. Exposed soffit of deck - F5.
label | Records - Concrete pre-pour checklist, Photos
checkpoint | 12 - Concrete casting
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Contractor to provide minimum of 9 concrete cubes for laboratory material compressive testing
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Minimum compressive strength of:
label | ○ 30MPa (3 days)
label | ○ 50MPa (28 days)
label | ○ Patchroc C (Fosroc) or equivalent should be used.
label | ○ All concrete supplied shall comply with NZS 3109
label | Records - Lab Test Report
checkpoint | 13 - Concrete curing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Curing
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Contractor to provide details of the proposed measures intended to protect the concrete during curing
label | Records - Proposed Methods
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Concrete curing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Prior to resurfacing, CPS Engineer to inspect the newly cast deck repair and make the decision whether crack injection is required
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Crack injection required if crack between newly cast concrete and existing deck exceeds 0.3mm
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Reinstate surfacing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Road surfacing reinstated to be consistent with rest of deck surfacing (Grade 3/5 racked in Chipseal). Contractor to provide methodology for resurfacing
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Methodology, Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Completion Sign-off
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Upon completion of works, Site Engineer to inspect works to confirm it is completed to required standard for sign off
label | Frequency - At completion of works
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Signatures from Site and CPS Engineers
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 18 - Completion Sign Off From Fields Below
label | Records - Signatures