## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - G1202A - Waikaretaheke Overslip #3 - Network Drainage | itp |  |  |  |  | ITP - G1202A - Waikaretaheke Overslip #3 - Network Drainage
section | Details
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Locate existing services by hand digging/hydro excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging/ hydro excavation
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
label | Records - As-built Drawings Doc. Review
checkpoint | 2 - Trenching and Excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Inspect trench profile and ensure it is correct to minimum drainage standards
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Line and level is correct
label | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint | 3 - Trenching and Excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - D/6 or 150mm whichever is greater on either side of the pipe
label | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint | 4 - Foundation Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test formation level on completion of excavation to check if undercut required
label | Frequency - One test per 20 linear metres
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | Conformance Criteria - If CBR is less than 50kPa , advise Engineer
label | Records - Scala Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Pipe Bedding Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Bedding material
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Bedding
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Bedding - Ensure correct thickness of bedding is placed and compacted
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - 150 mm thick bedding for all mm dia pipe
label | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint | 8 - Pipes and Precast Units
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Frequency - Per pipe
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
label | Records - Photos
checkpoint | 9 - Pipe Laying
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Pipe Laying - as only replacing section on outlet of existing pipe, grade is to follow existing levels
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Invert level following pre-existing grade
label | Records - Photos
checkpoint | 10 - Pipe Laying
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Pipe Backfill Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Compliance with requirements from Specifications
label | Records - CS-4025 Drainage Line Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Pipe Backfill Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill Construction Material
label | Frequency - 1 test per 50m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65
label | Records - Lab Test Report
checkpoint | 13 - Backfilling
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
label | Frequency - 1 test per 20 m length of trench per 300mm lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent
label | Records - Clegg or NDM Test Results
checkpoint | 14 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 15 - Completion Sign Off From Fields Below
label | Records - Signatures