## Construction ITP
[5 empty] | Inspection Test Plan |  |  |  | Approved / Signature
[5 empty] | Contract Name: |  |  |  | CPS Approver | Quality Approver | CPS Eng. | Angus Chapman
[5 empty] | Procedure: | D2004A-ID173 Tauwhatinui Bridge (BSN4593) |  |  | Name / Signature | Name / Signature | Site Engineer | Gurdeep Singh
Inspection & Test Plan / Checklist | [10 empty] | Quality Eng. | Dale Gibson
Lot No: |  |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-??-???? |  |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage: SH2 / RP443 / 16.290
No: | Inspection / Test Point | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Specification/Drawings Reference | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria |  | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
Section 1 : RECEIVING INSPECTIONS
1.1 | Rock Armour (D50=600) | Rock Armour (D50=600) | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | Prior to commencement | Submission, Visual inspection | Traceability of material required. Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 600 with a minimum specific Gravity SG of 2350kg/m3. | Traceability of material required. Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 600 with a minimum specific Gravity SG of 2350kg/m3. | Material source test results, Delivery dockets | Site Engineer | CPS Engineer
1.2 | Bulk Fill (AP65 or approved site won material) or similar | Bulk Fill (AP65 or approved site won material) or similar | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202, Technical specification sheet 1 of 3 | Prior to commencement | Submission, Visual inspection | Traceability of material required. Should comprise clean granular aggregate and have broken faces. Comply with Sampling & testing in accordance with item 2.2.2 Sampling of materials & 2.2.3 Testing Requirements listed in Technical Spec sheet 1 of 3 Maximum particle size of 65mm and not more than 5% by mass passing a percentage passing 75 micron sieve dry density water content relationship to NZS 4402 4.1.1 STD Compaction | Traceability of material required. Should comprise clean granular aggregate and have broken faces. Comply with Sampling & testing in accordance with item 2.2.2 Sampling of materials & 2.2.3 Testing Requirements listed in Technical Spec sheet 1 of 3 Maximum particle size of 65mm and not more than 5% by mass passing a percentage passing 75 micron sieve dry density water content relationship to NZS 4402 4.1.1 STD Compaction | Material source test results, Delivery dockets | Site Engineer | CPS Engineer
1.3 | Unaxial Geogrid RE540 or approved equivalent | Unaxial Geogrid RE540 or approved equivalent | W | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical specification Sheet 1 of 3 | Prior to commencement | Document Review | Traceability of material required. All rolls of Geogrid are to be inspected & bar codes collected/photographed. Geogrid to remain in their protective wrappers until required for use. Any defective rolls shall be returned to the supplier immediately | Traceability of material required. All rolls of Geogrid are to be inspected & bar codes collected/photographed. Geogrid to remain in their protective wrappers until required for use. Any defective rolls shall be returned to the supplier immediately | Delivery Dockets/ Storage photos, Material compliance cert | Site Engineer
1.4 | GEOTEXTILE FILTER FABRIC, FILTER CLASS 1, STRENGTH CLASS C | Geotextile Filter Fabric, Filter Class 1, Strength Class C | W | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical section and details, NZTA F/7: 2003 | Prior to commencement | Document Review | Class 1, Strength class C in accordance with NZTA F/7:2003 | Class 1, Strength class C in accordance with NZTA F/7:2003 | Delivery Dockets, Material compliance cert | Site Engineer
1.5 | Green Terramesh | Green Terramesh | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | Prior to backfill | Visual inspection | Terramesh shall be manufactured from steel wire coated with a protective coating of zinc-aluminium alloy and a plastic erosion protective coating. Construction observation reports on cutting and approval | Terramesh shall be manufactured from steel wire coated with a protective coating of zinc-aluminium alloy and a plastic erosion protective coating. Construction observation reports on cutting and approval | Material compliance cert, Delivery dockets, Photo's | Site Engineer | CPS Engineer
1.6 | Megaflow strip drain or drainage blanket for seepage if encountered | Megaflow Strip Drain Or Drainage Blanket For Seepage If Encountered | W | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | Prior to commencement | Submission | Subsoil drain shall be in accordance with TNZ F/2 (GEOFABRICS ENKADRAIN 5006H/2-2S/T110PP or similar). 110mm diameter Novaflo subsoil drain, or similar approved. | subsoil drain shall be in accordance with tnz f/2 (geofabrics enkadrain 5006h/2-2s/t110pp or similar). 110mm diameter novaflo subsoil drain, or similar approved. | Material compliance cert, Delivery dockets | Site Engineer
1.7 | Subsoil drain pipe | Subsoil Drain Pipe | W | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical specification Sheet 1 of 3, typical section and details | Prior to commencement | Visual inspection | 110mm Iplex smooth-Bore pre-wrapped Hi-way drain or similar approved | 110mm Iplex smooth-Bore pre-wrapped Hi-way drain or similar approved | Material compliance cert, Delivery dockets, Photo's | Site Engineer
1.8 | Subsoil drainage material | Subsoil Drainage Material | W | Ensure Material for Bedding, Side support and backfill are as per NZTA F/5:2013 | Prior to commencement | Visual inspection | Traceability of material required. Comply with NZTA F/5:2013 Ensure clean drainage chip | Traceability of material required. Comply with NZTA F/5:2013 Ensure clean drainage chip | Material source test results, Delivery dockets | Site Engineer
Section 3 : IN PROGRESS INSPECTIONS (Earthworks and Terramesh wall)
3.1 | Survey Setout | Survey Setout | H | Consistency with Construction Drawing | Prior to commencement | Survey | Set out extents of fill and check against design drawings | Set out extents of fill and check against design drawings | Survey receipt | Site Engineer | CPS Engineer
3.2 | Vegetation Clearance and removal of loose debris | Vegetation Clearance And Removal Of Loose Debris | M | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | Prior to commencement | Visual inspection | Remove and clear the vegetation | Remove and clear the vegetation | Photos | Site Engineer
3.3 | Subgrade Excavation | Subgrade Excavation | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | During Construction | Visual inspection, testing | Engineer to assess foundation material suitability HOLD POINT when excavation is 400mm above proposed level to do Scala Penetrometer testing to 1.5m below - MINIMUM ULTIMATE BEARING PRESSURE OF 300 KPA I.E., READINGS OF GREATER THAN 3 BLOWS /100 mm HOLD POINT when excavation is at level | engineer to assess foundation material suitability hold point when excavation is 400mm above proposed level to do scala penetrometer testing to 1.5m below - minimum ultimate bearing pressure of 300 kpa i.e., readings of greater than 3 blows /100 mm hold point when excavation is at level | CPS COR report, 1M Scala check sheet, Scala test reports | Site Engineer | CPS Engineer
3.4 | Subgrade Inspection | Subgrade Inspection | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | Per area as required | Visual inspection | Inspect fill foundation Fill foundation must be approved, in writing, before filling commences | Inspect fill foundation Fill foundation must be approved, in writing, before filling commences | CPS COR report | Site Engineer | CPS Engineer
3.5 | Megaflow strip or drainage blanket installation or 110mm Novaflo in 300x300mm trench for seepage if Encountered | Megaflow Strip Or Drainage Blanket Installation Or 110Mm Novaflo In 300X300Mm Trench For Seepage If Encountered | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | During Construction | Visual Inspection | CPS Engineer to assess suitable drainage location(s) and confirm on site. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required. | CPS Engineer to assess suitable drainage location(s) and confirm on site. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required. | Photos, COR report | Site Engineer | CPS Engineer
3.6 | Bulk Fill placement | Bulk Fill Placement | W,M | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | During Construction | Visual Inspection | Granular backfill to be placed in layers of maximum 200mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill should be placed on dry subgrade. | Granular backfill to be placed in layers of maximum 200mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill should be placed on dry subgrade. | Photos | Site Engineer
3.7 | Bulk Fill Compaction | Bulk Fill Compaction | W | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | During Construction | Testing | A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.1. 5 Clegg hammer readings shall be taken for each terramesh unit lift of 0.6m with the addition of 5 x NDM tests evey 1.2m lift (i.e every second terramesh unit) Testing to be carried out by IANZ accredited lab and results witnessed by CPS Engineer as they become available | A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.1. 5 x Clegg hammer readings shall be taken for each terramesh unit lift of 0.6m with the addition of 5 x NDM tests evey 1.2m lift (i.e every second terramesh unit) NDM Testing to be carried out by IANZ accredited lab and results witnessed by CPS Engineer as they become available | Clegg and NDM test reports, Clegg calibration certificate | Site Engineer
3.8 | Form and cut fill batter as per design 70 and 50degr. | Form And Cut Fill Batter As Per Design 70 And 50Degr. | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | During Construction | Survey | Engineer to assess the completed slopes suitability to the design guidance. Slope angle of buttress is to not exceed 70 and 50degr. Respectively | Engineer to assess the completed slopes suitability to the design guidance. Slope angle of buttress is to not exceed 70 and 50degr. Respectively | Survey as built | Site Engineer | CPS Engineer
3.9 | Placement of Geogrid / Geofabric / Terramesh | Placement Of Geogrid / Geofabric / Terramesh | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | During Construction | Submission | Grids are cut to the length stated in drawings. Grids are placed in the right direction (high tensile strength perpendicular to face), Grids are overlapped (see manufacturer's spec of the specific grid/fabric), laid flat and undamaged. | Grids are cut to the length stated in drawings. Grids are placed in the right direction (high tensile strength perpendicular to face), Grids are overlapped (see manufacturer's spec of the specific grid/fabric), laid flat and undamaged. | COR or photos | Site Engineer | CPS Engineer
3.1 | Filling Operation | Filling Operation | M | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | Daily | Visual Inspection | Geogrid protection - Minimum 150mm layer placed above geogrid before tracking onto it. Damaged grids need to be replaced | Geogrid protection - Minimum 150mm layer placed above geogrid before tracking onto it. Damaged grids need to be replaced | COR or photos | Site Engineer
3.11 | Fill material placement | Fill Material Placement | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | During Construction | Visual Inspection | during placing of the initial layers of the facing and geogrid reinforcement, the engineer shall be given the opportunity to inspect the onsite construction methodology. | during placing of the initial layers of the facing and geogrid reinforcement, the engineer shall be given the opportunity to inspect the onsite construction methodology. | COR or photos | Site Engineer | CPS Engineer
3.12 | Terramesh and Geogrid inspection | Terramesh And Geogrid Inspection | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | During Construction | Visual Inspection | once the installation of the terramesh green and the geogrid reinforcement have been completed, the engineer shall offered the opportunity to inspect the completed works. | once the installation of the terramesh green and the geogrid reinforcement have been completed, the engineer shall offered the opportunity to inspect the completed works. | COR or photos | Site Engineer | CPS Engineer
3.13 | Foundation Rock Riprap Placement | Foundation Rock Riprap Placement | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | Daily visual check | Visual inspection | Ensure that placement of rock material is done in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material. Rock riprap foundation thickness 1.20m and 3.70m wide | Ensure that placement of rock material is done in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material. Rock riprap foundation thickness 1.20m and 3.70m wide | COR | Site Engineer | CPS Engineer
3.14 | Riprap key into ground | Riprap Key Into Ground | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | During Construction | Visual Inspection, survey | Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 3m wide as per notes on drawing. | Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 3m wide as per notes on drawing. | COR, Survey as-built | Site Engineer | CPS Engineer
3.15 | Subsoil Drainage | Subsoil Drainage | M | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | During Construction | Visual Inspection, survey | Shall be installed as per manufacturers specifications & recommendations Drainage blanket shall be placed between the compacted fill and the excavated face to terminate at the subsoil pipe. 110mm smooth bore perforated top side subsoil piping and 110mm non-perforated HDPE outlet pipe with minimum pressure rating of 3.2 bar is required. | Shall be installed as per manufacturers specifications & recommendations Drainage blanket shall be placed between the compacted fill and the excavated face to terminate at the subsoil pipe. 110mm smooth bore perforated top side subsoil piping and 110mm non-perforated HDPE outlet pipe with minimum pressure rating of 3.2 bar is required. | Photos, Survey as-built | Site Engineer
3.16 | Subsoil Trenching | Subsoil Trenching | M | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical section and details | 10m intervals | Visual inspection and measurement | Inspect trench profile and ensure it is 0.300m wide and 1.000m below Edge of Seal level. | Inspect trench profile and ensure it is 0.300m wide and 1.000m below Edge of Seal level. | Photos with measurements | Site Engineer
3.17 | Subsoil Trenching | Subsoil Trenching | M | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical section and details | 10m intervals | Visual inspection and measurement | Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings. | Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings. | Photo / CS-4001 Subsoil Dip sheet Check Sheet | Site Engineer
3.18 | Subsoil | Subsoil | H | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall | As required | Visual Inspection | CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works. | CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works. | COR Report | Site Engineer | CPS Engineer
3.19 | Bedding, pipe installation and Backfill. | Bedding, Pipe Installation And Backfill. | M | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall | 10m intervals | Visual inspection | Upon completion of trenching Class C or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material | Upon completion of trenching Class C or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material | Photo | Site Engineer
3.2 | Bedding, pipe installation and Backfill. | Bedding, Pipe Installation And Backfill. | M | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall | 10m intervals | Visual inspection, survey as built | Ensure 100mm thick 3 to 7 Clean Drainage chip (Reject Chip) bedding is placed in base of trench. | Comply with NZTA F/5:2013 | Photo, survey as-built | Site Engineer
3.21 | Bedding, pipe installation and Backfill. | Bedding, Pipe Installation And Backfill. | W | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall | 10m intervals | Visual inspection | Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench | Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench | Photos | Site Engineer
3.22 | Bedding, pipe installation and Backfill. | Bedding, Pipe Installation And Backfill. | W | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall | 10m intervals | Document review | As built Survey the Pipe before backfill | As built Survey the Pipe before backfill | As-built receipt | Site Engineer
3.23 | Construct Terramesh Wall | Construct Terramesh Wall | H | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Typical section and details | As required | Visual / Survey | Install grid layers as per drawings and have Design Engineer signs off each layer. | Install grid layers as per drawings and have Design Engineer signs off each layer. | Survey Receipt | Site Engineer | CPS Engineer
3.24 | Construct Terramesh Wall | Construct Terramesh Wall | H | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Typical section and details | As required | Visual | Install Tenax Rivel / Maccaferri Green Terramesh cages as per Manufacturers specs along the front face of layers to ensure correct line and level. | Install Tenax Rivel / Maccaferri Green Terramesh cages as per Manufacturers specs along the front face of layers to ensure correct line and level. | Photo's and COR report | Site Engineer | CPS Engineer
3.25 | Construct Terramesh Wall | Construct Terramesh Wall | M | S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Typical section and details | Each Lift | Visual Inspection, survey | Ensure line and level of front face is as per design | Ensure line and level of front face is as per design | Photos, Survey as built | Site Engineer
3.26 | Rock Facing | Rock Facing | H | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | During Construction | Visual Inspection, survey | Boulders to be placed in front of the terramesh wall. The extent to be confirmed with the CPS engineer | Boulders to be placed in front of the terramesh wall. The extent to be confirmed with the CPS engineer | Photos, Survey as built | Site Engineer | CPS Engineer
| Rock Facing | Rock Facing | M | 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202 | During Construction | Visual | ALL ROCK SHALL BE PLACED IN A STABLE SECURE POSITION UTILISING THREE POINT BEARING ON THE UNDERLYING ROCKS. BEARING ON SMALLER ROCKS WHICH MAY BE USED FOR CHINKING VOIDS WILL NOT BE ACCEPTED. LOCAL SURFACE IRREGULARITIES OF THE RIP RAP PROTECTION SHALL NOT VARY FROM THE PLANNED SLOPE BY MORE THAN 300 mm MEASURED AT RIGHT ANGLES TO THE SLOPE | All Rock Shall Be Placed In A Stable Secure Position Utilising Three Point Bearing On The Underlying Rocks. Bearing On Smaller Rocks Which May Be Used For Chinking Voids Will Not Be Accepted. Local Surface Irregularities Of The Rip Rap Protection Shall Not Vary From The Planned Slope By More Than 300 Mm Measured At Right Angles To The Slope | Photos, Survey as built | Site Engineer
3.27 | As-built Survey | As-Built Survey | H |  | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
Section 4 : Final Inspection and Handover
4.1 | Quality Assurance deliverables | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's
4.2 | Completion Sign Off From Fields Below | Completion Sign Off From Fields Below | [6 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : | [5 empty] | Signature: |  |  |  | Date:
QA checked By Discipline Manager: | [5 empty] | Signature: |  |  |  | Date:
QA checked By Quality Manager: | [5 empty] | Signature: |  |  |  | Date:
Accepted By CPS Manager: | [5 empty] | Signature: |  |  |  | Date: