## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - D2004A - ID173 - Tauwhatinui Bridge (BSN4593) | itp |  |  |  |  | ITP - D2004A - ID173 - Tauwhatinui Bridge (BSN4593)
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Rock Armour (D50=600)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Visual inspection
label | Conformance Criteria - Traceability of material required.
label | ○ Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 600 with a minimum specific Gravity SG of 2350kg/m3.
label | Records - Material source test results, Delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Bulk Fill (AP65 or approved site won material) or similar
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202, Technical specification sheet 1 of 3
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Visual inspection
label | Conformance Criteria - Traceability of material required.
label | ○ Should comprise clean granular aggregate and have broken faces.
label | ○ Comply with Sampling & testing in accordance with item 2.2.2 Sampling of materials & 2.2.3 Testing Requirements listed in Technical Spec sheet 1 of 3
label | ○ Maximum particle size of 65mm and not more than 5% by mass passing a percentage passing 75 micron sieve dry density water content relationship to NZS 4402 4.1.1 STD Compaction
label | Records - Material source test results, Delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Unaxial Geogrid RE540 or approved equivalent
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical specification Sheet 1 of 3
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Traceability of material required.
label | ○ All rolls of Geogrid are to be inspected & bar codes collected/photographed. Geogrid to remain in their protective wrappers until required for use. Any defective rolls shall be returned to the supplier immediately
label | Records - Delivery Dockets/ Storage photos, Material compliance cert
checkpoint | 1.4 - Geotextile Filter Fabric, Filter Class 1, Strength Class C
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical section and details, NZTA F/7: 2003
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Class 1, Strength class C in accordance with NZTA F/7:2003
label | Records - Delivery Dockets, Material compliance cert
checkpoint | 1.5 - Green Terramesh
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - Prior to backfill
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Terramesh shall be manufactured from steel wire coated with a protective coating of zinc-aluminium alloy and a plastic erosion protective coating. Construction observation reports on cutting and approval
label | Records - Material compliance cert, Delivery dockets, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Megaflow Strip Drain Or Drainage Blanket For Seepage If Encountered
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Subsoil drain shall be in accordance with tnz f/2 (geofabrics enkadrain 5006h/2-2s/t110pp or similar). 110mm diameter novaflo subsoil drain, or similar approved.
label | Records - Material compliance cert, Delivery dockets
checkpoint | 1.7 - Subsoil Drain Pipe
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical specification Sheet 1 of 3, typical section and details
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - 110mm Iplex smooth-Bore pre-wrapped Hi-way drain or similar approved
label | Records - Material compliance cert, Delivery dockets, Photo's
checkpoint | 1.8 - Subsoil Drainage Material
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure Material for Bedding, Side support and backfill are as per NZTA F/5:2013
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Traceability of material required. Comply with NZTA F/5:2013. Ensure clean drainage chip.
label | Records - Material source test results, Delivery dockets
section | Section 3: IN PROGRESS INSPECTIONS (Earthworks and Terramesh wall)
checkpoint | 3.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Consistency with Construction Drawing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Set out extents of fill and check against design drawings
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Vegetation Clearance And Removal Of Loose Debris
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Remove and clear the vegetation
label | Records - Photos
checkpoint | 3.3 - Subgrade Excavation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, testing
label | Conformance Criteria - Engineer to assess foundation material suitability
label | ○ Hold point when excavation is 400mm above proposed level to do scala penetrometer testing to 1.5m below - minimum ultimate bearing pressure of 300 kpa i.e., readings of greater than 3 blows /100 mm
label | ○ Hold point when excavation is at level
label | Records - CPS COR report, 1M Scala check sheet, Scala test reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Subgrade Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Inspect fill foundation. Fill foundation must be approved, in writing, before filling commences.
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Megaflow Strip Or Drainage Blanket Installation Or 110Mm Novaflo In 300X300Mm Trench For Seepage If Encountered
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS Engineer to assess suitable drainage location(s) and confirm on site. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
label | Records - Photos, COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Bulk Fill Placement
label | ACTION (Hold, Monitor, Witness) - W,M
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Granular backfill to be placed in layers of maximum 200mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill should be placed on dry subgrade.
label | Records - Photos
checkpoint | 3.7 - Bulk Fill Compaction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.1.
label | ○ 5 x Clegg hammer readings shall be taken for each terramesh unit lift of 0.6m with the addition of 5 x NDM tests evey 1.2m lift (i.e every second terramesh unit)
label | ○ NDM Testing to be carried out by IANZ accredited lab and results witnessed by CPS Engineer as they become available
label | Records - Clegg and NDM test reports, Clegg calibration certificate
checkpoint | 3.8 - Form And Cut Fill Batter As Per Design 70 And 50Degr.
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance. Slope angle of buttress is to not exceed 70 and 50degr. Respectively.
label | Records - Survey as built
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Placement Of Geogrid / Geofabric / Terramesh
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Grids are cut to the length stated in drawings. Grids are placed in the right direction (high tensile strength perpendicular to face), Grids are overlapped (see manufacturer's spec of the specific grid/fabric), laid flat and undamaged.
label | Records - COR or photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Filling Operation
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Geogrid protection - Minimum 150mm layer placed above geogrid before tracking onto it. Damaged grids need to be replaced
label | Records - COR or photos
checkpoint | 3.11 - Fill Material Placement
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - During placing of the initial layers of the facing and geogrid reinforcement, the engineer shall be given the opportunity to inspect the onsite construction methodology.
label | Records - COR or photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Terramesh And Geogrid Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Once the installation of the terramesh green and the geogrid reinforcement have been completed, the engineer shall offered the opportunity to inspect the completed works.
label | Records - COR or photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.13 - Foundation Rock Riprap Placement
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure that placement of rock material is done in such a manner to minimise segregation and avoid displacement of underlying materials.
label | ○ Oversize rock to be placed such to minimise voids.
label | ○ Design Engineer given notice to visually inspect initial placement of riprap material.
label | ○ Rock riprap foundation thickness 1.20m and 3.70m wide
label | Records - COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.14 - Riprap Key Into Ground
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 3m wide as per notes on drawing.
label | Records - COR, Survey as-built
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.15 - Subsoil Drainage
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - Shall be installed as per manufacturers specifications & recommendations
label | ○ Drainage blanket shall be placed between the compacted fill and the excavated face to terminate at the subsoil pipe. 110mm smooth bore perforated top side subsoil piping and 110mm non-perforated HDPE outlet pipe with minimum pressure rating of 3.2 bar is required.
label | Records - Photos, Survey as-built
checkpoint | 3.16 - Subsoil Trenching
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical section and details
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | Conformance Criteria - Inspect trench profile and ensure it is 0.300m wide and 1.000m below Edge of Seal level.
label | Records - Photos with measurements
checkpoint | 3.17 - Subsoil Trenching
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical section and details
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | Conformance Criteria - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | Records - Photo / CS-4001 Subsoil Dip sheet Check Sheet
checkpoint | 3.18 - Subsoil
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | Records - COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.19 - Bedding, Pipe Installation And Backfill.
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Upon completion of trenching Class C or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
label | Records - Photo
checkpoint | 3.20 - Bedding, Pipe Installation And Backfill.
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - 10m intervals
label | Conformance Criteria - Comply with NZTA F/5:2013
label | Records - Photo, survey as-built
checkpoint | 3.21 - Bedding, Pipe Installation And Backfill.
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | Records - Photos
checkpoint | 3.22 - Bedding, Pipe Installation And Backfill.
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - As built Survey the Pipe before backfill
label | Records - As-built receipt
checkpoint | 3.23 - Construct Terramesh Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Typical section and details
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual / Survey
label | Conformance Criteria - Install grid layers as per drawings and have Design Engineer signs off each layer.
label | Records - Survey Receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.24 - Construct Terramesh Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Typical section and details
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Install Tenax Rivel / Maccaferri Green Terramesh cages as per Manufacturers specs along the front face of layers to ensure correct line and level.
label | Records - Photo's and COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.25 - Construct Terramesh Wall
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Typical section and details
label | Frequency - Each Lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - Ensure line and level of front face is as per design
label | Records - Photos, Survey as built
checkpoint | 3.26 - Rock Facing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - Boulders to be placed in front of the terramesh wall. The extent to be confirmed with the CPS engineer.
label | Records - Photos, Survey as built
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Rock Facing
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - All Rock Shall Be Placed In A Stable Secure Position Utilising Three Point Bearing On The Underlying Rocks. Bearing On Smaller Rocks Which May Be Used For Chinking Voids Will Not Be Accepted.
label | ○ Local Surface Irregularities Of The Rip Rap Protection Shall Not Vary From The Planned Slope By More Than 300 Mm Measured At Right Angles To The Slope.
label | Records - Photos, Survey as built
checkpoint | 3.27 - As-Built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
section | Section 4: Final Inspection and Handover
checkpoint | 4.1 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.2 - Completion Sign Off From Fields Below
label | Records - Signatures