## ITP Cover Page
Wetland 2 Outlet Rip Rap Protection - Inspection and Test Plan
Project: Tauriko Enabling Project SP2
Number and Revision: DN1210 - SP2 - 037-REV0 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project SP2 |  |  |  |  | ITP Number: |  |  | SP2 - 037-REV0
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | Approved - IFC
ITP Description: |  |  | Wetland 2 Outlet Rip Rap Protection |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-STW, 23273502-WSP-DR-GEO, 2-32735.02-WSP-DR-UDL
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Contract Specification
Quality Specified: |  |  | ISO9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-08-07 |  | Cordelia Girdler-Brown & Nick Adams | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams |  |  | #VALUE! |  | 25/08/2025 | Downer PM
Downer QM |  | Cordelia Girdler-Brown |  |  |  |  | 25/08/2025 | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Wetland 2 Outlet Rip Rap Protection - Inspection and Test Plan
Project: Tauriko Enabling Project SP2
Number and Revision: DN1210 - SP2 - 037-REV0 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIALS, PERSONELL & THIRD PARTY APPROVALS
3.1 | Earthworks Methodology | The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works. | Engineers Approval | Appendix V | Approved Methodology | Prior to Earthworks | HP | ENG
3.2 | Ecology Sign Off | Confirmation from Ecology that earthworks can proceed | Email | Internal Hold Point | Email from Ecology NZ | Prior to Earthworks | H | SE
3.3 | Erosion & Sedimentation Controls | Confirm that Erosion and Sedimentation Controls are in place prior to earthworks proceeding | As-built Completed | Internal Hold Point | ESC As-built | Prior to Earthworks | H | SE
3.4 | Design / Setout | Ensure that Design is approved and Drawings are of the latest revision | Visual inspection by Engineer | Internal hold point | Check Drawing Register | Prior to Earthworks | C | SE
|  | Site check for service features, any required design amendments to be resolved on site | Visual inspection by Engineer | Internal hold point | Engineer notified of design amendments to be resolved | Prior to Earthworks | C | SE
SECTION 4 | IMPORTED MATERIAL TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
4.1 | D50 = 250mm Rip Rap rock testing - Weathering Index of Coarse Aggregate | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA to CA | NZS4407:2015 Test 3.11 PS 21.7.4 | IANZ Accredited Report | 1 per 1000m3 | HP | ENG
4.2 | D50 = 250mm Rip rap rock testing - Crushing Resistance of Course Aggregate | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | > 150kN | NZS4407.3.10 PS 21.7.4 | IANZ Accredited Report | 1 per 1000m3 | HP | ENG
4.3 | D50 = 250mm Rip rap rock testign - Solid Density of Aggregate | NZS4407:2015, Test 3.7.1 - The Solid Density of Aggregate Particles | ≥ 2.65 tonnes per m3 | NZS4407.3.7.1 PS 21.7.4 | IANZ Accredited Report | 1 per 1000m3 | HP | ENG
4.4 | Rip rap rock testing - Grading | NZS4407:2015, Test 3.8.2 - Grading of Aggregates by method of dry sieving. | Sieve Size % Passing 230.0mm 85% passing 150.0mm 50% passing 95.0mm 15% passing | NZS4407.3.8.2 PS 21.5.14 | IANZ Accredited Report | Percentage Passing %50 | HP | ENG
4.5 | Rip rap rock testing - Point Load Strength | ASTM-D5731: 2017, Standard Test Method for Determination of the Point Load Strength Index of Rock and Application to Rock Strength Classifications | >1.5 MPa | ASTM D5731 PS 21.7.4 | IANZ Accredited Report | 1 per 1000m3 | HP | ENG
4.6 | Rip rap rock testing - UCS Rock | AS4133.4.2.1: 2022, Method 4.2.1: Rock strength tests – Determination of uniaxial compressive strength | >30 Mpa | AS4133.4.2.1 PS21.7.4 | IANZ Accredited Report | 1 per 1000m3 | HP | ENG
4.5 | Geotextile
4.5.1 | Geotextile | The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation. Class C & Filtration Class 1 | Engineers Approval | PS 16.5.7 Appendix V | Delivery Docket/Material certificate | Results to Engineer for Approval | HP | ENG
SECTION 5 | Imported/Site Won Material Testing - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
5.1 | SITE TOPSOIL
5.1.1 | Site topsoil - Laboratory Testing for Soil Suitability | Soil Test Results from Hill Laboratories to confirm that topsoil suitable to for reuse Soil Reaction Electrical Conductivity Mechanical Analysis (texture) Stone Content Nutrient Levels of nitrogen, available phosphorus, available potassium and available magnesium Organic Matter Content Check for Toxic or Hazardous substances | Engineers Approval | NZTA P39:2013 3.1 | Laboratories Test Report | 10 equal samples taken from site, mixed together, then 1kg of soil sealed into a plastic bag and sent to lab for sampling | I | SE
SECTION 6 - EARTHWORKS
6.1 | TOPSOIL STRIP & CONTOUR SUBGRADE
6.1.1 | Foundation / Subgrade Suitability - Free of organics / unsuitable material | Undercut all organic, soft, or unsuitable soils to below subgrade | Visual inspection | PS 16.6.4b PS 16.7.4 | Photos | Post contouring | C | SE
6.1.2 | Foundation / Subgrade Suitability - Scala Penetrometer | Scala testing to meet requirements of Project Specification for cut subgrade | Minimum 3 blows per 100mm penetration | PS 16.7.4 | Test Reports | 4 tests per 400m2 | C | SE
6.1.3 | Foundation / Subgrade Suitability - Shear Vane | Shear vane testing to meet requirements of Project Specification for cut subgrade | Average minimum SU > 60kPA Single test mininium SU > 50kPA | PS 16.7.4 | Test Reports | 4 tests per 400m2 | C | SE
6.1.4 | Foundation / Subgrade Suitability - Subgrade Inspection | Engineer to complete visual inspection of subgrade and review scala testing. Where directed by the Engineer, the unsuitable subgrade soils shall be undercut and/or improved. | Visual inspection | PS 16.6.4b | Site Instruction | Every 20m chainage on all major contours | HP | ENG
6.2 | RIP RAP LINED GULLY & CONTOUR ADJACENT LAND
6.2.1 | Rip Rap Lined Gully - Placement of Geotextile Fabric | Place Geotextile Fabric Strength Class C (AS440) & Flitration Class 1 across pavement area, with 500mm overlaps | Visual inspection | PS: 21.5.15 | Visual Inspection and photos | Before Rip Rap Placement | W | SE
6.2.2 | Rip Rap Lined Gully - Check Levels | Confirm that the rip rap is an average thickness of 600mm | String lines - or equivalent Tolerances width -20mm +100mm | TNZ B/02:2005 | Survey as-builts | Every 20m chainage on all major contours | I | SV
6.2.3 | Rip Rap Lined Gully - Shape/Placement of Rip Rap Rcok and Contoured Adjacent Land | Shape/placement of the rip rap and in relation to the existing ground level and the contoured land adjacent to the rip rap footprint | Visual inspection | TNZ B/02:2005 | Photos | Post Rip Rap Placement | HP | ENG
6.3 | RESPREADING TOPSOIL
6.3.1 | Reinstate Existing Topsoil Layer | Reinstate topsoil to existing ground levels pre construction in areas where contouring has not occurred. In areas where contouring has occurred topsoil should be 300mm in thickness | String lines - or equivalent Tolerances width -20mm +100mm | TNZ B/02:2005 5.1 | Survey as-builts | Post topsoil placmenet | I | SV
SECTION 7 – AS-BUILTS
7.1 | As-Builts | As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets. |  | PS 16.7.6 | Survey Records/ Redpen markups | Post Earthworks | D | SV