## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-037 ITP Wetland 2 Outlet Rip Rap | itp |  |  |  |  | DN1210-037 ITP Wetland 2 Outlet Rip Rap Rev 1
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIALS, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 3.1 - Earthworks Methodology
label | Detail - The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Approved Methodology
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Ecology Sign Off
label | Detail - Confirmation from Ecology that earthworks can proceed
label | Acceptance / Conformance Criteria - Email
label | Standard / Specification - Internal Hold Point
label | Verifying Document - Email from Ecology NZ
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3 - Erosion & Sedimentation Controls
label | Detail - Confirm that Erosion and Sedimentation Controls are in place prior to earthworks proceeding
label | Acceptance / Conformance Criteria - As-built Completed
label | Standard / Specification - Internal Hold Point
label | Verifying Document - ESC As-built
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.4 - Design / Setout (1)
label | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | Acceptance / Conformance Criteria - Visual inspection by Engineer
label | Standard / Specification - Internal hold point
label | Verifying Document - Check Drawing Register
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 3.4 - Design / Setout (2)
label | Detail - Site check for service features, any required design amendments to be resolved on site
label | Acceptance / Conformance Criteria - Visual inspection by Engineer
label | Standard / Specification - Internal hold point
label | Verifying Document - Engineer notified of design amendments to be resolved
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
section | SECTION 4 - IMPORTED MATERIAL TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
checkpoint | 4.1 - D50 = 250mm Rip Rap rock testing - Weathering Index of Coarse Aggregate
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA to CA
label | Standard / Specification - NZS4407:2015 Test 3.11 PS 21.7.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - D50 = 250mm Rip rap rock testing - Crushing Resistance of Course Aggregate
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - > 150kN
label | Standard / Specification - NZS4407.3.10 PS 21.7.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - D50 = 250mm Rip rap rock testing - Solid Density of Aggregate
label | Detail - NZS4407:2015, Test 3.7.1 - The Solid Density of Aggregate Particles
label | Acceptance / Conformance Criteria - ≥ 2.65 tonnes per m3
label | Standard / Specification - NZS4407.3.7.1 PS 21.7.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Rip rap rock testing - Grading
label | Detail - NZS4407:2015, Test 3.8.2 - Grading of Aggregates by method of dry sieving.
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 230.0mm ¦¦ 85% passing
label | 150.0mm ¦¦ 50% passing
label | 95.0mm ¦¦ 15% passing
label | Standard / Specification - NZS4407.3.8.2, PS 21.5.14
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Percentage Passing %50
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Rip rap rock testing - Point Load Strength
label | Detail - ASTM-D5731: 2017, Standard Test Method for Determination of the Point Load Strength Index of Rock and Application to Rock Strength Classifications
label | Acceptance / Conformance Criteria - >1.5 MPa
label | Standard / Specification - ASTM D5731 PS 21.7.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Rip rap rock testing - UCS Rock
label | Detail - AS4133.4.2.1: 2022, Method 4.2.1: Rock strength tests – Determination of uniaxial compressive strength
label | Acceptance / Conformance Criteria - >30 Mpa
label | Standard / Specification - AS4133.4.2.1 PS21.7.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.1 - Geotextile
label | Detail - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation. Class C & Filtration Class 1
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.5.7, Appendix V
label | Verifying Document - Delivery Docket/Material certificate
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 - Imported/Site Won Material Testing - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
checkpoint | 5.1.1 - Site topsoil - Laboratory Testing for Soil Suitability
label | Detail - Soil Test Results from Hill Laboratories to confirm that topsoil suitable to for reuse
label | ○ Soil Reaction
label | ○ Electrical Conductivity
label | ○ Mechanical Analysis (texture)
label | ○ Stone Content
label | ○ Nutrient Levels of nitrogen, available phosphorus, available potassium and available magnesium
label | ○ Organic Matter Content
label | ○ Check for Toxic or Hazardous substances
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - NZTA P39:2013 3.1
label | Verifying Document - Laboratories Test Report
label | Testing Quantity Required (based from schedule qtys) - 10 equal samples taken from site, mixed together, then 1kg of soil sealed into a plastic bag and sent to lab for sampling
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 6 - EARTHWORKS
checkpoint | 6.1.1 - Foundation / Subgrade Suitability - Free of organics / unsuitable material
label | Detail - Undercut all organic, soft, or unsuitable soils to below subgrade
label | Acceptance / Conformance Criteria - Visual inspection
label | Standard / Specification - PS 16.6.4b, PS 16.7.4
label | Verifying Document - Photos
label | Testing Quantity Required (based from schedule qtys) - Post contouring
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 6.1.2 - Foundation / Subgrade Suitability - Scala Penetrometer
label | Detail - Scala testing to meet requirements of Project Specification for cut subgrade
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - PS 16.7.4
label | Verifying Document - Test Reports
label | Testing Quantity Required (based from schedule qtys) - 4 tests per 400m2
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 6.1.3 - Foundation / Subgrade Suitability - Shear Vane
label | Detail - Shear vane testing to meet requirements of Project Specification for cut subgrade
label | Acceptance / Conformance Criteria - Average minimum SU > 60kPA
label | ○ Single test mininium SU > 50kPA
label | Standard / Specification - PS 16.7.4
label | Verifying Document - Test Reports
label | Testing Quantity Required (based from schedule qtys) - 4 tests per 400m2
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 6.1.4 - Foundation / Subgrade Suitability - Subgrade Inspection
label | Detail - Engineer to complete visual inspection of subgrade and review scala testing. Where directed by the Engineer, the unsuitable subgrade soils shall be undercut and/or improved.
label | Acceptance / Conformance Criteria - Visual inspection
label | Standard / Specification - PS 16.6.4b
label | Verifying Document - Site Instruction
label | Testing Quantity Required (based from schedule qtys) - Every 20m chainage on all major contours
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2.1 - Rip Rap Lined Gully - Placement of Geotextile Fabric
label | Detail - Place Geotextile Fabric Strength Class C (AS440) & Flitration Class 1 across pavement area, with 500mm overlaps
label | Acceptance / Conformance Criteria - Visual inspection
label | Standard / Specification - PS: 21.5.15
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - Before Rip Rap Placement
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 6.2.2 - Rip Rap Lined Gully - Check Levels
label | Detail - Confirm that the rip rap is an average thickness of 600mm
label | Acceptance / Conformance Criteria - String lines - or equivalent
label | ○ Tolerances width -20mm +100mm
label | Standard / Specification - TNZ B/02:2005
label | Verifying Document - Survey as-builts
label | Testing Quantity Required (based from schedule qtys) - Every 20m chainage on all major contours
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | 6.2.3 - Rip Rap Lined Gully - Shape/Placement of Rip Rap Rcok and Contoured Adjacent Land
label | Detail - Shape/placement of the rip rap and in relation to the existing ground level and the contoured land adjacent to the rip rap footprint
label | Acceptance / Conformance Criteria - Visual inspection
label | Standard / Specification - TNZ B/02:2005
label | Verifying Document - Photos
label | Testing Quantity Required (based from schedule qtys) - Post Rip Rap Placement
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3.1 - Reinstate Existing Topsoil Layer
label | Detail - Reinstate topsoil to existing ground levels pre construction in areas where contouring has not occurred. In areas where contouring has occurred topsoil should be 300mm in thickness
label | Acceptance / Conformance Criteria - String lines - or equivalent
label | ○ Tolerances width -20mm +100mm
label | Standard / Specification - TNZ B/02:2005 5.1
label | Verifying Document - Survey as-builts
label | Testing Quantity Required (based from schedule qtys) - Post topsoil placmenet
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
section | SECTION 7 – AS-BUILTS
checkpoint | 7.1 - As-Builts
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Survey Records/ Redpen markups
label | Testing Quantity Required (based from schedule qtys) - Post Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature