## ITP-019
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-19
[11 empty] | Revision : 2 | Date : 30/01/2025
Client: |  |  |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Watergardens Carpark Station |  | Line / Road Marking |  | Name: Jake Cardillo |  | Name: Patrick Fagan |  |  | Name: Shaun Kent
Job No: |  | 7432000 |  | Specifications: Australian Standards, Vicroads Traffic Engineering Manual, Vicroads Sect 721
|  |  |  | Structure / Component: Line Marking |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Watergardens Station |  | Date : 30/01/2025 |  | Date : 30/01/2025 |  |  | Date : 30/01/2025
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Setting Out |  | Prior to start | Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections | Drawings | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Set out the works for installation of pavement markings / raised markers |  | Prior to application | Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless a written exemption has been granted by the Superintendent | VicRoads 721.B05 | Visual inspection | This ITP signed off | HP | Fulton Hogan Engineer & Superintendent |  |  | N/A
2.3 | Materials |  | Prior to commencement | All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent‑borne paint or AS/NZS 4049.3 for water‑borne paint as listed in Section 175. | 712.A04(c) | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer
2.4 | General Markings |  | Prior to commencement | Linemarking shall be applied by a self propelled machine, and stencils shall be used with all roadmarking. All work must be undertaken by a contractor eligible for accreditation under the Painting Contractors Certification Programme (PCCP). This programme is administered by the CSIRO. | 712.D01(c) | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A
3 | Completion
3.1 | Tolerances |  | Each marking | The Contractor shall comply with the tolerances as shown in Table 721.A101 when installing pavement markings. (i) Distance between centreline of marking and set out marks <30mm (ii) Width of completed paint markings <15mm (iii) Length of completed stripes and blocks 0 to +10% of specified length | Table 712.A101 | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A
3.2 | As-Built |  | Post Completion | As built survey recorded to confirm installation within tolerances in the latest IFC drawings. | IFC Drawings Survey Records | Document Review | This ITP signed off | SCP | Project Engineer /Surveyor | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.