## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-028
[11 empty] | Revision : 2 | Date : 30/01/2025
Client: |  | MRPA |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Watergardens Station Carpark |  | Weld Mesh Fencing |  | Name: Jake Cardillo |  | Name: Patrick Fagan |  |  | Name: Shaun Kent
Job No: |  | 7432000 |  | Specifications:
|  |  |  | Structure / Component: Fencing |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Watergardens Station |  | Date : 30/01/2025 |  | Date : 30/01/2025 |  |  | Date : 30/01/2025
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | •Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Check Materials |  | Prior to commencing any activity | •Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements of SD3143 and IFC drawings. | Fencing Plan SD3143 | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Confirm Footings position |  | Prior to commencing any activity | •Confirm footings are set out to locations specified on design drawings | Fencing Plan SD3143 | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Footing Installation |  | Prior to post installation | •Concrete shall be of minimum strength N20 •Concrete footing shall be as per the IFC drawings | Fencing Plan SD3143 | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Post Installation |  | Each Lot | •Posts shall be set in concrete footings of the dimensions shown on the drawings and set at the correct height governed by landscaped area FSL. | Fencing Plan SD3143 | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Fence Panels |  | Each Lot | •Post centres shall be placed at 2455 mm intervals as shown on drawing SD3143. | Fencing Plan SD3143 | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.4 | Isolation Gaps |  | Each Lot | •Install isolation gaps where new fencing connects to existing. | Fencing Plan | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.5 | Installation of Gates and Backstays |  | Each Lot | •Gates and backstays to be installed as per the IFC drawings and adequately set as required. | Fencing Plan | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
3 | Completion
3.1 | Clean up |  | Post Completion | •Personnel to ensure that work areas are clean and free of excess materials | Fencing Plan SD3143 | Verify | This ITP signed off | SCP | Project Engineer /Surveyor | N/A |  | N/A
3.2 | Verification |  | Post Completion | •All material dockets and compliance certificates are to be provided to the client. | Fencing Plan SD3143 | Verify | This ITP signed off | SCP | Project Engineer /Surveyor | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.