## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | FHC-ITP-018 - Landscaping | itp |  |  |  |  | FHC-ITP-018 - Landscaping Rev1
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Submissions and Records
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The specified inspections, samples, records and certificates shall be made available or submitted to the Superintendent for acceptance prior to the commencement of associated work.
label | REFERENCE DOCUMENTS: 720.03
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.4 Permits
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The Contractor shall obtain all necessary permits and obtain approval from the Superintendent prior to the pruning or removal of local native vegetation.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.2 Setting out of landscape softworks
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The Contractor shall set out the location and shape of planting areas in accordance with the Landscape Drawings.
label | REFERENCE DOCUMENTS: 720.06
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.3 Supply of Materials
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All materials shall be supplied by the Contractor unless otherwise noted. If any materials are supplied by VicRoads, a joint inspection of the materials shall be made by the Contractor and the Superintendent following delivery of the materials to the site. The materials, if satisfactory, shall thereafter become the responsibility of the Contractor.
label | REFERENCE DOCUMENTS: 720.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
checkpoint | 2.4 Pest and Weed Control
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing. Weed control shall be programmed and implemented to deplete the potential weed seed bank within the topsoil to be used in planting beds.
label | REFERENCE DOCUMENTS: 720.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.4 Fertilisers
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Fertilisers for planting areas and advanced trees shall be slow release with a 9‑12 month release period and suitable for the establishment of plant types, sizes and species specified in the plant schedule(s).
label | REFERENCE DOCUMENTS: 720.04(f)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.5 Mulch
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All wood mulch shall be supplied, delivered, handled and applied in accordance with AS 4454.
label | REFERENCE DOCUMENTS: 720.04(h), AS4454
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.6 Weed Control Mat and Erosion Control Mat
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The Contractor shall supply and install jute or approved equivalent, biodegradable, fire retardant weed and erosion control mat as indicated on the Drawings or as specified. Weed Control Mat shall be minimum 700 grams per square metre and Erosion Control Mat shall be 300 grams per square metre. The surface of the mat shall permit water infiltration.
label | REFERENCE DOCUMENTS: 720.04(i)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.7 Ripping
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The Contractor shall make available each ripped planting area, individual tree planting and grassing area prior to mulching, planting or grassing. The Contractor shall not proceed until the Superintendent acknowledges requirements for ripping have been met. In areas where ripping is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
label | REFERENCE DOCUMENTS: 720.07 (b)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 Topsoil Finished Surface Levels
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The Contractor shall make available each ripped, topsoiled and cultivated planting area, individual tree planting and grassing area prior to mulching, planting or grassing. The Contractor shall not proceed until the Superintendent acknowledges requirements for topsoiling and cultivation have been met. In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
label | REFERENCE DOCUMENTS: 720.07 (e)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | FHC-ITP-035 - Line Marking | itp |  |  |  |  | FHC-ITP-035 - Line Marking Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Set out the works for installation of pavement markings / raised markers
label | FREQUENCY: Prior to application
label | ACCEPTANCE CRITERIA: Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless a written exemption has been granted by the Superintendent
label | REFERENCE DOCUMENTS: VicRoads 721.B05
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Materials
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent‑borne paint or AS/NZS 4049.3 for water‑borne paint as listed in Section 175.
label | REFERENCE DOCUMENTS: 712.A04(c)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 General Markings
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Linemarking shall be applied by a self propelled machine, and stencils shall be used with all roadmarking.
label | ○ All work must be undertaken by a contractor eligible for accreditation under the Painting Contractors Certification Programme (PCCP). This programme is administered by the CSIRO.
label | REFERENCE DOCUMENTS: 712.D01(c)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Completion
checkpoint | 3.1 Tolerances
label | FREQUENCY: Each marking
label | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances as shown in Table 721.A101 when installing pavement markings.
label | (i) Distance between centreline of marking and set out marks <30mm
label | (ii) Width of completed paint markings <15mm
label | (iii) Length of completed stripes and blocks 0 to +10% of specified length
label | REFERENCE DOCUMENTS: Table 712.A101
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 3.2 As-Built
label | FREQUENCY: Post Completion
label | ACCEPTANCE CRITERIA: As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | REFERENCE DOCUMENTS: IFC Drawings, Survey Records
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed off
label | SCP
label | RESPONSIBILITY: Project Engineer /Surveyor
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | FHC-ITP-038 - Weldmesh Fence Installation | itp |  |  |  |  | FHC-ITP-038 - Weldmesh Fence Installation Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Check Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements of SD3143 and IFC drawings.
label | REFERENCE DOCUMENTS: Fencing Plan SD3143
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Confirm Footings position
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
label | REFERENCE DOCUMENTS: Fencing Plan SD3143
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Footing Installation
label | FREQUENCY: Prior to post installation
label | ACCEPTANCE CRITERIA: Concrete shall be of minimum strength N20
label | ○ Concrete footing shall be as per the IFC drawings
label | REFERENCE DOCUMENTS: Fencing Plan SD3143
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Post Installation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Posts shall be set in concrete footings of the dimensions shown on the drawings and set at the correct height governed by landscaped area FSL.
label | REFERENCE DOCUMENTS: Fencing Plan SD3143
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Fence Panels
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Post centres shall be placed at 2455 mm intervals as shown on drawing SD3143.
label | REFERENCE DOCUMENTS: Fencing Plan SD3143
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Isolation Gaps
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Install isolation gaps where new fencing connects to existing.
label | REFERENCE DOCUMENTS: Fencing Plan
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Installation of Gates and Backstays
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: •Gates and backstays to be installed as per the IFC drawings and adequately set as required.
label | REFERENCE DOCUMENTS: Fencing Plan
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Completion
checkpoint | 3.1 Clean up
label | FREQUENCY: Post Completion
label | ACCEPTANCE CRITERIA: Personnel to ensure that work areas are clean and free of excess materials
label | REFERENCE DOCUMENTS: Fencing Plan SD3143
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | SCP
label | RESPONSIBILITY: Project Engineer /Surveyor
textbox | Date Completed:
checkpoint | 3.2 Verification
label | FREQUENCY: Post Completion
label | ACCEPTANCE CRITERIA: All material dockets and compliance certificates are to be provided to the client.
label | REFERENCE DOCUMENTS: Fencing Plan SD3143
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | SCP
label | RESPONSIBILITY: Project Engineer /Surveyor
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: