## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S121 - Earthworks - Section 1 - Inspection and Test Plan - Rev 1 | itp |  |  |  |  | DS2672-ITP-S121 - Earthworks - Section 1 - Inspection and Test Plan - Rev 1
section | 5.03 Clearing, Stripping, and Excavation
checkpoint | 5.03.05 - Tree and Bush Clearing
label | Acceptance / Conformance Criteria - No trees or bush shall be cleared without approval from the Engineer.
label | Standard / Specification - 14AED/AD4-C - 030.7.2
label | Verifying Document - Hold Point Release
label | Frequency - Prior to Removal
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.03 - Organic Material Removal
label | Acceptance / Conformance Criteria - All organic material shall be removed from the areas subject to excavation or filling. Turf, topsoil, and any scrub shall be removed to expose soil containing insignificant amounts of organic material.
label | Standard / Specification - 14AED/AD4-C - 030.7.1
label | Verifying Document - Site Records / Photos
label | Frequency - When encountered
label | Activity - A
label | By - PE
checkpoint | 5.03.01 - Excavation of Upper Dam Shoulder Inspection (Section 1)
label | Acceptance / Conformance Criteria - Excavation of upper dam shoulder at interface with spillway block and cut-off wall, placement of filter and drainage materials: full-time designer site presence must be inspected by the Engineer prior to further work being carried out in the area.
label | Standard / Specification - 14AED/AD4-C - 030.3
label | Verifying Document - Hold Point Release
label | Frequency - 48 Hours Notice Prior to Each Occurrence
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.04 - Topsoil Stockpiling
label | Acceptance / Conformance Criteria - All significant volumes of topsoil shall be stockpiled for later re-use. Materials containing insufficient amounts of topsoil for practical separation shall be disposed of in dump areas to be designated by the Engineer.
label | Standard / Specification - 14AED/AD4-C - 030.7.1
label | Verifying Document - Site Records / Photos
label | Frequency - When encountered
label | Activity - A
label | By - PE
checkpoint | 5.03.06 - Surface Water Control
label | Acceptance / Conformance Criteria - All earthworks shall be carried out in the dry. Both cut and fill areas shall be sloped adequately during construction so that they do not pond water and temporary drains shall be provided as necessary to ensure the effective removal of stormwater from the areas of operation into the site drainage system.
label | Standard / Specification - 14AED/AD4-C - 030.7.3
label | Verifying Document - Site Records / Photos
label | Frequency - During Works
label | Activity - R
label | By - SE
checkpoint | 5.03.08 - Water in Excavation
label | Acceptance / Conformance Criteria - The excavation shall be free of water at all times
label | Standard / Specification - 14AED/AD4-C - 030.10
label | Verifying Document - Site Records / Photos
label | Frequency - Daily
label | Activity - M
label | By - SE
checkpoint | 5.03.09 - Dewatering Sump Backfilling
label | Acceptance / Conformance Criteria - Sumps formed for the purposes of dewatering shall be backfilled and compacted in layers with suitable fill to the approval of the Engineer.
label | Standard / Specification - 14AED/AD4-C - 030.10
label | Verifying Document - Site Records / Photos
label | Frequency - Each Sump
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.07 - Unsuitable Material Removal
label | Acceptance / Conformance Criteria - Unsuitable material shall be excluded from the construction works and be placed in a disposal area as directed by the Engineer in loose layer thicknesses not exceeding 500 mm and be track rolled with a minimum of two passes.
label | Standard / Specification - 14AED/AD4-C - 030.14.7
label | Verifying Document - Site Records / Photos
label | Frequency - When encountered
label | Activity - R
label | By - SE
checkpoint | 5.03.10 - Bulk Excavation
label | Acceptance / Conformance Criteria - Excavation within the buttress footprint shall be to intact rock, which is anticipated to be weak siltstone.
label | Standard / Specification - 14AED/AD4-C - 030.8
label | Verifying Document - Site Records / Photos
label | Frequency - During Works
label | Activity - I
label | By - SE
checkpoint | 5.03.11 - Bulk Excavation Protection
label | Acceptance / Conformance Criteria - No compaction or trafficking on the exposed rock shall be undertaken, as it is likely that the surface will be sensitive to disturbance and deterioration.
label | Standard / Specification - 14AED/AD4-C - 030.8
label | Verifying Document - Site Records / Photos
label | Frequency - During Works
label | Activity - R
label | By - SE
checkpoint | 5.03.12 - Subgrade Inspection
label | Acceptance / Conformance Criteria - On completion of the bulk excavation, inspection and testing of the subgrade shall be performed by the Engineer.
label | Standard / Specification - 14AED/AD4-C - 030.8
label | Verifying Document - Hold Point Release
label | Frequency - 48 Hours Notice Prior to Each Occurrence
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.13 - Inspection Prior to Filling
label | Acceptance / Conformance Criteria - Before fill is placed in any area, the Engineer shall be notified so that he may inspect the stripping and/or removal of unsuitable materials to see that this prior work meets with the specified requirements. No filling shall be undertaken until inspections have been made and the Engineer has approved the commencement to fill.
label | Standard / Specification - 14AED/AD4-C - 030.11
label | Verifying Document - Hold Point Release
label | Frequency - Prior to Filling
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2672-ITP-S122 - Earthworks - Section 2 to 9 - Inspection and Test Plan - Rev 1 | itp |  |  |  |  | DS2672-ITP-S122 - Earthworks - Section 2 to 9 - Inspection and Test Plan - Rev 1
section | 5.03 Clearing, Stripping, and Excavation
checkpoint | 5.03.05 - Tree and Bush Clearing
label | Acceptance / Conformance Criteria - No trees or bush shall be cleared without approval from the Engineer.
label | Standard / Specification - 14AED/AD4-C - 030.7.2
label | Verifying Document - Hold Point Release
label | Frequency - Prior to Removal
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.03 - Organic Material Removal
label | Acceptance / Conformance Criteria - All organic material shall be removed from the areas subject to excavation or filling. Turf, topsoil, and any scrub shall be removed to expose soil containing insignificant amounts of organic material.
label | Standard / Specification - 14AED/AD4-C - 030.7.1
label | Verifying Document - Site Records / Photos
label | Frequency - When encountered
label | Activity - A
label | By - PE
checkpoint | 5.03.02 - Excavated upper dam shoulder Inspection (Section 2 to 9)
label | Acceptance / Conformance Criteria - Excavated upper dam shoulder, each subsequent 20m wide section prior to placement of filter and drainage materials must be inspected by the Engineer prior to further work being carried out in the area.
label | Standard / Specification - 14AED/AD4-C - 030.3
label | Verifying Document - Hold Point Release
label | Frequency - 48 Hours Notice Prior to each subsequent 20m wide section
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.04 - Topsoil Stockpiling
label | Acceptance / Conformance Criteria - All significant volumes of topsoil shall be stockpiled for later re-use. Materials containing insufficient amounts of topsoil for practical separation shall be disposed of in dump areas to be designated by the Engineer.
label | Standard / Specification - 14AED/AD4-C - 030.7.1
label | Verifying Document - Site Records / Photos
label | Frequency - When encountered
label | Activity - A
label | By - PE
checkpoint | 5.03.06 - Surface Water Control
label | Acceptance / Conformance Criteria - All earthworks shall be carried out in the dry. Both cut and fill areas shall be sloped adequately during construction so that they do not pond water and temporary drains shall be provided as necessary to ensure the effective removal of stormwater from the areas of operation into the site drainage system.
label | Standard / Specification - 14AED/AD4-C - 030.7.3
label | Verifying Document - Site Records / Photos
label | Frequency - During Works
label | Activity - R
label | By - SE
checkpoint | 5.03.08 - Water in Excavation
label | Acceptance / Conformance Criteria - The excavation shall be free of water at all times
label | Standard / Specification - 14AED/AD4-C - 030.10
label | Verifying Document - Site Records / Photos
label | Frequency - Daily
label | Activity - M
label | By - SE
checkpoint | 5.03.09 - Dewatering Sump Backfilling
label | Acceptance / Conformance Criteria - Sumps formed for the purposes of dewatering shall be backfilled and compacted in layers with suitable fill to the approval of the Engineer.
label | Standard / Specification - 14AED/AD4-C - 030.10
label | Verifying Document - Site Records / Photos
label | Frequency - Each Sump
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.07 - Unsuitable Material Removal
label | Acceptance / Conformance Criteria - Unsuitable material shall be excluded from the construction works and be placed in a disposal area as directed by the Engineer in loose layer thicknesses not exceeding 500 mm and be track rolled with a minimum of two passes.
label | Standard / Specification - 14AED/AD4-C - 030.14.7
label | Verifying Document - Site Records / Photos
label | Frequency - When encountered
label | Activity - R
label | By - SE
checkpoint | 5.03.10 - Bulk Excavation
label | Acceptance / Conformance Criteria - Excavation within the buttress footprint shall be to intact rock, which is anticipated to be weak siltstone.
label | Standard / Specification - 14AED/AD4-C - 030.8
label | Verifying Document - Site Records / Photos
label | Frequency - During Works
label | Activity - I
label | By - SE
checkpoint | 5.03.11 - Bulk Excavation Protection
label | Acceptance / Conformance Criteria - No compaction or trafficking on the exposed rock shall be undertaken, as it is likely that the surface will be sensitive to disturbance and deterioration.
label | Standard / Specification - 14AED/AD4-C - 030.8
label | Verifying Document - Site Records / Photos
label | Frequency - During Works
label | Activity - R
label | By - SE
checkpoint | 5.03.12 - Subgrade Inspection
label | Acceptance / Conformance Criteria - On completion of the bulk excavation, inspection and testing of the subgrade shall be performed by the Engineer.
label | Standard / Specification - 14AED/AD4-C - 030.8
label | Verifying Document - Hold Point Release
label | Frequency - 48 Hours Notice Prior to Each Occurrence
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.13 - Inspection Prior to Filling
label | Acceptance / Conformance Criteria - Before fill is placed in any area, the Engineer shall be notified so that he may inspect the stripping and/or removal of unsuitable materials to see that this prior work meets with the specified requirements. No filling shall be undertaken until inspections have been made and the Engineer has approved the commencement to fill.
label | Standard / Specification - 14AED/AD4-C - 030.11
label | Verifying Document - Hold Point Release
label | Frequency - Prior to Filling
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT