## zres_siteapp
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | DS2672-ITP-S110 - Earthworks Overarching and Diversion Test Plan - Rev 2 | itp |  |  |  | Yes | DS2672-ITP-S110 - Earthworks Overarching and Diversion Test Plan - Rev 2 | 29341e28-1c8c-48b4-97e5-9cebac59d606
checkpoint-group |  |  | section | 3.01 Site Requirements
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | cdebbe6e-7aac-5697-9d64-89fc94f4625e |  | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
label | d7deaf5b-4d42-5c51-ae79-151074072d0f |  | note | Standard / Specification - Downer
label | 31d3051f-55f4-5b11-b733-1fc696a25d66 |  | note | Verifying Document - Construction Pack
label | 9652d532-da2c-5285-af75-01d264a8ebbf |  | note | Frequency - Submit Prior to commencement of works
label | 855337ba-4e66-56af-8a5e-46946eeb7e59 |  | note | Activity - H
label | 37aa8135-96ac-5056-a319-9cd3112054e3 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | c9ff5ee4-3b8a-5def-b3db-b6cb71f93326 |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | 28dfe9ff-b32a-5958-8fb3-f880c6de6a23 |  | note | Standard / Specification - Downer
label | c9346dbf-42c2-522b-a5c5-a844f22f63f0 |  | note | Verifying Document - Survey Records
label | 784bd7d6-8066-5051-96d5-60c27e61ec7d |  | note | Frequency - Prior to Works
label | b5baa110-ce04-5652-baac-551d39ab9b5b |  | note | Activity - H
label | 5b53953f-2c31-5fd0-8607-970330fede66 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Service Location
label | ceaee4d9-9688-5bb7-bf41-9f902b2d2a4a |  | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | edcda89c-2832-5719-bd0a-76a73353fb6e |  | note | Standard / Specification - Downer
label | 21415d5e-a8e9-5dcc-8dee-79f8db443782 |  | note | Verifying Document - Excavation Permit
label | bab3922f-f4d9-57f8-86de-440efcec3383 |  | note | Frequency - Prior to Excavation
label | 18a0c0d2-2373-5c11-a3c4-2a140570d1f4 |  | note | Activity - H
label | f9df1c23-86c9-5eaf-a8b1-9210579b922c |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.04 - Internal Permits
label | ac32e5df-96d6-506c-807d-e80019975099 |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | 25a77f73-cd42-59aa-8273-5b64c482720f |  | note | Standard / Specification - Downer
label | eb503008-74e3-5ca7-b76a-e19ee9764813 |  | note | Verifying Document - Internal Permits
label | e4024ce9-197a-5297-8488-c0e7b6a9f1ec |  | note | Frequency - Prior to Excavation
label | 877580bc-3c93-53d0-817c-372bfc42e8c4 |  | note | Activity - H
label | 29bc361a-8df4-54c6-b037-15c630f9947b |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.05 - External Permits
label | 53eda759-f00a-571f-a79e-54e7a423a9fb |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | 46e4b246-1e0f-5ac3-98d3-0e79ae6bbbc7 |  | note | Standard / Specification - Downer
label | e72699a1-b323-5ce9-8ce1-42161c16e7cd |  | note | Verifying Document - External Permits
label | 2e62c864-e283-561b-bfb7-3bc75b593fcb |  | note | Frequency - Prior to Excavation
label | 17edb625-c4f9-55e1-a6a7-a42911267d30 |  | note | Activity - H
label | 77cfb2fd-0b74-5634-afee-02aef15fdf47 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.06 - Approved Construction Drawings
label | 2b89715d-6149-512d-a21b-7594581a9ec7 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 68b84372-18c4-53e6-83e7-84c88dd91af5 |  | note | Standard / Specification - Downer
label | 71ae5c5d-9898-5767-9058-9e7bb0552f5a |  | note | Verifying Document - IFC Drawings
label | 8f35e786-ae9e-526b-823b-0473ed1399bc |  | note | Frequency - Prior to works start
label | 9d8397d7-6e49-5ae2-b9bc-8259224adb95 |  | note | Activity - H
label | a6d7bae0-f529-5c26-b0f1-a0795fb6747b |  | note | By - PE
checkpoint-group |  |  | section | 3.02 Hold Points
checkpoint-status |  |  | checkpoint | 3.02.03 - Diversion Notice
label | fbe5d9d8-247c-5c43-8295-87c116dbee63 |  | note | Acceptance / Conformance Criteria - The Consent Holder shall inform a Compliance Officer of the Consent Authority at least five working days prior to any diversion taking place to allow an inspection of the works to be undertaken.
label | 1bd2fe70-9624-5ab9-9d03-5f72fb1e6113 |  | note | Standard / Specification - P&G 14
label | 8dd367bd-0641-5e13-9062-d50fb99b0db6 |  | note | Verifying Document - Notice
label | 87dd76f8-83d4-565a-a661-a1ebd2722641 |  | note | Frequency - At least five working days prior to any diversion
label | 5f29809c-66b1-5fc4-a9b3-3cd8a5677d73 |  | note | Activity - HP
label | 6828183c-16fc-5a93-810c-f0732b6170a8 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5.01 Erosion and Sediment Controls
checkpoint-status |  |  | checkpoint | 5.01.01 - Certification
label | b7461ef0-2c74-57c5-ab9e-50b5d451a885 |  | note | Acceptance / Conformance Criteria - Prior to bulk earthworks commencing, the nominated Contractor shall submit asbuilt drawings to the Engineer for approval, and to confirm the erosion and sediment controls have been constructed in accordance with the approved E&SCP and Resource Consent conditions.
label | 6b21c888-94ab-56d8-a81f-6594e7e6df4f |  | note | Standard / Specification - 14AED/AD4-C - 020.5.7
label | 9311060b-d1f8-53b6-b76a-f4b0e51a1def |  | note | Verifying Document - Jet-Grouting Asbuilt Drawings
label | b933ab9f-4675-5bbc-b711-03f6c6c4a8dc |  | note | Frequency - Prior to Bulk Earthworks
label | e61fbb3e-3518-50d4-a149-1f44215b1c3f |  | note | Activity - HP
label | 26dc9d90-78f4-5ce9-8223-9a861ab942c7 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.02 - Seasonal Restriction
label | 5456fdd7-6068-57dc-b73f-aa536affd957 |  | note | Acceptance / Conformance Criteria - No vegetation removal or earthworks on the site shall be undertaken between 30 April and 1 October in any year, without the written approval of the Engineer. Earthworks in this regard refers to bulk earthworks (cut/fill/waste) associated with the site.
label | 1fd54a40-5fc3-54da-b781-678dedd0de9d |  | note | Standard / Specification - 14AED/AD4-C - 020.5.9
label | 02b9abf6-dc7f-51e9-b4f4-1749128b69f8 |  | note | Verifying Document - Hold Point Release
label | 4d36a25c-725a-5f7b-a387-4a1318f926e0 |  | note | Frequency - Each Occurrence
label | e74c00d7-bd80-5cb9-8c65-8904237ee19a |  | note | Activity - HP
label | 5f15e967-f428-5b3e-9701-9a83836c8429 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5.02 Diversion
checkpoint-status |  |  | checkpoint | 5.02.01 - Diversion Management Plan
label | 881b5da7-4549-51f2-b329-2685d99c0056 |  | note | Acceptance / Conformance Criteria - The nominated contractor shall prepare a management plan covering all work below river level and submit it to the Engineer for review.
label | 531a2c6a-1b91-5d85-9c8c-7c2850081fcf |  | note | Standard / Specification - 14AED/AD4-C - 030.4
label | ce1293d4-63ce-5667-bd1c-6fec69a29316 |  | note | Verifying Document - Management Plan
label | c99dda97-184d-58aa-88db-8167e0734373 |  | note | Frequency - Prior to Works
label | cd2e4c6e-2b01-5cf9-b765-dcdd5361c5f8 |  | note | Activity - HP
label | 95c31e6d-5371-5d86-acb9-31e1890ca85a |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.02 - Diversion Bund Methodology
label | 243adcdf-95eb-58f7-9c34-00359e6295b1 |  | note | Acceptance / Conformance Criteria - The Diversion bund shall be constructed using site-derived granular soils, with rock rip-rap on both the upstream and downstream shoulders. The nominated Contractor shall provide a method statement for construction of the bund for the approval of the Engineer.
label | eec43e6a-37e3-52c3-a0ae-9aac49039444 |  | note | Standard / Specification - 14AED/AD4-C - 030.13.6
label | c4ca0299-c499-59ca-9657-9c0b2f006541 |  | note | Verifying Document - Methodology
label | 3de41b38-2f94-5c85-84ca-9d14a3579bb6 |  | note | Frequency - Prior to Works
label | 20089a8f-17cc-5b28-8d82-ec3c98175b7e |  | note | Activity - HP
label | bd82f7d3-6956-5e22-8a85-b274d527b19c |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.03 - Completed spillway strengthening works
label | 14cdffb8-cb0d-56a3-bd86-5bfdca768db8 |  | note | Acceptance / Conformance Criteria - Completed spillway strengthening works (by others) prior to commencement of diversion works must be inspected by the Engineer prior to further work being carried out in the area.
label | f8860e6f-676a-586b-99a8-836f80034b01 |  | note | Standard / Specification - 14AED/AD4-C - 030.3
label | 01d1dd1e-ab83-5cab-9090-7a79befff412 |  | note | Verifying Document - Hold Point Release
label | 3f49506d-f45e-57d0-ba6c-249fc3f4570d |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | d865a06d-6e8f-52d1-9de5-5425c97e3b8e |  | note | Activity - HP
label | ee0e4ce6-d824-56d1-b92b-784684343b0e |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10.01 Site Post Construction Activities
checkpoint-status |  |  | checkpoint | 10.01.01 - Construction Record Compilation
label | 06635f71-6f33-5a17-8932-82cca3cef837 |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | 69826344-3550-5731-99c4-e3c0f58aa2b7 |  | note | Standard / Specification - Downer
label | 25eac490-124b-5117-b33d-503b4b0f4f17 |  | note | Verifying Document - Records
label | 80edfc19-c428-5a92-9f4f-1ae91d477ce9 |  | note | Frequency - Post construction
label | 7d31dc59-31e8-548b-ade4-37fb11b9c45c |  | note | Activity - H
label | 38c176d6-7564-5d9b-aca4-c9283668b1b9 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 10.01.02 - Survey Records
label | 315685ab-e375-53e1-a9b7-3b6eb8f356e4 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | 2dacf141-fb0d-5525-a1d2-159fff2c7230 |  | note | Standard / Specification - Downer P&G 20.1
label | e7945523-886d-5a03-ba41-665720a59b8e |  | note | Verifying Document - Records
label | 0d1caf63-0465-512e-ab2e-86c42f621499 |  | note | Frequency - Post construction
label | 3bb8bf62-1350-5137-a3af-4b75636ca97d |  | note | Activity - H
label | f47cd56c-a768-5836-9d0d-2c4d1f5fd50a |  | note | By - SV
checkpoint-status |  |  | checkpoint | 10.01.03 - Redline Drawings
label | 5af66e83-1232-575d-a15a-0262d64330e0 |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red-pen mark-up copies of the Drawings and Specifications and other design documentation showing any deviations from the specified details and requirements produced in accordance with industry good practice.
label | 52fb12b2-126c-5132-8751-9948b97c2595 |  | note | Standard / Specification - Downer P&G 20.1
label | 03ffca0d-4c61-5543-8235-3d237eaab522 |  | note | Verifying Document - Redlines
label | c8d39087-e6e8-5262-8cc2-623d266d410f |  | note | Frequency - Post construction
label | ba6aaa93-c246-5678-9c50-46ddb26246b8 |  | note | Activity - H
label | 581784bd-fbb4-5b77-ad17-5fd08d5d19e6 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 10.01.04 - Defect, Snag and Punch List
label | b5109874-20e3-5d1a-a6fe-9476acd38dbd |  | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | c5d5a9b0-f1d5-5f9d-81f5-6c60bcd3653e |  | note | Standard / Specification - Downer
label | 0c7ffdea-a37e-5918-9a50-95165781109d |  | note | Verifying Document - Register
label | 90b0cefd-b80b-5720-91b7-06157e92e4d6 |  | note | Frequency - Post construction
label | 5a38b1c4-a271-5184-b51d-607c7b8e9ec5 |  | note | Activity - H
label | 12674aed-91a0-5df3-a7a1-bfea05b3a018 |  | note | By - PE
checklist-sectioned |  |  | checklist | DS2672-ITP-S111 - Drainage Inspection and Test Plan - Rev 2 | itp |  |  |  | Yes | DS2672-ITP-S111 - Drainage Inspection and Test Plan - Rev 2 | 347ef522-2e21-4ca6-a5cf-748a9da40536
checkpoint-group |  |  | section | 5.04 Placement and Compaction of Fill General
checkpoint-status |  |  | checkpoint | 5.04.02 - Surface Water Control
label | 30c36450-acdd-51cc-8ffc-cc265f7f67fb |  | note | Acceptance / Conformance Criteria - Cut and fill areas shall be sloped and graded adequately so that they do not pond stormwater, and drains shall be installed as necessary on a regular basis to deflect run off from the areas of operation, or to drain ponded water as soon as ponds are seen to develop.
label | db007c98-01f1-54bb-8c72-559356caaa7f |  | note | Standard / Specification - 14AED/AD4-C - 034.14.1
label | 0f00d324-b88c-5246-bfc7-532e6b27a5a5 |  | note | Verifying Document - Site Records / Photos
label | d1819a55-1242-5d07-891f-72fa1714e950 |  | note | Frequency - Daily
label | 41dd0a47-b5fc-55cc-9fe2-a4cf6128c681 |  | note | Activity - R
label | b8ebe630-302a-5996-95e8-1d5d696c0916 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.04.03 - Wet Weather
label | 65f8dd07-6809-5238-aa26-e2230b787c41 |  | note | Acceptance / Conformance Criteria - No fill shall be placed during periods of wet weather.
label | 2ffc6911-21db-520e-b6f3-55b50f0c27ef |  | note | Standard / Specification - 14AED/AD4-C - 034.14.1
label | 31a6b1c0-cc04-5b3e-bf67-77cd0da9082f |  | note | Verifying Document - Site Records / Photos
label | c19f0aae-12f9-5c88-9473-9582966a3aa3 |  | note | Frequency - Daily
label | dba1577d-b758-515f-8793-53b43d14ca49 |  | note | Activity - M
label | 59e2093a-0b26-5eb7-bc12-48576d87ef5c |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.04.04 - Extended Wet Weather Resumption Approval
label | ccebc2f2-751f-5425-9aa2-746cdd26211c |  | note | Acceptance / Conformance Criteria - In the event of fill operations ceasing in any area on account of wet weather or for more than one week for any reason, the nominated Contractor shall obtain the Engineer’s approval of the conditions of the fill surface before recommencing fill operations.
label | 93405217-2004-50b5-bae2-0a421d8f2acc |  | note | Standard / Specification - 14AED/AD4-C - 034.14.1
label | 8445f3f4-341a-572c-870d-850e99032c18 |  | note | Verifying Document - Hold Point Release
label | b7d67654-a2bb-5564-9ff7-65fc85968d3f |  | note | Frequency - Each Occurrence
label | fb867989-6c49-5a84-a219-39d422e386b9 |  | note | Activity - HP
label | d237d094-a29d-59b0-a078-834b6a3f8777 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.04.05 - Compaction Adjacent to Retaining Structures
label | 19aeac2e-d4bd-53d8-a683-f0de12d42f14 |  | note | Acceptance / Conformance Criteria - Rollers shall not be operated within 2m of retaining walls with placement of fill in 200mm maximum thickness lifts and compaction shall be via hand equipment or a small roller without vibration.
label | 8852e983-d904-5f82-83e3-c791f414170b |  | note | Standard / Specification - 14AED/AD4-C - 034.14.3
label | fa9379d3-a311-56f6-b6bd-1d5574147146 |  | note | Verifying Document - Site Records / Photos
label | 67e449fa-a483-5a1b-b840-e06b4129ae44 |  | note | Frequency - Each Structure
label | 292dccf9-bd25-5754-bfdc-02a6364dbfea |  | note | Activity - V
label | 88ce0d69-1b64-5494-aff3-3cfcb374850e |  | note | By - SE
checkpoint-group |  |  | section | 5.05 F1, F2 and F3 Placement and Compaction
checkpoint-status |  |  | checkpoint | 5.05.01 - Preparation of stripped ground surface inspection
label | ec004073-162f-5599-8264-d1036edcc700 |  | note | Acceptance / Conformance Criteria - Preparation of stripped ground surface prior to placement of site concrete must be inspected by the Engineer prior to further work being carried out in the area.
label | 88c4dc4c-2fbc-5ee2-9925-f6827a63e37f |  | note | Standard / Specification - 14AED/AD4-C - 030.3
label | 94f70e59-ae42-56f0-a6f2-7ecde96b87b0 |  | note | Verifying Document - Hold Point Release
label | e4d098aa-8a94-570b-a4f1-b1f986e9eddb |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | d2d6293e-8c40-5907-baf6-a3b2dc8b8385 |  | note | Activity - HP
label | c284aec8-9aa7-5eb7-9bca-a4a5f10bd97a |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.05.02 - Excavated lower dam shoulder / foundation Inspection
label | 64528ed6-2415-59d2-a999-8d8e3dffb82a |  | note | Acceptance / Conformance Criteria - Excavated lower dam shoulder/foundation, each 20m wide section prior to placement of filter and drainage materials must be inspected by the Engineer prior to further work being carried out in the area.
label | 48f381e4-e41d-5fae-b22a-5ad3900a9850 |  | note | Standard / Specification - 14AED/AD4-C - 030.3
label | 098644b6-bb5c-5368-b7ce-7b16a1bd6387 |  | note | Verifying Document - Hold Point Release
label | 3c2c33b6-a728-573f-b59c-d1ae83469a86 |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | 3b5c7ab9-9805-5ee3-a195-b779242cea26 |  | note | Activity - HP
label | 606cf143-fb27-5ce9-a329-946a83668a4c |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.05.03 - Placement of filter and drainage material Inspection at Upper dam shoulder
label | aa0dbf94-f441-5868-8c64-845c0150a724 |  | note | Acceptance / Conformance Criteria - Placement of filter and drainage material, a full-time designer site presence must be inspected by the Engineer prior to further work being carried out in the area.
label | 28fbc966-d2f0-5b7a-8bb7-109e8714ed8d |  | note | Standard / Specification - 14AED/AD4-C - 030.3
label | cc4e0093-606f-5a71-833e-03d7018bfd82 |  | note | Verifying Document - Hold Point Release
label | d66958d9-9b23-540d-9052-875eb1882e87 |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | 1858c793-51ea-5c16-9eff-51fb525114d7 |  | note | Activity - HP
label | 81319ec4-1a5a-58c8-9fa4-8d17d6d4de9f |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.05.04 - Placement of Drainage Material
label | 1193fc84-0317-5a81-8cf0-5353c16cd62d |  | note | Acceptance / Conformance Criteria - Filter/drainage material shall be placed in a way which prevents segregation, contamination or breakdown of particles with the maximum loose lift thickness for filter/drainage materials is 200mm.
label | 21c35091-36ed-5648-8299-77b70c98baad |  | note | Standard / Specification - 14AED/AD4 -C -034.14.5
label | 21c3304b-0a6f-5da3-9055-5941dc9d15a5 |  | note | Verifying Document - Site Records / Photos
label | 5f1fca08-d89c-5fb8-baf9-fac438c9d142 |  | note | Frequency - Each Layer
label | 246eddf3-1a60-5d9d-9be1-7992c4dd06a6 |  | note | Activity - C
label | 874c5a9c-4dca-5d6a-9e99-7d9df3f1d08d |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.05.05 - Compaction of Drainage Material
label | f33798e1-ed37-5744-8981-4ab628665cdb |  | note | Acceptance / Conformance Criteria - Where space constraints allow, compaction shall comprise two passes with a self-propelled smooth-drum roller without vibration. In areas where space constraints prevent the use of a roller, compaction shall comprise two passes with a vibrating plate compactor or similar.
label | 02c740d3-d741-5442-856c-e27bc7ec608b |  | note | Standard / Specification - 14AED/AD4 -C -034.14.5
label | 53cfa271-823f-50b5-8722-26133a4bf96a |  | note | Verifying Document - Site Records / Photos
label | b88d9746-7388-5948-82e4-5f00ca1941fe |  | note | Frequency - Each Layer
label | 9d067b5f-d178-5bc3-9749-990bf722c449 |  | note | Activity - C
label | ee4b6e92-e71f-56b9-a5fc-a3b9e7f8a90a |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.05.06 - Excessive Compaction of Drainage Material
label | a732c48e-a3d8-5780-a155-b798ea1d67d8 |  | note | Acceptance / Conformance Criteria - The nominated Contractor shall ensure excessive compaction is avoided as this may reduce drain permeability. The nominated Contractor shall avoid damage to pipes. If pipes are damaged, they shall be removed and replaced.
label | 92bf3a24-e3f9-59d3-83bb-fcdf0f297b4d |  | note | Standard / Specification - 14AED/AD4 -C -034.14.5
label | 68c50a28-355e-5e62-bce6-5b1b25656a2c |  | note | Verifying Document - Site Records / Photos
label | 516c8400-8ecf-5645-89ae-2c9f8345237c |  | note | Frequency - Each Layer
label | 0cc96ea8-33ae-5a55-b0bd-12db06cff301 |  | note | Activity - M
label | fb96146d-bf84-5bc2-9105-75b418373dbb |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.05.07 - Surface Drainage
label | 76dcbe4e-5c95-5817-99ce-2c1c5ceb0ed7 |  | note | Acceptance / Conformance Criteria - Construction of drainage works shall be staged such that sub-surface drains do not act as surface drains or can be otherwise contaminated by siltation or vehicle trafficking prior to placement of buttressing bulk fill.
label | ddf166f2-fa81-5b20-84a8-3a2dbd875ac6 |  | note | Standard / Specification - 14AED/AD4 -C -034.14.5
label | 488e1bc9-14ab-5ffa-b438-eecd84591e1a |  | note | Verifying Document - Construction Pack
label | 9930975a-7905-563d-a423-b7c1c462cbc5 |  | note | Frequency - Prior to works
label | 2864f14f-64ef-5393-8f75-da122508bd01 |  | note | Activity - M
label | 0722d426-3fb9-5009-a884-ede6fffecedf |  | note | By - SE
checkpoint-group |  |  | section | 5.06 Subsoil Drainage
checkpoint-status |  |  | checkpoint | 5.06.01 - Subsoil Drainage Timing
label | 75f3e9ee-25f7-5826-8c75-2ffed60eca01 |  | note | Acceptance / Conformance Criteria - The subsoil drainage system shall be installed prior to the commencement of filling operations.
label | 6784c83d-cea8-50f5-94a0-620fb66515d6 |  | note | Standard / Specification - 14AED/AD4-C - 030.12
label | 55be2569-ac3c-502b-9bf6-2da2ecf79d53 |  | note | Verifying Document - Site Records / Photos
label | f9348170-f099-557f-a7a7-956ace725c51 |  | note | Frequency - Prior to the commencement of filling
label | 8c1d76aa-485c-5a72-bd4b-035a4f228519 |  | note | Activity - R
label | 4b9c23b9-9f54-5696-bfa3-89643d2f776d |  | note | By - PE
checkpoint-status |  |  | checkpoint | 5.06.02 - Installation of all new drainage pipes Inspection
label | d693e1ae-099b-5903-b923-e8e7dd5d3b7b |  | note | Acceptance / Conformance Criteria - Installation of all new drainage pipes in buttress, prior to backfilling must be inspected by the Engineer prior to further work being carried out in the area.
label | 62a1b8aa-4ed8-5c8e-8188-edba59a3253d |  | note | Standard / Specification - 14AED/AD4-C - 030.3 / 040.4.1
label | 32e8b8d8-e779-55f3-94a9-ff45e4abf2f2 |  | note | Verifying Document - Hold Point Release
label | 01601da6-bf7f-5740-8084-f152224f7823 |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | 529b0121-b9fa-5fe0-8f2e-8148effc8664 |  | note | Activity - HP
label | 80bf2c5d-515f-52f8-bd51-deb13c7c7fa4 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.06.03 - Subsoil Drainage Grading
label | 287170d4-6671-5c2f-9778-a18bb239e734 |  | note | Acceptance / Conformance Criteria - The subsoil drains and collector pipe shall be uniformly graded to ensure they do not hold water and evenly jointed to ensure unimpeded flow.
label | 70ca9733-ce29-5b18-870f-775896c8be3a |  | note | Standard / Specification - 14AED/AD4-C - 030.12
label | 63246c01-9d18-5195-8ca9-1440a7946438 |  | note | Verifying Document - Survey Records
label | 0f8cc2b4-0dc5-5391-8168-d3736e8f5561 |  | note | Frequency - During Installation
label | aff83b2f-8ed7-59cb-b768-fd6ec3d8aabb |  | note | Activity - D
label | 94b76eae-c5eb-55ef-bd78-a974d3e93b78 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 5.06.04 - Bedding for Pipes
label | a6c9c0f9-8f29-535f-8998-3b01cbef8113 |  | note | Acceptance / Conformance Criteria - Embedment material for drainage pipes within the buttress shall comprise Zone F3 drainage material.
label | 67906667-1e7d-5ec8-b166-706da51f8b78 |  | note | Standard / Specification - 14AED/AD4-C - 040.4.3
label | 4bd1dda1-23b7-5883-b4d8-73ecd917ad6b |  | note | Verifying Document - Site Records / Photos
label | 881d0089-7906-5d07-bf0c-1631f668e533 |  | note | Frequency - Each Pipe
label | 9111df0c-f868-57cf-9b78-55a20d8ee07f |  | note | Activity - I
label | 0b43484b-dba6-522e-b167-17c8d4a83dea |  | note | By - SE
checklist-sectioned |  |  | checklist | DS2672-ITP-S112 - Buttress Fill Inspection and Test Plan - Rev 2 | itp |  |  |  | Yes | DS2672-ITP-S112 - Buttress Fill Inspection and Test Plan - Rev 2 | 5aef567f-d59a-4fa0-984d-9aaf58c01350
checkpoint-group |  |  | section | 5.04 Placement and Compaction of Fill General
checkpoint-status |  |  | checkpoint | 5.04.02 - Surface Water Control
label | 3158d5da-edb3-5c09-a61f-222d9ddba844 |  | note | Acceptance / Conformance Criteria - Cut and fill areas shall be sloped and graded adequately so that they do not pond stormwater, and drains shall be installed as necessary on a regular basis to deflect run off from the areas of operation, or to drain ponded water as soon as ponds are seen to develop.
label | f4e10a1a-46ea-5c20-bd12-01fc733c8ada |  | note | Standard / Specification - 14AED/AD4-C - 034.14.1
label | aba63b5a-7a8b-513e-b4ca-66620e92c40b |  | note | Verifying Document - Site Records / Photos
label | 188f1b95-3b4c-5817-b726-065cf6d9e45d |  | note | Frequency - Daily
label | 07267c16-4fdc-5782-ba8d-9a248f72dd67 |  | note | Activity - R
label | bbe668f6-172b-5cdc-a3f8-76bc0c7f1767 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.04.03 - Wet Weather
label | 8288d616-7a3e-5cba-98bd-92dcbec2adb1 |  | note | Acceptance / Conformance Criteria - No fill shall be placed during periods of wet weather.
label | fde4c2a6-5083-50b3-99e3-ce471dbc9ed8 |  | note | Standard / Specification - 14AED/AD4-C - 034.14.1
label | f2c65ba1-423c-506e-8d5c-0d520b8321e0 |  | note | Verifying Document - Site Records / Photos
label | 2b8a621f-ad30-55ab-8799-a128a27c8296 |  | note | Frequency - Daily
label | 67942368-38c1-5d2d-9e5e-837b3ef8bf76 |  | note | Activity - M
label | 05fb9376-94f4-5bc5-a617-2df857ad38bd |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.04.04 - Extended Wet Weather Resumption Approval
label | b79473a8-a168-51a0-ac14-5ec2c98d0734 |  | note | Acceptance / Conformance Criteria - In the event of fill operations ceasing in any area on account of wet weather or for more than one week for any reason, the nominated Contractor shall obtain the Engineer’s approval of the conditions of the fill surface before recommencing fill operations.
label | 84c575a9-cd67-5b4e-bf50-839bd57d6cc1 |  | note | Standard / Specification - 14AED/AD4-C - 034.14.1
label | 2d344b37-257d-5fde-9b60-bddfa26b8831 |  | note | Verifying Document - Hold Point Release
label | 9a1e4f11-92cc-591f-967b-94cc3a45b245 |  | note | Frequency - Each Occurrence
label | 7b930b33-cf9f-524e-94c3-8fed0bbe71cd |  | note | Activity - HP
label | b1e9094e-005f-584b-a27c-f8a212ecaae6 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.04.05 - Compaction Adjacent to Retaining Structures
label | a4b276cf-7000-5638-a4d2-cb8caa49512f |  | note | Acceptance / Conformance Criteria - Rollers shall not be operated within 2m of retaining walls with placement of fill in 200mm maximum thickness lifts and compaction shall be via hand equipment or a small roller without vibration.
label | e976cb37-d878-54d3-b436-aaf0f6418255 |  | note | Standard / Specification - 14AED/AD4-C - 034.14.3
label | 4e574152-2fd2-560f-88e6-217521e5c8cb |  | note | Verifying Document - Site Records / Photos
label | 962c55e3-1bdc-5a73-a358-d7e26d24fdb3 |  | note | Frequency - Each Structure
label | 386d2d01-6d1e-5aac-8757-7b319c50cd56 |  | note | Activity - V
label | 718bbe05-8802-53e3-b2a3-9c9ed9fd6345 |  | note | By - SE
checkpoint-group |  |  | section | 5.07 Buttress Fill Placement and Compaction
checkpoint-status |  |  | checkpoint | 5.07.01 - Start of the buttress filling Inspection
label | 7b72f12d-38c7-5d15-be21-cabdc6f089a5 |  | note | Acceptance / Conformance Criteria - Start of the buttress filling operation must be inspected by the Engineer prior to further work being carried out in the area.
label | f36880d9-1d1f-5758-92e7-02788db5d4b0 |  | note | Standard / Specification - 14AED/AD4-C - 030.3
label | b83f72c0-5add-5941-baee-53c3595bdc7b |  | note | Verifying Document - Hold Point Release
label | 810203bc-f7ae-52b2-b96c-49c187669dce |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | c045f048-df8a-533f-9d1b-aeab0f8ac2e7 |  | note | Activity - HP
label | 1cb547f1-4e1f-545f-b47d-6fd0384b03a1 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.07.02 - Compaction Effort
label | 8ca39fbe-e24f-5bd8-abcb-3541ba8bcf1b |  | note | Acceptance / Conformance Criteria - Compaction of granular earthfill shall be carried out using a 10-tonne (minimum static weight), smooth steel drum vibrating roller, or approved equivalent and shall be demonstrated and conformance confirmed via a compaction trial.
label | ac0ef6e7-e808-5c4c-9938-a7efbf843eba |  | note | Standard / Specification - 14AED/AD4-C - 034.14.2
label | 77553483-cbd3-5cbf-ab9b-72cf87b85f20 |  | note | Verifying Document - Site Records / Compaction Trial
label | d7964f68-66b1-5a64-9e83-8e2e947013c1 |  | note | Frequency - Prior to Works
label | 511c4797-5245-5300-b2eb-ac806df7a530 |  | note | Activity - V
label | c618cbc6-78c6-58ae-ba2b-8048c2191e60 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 5.07.03 - Buttress Fill
label | 9490fd2d-6916-5a07-8a2d-83957ac57c8c |  | note | Acceptance / Conformance Criteria - Each fill layer for dam fill shall be given the higher of the trail result or four passes with vibration, even if the acceptance standard is met with fewer passes. No pumping of weaving of granular fill is permitted.
label | 306ed567-9939-5d76-b0f4-812cc0d48117 |  | note | Standard / Specification - 14AED/AD4 -C - 034.14.4 / 034.14.1
label | 1fe7c088-9374-5958-868d-56f4b82d9d1f |  | note | Verifying Document - Site Records / Photos
label | b57db6c7-4921-5a3d-83a0-d0fcf3699d56 |  | note | Frequency - Each layer
label | 75f7a412-b9f0-57e2-ba78-ecc64b831fbf |  | note | Activity - V
label | bb006b6a-ec3f-5a8a-9eb6-9a05465245f2 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.07.04 - Borrow Fill Moisture Content
label | 97a39c37-4e17-56b6-b3a6-86d256ffb9c1 |  | note | Acceptance / Conformance Criteria - Prior to removal of material from a borrow area wet or dry the material to a uniform moisture content close to optimum for the material.
label | 86d55614-e01b-54da-a7c5-65cfebbb2879 |  | note | Standard / Specification - 14AED/AD4-C - 034.14.2
label | 37b1e68c-b2e8-50b1-991a-0ba00529f583 |  | note | Verifying Document - Site Records / Photos
label | d6a1a35c-2e9d-5cd7-ba25-f4e302a1a250 |  | note | Frequency - Daily
label | 20e0b31e-528e-560d-a9ba-b2d1d856f04d |  | note | Activity - C
label | 7cbc9e11-a4d9-5ceb-a13a-a26ff8bfd4cd |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.07.05 - Placement and Compaction of Dam Fill
label | ab913350-79ab-5015-815d-13399b661de0 |  | note | Acceptance / Conformance Criteria - Spread out the fill in a layer of uniform loose thickness. Loose layer thickness shall not exceed 300mm for granular earthfill.
label | e18e79ca-69ca-5cc9-a3e3-6d4e44fcbd6f |  | note | Standard / Specification - 14AED/AD4-C - 034.14.2
label | f8683c7a-8f6f-5798-bbf9-858ca051b351 |  | note | Verifying Document - Site Records / Photos
label | dc33ad33-1408-5393-8b12-6195cf81bdd8 |  | note | Frequency - Each layer
label | bd028218-6a69-538f-a27a-599b14cd6ee3 |  | note | Activity - V
label | ae19eb77-b7ea-522f-acd1-1afbe51d830c |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.07.06 - Buttress Fill Compaction
label | 5b3ee45f-36b4-5e40-bf9c-5a4aace207fd |  | note | Acceptance / Conformance Criteria - Buttress Fill shall be compacted to an average density to 97%MDD and a minimum of 95%MDD for any one test over 10 consecutive test sets. A set of tests shall comprise two or more individual tests made within an area of 0.5m². In-situ moisture/ density (NDM method with laboratory moisture content)
label | dc22b787-7807-57df-a314-3efa4b66d4a3 |  | note | Standard / Specification - 14AED/AD4-C - 034.14.4 / 030.18.1
label | 6822fe3c-2b12-5157-bed5-87a0536630e3 |  | note | Verifying Document - NDM Records
label | 0e991da7-4fec-5c6f-add3-848bc1fdebc1 |  | note | Frequency - 10 tests (5 sets) per 500mm placed
label | 65a80934-bc11-5c6a-846e-d8d06425aedb |  | note | Activity - I
label | c12c4205-280e-5f80-a686-23e63ae219bb |  | note | By - SE
label | 56891694-1c26-5cf3-b17c-74924cd5eebb |  | note | Comments / Closeout Details - RFI With Kerry B.
checkpoint-status |  |  | checkpoint | 5.07.07 - Buttress Fill Proof Rolling
label | e984571b-2e0f-5971-9c60-5b6e88fb3051 |  | note | Acceptance / Conformance Criteria - The deflection of the compacted fill surface for any lift during a proof roll with a 10t smooth drum roller shall be less than 7mm.
label | 8690bed0-2cb4-5b60-a3ae-a0073eda6e19 |  | note | Standard / Specification - 14AED/AD4-C - 034.14.4 / 030.18.1
label | 8ef62e97-1ddc-5bba-9243-c90cf5c5cd21 |  | note | Verifying Document - Proof Roll
label | 07595c2a-a86f-5e48-8ddc-f1939b5f1864 |  | note | Frequency - Each layer
label | 1d5ad4b4-176a-5287-8749-32936572ea00 |  | note | Activity - I
label | 75807b09-fb09-5f01-9a73-9c2922f44392 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.07.08 - Steep Slope Key
label | e6e7ab9e-3f83-5a0c-8bc5-76b2b71ddf72 |  | note | Acceptance / Conformance Criteria - Where dam fill abuts sloping ground steeper than 18º (1V:3H), the natural ground or fill being filled against shall be keyed in. The horizontal width of the key shall be equal to the thickness of the compacted layer.
label | a4ce453d-dcea-526d-8c4a-9e56a51b5c27 |  | note | Standard / Specification - 14AED/AD4-C - 034.14.2
label | 8be2718f-ef59-5a8f-9294-ab5ceab9c5d7 |  | note | Verifying Document - Site Records / Photos
label | 3234e5c6-01d3-5904-b025-86c0a8e7d930 |  | note | Frequency - Each Occurrence
label | c4d1431d-a736-5880-a133-2af32483e64f |  | note | Activity - C
label | 04221e0b-2216-5bc3-a6bc-d7c0cc7d4bb0 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.07.09 - Overfilling dam embankments
label | 6013f93a-361f-53a8-af45-ade197347b98 |  | note | Acceptance / Conformance Criteria - During construction, the batters shall be overfilled by a minimum of 1m (horizontal), and this overfill should be pulled up by digger, and used as the final lift(s) of fill on the dam crest.
label | 0263a85d-fdeb-5ae1-80fb-094643fa2c14 |  | note | Standard / Specification - 14AED/AD4-C - 034.14.2
label | 1510412c-0dbf-5c01-bac0-d74b6263bbff |  | note | Verifying Document - Site Records / Photos
label | e819f8a5-4cab-5cb9-b0c7-93f4d854ba0e |  | note | Frequency - Final Embankment Layer
label | dd7ffd04-fc99-5ad7-bbc4-a47f54cb01ae |  | note | Activity - C
label | bfa8794e-60b2-5a30-9269-77839b0f3d90 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.07.10 - Dam Fill Tolerances and Profiles
label | d15f2135-be49-53ae-a7e0-3503698794c3 |  | note | Acceptance / Conformance Criteria - The finished tolerances for the dam crest level is -0/+200mm. For upstream and downstream batters finished tolerances are –100/+200mm (vertical height), and the surface shall be visually regular.
label | 5058168d-0340-592e-af86-46a21becc09e |  | note | Standard / Specification - 14AED/AD4-C - 030.14.8
label | c7e845c2-28f1-53ff-863e-f56b29d7c60f |  | note | Verifying Document - Survey Records
label | cf55bb15-dd95-5ff2-a5ee-5830555826dd |  | note | Frequency - Finished Fill
label | bd61904d-6bab-50e7-bb58-d01272a360f8 |  | note | Activity - D
label | 84046aa1-a76d-5935-a0eb-c62b84ca14d8 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 5.07.11 - Completed buttressing works Inspection
label | 1cbd3705-0e7a-511a-b9ee-164f2459a494 |  | note | Acceptance / Conformance Criteria - Completion of buttressing works to final level must be inspected by the Engineer prior to further work being carried out in the area.
label | 621e1874-1659-54f0-9c32-f6069a4d20db |  | note | Standard / Specification - 14AED/AD4-C - 030.3
label | ae8d760f-fc39-5f6a-828f-bc171406d821 |  | note | Verifying Document - Hold Point Release
label | 28ea9a58-260d-54dd-b2c9-441a7da60a8b |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | ff864455-0759-5605-9131-adf97a8a9d7e |  | note | Activity - HP
label | 4190d018-18c8-5575-9404-23bd3fcfe7cf |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT