## zres_siteapp
SECTION 5 – CONSTRUCTION ACTIVITY – BULK EARTHWORKS AND DRAINAGE
5.04 | Placement and Compaction of Fill General
5.04.02 | Surface Water Control | Cut and fill areas shall be sloped and graded adequately so that they do not pond stormwater, and drains shall be installed as necessary on a regular basis to deflect run off from the areas of operation, or to drain ponded water as soon as ponds are seen to develop. | 14AED/AD4-C - 034.14.1 | Site Records / Photos | Daily | R | SE
5.04.03 | Wet Weather | No fill shall be placed during periods of wet weather. | 14AED/AD4-C - 034.14.1 | Site Records / Photos | Daily | M | SE
5.04.04 | Extended Wet Weather Resumption Approval | In the event of fill operations ceasing in any area on account of wet weather or for more than one week for any reason, the nominated Contractor shall obtain the Engineer’s approval of the conditions of the fill surface before recommencing fill operations. | 14AED/AD4-C - 034.14.1 | Hold Point Release | Each Occurrence | HP | ENG
5.04.05 | Compaction Adjacent to Retaining Structures | Rollers shall not be operated within 2m of retaining walls with placement of fill in 200mm maximum thickness lifts and compaction shall be via hand equipment or a small roller without vibration. | 14AED/AD4-C - 034.14.3 | Site Records / Photos | Each Structure | V | SE
5.07 | Buttress Fill Placement and Compaction
5.07.01 | Start of the buttress filling Inspection | Start of the buttress filling operation must be inspected by the Engineer prior to further work being carried out in the area. | 14AED/AD4-C - 030.3 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG
5.07.02 | Compaction Effort | Compaction of granular earthfill shall be carried out using a 10-tonne (minimum static weight), smooth steel drum vibrating roller, or approved equivalent and shall be demonstrated and conformance confirmed via a compaction trial. | 14AED/AD4-C - 034.14.2 | Site Records / Compaction Trial | Prior to Works | V | PE
5.07.03 | Buttress Fill | Each fill layer for dam fill shall be given the higher of the trail result or four passes with vibration, even if the acceptance standard is met with fewer passes. No pumping of weaving of granular fill is permitted. | 14AED/AD4 -C - 034.14.4 / 034.14.1 | Site Records / Photos | Each layer | V | SE
5.07.04 | Borrow Fill Moisture Content | Prior to removal of material from a borrow area wet or dry the material to a uniform moisture content close to optimum for the material. | 14AED/AD4-C - 034.14.2 | Site Records / Photos | Daily | C | SE
5.07.05 | Placement and Compaction of Dam Fill | Spread out the fill in a layer of uniform loose thickness. Loose layer thickness shall not exceed 300mm for granular earthfill. | 14AED/AD4-C - 034.14.2 | Site Records / Photos | Each layer | V | SE
5.07.06 | Buttress Fill Compaction | Buttress Fill shall be compacted to an average density to 97%MDD and a minimum of 95%MDD for any one test over 10 consecutive test sets. A set of tests shall comprise two or more individual tests made within an area of 0.5m². In-situ moisture/ density (NDM method with laboratory moisture content) | 14AED/AD4-C - 034.14.4 / 030.18.1 | NDM Records | 10 tests (5 sets) per 500mm placed | I | SE
5.07.07 | Buttress Fill Proof Rolling | The deflection of the compacted fill surface for any lift during a proof roll with a 10t smooth drum roller shall be less than 7mm. | 14AED/AD4-C - 034.14.4 / 030.18.1 | Proof Roll | Each layer | I | SE
5.07.08 | Steep Slope Key | Where dam fill abuts sloping ground steeper than 18º (1V:3H), the natural ground or fill being filled against shall be keyed in. The horizontal width of the key shall be equal to the thickness of the compacted layer. | 14AED/AD4-C - 034.14.2 | Site Records / Photos | Each Occurrence | C | SE
5.07.09 | Overfilling dam embankments | During construction, the batters shall be overfilled by a minimum of 1m (horizontal), and this overfill should be pulled up by digger, and used as the final lift(s) of fill on the dam crest. | 14AED/AD4-C - 034.14.2 | Site Records / Photos | Final Embankment Layer | C | SE
5.07.10 | Dam Fill Tolerances and Profiles | The finished tolerances for the dam crest level is -0/+200mm. For upstream and downstream batters finished tolerances are –100/+200mm (vertical height), and the surface shall be visually regular. | 14AED/AD4-C - 030.14.8 | Survey Records | Finished Fill | D | SV
5.07.11 | Completed buttressing works Inspection | Completion of buttressing works to final level must be inspected by the Engineer prior to further work being carried out in the area. | 14AED/AD4-C - 030.3 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG