## ITP - Pavement
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # CTN-ITP-021
[11 empty] | Revision : 00 | Date : | 2024-02-14
Client: |  | Department of State Growth |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Midland Highway Campbell Town North |  | Ride Quality Testing |  | Name: | Liam Dale | Name: | David Shaw-Johnston |  | Name:
Contract No: |  | 3170 |  | Specifications: Specifications Section 180 (Contract Specific Clauses)
|  |  |  | Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: North of Campbell Town (Campbell Town to Epping Forest) |  | Date : | 2024-02-14 | Date : | 2023-02-14 |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Independent QA Verifier | Date
1 | Preliminary Works
1.1 | Plant and Equipment |  | Prior to commencing works | Plant and equipment used in the Works are appropriate to achieve specification requirements | N/A | Visual Inspection | This ITP signed | IP | Site Engineer | N/A |  | N/A
2 | Testing and Conformance
2.1 | Measurement of Ride Quality |  | Each lot | The Contractor shall comply with the requirements for both the Maximum Individual Lane Roughness and Maximum Mean Lane Roughness as follows: (a) Individual Lane Roughness Where an Individual Lane Roughness Value in any 100 m sub-section is greater than the specified Maximum Individual Lane Roughness Value specified in Table 180.092, the Contractor shall rectify work within the sub-section to comply with this requirement. The minimum length of rectification work undertaken shall be 100 m. All rectified 100 m sub-sections shall be re-tested following completion of rectification work. (b) Mean Lane Roughness Where the Mean Lane Roughness Value of a lot is greater than the Mean Lane Roughness specified in Table 180.092, the work shall be rectified unless the Superintendent agrees to accept the work at a reduced payment. Where the lot is to be rectified, the minimum length for any rectification work undertaken shall be 100 m. Where the Superintendent agrees to accept the lot at a reduced payment, a deduction to the contract sum shall be made in accordance with Clause 180.06. The Contractor shall re-test the lot following completion of any rectification work. | 180.05, Table 180.092 | Measure | Test Report | TP | Site Engineer | N/A |  | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Fulton Hogan | Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent