## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | CTN-ITP-001 - Clearing and Grubbing | itp |  |  |  | Yes | CTN-ITP-001 - Clearing and Grubbing | 0626d9af-9445-4529-a53b-9cf4eeaa1a76
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 28dae962-4000-580e-91ff-d56c491600d0 |  | note | Frequency - Prior to commencing any activity
label | e3ab3435-4c30-5c2a-ba3f-631e0c019b98 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | 16f17860-262b-5aa0-b51c-28b3d4657453 |  | note | using the correct and complete set of drawings & all drawings are the latest revision
label | 44e609a1-5714-5a9c-9876-0bfe9b471c10 |  | note | Signed onto work pack
label | 0273636f-aff1-54e5-a6f7-b627a98314af |  | note | Reference Documents - Drawings and drawing registers
label | 118fd15b-7727-563b-9679-99425ef84efb |  | note | Inspection / Test Method - Visual inspection
label | ca7d67bc-4edc-5754-9376-abf0bc49ff77 |  | note | Record of conformity - This ITP signed
label | 52b35895-3ce7-59e3-819b-a39285014205 |  | note | HP*
label | 4d43133e-cab8-5538-b97d-602c438e000d |  | note | Responsibility - Site Engineer
text | 51fc8b86-890d-52b5-8de8-055e3aaf8b3e |  | textbox | ITP Opened:
date | 19d1b2fd-5783-5ce1-b5aa-a440efe19751 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | aaad398d-9e7a-5671-a398-5818c95adb84 |  | note | Frequency - Prior to commencing any activity
label | 2ef75401-224d-5b34-b4d8-86f21717de90 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, including: PSP, EMP, TMP, SWMS & WP
label | 372182b0-6882-5f41-93ad-6e1e1df17458 |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | ff6c8d31-d0ce-5bae-8222-25eadfa05b52 |  | note | Inspection / Test Method - Visual Inspection
label | a0faf226-e222-50e8-9671-d4304212c675 |  | note | Record of conformity - This ITP signed
label | c97487e3-4b82-5b6b-bfa3-de5177356a46 |  | note | HP*
label | 90fba238-4f30-5652-8adc-b639645e3a54 |  | note | Responsibility - Site Engineer
date | 830aac58-3e51-53da-8bdf-5145a4a35fdf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Implementation of environmental measures and controls
label | 75fee04f-e661-5d63-988c-a7df526c7011 |  | note | Frequency - Prior to commencing any activity
label | 23a13192-482b-5322-8fac-a8b3906f1838 |  | note | Acceptance Criteria - EMP meets the requirements of the specification and all controls have been implemented as per approved EMP
label | 5c637abc-26ce-5ba1-b273-542e916c2fd0 |  | note | Reference Documents - Project Spec, Cl176.A3, EMP
label | cc6f5b1d-cd76-51b1-847e-ccdebe2e9b9b |  | note | Inspection / Test Method - Verify
label | 39e637d0-d477-5bc6-866d-0927baae1ae2 |  | note | Record of conformity - This ITP signed
label | 20b18c0d-5be1-50a3-baa8-cbf1e410d351 |  | note | IP
label | 6a5014e0-9683-5642-b4c1-1ed868539abe |  | note | Responsibility - Site Engineer
date | 888286b9-42d5-538a-b708-5be7eeadd1a6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Flora and Fauna
label | a73fae59-42be-56e4-8d77-97ce3f85e7c8 |  | note | Frequency - Prior to removing vegetation
label | 72573289-12c6-5ffe-bbd7-cac1a19b4522 |  | note | Acceptance Criteria - Hold Point Vegetation to be removed clearly marked and agreed. All removal consistent with contract drawings and permits.
label | 3ba9e640-aae7-5838-bce0-da6c02fe4bb0 |  | note | Shall fence and sign all sites nominated as No-Go Zones.
label | 204eeba6-db47-53d2-a4fe-d648285ed821 |  | note | Reference Documents - Cl176.I1
label | 7f2b0b6c-f108-5c67-9274-a134eb02ec0a |  | note | Inspection / Test Method - Verify
label | e2e0d915-713f-5136-985c-321a992dad07 |  | note | Record of conformity - This ITP signed
label | c2992ad4-d288-510d-b3df-0c03c8a65bc6 |  | note | HP
label | ffaf45c2-4785-5774-8847-0d693505d989 |  | note | Responsibility - Site Engineer / QAV
date | 11b4a912-c6bd-510a-a205-dbc8812fcd89 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Protection of Existing Vegetation
label | faf2a13b-1ed7-57d6-a4ec-9b51118dd41a |  | note | Frequency - Prior to commencement of any work
label | 8589e155-812a-54e9-bcdb-9cc6f7497dd2 |  | note | Acceptance Criteria - Prior to the commencement of any work, the Contractor and the Superintendent shall conduct a joint inspection of the site to identify vegetation to be retained and protected.
label | 4f61aa5e-50c9-5c5f-bed8-12f04b45a569 |  | note | If directed by the Superintendent, existing trees, shrubs, native grasses and groundcovers and other areas of existing vegetation shall be protected by temporary fencing and incorporated into the works by the Contractor.
label | ea18b94f-32a6-5695-a4be-c6604ac107e1 |  | note | Protective fencing shall consist of, as a minimum, star pickets with three strands of wire and parawebbing.
label | b17116ab-28e4-52a8-8fa9-f4abdfb80697 |  | note | Reference Documents - EMP Cl201.1
label | 29d95d12-1040-516d-817c-144a41ae37c4 |  | note | Inspection / Test Method - Visual inspection
label | 03f0b062-5bd9-5b8d-b58d-99b0c17095ed |  | note | Record of conformity - This ITP signed
label | bdd99ddb-3bd0-506a-b71b-6ac6e42073c4 |  | note | IP
label | 841c5ef8-680a-5770-ad7d-07597c14728d |  | note | Responsibility - Site Engineer / Superintendent
date | 6db0f61f-4f77-5556-b63b-b6f454b301cb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 - Flora and Fauna
label | 94ec269c-2e1b-50cb-b52d-abff467de587 |  | note | Frequency - Prior to removal of vegetation
label | 0cb819fb-fd6f-5a7e-8678-da9d35f58f0f |  | note | Acceptance Criteria - Hold Point Nominated sites of archaeological and / or heritage significance inspected on-site and clearly identified and protected as No-Go zones
label | 238f1cfa-793d-514a-9c0a-38dfd53771be |  | note | Reference Documents - EMP Cl176.J1
label | 765cfc9e-1be9-5381-92fb-4418c45737f6 |  | note | Inspection / Test Method - Verify
label | cd62053e-890a-53ed-965d-3c66a67c7e5a |  | note | Record of conformity - This ITP signed
label | c6d7f262-abec-578a-8c46-16e1896c4c1a |  | note | HP
label | 92b3afce-fe43-5143-ad71-c5afb68ed0f6 |  | note | Responsibility - Site Engineer / QAV
date | 2fc86271-8236-5336-9032-4ef354f601e2 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Authorisation for works
label | c3f09d7b-66f7-5ec8-b82d-cd3e3300cc32 |  | note | Frequency - Prior to commencing works
label | cee753ca-1498-5976-8f2d-c192ad279aaa |  | note | Acceptance Criteria - Check that all relevant approvals have been granted including verification of the works area. Ensure work pack is reviewed & signed
label | 7b05889e-a313-5a40-90cf-9ec775b7f6c7 |  | note | Reference Documents - Work Procedure
label | cb7e464b-c47a-5172-b4a9-64aea7365277 |  | note | Inspection / Test Method - Verify
label | f221bf83-b1aa-56e0-bd87-752925539127 |  | note | Record of conformity - This ITP signed
label | 644a2f91-237a-5be0-ba84-c2441f0e2cdd |  | note | HP*
label | 94c10452-042a-5784-a16d-b7b5210d45af |  | note | Responsibility - Site Engineer
date | b0593449-d47d-5c52-9888-b96713f29836 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.8 - Utilities
label | 3dac7406-c226-57ae-9507-8b82de374455 |  | note | Frequency - Prior to commencing works
label | a04932ac-e22f-51c6-ac6e-9181de660d5d |  | note | Acceptance Criteria - DBYD - locate and mark all existing services and confirm clearance from proposed work
label | 5ad75428-6a45-5918-b1bc-49959578225e |  | note | Reference Documents - DBYD Records, Plan Mark-Ups
label | db2f64bd-1ca7-5c43-972a-bec6dda2c73b |  | note | Inspection / Test Method - Verify
label | e360932a-9f4a-524b-bd16-72181ced0a6b |  | note | Record of conformity - This ITP signed
label | d70dfc3f-57b2-52d4-8f06-86d99bc2604a |  | note | IP
label | ad17bef3-1790-52c3-ab66-8a846c719ec5 |  | note | Responsibility - Site Engineer
date | dcd40976-1ecb-5696-bbe4-08083ebbe517 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.9 - Traffic Management
label | ecd55b75-68d8-5f91-8a80-d788422ed112 |  | note | Frequency - Prior to commencing works
label | 3c5e8d5d-6efa-570b-8815-20d250ccfd2c |  | note | Acceptance Criteria - Consider the requirements for traffic management, ensuring all works comply with required TMS, TMP and TGS.
label | 703d4653-8aa2-51c4-a4e8-175618be895b |  | note | Reference Documents - TMS
label | 7b8b3f51-549d-5753-99a4-9b151ca09dc4 |  | note | Inspection / Test Method - Verify
label | 2b6bd667-7014-5e39-8add-427711433b1f |  | note | Record of conformity - This ITP signed
label | 6f9fcc90-33bf-53e4-8174-eedfa90b55f4 |  | note | IP
label | 093bb9bc-6beb-5bbf-994f-bd148ad16fc2 |  | note | Responsibility - Site Engineer
date | 2b44b77e-5e5b-56af-91dc-d87f8a33dff8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Limits of work
label | d225fff7-5a55-5592-b6cc-9e04ec0b2a5d |  | note | Frequency - Each Lot
label | 7c1738c9-a27c-5b22-9230-030fcfba99fe |  | note | Acceptance Criteria - Limits of clearing and grubbing shall be the whole length between the following chainages:
label | b3ed0d34-1530-52ea-8f30-f61c70aba69b |  | note | - Separable Portion A: Link 74, Ch 0.00 (Chainage 125000m) to Link 74, Ch 11.45 (Chainage 136450m)
label | 855638be-3c21-5ba3-ac3a-bd5726823d35 |  | note | -Separable Portion B: Link 68, Ch 2.75 (Chainage 115700m) to Link 68, Ch 12.05 (Chainage 125000m)
label | 95bef6be-5be5-5e95-9d1e-d99b9bd9f7ce |  | note | Reference Documents - Cl201.03
label | bd3e9fc7-78b8-5d42-9594-05eb6fd18a2d |  | note | Inspection / Test Method - Visual Inspection
label | 280864cd-5d34-5ed8-abbf-33ca0bad941a |  | note | Record of conformity - Gradco ITP
label | abe96adc-94ba-5692-8cfc-9e1fa2427607 |  | note | IP
label | 0352f26c-176d-5fb6-92cc-c107b4c4d5cd |  | note | Responsibility - Site Engineer
date | 2b3c4c4b-d642-5714-b01e-774645e1aac7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Clear and grub trees and vegetation
label | 19a1e3ab-48e1-5b73-bca3-834d213b882a |  | note | Frequency - Each Lot
label | d9c4e5c9-0175-567e-8252-2d7b4498d4d1 |  | note | Acceptance Criteria - Area within specified limits cleared of all vegetation, refuse and obstructions down to natural surface.
label | bdcb315d-dfdd-5d2a-8f95-870e51c53e83 |  | note | Trees brought down in a manner so as to avoid danger to personnel and traffic as well as damage to other trees, structures and property.
label | 417c72fa-60ad-5d80-8413-1051b66c7673 |  | note | Reference Documents - Cl201.04
label | 67507a0a-eea8-5691-afce-293ca2a5666b |  | note | Inspection / Test Method - Visual Inspection
label | 9fd6cab8-2a22-50e3-b1d6-c0b9e4d817c3 |  | note | Record of conformity - Gradco ITP
label | b4da5d81-7815-5682-8c63-919b83d7164e |  | note | IP
label | c0f5f5c2-2dbf-5a3d-a50a-6957a162ef5c |  | note | Responsibility - Site Engineer
date | 83d240df-3415-518b-b8a8-2da4c140ac0a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Clear and grub trees and vegetation
label | 43b612c4-e116-56f9-a608-875ff6f7a2fb |  | note | Frequency - Each Lot
label | 80648f86-da8c-5193-aceb-5d81c8ae68cb |  | note | Acceptance Criteria - In areas where excavation is to occur: all vegetation, refuse and obstructions totally grubbed or grubbed > 0.3m
label | 5d534ad9-a8e3-5767-b1ad-ac63301fab03 |  | note | below subgrade and batters (whichever is the lesser treatment)
label | df5cb22f-c09d-5096-935d-0e956fbb3c94 |  | note | Reference Documents - Cl201.05
label | a2be070a-5da9-5133-a1b0-7570c707fe5f |  | note | Inspection / Test Method - Visual inspection
label | 29bab6f9-892e-5f5a-b880-30a3e39ab970 |  | note | Record of conformity - Gradco ITP
label | fc6e33f4-1264-5b55-82cf-c225fbe2ee79 |  | note | IP
label | 145b1981-c773-5972-b0b8-16d12ef17645 |  | note | Responsibility - Site Engineer
date | d90bcfa1-1772-53bb-a90d-cb144a151594 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Clear and grub trees and vegetation (embankment areas)
label | d651d949-beb8-5c4d-a255-ab78a08a2506 |  | note | Frequency - Each Lot
label | cc687fb9-361e-530c-a9cf-0df28aeb8963 |  | note | Acceptance Criteria - In areas to be covered by embankments < 1.0m in height: all vegetation,
label | c26f1763-a452-5055-8dd9-11adcf569f3d |  | note | refuse and obstructions grubbed > 0.3m below stripped surface OR > 0.6m below subgrade level (whichever is the lesser treatment)
label | 448b5663-7448-53b7-9a0c-a15f02727a86 |  | note | In areas to be covered by embankments > 1.0m in height: foundations may remain if located or cut off not more than 0.4m above natural surface but not less than 1.0m below subgrade
label | 1c278122-737d-58d9-ade4-c0e5ba6e3b8f |  | note | Reference Documents - Cl201.05
label | bb64e0c4-2d50-5cfd-8c16-08b6c4728402 |  | note | Inspection / Test Method - Visual inspection
label | 9851df8f-a953-51d1-b2d2-fe7bc1d9eb57 |  | note | Record of conformity - Gradco ITP
label | 49026e87-4978-5e2b-96d6-6f024da974b1 |  | note | IP
label | c098af4a-4e76-5c7e-8d20-2159b96df2b5 |  | note | Responsibility - Site Engineer
date | 21a9e253-c94b-549c-b610-e025ba36c7cc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Clear and grub trees and vegetation at culvert sites
label | aed1b156-10f9-5bdb-a3d7-2fe3161b95d9 |  | note | Frequency - Each Lot
label | 1f0be27d-02ba-5573-afd9-ad28b1d7df40 |  | note | Acceptance Criteria - Clear and grub trees and stumps within 10m of any proposed bridge or culvert having a waterway area > 6m2 (unless otherwise shown on drawings)
label | 39158d26-4106-5ad9-8808-c1e5577d4083 |  | note | Reference Documents - Cl201.06
label | c6fe4bcf-6df0-5f68-a7d5-f888146cad67 |  | note | Inspection / Test Method - Visual inspection
label | ce8807ed-b577-5250-9450-0790623a2930 |  | note | Record of conformity - Gradco ITP
label | 8cd5818e-8c06-55a6-b6e4-f739ce706aff |  | note | IP
label | e0ea3c37-3449-5717-8855-179961443c4d |  | note | Responsibility - Site Engineer
date | 59bd7deb-b537-597b-8a69-648e1a03298c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Backfill holes
label | 304a7470-7204-5145-8502-9a824fd6be67 |  | note | Frequency - After clearing
label | 6ca93847-de52-5950-8c14-efcfe9efe742 |  | note | Acceptance Criteria - Any holes produced from grubbing operations have been backfilled with similar material and compacted to the same degree as the surrounding material
label | a35ba8c8-ab55-54f7-a5f3-8f69eba98c4f |  | note | Reference Documents - Cl201.05
label | af1b6492-1059-5a02-a8f0-cbd05f3dcf08 |  | note | Inspection / Test Method - Verify
label | a09b9bc3-8505-5129-a70f-e6360cacca69 |  | note | Record of conformity - Gradco ITP
label | eced1828-5ed2-5526-8af4-bf1113ddc9eb |  | note | TP
label | 2d1678d7-f4bf-53d1-abcb-7d4e91faf0e0 |  | note | Responsibility - Site Engineer
date | eb383229-b27e-5628-9335-506063c37163 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Dispose of Trees and vegetation
label | 3bf6ea41-7521-5bdc-8603-7c7865ff1831 |  | note | Frequency - After clearing
label | 68b7dce8-6fbc-589a-b293-91ad1115089c |  | note | Acceptance Criteria - Tree trunks and large branches shall be removed from site. Small tree branches, weeds and shrubs shall be disposed of by chipping and mulching.
label | 46a18c44-2e35-58b0-8fc9-9a76f62936a2 |  | note | Reference Documents - Cl201.07 (b)
label | e2fc888f-e748-51cf-b251-089c57798b34 |  | note | Inspection / Test Method - Visual inspection
label | 823f5bf4-3bdf-5176-ae89-2b63cc4bc465 |  | note | Record of conformity - Gradco ITP
label | a256561e-acdb-5950-ae56-62fc56951baa |  | note | IP
label | 0b076b37-743e-5231-8c66-d1a427ee95e5 |  | note | Responsibility - Site Engineer
date | 5e224e3b-5bea-5443-a9e9-8d1f82368285 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Damage to Fencing
label | 31b6ef96-927d-52bd-b4dc-86f3d4a39358 |  | note | Frequency - During Clearing
label | d8c94974-2554-5092-9ae6-e86ac4542de8 |  | note | Acceptance Criteria - Immediately repair any damage to fences to a condition at least equal to that before damage
label | 484899b9-250f-54ed-ad43-43579b13b39b |  | note | Reference Documents - Cl201.09
label | 0a819a7c-cb15-5852-a03a-ce20b53f399d |  | note | Inspection / Test Method - Verify
label | e0e201f4-010e-583f-97f3-baae031a6208 |  | note | Record of conformity - Gradco ITP
label | 21a587d6-85f3-5ce5-bd20-2caeaff6d19d |  | note | IP
label | 92cc52a4-5da4-5f4a-a4d1-580b6915b3e6 |  | note | Responsibility - Site Engineer
date | cb2e5244-657b-51f0-ae5a-8c9a0cd097c7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Gradco ITP sign off
label | 88f09626-c2ed-582e-86fa-f12c57cfacd8 |  | note | Frequency - Upon completion of each lot
label | 8a284380-8228-59dc-9bfd-3b29244143b3 |  | note | Acceptance Criteria - Check Gradco ITP is complete and fully signed off
label | 6ca39bf1-f51b-5bf3-9b9e-9ddcd342514a |  | note | Reference Documents - N/A
label | 92f218f9-1fc4-5c81-bd0c-7b539e4e44b8 |  | note | Inspection / Test Method - Document Review
label | 50319c9c-63d0-595c-9047-84d3a0d67184 |  | note | Record of conformity - Gradco ITP, This ITP signed
label | 69815d76-1633-5698-bb35-505d292ae10d |  | note | IP
label | 75f96a0d-9d39-570c-b4fb-e1ee9961d283 |  | note | Responsibility - Site Engineer
date | e93a3223-aaca-556e-a24a-1346e195f2fd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection - Gradco
label | 51e21452-d6a0-5be1-8523-fce482cb8a0b |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | f9956b75-ea29-5eb4-a5ef-03a5a3c51dc9 |  | textbox | Print Name:
text | 1214c24c-43ec-5d7e-9bf8-f3344abc6600 |  | textbox | Position:
date | 77839d30-4ef8-533a-b6e4-e207cca85c95 |  | date | Work Completed On:
date | 6382cc59-a25d-5a0d-9c80-ad279caf807e |  | date | Date:
checkpoint-status |  |  | checkpoint | Final Inspection - Fulton Hogan
label | 5ecaeec7-c691-5a13-8be3-0c0e7a65ab52 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 7235306f-3c57-54d1-998e-2552dc5c7860 |  | textbox | Print Name:
text | eb5013f7-0146-5192-b557-52e43ed40439 |  | textbox | Position:
date | 90fe2648-5d25-5e43-ac85-354b29bf667d |  | date | Work Completed On:
date | 70a484dd-e596-5011-8e89-86fdef2b4556 |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-010 - Installation of Guardrails | itp |  |  |  | Yes | CTN-ITP-010 - Installation of Guardrails | 06be1540-31fb-442e-b471-f63b4be62728
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | ba6bdbaa-c3af-58b3-8f4a-8a663c5b649b |  | note | Frequency - Prior to commencing any activity
label | cc44eb30-7b9c-5119-89f4-b603219a312e |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are: using the correct and complete set of drawings; all drawings are the latest revision
label | 1ea747a0-64be-539e-9719-618c7fc00b41 |  | note | Reference Documents - Drawings
label | abe213a1-c070-59d2-b6b0-a06d65fbc62a |  | note | Inspection / Test Method - Verify
label | ef6be5f0-bbcf-5978-99c3-8696211f0673 |  | note | Record of conformity - This ITP signed
label | 6b8110b6-e49a-5a94-ac63-c1cf76d2018d |  | note | HP*
label | af152b55-82c3-5d1e-9053-e6c01b5dee40 |  | note | Responsibility - Site Engineer
text | fb9b4f8b-4c51-5dc8-bf38-998ad92a6539 |  | textbox | ITP Opened:
date | 7ae94e09-7a1e-5703-8cc9-2613bee073f7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | b7cb7a3e-a390-5ae2-9cdf-3b504e4f2b36 |  | note | Frequency - Prior to commencing any activity
label | 84f8bb87-a0ec-5a83-98c0-86fec316ff49 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 3e07b4bc-63fc-5ea8-86cd-4274e2c97903 |  | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | c510907a-48ec-5305-8e07-6803ab8d2faa |  | note | Inspection / Test Method - Visual Inspection
label | 83e2f317-153c-5ae0-b6e3-acb2ad7da797 |  | note | Record of conformity - This ITP signed
label | db743b8b-a6e0-551d-aee2-bbe97ab2eba9 |  | note | HP*
label | 31dba02d-9161-5cea-9ad2-61ae05f7eeaf |  | note | Responsibility - Site Engineer
date | 80e1b924-ca08-560f-a48d-9815e2db7fe2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Approved Steel supply
label | b6046cda-6c51-563d-a0a1-b8e3f0a9149c |  | note | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
label | c9f5f02b-dc4e-5a3a-bcb8-bd65b09b53e0 |  | note | Acceptance Criteria - W-beams and terminal sections shall comply with AS/NZS1594 Grade HA350. Steel posts and blocks shall comply with AS/NZS1594 Grade HA250. Treated in accordance with AS1627- Parts 1 & 4. All test certificates related to the supply of steel for the works shall be submitted at least 14 days prior commencement of installation.
label | b0bb80b9-9743-5f24-905d-ee7f7110d2e8 |  | note | Reference Documents - Cl.708.04(b) AS/NZS 1594, AS1627, AS 4680
label | d81b2b07-c122-5e8d-ae03-911919c86ade |  | note | Inspection / Test Method - Document review
label | e0552eee-fff2-59e2-9261-92ee07609479 |  | note | Record of conformity - Supplier's NATA (or otherwise approved). Material Test Certificates
label | 88d8417a-4a61-5697-a2da-6b66f98c9307 |  | note | HP
label | 84cd1323-9dd9-518a-ba02-37dfe58c203d |  | note | Responsibility - Project Engineer/ QAV
date | 926dc06d-d143-53f1-b2e1-42f01e116f37 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4 - Approved galvanisation records
label | d2de0d0d-4557-5f45-9240-f06db5887f21 |  | note | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
label | f942dfaa-d329-5344-bfc6-148ff9793c4a |  | note | Acceptance Criteria - Surface preparation in accordance with AS1627 parts 1 & 4. Zinc coating mass of galvanised components to be in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform
label | 764db902-4564-5d62-b655-758076b5cf64 |  | note | Reference Documents - Cl.708.04(b &d)
label | f0fb52c2-0545-5817-b902-ea6797747452 |  | note | Inspection / Test Method - Document review
label | b8fa4283-e7b8-5e7e-9aba-9d4ec3f461c1 |  | note | Record of conformity - Supplier's NATA (or otherwise approved) Manufacturer's certificate of compliance. Test Certificates
label | e5cf1d18-94ad-585c-8148-1bd586af0f7d |  | note | HP
label | 549a8635-bc8f-5f3b-b83d-cc17b8489f4f |  | note | Responsibility - Project Engineer/ QAV
date | cb59a519-0191-50fd-b7be-6f79c0e15dc5 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.5 - Identification of guard fence components
label | 5fb59457-64d3-587b-84b4-6204a5b6418a |  | note | Frequency - Prior to Commencing
label | e86e3d92-7c68-5419-8e8e-02e993055bc6 |  | note | Acceptance Criteria - w-beam sections, both ends of posts and all plastic end treatments to be permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams
label | ca1027ab-ed1f-520d-88a8-af5884881991 |  | note | Reference Documents - Cl.708.04 (a)
label | 8f1cccf4-7f11-5d38-bb7b-36337925507c |  | note | Inspection / Test Method - Visual Inspection
label | 0f743175-99b9-525f-aa54-1a046103f4df |  | note | Record of conformity - Receival Inspection Checklist
label | 75edfeff-20ed-5a64-bfac-9a2f63beab7f |  | note | IP
label | 212aa807-e124-58c0-95bc-ada7ebf04b67 |  | note | Responsibility - Site Engineer
date | d9ff44d7-ea44-53e4-a6f4-af4648930867 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 - Concrete mix design
label | 8e9b7ea0-84de-5791-b21d-d022e4519316 |  | note | Frequency - Prior to Commencing
label | e5d3d76f-d0dd-5bc2-add8-731153091a85 |  | note | Acceptance Criteria - Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either:
label | 8d4a5949-f49b-5dab-be5e-9e1a420e4439 |  | note | (i) Portland cement-based concrete, N20 strength grade, or
label | d4ee1d19-0492-53f6-b8f3-6361676c3f43 |  | note | (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
label | 13467229-410e-574d-835c-7d367024c06b |  | note | Reference Documents - Cl.703, Cl.708.04, AS1379
label | 26e08f6a-66f0-5f11-b197-5d17ea1e5b50 |  | note | Inspection / Test Method - Document Review
label | 1b84c961-8cf2-5b7e-b547-b0fc7ee64a2b |  | note | Record of conformity - This ITP signed
label | d3a6ea00-0683-5c9f-a0f6-0eed645e9de9 |  | note | IP
label | ae9a8c5b-02c1-5b32-8236-999c8f959fcf |  | note | Responsibility - Site Engineer
date | 1a5b8a10-4d8d-55ba-bb83-139387f5bc3c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Survey set-out
label | 92da7150-1402-5e38-bdd6-f2cfcef84e39 |  | note | Frequency - Prior to Commencing Excavation
label | 6f75e12e-845c-525b-83ca-0a47a8836801 |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
label | 19bf7e41-342c-5128-a4b5-c99eeac7612d |  | note | Reference Documents - Latest IFC Drawings
label | 7f249bee-ac46-5fff-ad63-1b6416e8dc7e |  | note | Inspection / Test Method - Verify
label | 7c3a6190-a594-5f4e-aa05-445859d7c97a |  | note | Record of conformity - Survey records & pegs on the ground
label | e2ac56b8-dd0f-56ee-9f0b-53822f0b31f2 |  | note | SCP
label | 7a3c3dff-6984-58b4-b61e-2bf012a2d394 |  | note | Responsibility - Site Engineer
date | c9eb377e-633e-5169-8a6c-fbcf6d423ea6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Service Location
label | 2e5adc5f-33fa-58b4-a358-00eaa5544656 |  | note | Frequency - Prior to Commencing
label | da01fa93-ad34-5c9b-a8ca-438c6f4fb324 |  | note | Acceptance Criteria - Current DBYD documents received and works executed by qualified service locator.
label | 54f03003-877e-515c-b42e-76e537e8da15 |  | note | Reference Documents - DBYD
label | 0926510a-dd4f-50e4-a163-546f0faebb54 |  | note | Inspection / Test Method - Verify
label | 7e0ddc90-e8ad-50d5-965e-fdc9e22ba27e |  | note | Record of conformity - Ground Penetration Permit
label | b8c21a41-925a-5f99-a8a8-ba3cb5247b40 |  | note | HP*
label | fa84feb3-5a30-55f6-abfb-90ef0a4f91e6 |  | note | Responsibility - Site Engineer
date | 76d59b17-d624-5802-856e-ea7e0e514a6a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Approval of location and length
label | dfc37b61-9eb2-5fcd-8255-5008ca5619ab |  | note | Frequency - Prior to Installation
label | 999ec9d5-5a34-509c-9852-0e83d42a6a0e |  | note | Acceptance Criteria - Hold Point: Prior to installation the Contractor shall confirm with the Superintendent the required location and length of all guard fence.
label | 6eb8162d-893a-55f1-8a15-20c8cbe893bb |  | note | Reference Documents - Cl.708.07
label | 4c167c5c-d19c-54d4-9309-2694e7b3dd64 |  | note | Inspection / Test Method - Site Inspection
label | 159167e3-5866-5a41-a280-2b6f78650416 |  | note | Record of conformity - This ITP signed
label | 7b03f1d8-1524-5b8b-a403-c28f8463aae8 |  | note | HP
label | d3ea7518-ba5f-5846-83cc-6dfa848f6c9e |  | note | Responsibility - Site Engineer / QAV
date | 16add74f-a587-5093-9d54-20a018ab1181 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4 - Installation of non standard post lengths or other special measures
label | 5615119d-1cb2-5d2c-99fe-a1faf9bcc9c9 |  | note | Frequency - Prior to Installation
label | 3db19aa5-1568-5007-b583-42346549f0bd |  | note | Acceptance Criteria - Hold Point: any w-beam barrier system where non standard post lengths are required or other special measures (e.g. shallow concrete foundations) are proposed to be used, the Contractor shall provide details of the measured proposed and evidence that the effectiveness of the barrier system will be maintained, for consideration by the Superintendent. Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a Department of State Growth pre-qualified consultant.
label | 14cba97a-3a64-5fb6-979a-df04cf50d309 |  | note | Reference Documents - Cl.708.07
label | f89a1f2f-2024-5e4e-a356-10a45a093cff |  | note | Inspection / Test Method - Verify
label | 72f11782-731f-53c5-9fe5-c555af4ebd08 |  | note | Record of conformity - This ITP signed
label | 9aba4d82-3246-5a92-8217-063429da2df7 |  | note | HP
label | e4d48802-9919-51a2-a9d7-4fdfe9f4d6e2 |  | note | Responsibility - Site Engineer / QAV
date | 026106f2-0889-5f9b-908e-143387033132 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.5 - Install posts, rails and terminations
label | 2a28b53a-13d2-5bb8-ac99-cdddb84d3bee |  | note | Frequency - Each lot
label | e99c9aee-8baa-5840-8628-72328bbca57f |  | note | Acceptance Criteria - Posts and w-beams shall be installed to the depth, line and spacing shown on the drawings. Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
label | 1d6ab54e-b520-5320-bb51-c1b6f55e0bf0 |  | note | Reference Documents - IFC Drawings, Cl.708 .07(d)
label | 3d56e5ab-45fd-5887-9f00-78f9c474cca0 |  | note | Inspection / Test Method - Measure
label | e625753c-1c34-5f99-a02e-8a01ef5fd7a9 |  | note | Record of conformity - This ITP signed
label | a909f92e-9bb4-5ec2-8309-102c23a76f15 |  | note | IP
label | 8d96df6d-94ad-5cb3-bd52-ccc77b904ce8 |  | note | Responsibility - Site Engineer
date | 8379f66f-62de-5379-aaf1-db5db0e42fca |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Curing of concrete
label | ebe497cb-b7b8-5fbe-8d10-bc25e4ba7ab4 |  | note | Frequency - Each lot
label | 25b9d121-843c-5310-b56f-30a0de15bb21 |  | note | Acceptance Criteria - Curing of exposed concrete shall comence immediatly and shall continue uninterupted for not less than 7 days. Concrete shall be cured either by water curing,wet hessian,polyethlyene sheeting adequately sealed against moisture losses, curing compound or combination thereof. Curing compounds to be in accordance with AS3799.
label | 8177b669-bde4-571d-b1a0-d52a497bde0e |  | note | Reference Documents - Cl.708.17 Cl.703
label | e24159b4-43bf-5651-a4f2-6138ec033d1c |  | note | Inspection / Test Method - Visual Inspection
label | 2a696827-d6f0-53d5-a687-aab4c1025d8e |  | note | Record of conformity - This ITP signed
label | 73062cab-642c-551d-a4ae-a336392d9d38 |  | note | IP
label | c5f37c0f-27ff-5b10-acaf-ebb707fe0dae |  | note | Responsibility - Site Engineer
date | 72431a01-e127-5b49-b5d3-fa39064c50d3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Compliance Audit of Barrier System Installation
label | d14ebd6c-7f91-513b-b773-0769f0f2f365 |  | note | Frequency - Prior the issue of the Certificate of Practical Completion
label | 432128aa-5290-5490-b9fc-e6738a132aa6 |  | note | Acceptance Criteria - Hold Point: A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A CAR shall be provided for each end treatment installed. A signed copy of the manufacturers Installation Checklist / Inspection and Test Plan as per the manufacturers Product and Installation Manual shall be completed and submitted to the Superintendent..
label | a04d5410-3f3e-5529-a50f-f8b7fe91ccc1 |  | note | Reference Documents - Cl.708.09
label | 1ac84e0a-d7a7-5b22-9fda-7341a65ed261 |  | note | Inspection / Test Method - Safety Audit
label | 40c187d8-72c2-59bb-af5c-8d9e29249774 |  | note | Record of conformity - Compliance Audit Report (CAR) for each treatment installed. Completed copy of the manufacturers Installation Checklist / Inspection and Test Plan as per the manufacturers Product and Installation Manual submitted to Superintendent
label | 4e268190-d2dd-568d-98e5-4b6ade8f81fb |  | note | HP
label | 68051005-1c1f-57f9-88a9-eeef89f42a19 |  | note | Responsibility - Site Engineer / QAV
date | 9d69ea6d-bce7-5c55-aee0-eb8463111651 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.1 - Delineators
label | 8c821625-e202-578c-9704-2a53ab472b7e |  | note | Frequency - Once installation of assets completed.
label | 75a537b2-06a7-587a-9664-a7dce95d9b27 |  | note | Acceptance Criteria - Appropriately coloured delineators fastened to top of w-beam at 15m spacings, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2
label | cbca4ca1-a9ae-535d-93a8-4c31c4e73376 |  | note | Reference Documents - Cl.708.10
label | ea373f5a-a851-5d33-8a3a-33b9d7685959 |  | note | Inspection / Test Method - Visual Inspection
label | 081aab5b-cab2-5cb2-b8fd-675d3ffac862 |  | note | Record of conformity - This ITP signed
label | 278e6510-a61e-52a4-8b24-f68a8ba250d6 |  | note | IP
label | 0315285f-7e90-5173-a8af-49d2c18d8613 |  | note | Responsibility - Site Engineer
date | 81137059-62f5-5dc9-9208-0e70e9ffbf16 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Surface Reinstatement
label | 39a562d4-b29e-51a3-9154-11deb9ef205b |  | note | Frequency - Completion of works
label | 5cd06e1e-7d4b-552a-87bd-1bf7baed44a2 |  | note | Acceptance Criteria - Surface reinstatement similar to adjacent undisturbed materials, visually accepted by Superintendent's Represented
label | 5900da72-8edc-5e48-87f8-f0a1eb466732 |  | note | Reference Documents - Cl.708.22
label | f4e9f502-5f61-5258-9377-0dd42d3f1a44 |  | note | Inspection / Test Method - Visual Inspection
label | 9ca9f0ce-9256-5758-8e25-ce5e1e6235a6 |  | note | Record of conformity - This ITP signed
label | e51561ab-c110-50f1-944b-65e288bd1829 |  | note | IP
label | b5a5fa12-6133-5767-8f22-e12797a7ad16 |  | note | Responsibility - Site Engineer
date | f2c4409d-6ee0-55bb-8e56-9f9bde5ab252 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Grassing of Disturbed Areas
label | 2a192d54-3baf-501f-831d-3deb18a8bb88 |  | note | Frequency - 3 months after sowing
label | 49e393ad-5d07-5c12-aa26-749d0de8b8ec |  | note | Acceptance Criteria - Hold Point: A joint inspection of all grassed areas shall be carried out between the contractor and superintendent three months after sowing has taken place
label | 62698f0a-8e8a-5b9d-8d78-caf6199d600a |  | note | Reference Documents - Cl.708.22
label | d77fb0f5-479b-5ed2-a6c6-622e5e1c2b6a |  | note | Inspection / Test Method - Site Inspection
label | b5ade378-c635-52e6-bc25-56dedcfdb535 |  | note | Record of conformity - This ITP signed
label | 11911666-5ef8-5770-8cec-f756f6f832b2 |  | note | HP
label | ef258ef2-cf20-5641-9cae-25c30817f668 |  | note | Responsibility - Site Engineer / QAV
date | a6fc9609-953d-5d9d-858a-5e85e597b282 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.4 - Survey data captured for as-built purposes
label | 26aefe37-e4c6-5339-bcf5-ef815d89f636 |  | note | Frequency - Completion of works
label | 0480b207-134b-5e88-a132-36ed8b9feed8 |  | note | Acceptance Criteria - As-built Drawings. Tolerances as per VicRoads Specifications, Clause 708.
label | 98e4030b-1bf6-5964-bb67-490364969788 |  | note | Reference Documents - Cl.708
label | 6be671da-ee82-566c-af41-5a65740338f8 |  | note | Inspection / Test Method - Document review
label | 48b854ef-4ad0-5b2f-8091-004a48397d1c |  | note | Record of conformity - As-built survey records
label | a89cae1f-5b41-5cc4-8752-9bc1aa3d7547 |  | note | SCP
label | 8e30168b-20e7-5f5c-ace5-1016e0dd8f74 |  | note | Responsibility - Site Engineer
date | 90c7dd75-f80a-548b-87ca-29ce383d455c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection - Fulton Hogan
label | 2ad7b67e-4a66-51c3-99ae-ee4fe311d368 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 33c74c7c-bf5e-5792-9b8b-96dcf120a309 |  | textbox | Print Name:
text | 5d6d2fef-26a6-5977-a97d-441b780245ab |  | textbox | Position:
date | 2e792dd4-2e81-5963-ac6d-150b00d33e81 |  | date | Work Completed On:
date | aa04b5b2-b11d-5efd-a814-21a3866d60c6 |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-005 - Unbound Flexible Pavement Construction | itp |  |  |  | Yes | CTN-ITP-005 - Unbound Flexible Pavement Construction | 210f010d-02c6-4ed5-a6a0-ef540f826f54
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | d432ab4a-729b-5e0e-91dd-4136f843a99f |  | note | Frequency - Prior to commencing any activity
label | 07d22d15-251d-5914-9b24-386ee3353642 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
label | 8048286e-f330-561e-82db-67d93351d05f |  | note | Reference Documents - Drawings and drawing registers
label | 24ae5099-99ce-567b-a1c4-1151a8d0fb77 |  | note | Inspection / Test Method - Visual inspection
label | 088d883f-b1db-5789-b5d1-83994667cb97 |  | note | Record of conformity - This ITP signed
label | 672eef6c-6cfc-5617-a4a3-e6ca50317f97 |  | note | HP*
label | 757d01c3-ec8d-55c9-96b9-7162c14a72da |  | note | Responsibility - Site Engineer
text | 5d9a9520-ce70-532e-a049-a5659150ae97 |  | textbox | ITP Opened:
date | 245ad061-8fc9-5b0d-a627-e45599ed2c9a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Material Classification
label | 9da7f4b6-1347-5797-9ada-1c2d12409596 |  | note | Frequency - Prior to commencing works
label | 71c29b54-ebc7-52de-833a-c1ff470d446c |  | note | Acceptance Criteria - Hold Point: All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads RC500.02 and conform to specified requirements applicable to that class of product
label | 79fe1cb0-2180-5ea1-8fc5-7e28ed29bfb5 |  | note | Reference Documents - 812.04 VicRoads RC500.02
label | 7b7bb06f-21eb-55e5-b685-1d72458f98b3 |  | note | Inspection / Test Method - Document Review
label | 43b501e7-c752-59ef-a8da-93ff4a75f053 |  | note | Record of conformity - This ITP signed
label | a6f61ff7-8cd3-56b3-8c66-c6aadb1c2af8 |  | note | AP
label | 0b4a05fc-f5d7-5a31-8058-96de25f43e7c |  | note | Responsibility - Site Engineer / QAV
date | bc9b00b3-47de-5bd2-b9ea-5c40628893c1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Implementation of all measures and controls
label | 5d0c9ed0-45c2-5153-a547-01ee500dfeca |  | note | Frequency - Prior to commencing works
label | ce5b9ba7-92c7-5a28-bceb-867eb78986f3 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP`
label | 5d005a5f-8188-5cb9-854c-591be4dfc25c |  | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | 887c1d92-0dea-5913-a846-5105930cb52f |  | note | Inspection / Test Method - Visual Inspection
label | 8f075455-4b78-5307-9376-4761020bd3ac |  | note | Record of conformity - This ITP signed
label | fbe63176-7a6e-510f-99ca-5a4735cfa37e |  | note | HP*
label | 5ced4e32-7920-5c18-9d0f-56d82e1b35df |  | note | Responsibility - Site Engineer
date | 8daf77e2-5aa4-52b6-8d83-7a6504866e2a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Plant and Equipment
label | 6981d912-0e6a-53be-b232-8e7e3c85e18a |  | note | Frequency - Prior to commencing works
label | 7bb6ead2-4de1-519e-b0f8-a98e523f62f9 |  | note | Acceptance Criteria - Plant and equipment used in the Works are appropriate to achieve specification requirements and is inducted
label | e0804891-2c43-5e76-8190-ba1e1063de16 |  | note | Reference Documents - N/A
label | 029d323a-fbaf-501e-b618-0197bdeb0b7f |  | note | Inspection / Test Method - Visual Inspection
label | 61abea53-148f-5e86-8133-6eebe5154f77 |  | note | Record of conformity - This ITP signed
label | c5ae55c4-a5a9-5697-95f1-39e165c6abed |  | note | IP
label | 3384a8e7-ec70-5307-b5aa-f734543389fe |  | note | Responsibility - Site Engineer
date | e942955b-2553-520e-abb7-23c140b3fe44 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - The commencement of construction of base and subbase
label | a05fcfc3-dd60-5101-a88e-6e3268c8e69d |  | note | Frequency - Prior to placing subbase
label | 2ba88fba-5a7f-58ad-9bd4-40e7024d8c32 |  | note | Acceptance Criteria - Underlying ITP signed off Identifying and removing soft areas to a minimum of 300mm depth. Underlying layer shall be clean of all foreign matter.
label | a267fae4-4992-534d-92f9-2e1e82b7a83c |  | note | The edges of previously placed materials shall be watered. Proof roll underlying layer prior to commencing
label | d63db581-0d34-5cbd-9088-20d0b2e979f1 |  | note | Reference Documents - Drawings
label | fe439bc6-fd22-54f0-a2a3-be84232def82 |  | note | Inspection / Test Method - Verify
label | 8d5e32e0-1fc1-505a-8411-18ea43deb2d3 |  | note | Record of conformity - This ITP signed
label | 8bbce96f-3de0-50aa-b41e-1921502132c6 |  | note | IP
label | 8b13540d-3dc6-5639-94a6-c680588cc5d6 |  | note | Responsibility - Site Engineer
date | ac783219-7a4e-5b22-a8a8-92a04c32f397 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Delivery Dockets
label | a8d333ce-4139-503d-ae83-f304a0ae3624 |  | note | Frequency - Each lot
label | c84e3bf7-650d-50df-83e7-a99855b7a3a5 |  | note | Acceptance Criteria - Where material is scheduled for measurement by loose volume in delivery vehicles or by mass, a delivery docket for each load shall be issued to the Superintendent at the point of delivery.
label | fff796dd-9118-5c8c-90a8-5c91f47ee84c |  | note | Reference Documents -
label | e0a27689-e3f2-5d68-a966-0f1d3e268e2c |  | note | Inspection / Test Method - Verify
label | b759add8-cc85-552f-b8bb-983e4759834b |  | note | Record of conformity - This ITP signed
label | 00ad074c-f4e7-5cf8-8b38-54c6ef03aece |  | note | IP
label | 54a95668-92b6-56e0-971c-6c1cc02d2ef0 |  | note | Responsibility - Site Engineer
date | 51279b84-e006-59da-953c-40057416f4d4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Layer Thickness
label | 6356818c-9eba-5ed0-a9e8-17ff617cec7a |  | note | Frequency - Each layer
label | f2704673-080b-56c3-afd6-017673f725f3 |  | note | Acceptance Criteria - Material is to be compacted to the overall thickness shown in the drawings (dependent on pavement type), subbase not less than the specified thickness by more than 15 mm
label | 3ad80d68-c0cf-5776-8816-47ef5b7b0958 |  | note | Reference Documents - Drawings and 304.06(c)
label | c0cd6f67-d9d6-5446-ae19-771a1d74ea78 |  | note | Inspection / Test Method - Visual and Measure
label | 024e13e3-e377-5dfa-a8fe-5e268505f9df |  | note | Record of conformity - This ITP signed
label | e303695b-c6ee-5971-a02b-0dff742c5160 |  | note | IP
label | 59d50214-a8b5-5acc-85c9-953d97cd08ca |  | note | Responsibility - Site Engineer
date | f693b721-fc2a-5f4a-868f-2d5feab12c20 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Conformity with Drawing
label | 768436d2-fef0-5e80-963b-148100964f2f |  | note | Frequency - Each lot
label | 8d8820c9-345b-5560-bc40-f8f493c3aebc |  | note | Acceptance Criteria - Width of each side of the pavement shall not be less than the specified offset width or
label | 901a5c37-60cb-54d2-8829-93e0d6c09534 |  | note | more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
label | 8129c4f2-ef19-5118-9076-4b8d15a83fd0 |  | note | Where pavement is to be constructed to the lip level of kerb and channel, it shall be constructed flush with the lip of the channel or not more than 5 mm above.
label | 624ab9d0-606b-5bef-b69c-4c86a19f71ca |  | note | Any material that has been compacted and then trimmed from the compacted surface to conform
label | 3c6a2d65-0f62-57e9-87ae-7e3709923ecb |  | note | Reference Documents -
label | fbefb15e-d373-5dc8-96ed-f0a3ceff1758 |  | note | Inspection / Test Method - Verify
label | b8ea0b1b-95b6-5a29-849b-e6d2fd306059 |  | note | Record of conformity - This ITP signed
label | 490b8f6d-b35d-5c2e-a5b1-708cdac921a3 |  | note | IP
label | 5e1e1e61-8583-5721-8b67-55cbce5c8b92 |  | note | Responsibility - Site Engineer
date | bde72002-78b9-5976-86b0-ec70e810af01 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Jointing
label | 17ec47dd-cdca-5bd4-a584-a1da76fb7d24 |  | note | Frequency - Each lot
label | 3fe99152-ce82-5487-8e00-7aa02d316ffb |  | note | Acceptance Criteria - (a) material shall be spread in such a manner as to minimise the number of joints
label | a279526e-e744-5c4f-b9d9-446a47fe5b02 |  | note | (b) transverse joints shall be offset from one layer to the next by not less than 2m
label | a3034968-7505-58dd-82d1-ba10e3af2a63 |  | note | (c) longitudinal joints shall be offset from one layer to the next by not less than 150mm
label | 239e8e9f-06a9-503d-96fa-3b3390fcc762 |  | note | Reference Documents - 304.07
label | f48b6bd7-effb-54f6-ac2f-ef81ca60784b |  | note | Inspection / Test Method - Visual Inspection
label | 55a0a238-3487-561b-ac51-936494cd506b |  | note | Record of conformity - This ITP signed
label | 4f12ae12-5a1a-5111-a748-19a807addf4d |  | note | IP
label | 3a2a9e56-3662-562d-b3b0-51512b1d34a8 |  | note | Responsibility - Site Engineer
date | 81d45c4d-c9fe-5c7c-887a-9f12bf302bc9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | 822ca4ec-43e5-5b0e-9845-121f30ba9b05 |  | note | Frequency - Prior to Testing
label | cf7c04cc-2f77-54a5-8d48-99db0e9ee568 |  | note | Acceptance Criteria - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
label | 74e59d01-fa55-5a65-9d1d-bc5ca9cee072 |  | note | Reference Documents - Table 204.161, 304.08 (a), 304.11 (b), 304.11 (c)(i), Table 304.111
label | f813dd9d-97ad-5655-a881-61f6482812b4 |  | note | Inspection / Test Method - Document Review/ Site Inspection
label | 701485e2-b43c-5656-ae11-8e4c5ffee366 |  | note | Record of conformity - This ITP signed
label | 680b618a-7f32-5123-8553-981f60b56f1d |  | note | AP
label | 9da15b0a-ce65-5312-a9fa-81d8f410bf34 |  | note | Responsibility - Site Engineer
date | 4f08da2d-cea6-5d36-bbaf-ba807b307579 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Test Rolling
label | b9fe648f-7ef9-51ff-97c4-a635f0d04c77 |  | note | Frequency - Each lot
label | 362e5b58-8bcb-58f2-b3c7-f48b0f05a8a5 |  | note | Acceptance Criteria - Hold Point: All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173, prior to acceptance of the layer.
label | 2438179a-d3b1-5000-962d-3245b33a1756 |  | note | Reference Documents - 304.08
label | f36b0f70-3613-50e8-8b0c-cc9d9c23b1b0 |  | note | Inspection / Test Method - Test Roll
label | a9aaf374-30c7-5a7d-a428-a85fb16ceee1 |  | note | Record of conformity - This ITP signed
label | efec41ac-d82c-550b-aa5b-fdc291221a47 |  | note | HP
label | 01abe61a-914f-51b7-aa60-0bc1d935d536 |  | note | Responsibility - Site Engineer / QAV
date | 03db7e30-654a-5723-97b4-ed50f957f13c |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Compaction Testing
label | ca9fdc4a-3a23-5160-bfb7-dd5b9d8fc7fd |  | note | Frequency - Every Lot Every second lot (reduced frequency)
label | 29ae401d-4fee-59be-b9df-1134fdf4944b |  | note | Acceptance Criteria - The calculation of density ratio shall be based on tests performed using Modified
label | e3d43116-726c-5317-b227-a5aacb6803ab |  | note | compactive effort. The work shall be assessed for compliance with Scale A, Scale B or
label | 671cd601-34d7-5b98-9f5a-b760c761b3a2 |  | note | Scale C requirements for testing and acceptance of compaction as specified in the table below
label | e1d21c12-0228-5c63-ad3d-1c1895e0ca16 |  | note | Reference Documents - 304.08 Table 3040.061 304.11 (b) Table 304.111
label | d1cce89f-d55d-5849-bef2-70e884990b29 |  | note | Inspection / Test Method - Test point
label | f1de5025-5edd-5784-a972-34d54dd841b3 |  | note | Record of conformity - This ITP signed
label | 81bde738-a559-5b6a-8a80-b5dee6a8cec8 |  | note | TP
label | d552cf8a-7553-5f98-b74c-8c8eec4c5740 |  | note | Responsibility - Site Engineer
date | b94b0434-6663-5af2-b04b-7e88098de99c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Post Compaction Testing
label | 3d226811-77b4-57c7-8c7c-05d0f85e62ca |  | note | Frequency - Refer to table 304.111 for various minimum frequency or testing for Grading and PL
label | 5ca78fdb-a803-552f-8b38-a76d98d277d1 |  | note | Acceptance Criteria - If specified in Clause 304.10(c) or Clause 304.10(d), following completion of compaction, material
label | 5e5c4ba7-ca07-589f-89fb-fc05669c5ce8 |  | note | shall be tested for post-compaction grading or Plasticity Index (PI) at the frequency specified in
label | e494da9e-33df-5698-8987-d1d7c2d4036d |  | note | Clause 304.11 for the appropriate Scale of Testing specified in Clause 304.12(a).
label | ca4e64cf-bfc1-58f0-a5e3-3ea8091af2c3 |  | note | Reference Documents - 304.10, Table 304.101 304.102
label | 16960a6f-a0e4-5fa9-be9e-32560e66e7f5 |  | note | Inspection / Test Method - Test point
label | 1974ea73-771c-506d-a5b1-4c74650b0715 |  | note | Record of conformity - This ITP signed
label | 64812540-b373-5112-adbd-6ad11bdd6f1e |  | note | TP
label | 363c1975-5ea0-59b3-9cfe-05063ad6978e |  | note | Responsibility - Site Engineer
date | 923ce5e5-b3bc-5a62-ab00-654e2a2d0907 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Shape
label | f7748dd5-f628-59c4-90c2-f112f988f815 |  | note | Frequency - Each lot
label | d8fef36a-95d1-5873-94ad-85ee2cf26451 |  | note | Acceptance Criteria - Layer to be finished to a smooth and uniform surface and after compaction shall have no point deviation > 8mm from 3m straight edge.
label | f1c8945a-f14b-54ca-9ba0-0ff0f394f874 |  | note | The subbase shall also not be less than the specified thickness by more than 15mm
label | 6ad58635-aff7-50a1-8ab4-fd3398aed788 |  | note | Reference Documents - 304.06(b, d, i) Drawings Table 304.062
label | 1167a159-4b15-57a3-850b-4ec6acc90439 |  | note | Inspection / Test Method - Survey
label | 1d763fc7-f6a9-554f-92f4-7c56cdeee090 |  | note | Record of conformity - This ITP signed
label | 1b470538-85ae-5bf9-bcaf-bb4027291583 |  | note | IP
label | d3cb0f3e-0d42-56b0-98d8-ae8436f91e4d |  | note | Responsibility - Site Engineer
date | 7d5feed6-5370-50ab-b354-5efd750c68ab |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Completed Surface Level Compliance
label | 16ac8819-0e34-5d14-ae56-9353f100f3be |  | note | Frequency - Each lot
label | aa97c030-21ef-5eca-9ec3-6e81a44aa281 |  | note | Acceptance Criteria - Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and
label | fcd0f911-d525-5db6-abbb-badd4f279c9d |  | note | the number of measurements taken within each lot shall not be less than the number specified in Table 304.061.
label | 2b093a59-d010-5727-aeda-db7d2b24c076 |  | note | The mean and standard deviation of the departures from the design surface level for the pavement courses at their respective levels within each lot shall meet the requirements of Table 304.062.
label | ab7a431c-b410-5f40-84af-30a84ff83bc5 |  | note | Reference Documents - 304.06(b) , Drawings, Table 304.062
label | e2ec348b-9fe1-5b8d-bbd9-e1713fa837e8 |  | note | Inspection / Test Method - Survey
label | 85e7e38c-1aae-547b-94d8-b30aee8123c8 |  | note | Record of conformity - This ITP signed
label | 69259160-c7c4-5566-81ef-30a4c40112f5 |  | note | SCP
label | 2395f836-0f0b-5899-af76-c3aa79e6b729 |  | note | Responsibility - Site Engineer
date | 189f70b7-32ea-58bc-8900-fea84bf8818d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection - Gradco
label | 231bda88-3dcc-53a7-8ea0-5cfc6c9e7999 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 28166835-bc81-5080-8c2a-6504302a5c29 |  | textbox | Print Name:
text | e02afaa2-ae3b-5ce6-8466-acdfd8a10917 |  | textbox | Position:
date | 4829d43e-30f6-55dc-a2f8-8e068ffdabf1 |  | date | Work Completed On:
date | 75f622dc-5d19-5ccd-a2a0-4fd72385b748 |  | date | Date:
checkpoint-status |  |  | checkpoint | Final Inspection - Fulton Hogan
label | 2ca7dfdd-9cd0-569b-94b8-cc01e19f96d8 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | dda1ac05-3733-51cc-be53-ea7a7fc13c66 |  | textbox | Print Name:
text | 216ea659-76dc-52c6-b29c-d7c7edc704cf |  | textbox | Position:
date | 1b3e53c8-6589-541b-ac41-bdfc9252a84c |  | date | Work Completed On:
date | 8b7422c8-78e3-5ec2-aa84-a5d98dc7a452 |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-002 - Fencing | itp |  |  |  | Yes | CTN-ITP-002 - Fencing | 276f644d-0cc3-4ea4-9e1e-2322b3f471b7
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | d4a9a5fd-622b-5e89-8504-60907f920cb2 |  | note | Frequency - Once, prior to commencing any activity
label | 503f238e-3e91-5832-b7a1-ae4f79b9242f |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | 40a825b0-f359-50c6-a86a-e354f0b08fb8 |  | note | #NAME?
label | 40747da3-91f0-5cea-8805-31b7b04da352 |  | note | #NAME?
label | 3ab4e535-e79f-5a1a-b6a2-767ad5d87a02 |  | note | #NAME?
label | e7853f13-7f1f-5ce7-93b4-a9ac824c3080 |  | note | Reference Documents - IFC Drawings Drawing register
label | 63b64166-8fd3-52d8-ab1e-b55adfe27d4f |  | note | Inspection / Test Method - Document Review / Visual inspection
label | 79a5a3c4-baf7-5a73-bed4-ecc008c52255 |  | note | Record of conformity - This ITP signed
label | 6a80612d-5e42-5154-aa2c-18fa7b7b0998 |  | note | IP
label | 31360431-b0c7-522f-a0f0-ac122444125e |  | note | Responsibility - Site Engineer
text | b61d01f8-ecd3-5881-9a31-ae5ca12ee211 |  | textbox | ITP Opened:
date | 244ba682-a4a6-5434-8af8-20cb7e78fdcf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 59d1bef5-d7a8-5537-a523-5054c43aadcd |  | note | Frequency - Once, prior to commencing any activity
label | 951e0fc3-0067-591b-8b11-fdc9bd78653c |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: OHSMP, EMP, SWMS & WP. Access and egress inspected and assessed.
label | 45da20ba-03e3-57df-9729-f0c8b148a1e4 |  | note | Reference Documents - HSMP, EMP, SWMS, WP
label | 7ba1f4c2-2281-5009-99e1-a264020c7ae1 |  | note | Inspection / Test Method - Visual Inspection
label | 5616f04a-f964-527f-b01d-5be175c0021c |  | note | Record of conformity - This ITP signed
label | 901aa93b-5098-594d-a2fd-324a18b20421 |  | note | IP
label | 19baa182-8b2f-52f6-8c63-9b0e9c96102c |  | note | Responsibility - Site Engineer
date | 7d987476-8e86-5149-894a-7c494e588a2e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Survey set-out
label | b5ab6336-884c-5af1-97b0-b151abf537b2 |  | note | Frequency - Once, prior to commencing any activity
label | 02cf7fde-73dc-5e26-a56b-f93f3359dd67 |  | note | Acceptance Criteria - The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity.
label | e722468d-30ce-599f-aa15-a3aefbb6f651 |  | note | Survey activities undertaken to ensure and validate that all works meet level and location requirements. Verification of conformity with latest IFC drawings.
label | b360cfe9-f2e6-543f-80a9-85731dca4c50 |  | note | Reference Documents - Cl 707.04, Drawings
label | 41f7cbea-6f8e-5219-9dd6-d231bb7bbfa1 |  | note | Inspection / Test Method - Visual Inspection
label | 28fd5ed4-1316-5f2b-82f1-b1daea126be3 |  | note | Record of conformity - Survey records and pegs on the ground
label | 6b6bb033-b2b4-5b67-90f2-8e4b1a1d86af |  | note | IP
label | fd2ebf06-3523-5df9-9501-4605b6761494 |  | note | Responsibility - Site Engineer
date | 6177d520-08a9-52ef-948f-76f9b34987b3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Fencing material
label | 173079a6-08ba-5591-975f-6241b6759a63 |  | note | Frequency - Each Product or Material
label | 7240c0cd-afc2-5f17-a070-891ccccad486 |  | note | Acceptance Criteria - Unless specified otherwise, all fencing materials and products shall be supplied by the subcontractor and shall be accordance with the requirements of DSG 707.03
label | bcd725a8-3d88-5e66-80ab-3ec8bbafc6b5 |  | note | Reference Documents - Cl 707.03
label | 13e585ae-11c2-555b-b4e3-bb99802942da |  | note | Inspection / Test Method - Document review
label | 80f085e1-a947-5d33-8699-eff6e88a4999 |  | note | Record of conformity - Certificate of Conformance
label | 7108132a-69a3-588b-bd34-4e74c817695d |  | note | AP
label | fb06667a-af65-5b7e-ad51-9ca3d04e3d70 |  | note | Responsibility - Site Engineer
date | f1ad1a69-7fd5-51ac-ba6c-2eacb95ca599 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Fence post installation
label | 678a002d-e804-5098-a053-83e2e37824e1 |  | note | Frequency - Each Fence Post Location
label | e661dee2-69a5-576e-ba46-806a0ee61aa3 |  | note | Acceptance Criteria - All posts to be installed on the roadside. Post type and spacings as per landowner notices of accomodation (Spec appendix G and M). All posts vertical following installation
label | 3dc85d3d-e447-59e2-8466-61d120d280ae |  | note | Reference Documents - Drawings, Spec Appendix G, Spec Appendix M, Cl707.04
label | 35674f3f-2a9a-5826-8336-6db0a016eca5 |  | note | Inspection / Test Method - Visual Inspection
label | 309aab53-95ed-5034-b89a-398e0da3f95c |  | note | Record of conformity - This ITP signed
label | c15e898d-7bc0-5be0-874a-b18e76baaaac |  | note | IP
label | 38a13350-a300-5809-bfe0-9c93a77be39b |  | note | Responsibility - Site Engineer
date | ccc78b56-3e6c-59a8-a19e-24c3bbdc0632 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Wire installation
label | c419745d-623a-5d57-b9fe-3337365bf337 |  | note | Frequency - Each wire run
label | 07fd8a35-107a-5202-9bfe-ebc8a4e5cbf5 |  | note | Acceptance Criteria - Plain wires reeved through holes in posts unless treated round posts are used in which case wires may be attached with staples after straining.
label | 79dbfdf8-a481-51e3-8cd7-d34e8b71b104 |  | note | Barbed wire secured with galvanized tie wire.
label | 51b134cf-5154-5d5c-9a7c-843bee7aaea9 |  | note | Top and Bottom wires firmly attached to droppers and intermediate wires threaded through bored holes in droppers.
label | 6b7af0dd-f596-5013-82bc-abeeac86ad7a |  | note | Reference Documents - Cl 707.04(a)
label | 3426a99d-fa23-5095-a4e8-97440abf6747 |  | note | Inspection / Test Method - Visual Inspection
label | 78eec037-7955-5d14-884d-586ae8c0c741 |  | note | Record of conformity - This ITP signed
label | 2fd28f83-4f71-5ab6-bfd2-9df5480fa4e0 |  | note | IP
label | b8cf1bbf-d177-556e-af7f-dc745f56f66d |  | note | Responsibility - Site Engineer
date | bbec8e56-703d-59b7-b65c-70ec0bcc18bf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Wire Mesh Installation
label | 98597b51-19bb-586a-8ec5-4c3ad46b4885 |  | note | Frequency - Each wire mesh run
label | 7b523d91-3734-520d-b4e4-9c033bfc3ff1 |  | note | Acceptance Criteria - Wire mesh shall be attached to posts and droppers by stapling or tying the top and bottom line wires and at least every alternate intermediate wire to each post after straining.
label | 9d6d3d6d-466b-5d7b-91fe-58caed9ff716 |  | note | Reference Documents - Cl 707.04(c)
label | fb3d7001-baf0-54eb-8117-e9450f847ce0 |  | note | Inspection / Test Method - Visual Inspection
label | fc74955f-4f6d-58ba-8ae6-ce19cc1be7ad |  | note | Record of conformity - This ITP signed
label | 2199f11b-1186-5dd6-85a2-c135dd242c27 |  | note | IP
label | 55217164-5172-5713-86ad-310518ce5f72 |  | note | Responsibility - Site Engineer
date | 1455c4df-e088-5979-9535-76bfd3200441 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Gate installation
label | bcf46eb8-7296-5aa5-baed-840d0fca50b8 |  | note | Frequency - Each Gate Location
label | b9b2754c-92cb-56c9-95a0-80ed01f07056 |  | note | Acceptance Criteria - The Contractor shall install gates of the type, size and location as specified in Spec Appendix G and M, or shown on the drawings.
label | 6bb8e45c-56f1-5077-aa33-9e80128d4e62 |  | note | All gates shall be hung with galvanized hinges securely attached to the gate posts and be able to swing freely. Each post fitted with a strut as shown on drawings.
label | 9baeb9a6-159a-522a-ba7e-db883125f0d6 |  | note | Each gate shall be fitted with a galvanized catch for holding them securely closed, of a type to suit the gate and adjoining fence. For wire netting fences, gates shall be finished so as to be rabbit-proof when closed.
label | cf059cdb-cd10-507a-a18a-5a348c5b361b |  | note | Reference Documents - Drawings, Spec Appendix G, Spec Appendix M Cl 707.05
label | b9d72549-8f09-582b-b479-f5b6f4e134cf |  | note | Inspection / Test Method - Visual Inspection
label | a94ed9fb-731e-51bc-928e-ed73368d554d |  | note | Record of conformity - This ITP signed
label | 708c271b-d37e-5458-9842-da3fca41a7f1 |  | note | IP
label | 071d4066-c97c-5c39-81cf-cd771dc32ad1 |  | note | Responsibility - Site Engineer
date | b2668817-0558-5944-90d2-c8bb84b35dca |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 - As Built Documentation
label | 6319c700-e827-5c04-85a3-92ca21053115 |  | note | Frequency - Each Lot
label | 6b687432-41ac-5414-bce8-b4e1e8f26661 |  | note | Acceptance Criteria - Survey pick-up and as-built information to be progressively completed. Tolerances are: i. ±20mm from design height ii. ±20mm in alignment (or ±20mm from central location if being attached to a new structure) iii. 1 in 50 in verticality
label | 04c36a39-ef17-5787-8536-86f36f3f8675 |  | note | Reference Documents - Cl 707.08
label | 1077107c-0216-5a4d-b41d-098ab807ef62 |  | note | Inspection / Test Method - Document review
label | faf2f5a9-ed07-5922-b7cf-bfda5d7180fd |  | note | Record of conformity - As built Drawings/Records
label | 1326421c-c1df-5311-84f3-a63c137071ce |  | note | HP*
label | a7da19c9-c5c0-5a8f-973c-cb8aefdf5ca4 |  | note | Responsibility - Site Engineer
date | 76fa5fb5-4033-53f6-88dd-3db072bb53f5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | d9345e8d-fd25-5f65-8c06-1d02b4ec5df7 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 7b0eeb71-c88c-5e60-9dea-7d2794fa964f |  | textbox | Print Name:
text | a579a7c6-4e4e-52c4-bf93-856eb1df2561 |  | textbox | Position:
date | ac3c2255-0c5d-5979-b695-f83eb96dd1cb |  | date | Work Completed On:
date | 09dbddae-a4c1-56cf-99d2-4e6a4d2e83aa |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-008 - Subsurface Drains | itp |  |  |  | Yes | CTN-ITP-008 - Subsurface Drains | 289667cc-bb2b-40fd-87b7-927143714146
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | b0fe8ad4-0fdf-5b53-bfda-a9e6abfa6d5e |  | note | Frequency - Prior to commencing any activity
label | ceb6b891-950d-509f-b31a-30ad314fc0f0 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are: using the correct and complete set of drawings; all drawings are the latest revision
label | a7633611-d501-5487-aea6-ec0d19f56864 |  | note | Reference Documents - Drawings and drawing registers
label | 6e502667-8ec1-5884-89f1-4a5618ee082a |  | note | Inspection / Test Method - Visual inspection
label | ba83459f-2a9e-5be1-9d25-200c2c3760cf |  | note | Record of conformity - This ITP signed
label | bcb61cc9-6b6f-58f5-8ab1-db3688eee4ca |  | note | HP*
label | 916867d7-96c8-5c7a-88ff-3e59f57ae686 |  | note | Responsibility - Site Engineer
text | e5c990e0-ae83-57af-a664-abfd71ee1065 |  | textbox | ITP Opened:
date | 6b761dc0-3e10-5c2b-a818-82dafc48173b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 27b119e6-4d1e-5c5e-811b-8d82be2c91da |  | note | Frequency - Prior to commencing any activity
label | 4158641f-be4c-5c5f-bd0f-1390440e670f |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 4e1d100c-5052-5c54-a5df-b406b1149485 |  | note | Reference Documents - PSP, EMP, TGS, SWMS, WP
label | a82a9a9e-115c-5b60-b738-7843b92d4bec |  | note | Inspection / Test Method - Visual Inspection
label | 4890c995-9e91-583f-9424-8adf4500edf0 |  | note | Record of conformity - This ITP signed
label | 6a5c7b6b-e23f-5a88-a250-efdff2da48a1 |  | note | HP*
label | 8f79f4b0-66c7-554b-bc11-cd8eb0d67bcf |  | note | Responsibility - Site Engineer
date | a75331ff-c54f-52c7-a874-d94881150c0b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Material Classification
label | 7e557ef6-ccd9-5dbf-aade-f2d133bd7595 |  | note | Frequency - Each Lot
label | 9c43fbff-4eaa-5535-a84d-9c4501ac401e |  | note | Acceptance Criteria - Pipes supplied shall be of the category and diameter shown on the drawings or specified in clause 702.12 and shall comply with the requirements of the appropriate Australian Standard in accordance with Section 175 or as follows:
label | c06e54c0-1996-5674-8bbe-64a46105e1fc |  | note | Category 1: Perforated plastics Class 1000; Precast concrete Class "2"
label | 08b17778-88fb-5073-8bed-bc7d5489ed37 |  | note | Category 2: Perforated plastics Class 400
label | 6edef44a-8903-5a98-b0bf-8f2bbfac6305 |  | note | Category 3: Geocomposite drains Granular material as per clause 702.05, Geotextile material as per clause 702.06
label | 3be7d734-d64e-5def-bff2-7c6f1cf27177 |  | note | Reference Documents - Cl 702.04, Cl 702.05, Cl 702.06
label | 5dd79336-03fb-596f-935a-bcc690e668a9 |  | note | Inspection / Test Method - Verify
label | b5b4e0e6-7da9-5102-8e61-17dca83816c2 |  | note | Record of conformity - Order acceptance certificate, This ITP signed off
label | 5232f7cd-ead6-512f-8093-7f82118e3890 |  | note | IP
label | 3d3edb51-e594-563e-b5a4-91a96091c310 |  | note | Responsibility - Site Engineer
date | 85acf82e-ed34-5e93-86dd-4f2e5f81ed5d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Excavation Permit
label | 47d66fc8-cab2-5edb-b735-e5f05cb21e13 |  | note | Frequency - Each lot
label | 295aa7bd-0679-5349-af4c-9792b68c0cc8 |  | note | Acceptance Criteria - An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
label | ba621547-9995-5c6d-a7ac-6dbbabad582e |  | note | Reference Documents - Excavation permit
label | 5845671b-4525-54b0-a133-bca44ca53352 |  | note | Inspection / Test Method - Verify
label | 266b4a99-bb3a-5967-9b25-eac05cc26c21 |  | note | Record of conformity - This ITP Signed
label | e84fe3f7-da5a-5e1d-86f0-9f827610e2b6 |  | note | HP*
label | fe2c2105-a984-5c83-853a-0b1e383db392 |  | note | Responsibility - Site Engineer
date | 96268114-9ac1-5244-9f25-0046c82810f2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Excavation of Trench
label | 90fac762-efec-505a-b2ff-db99683b3379 |  | note | Frequency - Prior to placing bedding
label | f2fa5604-c957-522a-ba27-bea1db66b36f |  | note | Acceptance Criteria - Hold Point: Base of trench inspected to verify compliance with clause 702.08 prior to placing bedding in completed excavations. The superintendent must be notified at least 24 hours prior to the inspection
label | 3ed23f17-b7b7-5aee-86c3-15f050aebc6b |  | note | Reference Documents - Cl 702.08
label | 598f9651-3621-589e-9280-fda0e0398cb9 |  | note | Inspection / Test Method - Visual Inspection
label | 9ee43250-e4e1-54df-9694-b5e110192d49 |  | note | Record of conformity - This ITP signed
label | 3a2c7a21-b85b-581f-99df-843283d1fc76 |  | note | HP
label | aced6c6c-5f8d-5b00-80ab-9f9cc37e5b10 |  | note | Responsibility - Site Engineer/ QAV
date | 39622a4b-acdd-51bc-9581-887eeddd8e46 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3 - Placement of bedding
label | 7aac6195-3ff1-557f-96d4-932c9a03a699 |  | note | Frequency - Each Lot
label | 4f6f1ded-922a-53a3-9f0a-6341b2d713f4 |  | note | Acceptance Criteria - Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | 1a9c048d-a78a-5978-9a04-9ca86da09945 |  | note | Reference Documents - Cl 702.09 (c )
label | 96e08169-4dd7-5ee0-88db-3b401da77a97 |  | note | Inspection / Test Method - Visual Inspection
label | 373e0367-e700-558d-9299-61273998a493 |  | note | Record of conformity - This ITP signed
label | a8edb244-21eb-5813-b63f-a653f985f7e3 |  | note | IP
label | fbecb888-677a-537c-a4aa-bc785715e697 |  | note | Responsibility - Site Engineer
date | 188fa1e4-11fc-5d65-8382-9d9ca46020b6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Placing pipes
label | 9f395306-1da6-5017-9b9f-6b963a795b38 |  | note | Frequency - Each Lot
label | d28d5cee-3fc6-53d5-a628-62534b380d42 |  | note | Acceptance Criteria - Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
label | afcb6e77-fce1-55d0-9c2d-48a4cd285ff5 |  | note | Reference Documents - Cl 702.09 (d)
label | c1616a41-8ab9-5f88-bc13-df9f30bdd602 |  | note | Inspection / Test Method - Visual Inspection
label | ece8c1f1-3c97-5261-b70f-e5f602540ddd |  | note | Record of conformity - This ITP signed
label | 39e37707-26ea-5e53-b334-0b75e2671764 |  | note | IP
label | bb150261-e564-5eb8-8d7f-b96da3467218 |  | note | Responsibility - Site Engineer
date | 46f46482-e47e-539b-ae70-220cf12f3105 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Placement of granular backfill
label | d78dfa4a-d68b-5d19-97d8-071495c73d1d |  | note | Frequency - Prior to backfilling
label | fdee790a-7322-59e6-bf10-e13f1744c821 |  | note | Acceptance Criteria - Hold Point: Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the submitted quality procedures
label | 481f50b8-0b41-5eda-aae6-e797c4788ff4 |  | note | Reference Documents - Cl 702.09 (g)
label | 889a82cf-85d8-572a-8da0-15ee0ba1cf5c |  | note | Inspection / Test Method - Verify
label | d550a3b9-fd89-5369-9dfb-254ac35d1c50 |  | note | Record of conformity - This ITP signed
label | 9131de0f-7e0e-558b-9c25-436974e307bf |  | note | HP
label | 26626830-7aa2-56c5-851c-e4a1fa280d95 |  | note | Responsibility - Site Engineer/ QAV
date | 07e92861-88ab-5f41-aee2-f87b2b62c6c9 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.6 - Placement of no fines backfill
label | 3261e007-08ce-5b23-8105-d4ff6481a7da |  | note | Frequency - Each Lot
label | e23fc3a3-9bd6-51fa-a919-bfd5a16b498f |  | note | Acceptance Criteria - Hold Point: Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete to prevent segregation and the formation of a slurry layer at the surface of the concrete which may prevent the passage of water into the filter material.
label | cebe686a-e164-5b67-a087-bcd17c04216c |  | note | Reference Documents - Cl 702.09 (g)
label | 3735274b-a59a-51b5-a9a9-132849f7de2d |  | note | Inspection / Test Method - Verify
label | 17163835-4f53-52bc-bed2-33081f24d8c2 |  | note | Record of conformity - This ITP signed
label | e078d03b-5b6d-5be8-a59f-048a2bde7923 |  | note | HP
label | 3cbc5996-3bda-5991-8cf1-2335fc97bc24 |  | note | Responsibility - Site Engineer/ QAV
date | cc0b7fc9-1edc-5af0-af09-aac56f853569 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.7 - Access Points and Flushouts
label | 31b97b27-17f2-511b-9157-1590d86f8d7e |  | note | Frequency - Each Lot
label | fab8ea92-858f-5e10-8c98-8002e581577b |  | note | Acceptance Criteria - Access point installed at the beginning and end of the drainage run and inspection openings at intervals between 100m and 150m. Flushout risers have same diameter as pipe.
label | cd90ef6f-6e24-5063-82cd-2374f5025572 |  | note | Reference Documents - Cl 702.10
label | 0e53ed30-5711-57dd-8b7d-041e724a4cef |  | note | Inspection / Test Method - Verify
label | 4f4583c3-3a2b-5840-98d9-37c0d0252330 |  | note | Record of conformity - This ITP signed
label | 5744b74c-12f5-57b9-857f-419dad8280d8 |  | note | IP
label | 090e898d-4066-59d5-b1a2-f161b506ed92 |  | note | Responsibility - Site Engineer
date | 759e69fd-9887-5cdb-8d7c-dba33a35576c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Flushing Test
label | 4cbe577b-88b8-5fa9-9762-5b213d006976 |  | note | Frequency - At completion of stage
label | ebf38e03-8102-5da0-9508-9cb8ce20b5fd |  | note | Acceptance Criteria - Flushing test undertaken on each subsurface drainage line after completion of the drains, flushers and risers, and after completion of barriers and road furniture. The test should be witnessed by a representative nomitated by the superintendent. Record of flushing tests must be kept.
label | 425d311f-6cd2-51a4-b437-3e2dd9e1cd04 |  | note | Reference Documents - Cl 702.09(h)
label | af6fbddb-0b9b-56ed-8eba-b909bfadd265 |  | note | Inspection / Test Method - Site inspection
label | 8583c503-ed2e-5f84-bbe9-8c296edb364e |  | note | Record of conformity - Signed ITP/ Record of flushing tests
label | 5098a61a-e696-5c99-bad8-d4e0b03a6f43 |  | note | TP
label | ac2f6b93-ebb1-5cc6-8c30-5ef27ebc2ce9 |  | note | Responsibility - Site Engineer / QAV
date | 230fb0d3-e96c-5a3f-a545-3e5245a176a1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Inspection of subsurface drainage lines
label | 30863940-28e5-5fad-8545-36a663b9ae67 |  | note | Frequency - At completion of stage
label | 62173a8b-f193-5f45-abf3-8010f24f2522 |  | note | Acceptance Criteria - Hold Point: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | a1acfede-dcfd-5254-9ef9-84c84e96276e |  | note | Reference Documents - Cl 702.09(i)
label | 5fd4f030-1dbb-5e30-abdd-d41a0889956a |  | note | Inspection / Test Method - Site inspection
label | 46bc0941-3880-5bf9-9713-78640d718d60 |  | note | Record of conformity - This ITP signed
label | 75c2eeba-7a95-5bc9-a56a-576823a67d1f |  | note | HP
label | 3921e775-a037-59c1-a1a5-ff11de6cc945 |  | note | Responsibility - Site Engineer / QAV
date | 216749c4-ec7c-50c4-8697-7cd4cfed3e31 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Inspection of subsurface drainage lines
label | acf9471f-8740-5e90-8539-9b17da31fb48 |  | note | Frequency - At completion of stage
label | 4db7782e-ac4b-5f4c-a39b-55d0f2d2eb12 |  | note | Acceptance Criteria - Hold Point: Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition if subsurface drainage lines has been verified by the Superintendent.
label | 6cd8702e-2913-510e-9841-2afc98b5743c |  | note | Reference Documents - Cl 702.09(i)
label | 39781e9e-f617-5f49-8fc5-f03d21310f0a |  | note | Inspection / Test Method - Site inspection
label | 16d60e4d-3418-5e9e-b01a-dc813a2857c5 |  | note | Record of conformity - This ITP signed
label | 13b48d7a-2f90-50f8-bb39-b751ffb553b1 |  | note | HP
label | bd16d620-c52a-547d-b210-7fb8ee414d3d |  | note | Responsibility - Site Engineer / QAV
date | 3bc3ed5e-f044-55e2-9461-2254d3fd7a9f |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Final Inspection - Fulton Hogan
label | 05abb1ee-579f-589a-9f82-3481a6bd65a2 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 7325628d-8080-5c12-b761-1a780dd687ed |  | textbox | Print Name:
text | ec57c56a-7ee4-58e9-a62f-27d352d326fd |  | textbox | Position:
date | 5cd5df48-da32-5acf-88b5-171e6d4a5f6f |  | date | Work Completed On:
date | 4bb8d40c-c078-566f-baa8-486c88a45686 |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-013 - Road Furmiture and Signage | itp |  |  |  | Yes | CTN-ITP-013 - Road Furmiture and Signage | 2d045f5c-95e7-442d-bc9f-b31c7a970a84
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | a0a6e1e8-755c-5f2c-8ca7-1c8bdf810045 |  | note | Frequency - Prior to commencing any activity
label | 7b9222ac-dbc3-56cc-8174-10ef45789afb |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are: using the correct and complete set of drawings; all drawings are the latest revision
label | d008e83e-7699-51fc-b9ce-19a0fc1834ac |  | note | Reference Documents - Drawings and drawing registers
label | 03bb3c0b-811d-5746-9689-5599bab8f91d |  | note | Inspection / Test Method - Visual inspection
label | 3935e913-1570-5c6d-a2fa-6f6bcdd760b3 |  | note | Record of conformity - This ITP signed off
label | 35e51729-79e7-5eb3-a024-7f999e499e9d |  | note | *HP
label | 61ab3ab8-c380-56d4-a5ff-eb8b678f8e22 |  | note | Responsibility - Site Engineer
text | 4e9aa081-600e-544f-8d9b-1c55e5e8d729 |  | textbox | ITP Opened:
date | e517aff6-a6c1-552b-8023-69ae892b589a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 589ca386-487f-5ede-81d4-e6ac368e36c4 |  | note | Frequency - Prior to commencing any activity
label | 5fc33b33-7888-5a6a-a938-57b2d8bcc352 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | f6bebe9c-06b3-5d7b-a224-7fafea74ed15 |  | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | 611b56d2-87fd-5bca-bca7-20435f85886a |  | note | Inspection / Test Method - Visual Inspection
label | 7362b6c1-7d6d-57d6-822a-3e8bb948414d |  | note | Record of conformity - This ITP signed off
label | 32c9195c-aef2-5776-bddd-1e152269b530 |  | note | *HP
label | 2ad74c2e-a212-5d2b-8f13-ec13d2ca4804 |  | note | Responsibility - Site Engineer
date | 919dcb8c-be42-5998-830c-20e45983da2b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Signage Conformance
label | 6b1a438c-0a9f-54c4-b34b-2e9aba9cf5a3 |  | note | Frequency - Before commencement of activity
label | 63ba7d06-99b1-54c1-a468-10a3acc6a450 |  | note | Acceptance Criteria - Ensure sign size and image correspond with contract drawings
label | 3fea4ecf-7348-5db6-8ca8-a2b7176a88cb |  | note | Reference Documents - Drawings 4853 to 4951
label | d8c8c4e8-3e17-5d09-9f2c-c30e7ea1153b |  | note | Inspection / Test Method - Verify
label | 08c122b3-2ff6-5369-bea6-12d658ee7722 |  | note | Record of conformity - This ITP signed off
label | 2bab03d8-63ae-57b4-8753-bb3c2db78ff4 |  | note | IP
label | bd870249-7aa6-53e9-9a72-0a221eca0bc2 |  | note | Responsibility - Site Engineer
date | c0ece20b-577b-5aff-a099-9ab4c6209008 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Service Identification
label | 496a109e-8428-5011-bbe7-fc048c21f476 |  | note | Frequency - Prior to start
label | c478c2e0-4f78-58b8-9782-86d3ec35a172 |  | note | Acceptance Criteria - Check for any services in proximity to points of installation of posts
label | 4d7d9352-8edd-53db-ac9c-74cae3c3d29f |  | note | Reference Documents - DBYD
label | 69c5cc4b-d50f-5552-ad29-4d1f56d48183 |  | note | Inspection / Test Method - Verify
label | b355c7dd-5467-5337-86ce-6573204ec725 |  | note | Record of conformity - Ground penetration permit, This ITP signed off
label | 9f92d70c-48de-5701-a765-ed73b050f70c |  | note | IP
label | fbb89d4e-8587-540a-ab75-8758f6171a43 |  | note | Responsibility - Site Engineer
date | a768b75b-2c0d-5fd1-a1e8-21be1094be94 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Setting Out
label | a889d1de-2684-558d-8c27-64a6b6038fca |  | note | Frequency - Prior to start
label | 76566718-8519-5081-9022-69e8b6986e18 |  | note | Acceptance Criteria - Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
label | 76bc7cb9-1e0f-5195-91be-1f09a097de7d |  | note | Reference Documents - Drawings 4853 to 4951
label | 810e2743-7a92-5563-84a7-888ea381d26f |  | note | Inspection / Test Method - Visual Inspection
label | 24afd4fd-52e4-5e8d-9f46-bac6db15d705 |  | note | Record of conformity - This ITP signed off
label | 1ed34e3c-9b03-56be-9217-857bc6aa8553 |  | note | IP
label | 7f400435-a743-5dae-b706-b519aa394c5e |  | note | Responsibility - Site Engineer
date | e0a053c3-5045-5fca-b9de-bfdd99fa74af |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Conformity with drawings
label | 731217c6-5519-58a0-81a8-34f68d180c00 |  | note | Frequency - four weeks prior to installation
label | 92e853bd-e402-5cc8-8453-9ed4d5a6fa8c |  | note | Acceptance Criteria - Witness Point: If the Contractor proposes to use an alternative method of installation, the Contractor shall submit full details to the Superintendent for approval not later than four weeks before the commencement of sign installation
label | 4ea39bf0-4a69-5b1a-9b0d-24e7b22a4e88 |  | note | Reference Documents - Cl 714.04
label | bdf779a9-2265-5e2b-8d8c-d706e7c1e625 |  | note | Inspection / Test Method - Verify
label | cd182341-e37b-5094-be90-c6969dee633b |  | note | Record of conformity - This ITP signed off
label | c8e2f56d-fb65-564f-b9c1-03945d68af86 |  | note | WP
label | 85bdf1d5-be39-57e3-8ef8-a546660e30b6 |  | note | Responsibility - Site Engineer / QAV
date | b5bb8555-c653-508c-81b4-7205c96f4af7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Post & Foundations
label | a88fda95-eccf-54dd-97e7-966dda7e1939 |  | note | Frequency - Prior to Start
label | 17401383-2919-5b97-b71e-414b6f12e2bd |  | note | Acceptance Criteria - Hold Point: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
label | 81de3101-e9f9-5ca8-8bff-8df75fb8ffd8 |  | note | Reference Documents - Cl 714.06
label | d5f7c1eb-247a-5814-8107-11c29560af52 |  | note | Inspection / Test Method - Visual inspection
label | 46e39c15-b38c-5ca9-b512-7e8ba5981cf1 |  | note | Record of conformity - This ITP signed off
label | 7aa08fcd-9159-5622-b8df-0a08e7d1fae4 |  | note | HP
label | bd485284-400b-5eb5-994a-246f669a617c |  | note | Responsibility - Site Engineer / QAV
date | dabb9622-b1b6-5b14-9fef-15da6b2b5241 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4 - Signage Install
label | afd8c2d1-ec3a-535e-bccb-f66c4ea96cff |  | note | Frequency - Each Sign
label | 9a3deb3b-9d9a-553a-bd06-a009a73f3ddb |  | note | Acceptance Criteria - Sign to be installed as per most current project and DSG standard drawings, local council documentation, and to the correct height and position. Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
label | 72bbb890-d4a1-5dd4-81c1-1cb1ebd286ed |  | note | Reference Documents - DSG standard drawings; Drawings
label | 6a411903-a7bb-52df-9248-6fe9ac32fc62 |  | note | Inspection / Test Method - Verify
label | ea4bf4d7-c2f1-567f-8a69-4f6228184162 |  | note | Record of conformity - This ITP signed off
label | a6542190-cba8-536e-aa2a-4e24a013eda6 |  | note | IP
label | 9e36d768-7fd1-511b-8165-be1f9b0175ff |  | note | Responsibility - Site Engineer
date | e40442e9-8d34-5ed4-bd4a-5d226e215b80 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Tolerances
label | 042f0f8d-d6ee-597b-8747-6bc09ef4f6a7 |  | note | Frequency - Each Sign
label | f663c4af-1f6e-5fa5-bfe4-08cf5ce4ba51 |  | note | Acceptance Criteria - Posts vertical with maximum deviation of 1 in 100
label | a16ce87f-423c-5582-8ff0-a36bc1990a13 |  | note | Post tops 50mm +-10mm below top edge of sign
label | b10e94f9-89a0-5fe4-bdf6-3d22a6e104d4 |  | note | Signs mounted level with maximum deviation of 1 in 100
label | a068b4cd-44f8-5100-99e5-19f84e5e3de3 |  | note | #ERROR!
label | 284df17b-4b16-5b78-8d87-0a30ea20d1a6 |  | note | #ERROR!
label | 08e08f8b-123d-5666-b575-ab81398211c0 |  | note | Reference Documents - Cl 714.05, Cl 714.07
label | 855b34dc-b89d-505d-9cd4-24b7f9dd4ad1 |  | note | Inspection / Test Method - Measure
label | f47877a5-8220-53b5-b4ca-d8f887a588fb |  | note | Record of conformity - This ITP signed off
label | 8e85dfb0-3b9b-5f5d-a9e6-d5b96835492d |  | note | IP
label | eee6ec97-4a7c-51f9-a0df-172eab1e7afc |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection - Fulton Hogan
label | ecdd4e03-9832-5dc2-b2d1-5373b1bccc16 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 88119a11-7bf7-5f9d-a505-ee6929a37274 |  | textbox | Print Name:
text | c8502061-0566-517f-8a3b-865abdda935d |  | textbox | Position:
date | 70a3a2d1-cd9d-5031-a8b8-13db32acf7eb |  | date | Work Completed On:
date | 3da354d2-98ee-5c69-81ff-dd79b6704878 |  | date | Date:
checklist-flat |  |  | checklist | CTP-ITP-014 Lime Stabilisation | itp |  |  |  | Yes | CTP-ITP-014 - Lime Stabilisation | 45b3faa6-dd31-4a41-b018-60be4d9cbb13
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 8c05a5c5-619d-5960-a63d-cfc499be31e7 |  | note | Frequency - Prior to commencing any activity
label | 9c6eb282-d53b-5207-9de1-5f52069b7cc7 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are: - using Issued for Construction (IFC) drawings - using the correct and complete set of drawings - all drawings are the latest revision
label | 49c5cc1f-e3b5-5a92-8926-b8c8208fe83d |  | note | Reference Documents - IFC drawings and drawing registers
label | 2d47d246-2eed-5da7-8f3e-f1e18034acc0 |  | note | Inspection / Test Method - Document Review / Visual inspection
label | 748450ed-eb42-5b0a-882b-25120758bf60 |  | note | Record of conformity - This ITP signed
label | b3d7702f-2fe8-54bf-b66e-6a2a86b85664 |  | note | HP*
label | 3665fc21-cd60-5f8a-b63d-f4dac65e6614 |  | note | Responsibility - Site Engineer
date | 0f2ba6c6-fa93-5286-9662-acea66a72236 |  | date | Date Completed:
text | 96de161b-e1ff-5820-b9e5-707db7d83465 |  | textbox | ITP Opened:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 928a1c58-3fe2-5452-87ad-3b5616e71f01 |  | note | Frequency - Prior to commencing any activity
label | 8784c6b1-1d96-55d0-9731-cdd692f72fd3 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: OHSMP, EMP, TMP, SWMS & WP. Access and egress inspected and assessed for stability.
label | 4b074c1f-81e3-5652-85d3-b8c9285d6609 |  | note | Reference Documents - OHSMP, EMP, TMP, SWMS, WP
label | aaca8fb0-94fa-5210-9f99-9bee094a4e8b |  | note | Inspection / Test Method - Visual Inspection
label | e0c932aa-dcba-5974-8e93-99fb07e7c91a |  | note | Record of conformity - This ITP signed
label | 7106a11e-9791-5c7f-92a0-f4b1b2a6a684 |  | note | HP*
label | 56d36d09-da1e-5b0a-b032-02bd9c00af08 |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 1.3 - Lime Stabilisation mix design
label | 68232ccf-f512-50c5-9729-a2eeb2493ce2 |  | note | Frequency - Prior to commencing
label | f5810b47-14c4-5447-92db-fe1a3bcb2ace |  | note | Acceptance Criteria - Hold Point The Contractor shall not commence work until all mix design details including the stabilising binder spreading rates have been presented to the Superintendent for review. If the Contractor is required to determine the Design Distribution Rate of the stabilised binder(s), evidence shall be produced to show that the material properties specified in clause 290.07(a) or clause 290.17(a) as appropriate have been met.
label | 2ef0fb49-76f2-55e0-88b5-5b62408a9316 |  | note | Reference Documents - Cl 290.08 - VicRoads Test Method RC 301.04 - DWG: IA250204-CPT-4000-CR-DRG-4551
label | d1bd1910-e6f6-5682-8cdf-df331aec7a60 |  | note | Inspection / Test Method - Verify
label | e6f58ad1-fcd9-5292-9363-0707d7a7ed53 |  | note | Record of conformity - This ITP signed
label | 08418f63-9d8d-5d27-8e65-66dbb0867344 |  | note | HP
label | 1767cb83-c8b4-5b0c-8f81-58689bb26c44 |  | note | Responsibility - Site Engineer/ QAV
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Survey set-out
label | 84877e0a-12ed-5481-ae7d-997dd1c52095 |  | note | Frequency - Prior to commencing
label | a37d4033-6a68-5102-8efb-e063fe4a40d9 |  | note | Acceptance Criteria - The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. Survey activities undertaken to ensure and validate that all works meet level and location requirements. Verification of conformity with latest IFC drawings.
label | 8dc88b22-dde4-5b24-8c9e-1452995b6671 |  | note | Reference Documents - Section 160, A0113.029
label | 0b9c6198-1e85-55c5-baa4-f03db865a459 |  | note | Inspection / Test Method - Visual Inspection
label | 6d0d506e-34ba-5a06-9c03-458298e56ccf |  | note | Record of conformity - Survey records and pegs on the ground
label | 9c0dd630-e24b-5ab9-aa45-910526614fde |  | note | IP
label | 9d81ce28-6692-5f0f-9be7-df5feeeef7db |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 1.5 - Ground Penetration Permit
label | 0dd013b2-8ac2-59a4-8c8e-82b1e8ef2855 |  | note | Frequency - Each Lot
label | 12a75736-90cb-5d81-8deb-c3ce4822e045 |  | note | Acceptance Criteria - A ground penetration permit must be issued prior to excavation commencing. - Plant and equipment must be appropriate for the task. - Excavation operations shall not disturb areas outside the limit of excavation.
label | b0f58fb6-a00a-5ee9-9324-0900872ff05e |  | note | Reference Documents - Ground Penetration Permit
label | bd8e408f-5cc9-52ba-aa6f-185026b09884 |  | note | Inspection / Test Method - Verify
label | fa49feef-de7d-5479-83a0-a90e2802c74e |  | note | Record of conformity - This ITP signed
label | 921e8436-2174-5122-98e7-2555886667f7 |  | note | IP
label | 0aeb4663-385a-5fd2-b874-1fa247d81945 |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 2.1 - Lime Stabilisation trial
label | 410d1616-3d84-513e-91c1-437832359c6e |  | note | Frequency - Once unless further trials required
label | 31bb9690-49d0-5e1a-ab8d-affdeba24cab |  | note | Acceptance Criteria - Hold Point Stabilisation shall not proceed outside the trial sections until the Superintendent has reviewed all aspects of the work. If the Specification requirements are not met for the trial, the Superintendent may direct that another trial be undertaken or that the work be re-stabilised and presented for re-assessment.
label | 9805b4ee-a3a0-5e4a-a9b2-a2dd40b6e891 |  | note | Reference Documents - Cl 290.11
label | c4c5bb16-7d2c-5743-8784-b18eb5c0f9b5 |  | note | Inspection / Test Method - Verify
label | 5abcddc6-49dc-5f28-a941-105828fefc34 |  | note | Record of conformity - This ITP signed
label | b7670d6b-bf61-5106-8bff-a2dcc618d177 |  | note | HP
label | 2d641708-688f-5b7e-af31-014dc10b6f19 |  | note | Responsibility - Site Engineer / QAV
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Compaction
label | bae4a920-27ca-5aa0-a545-8d18f63988aa |  | note | Frequency - Each Lot
label | 0ca08794-fc7d-5cc5-8ba4-75b6cbb1b381 |  | note | Acceptance Criteria - Compaction of the stabilised layer shall commence immediately after mixing but only after the requirements of clause 290.10(f) or (g) or (h), as appropriate have been met. All compaction shall be completed within the times specified in Table 290.101 after addition of the stabilising binder. If necessary during compaction, the Contractor shall water the material to maintain the moisture content within 80% to 100% of the stabilised material's optimum moisture content.
label | 8e4ca930-a704-5a81-8c6a-cedceb813a91 |  | note | Reference Documents - Cl 290.10 (i) Table 290.101
label | 592d338c-c404-5c7b-9716-cad3e838aacb |  | note | Inspection / Test Method - Visual Inspection
label | 22506d43-6d95-5e22-bcfb-9c857889269a |  | note | Record of conformity - This ITP signed
label | 5f714c61-80e8-5b99-9f9c-8e6156cf6497 |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 2.3 - Maximum Layer thickness
label | 64831075-6110-5cb0-a8d4-693e7b63b604 |  | note | Frequency - Each Lot
label | ca9da897-a570-54e9-9ebd-97f37f17ad4e |  | note | Acceptance Criteria - The maximum compacted layer thickness for any stabilised material shall not exceed 250 mm, unless otherwise approved by the Superintendent
label | 52409901-2498-52ee-a806-7e54f71a4c1b |  | note | Reference Documents - Cl 290.10 (j)
label | e702c141-10e1-5d95-9433-fa0fd010abb7 |  | note | Inspection / Test Method - Verify
label | 93c22a5c-2a30-5ff0-8a13-73eab2511285 |  | note | Record of conformity - This ITP signed, Survey report
label | 6a114657-2f20-5408-ba36-4d14efe88166 |  | note | SCP
label | 06144fd6-7762-53a5-b387-2849811358e6 |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3.1 - Test Rolling
label | c36eb2af-0ff9-548f-8c7f-f7dc5373df99 |  | note | Frequency - Each layer
label | 852ca6af-eb9c-5b04-b8ea-639972b6d0bb |  | note | Acceptance Criteria - All stabilised material shall be test rolled in accordance with Section 173. Any unstable areas detected by test rolling shell be rectified by the Contractor.
label | d50347cf-5eb8-50a0-992d-4d0d4699cddf |  | note | Reference Documents - Cl 173.03 Cl 290.12
label | cdb23598-9996-5dd8-a80b-aa0a774e3b8b |  | note | Inspection / Test Method - Visual Inspection
label | c0d20212-6b99-574e-a851-ec63423a213d |  | note | Record of conformity - This ITP signed
label | e16a7ee6-088e-54f5-a49e-d46323c1bd29 |  | note | HP
label | 4ac1d9a4-447a-5b2c-bd55-38ed28ea8bb7 |  | note | Responsibility - Site Engineer / QAV
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Density testing
label | 46b3ae72-17f4-518b-8a0e-5f29308cec5d |  | note | Frequency - Every lot initially, and shall continue until three consecutive lots of like material or work have achieved the specified standard when tested for the first time as per Cl 290.15
label | 05d54710-6c9d-5b04-a1bc-29f573ff55f1 |  | note | Acceptance Criteria - For stabilised earthworks incorporating lime only, density testing shall be undertaken within 24 hours after completion of compaction. Lime stabilised material shall be compacted to comply with the requirements of Table 290.141. - Scale A - 99% - Scale B 98% - Scale C - Acceptance of work will be based upon on compaction plant to be used, compaction routine and a density monitoring procedure using a nuclear gauge (with three tests per lot to have a minimum mean value of 98.0%) and proof rolling as specified or agreed between the Superintendent and the Contractor.
label | 0dd9fe8c-feb5-5a64-8235-1a9a26f062d1 |  | note | Reference Documents - Cl 290.14 (b) Table 290.141
label | c34c2d49-3602-5702-a043-fba9a885aa8e |  | note | Inspection / Test Method - Verify
label | 16cb5965-368c-5a22-832d-433693ffdae3 |  | note | Record of conformity - This ITP signed, Test reports
label | 4eed9182-a801-5561-83e7-c6563535decc |  | note | TP
label | d16e2666-ea28-5a1a-bc60-31d00d48ca5e |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3.3 - Lime Stabilisation testing
label | 68e00371-74f3-5b6d-bf31-77fd99ff7c36 |  | note | Frequency - As specified in Table 290.151
label | a8b0ff66-1da9-5613-8af3-8e8e172c3b96 |  | note | Acceptance Criteria - Testing of the following undertaken at frequency specified in Table 290.151: - ALI (require minimum 80%) - Uniformity of mixing - Uniformity of spreading rate - Average spreading rate for stabilising binder - Characteristic Density Ratio (require minimum 98%) - CBR of stabilised material
label | 350c132a-6af2-530c-903a-7fb03be48605 |  | note | Reference Documents - Cl 290.15 Table 290.151
label | 36237b3c-fd25-568b-aa38-23cd05d83509 |  | note | Inspection / Test Method - Verify
label | 3d160395-b6fc-5bcf-a6d3-4d8b7f33cab2 |  | note | Record of conformity - This ITP signed,Test reports
label | 953b812f-83d5-51d1-a3d2-059cbd53d4e3 |  | note | TP
label | 0a125693-e870-57ec-b91e-99959a5bde0a |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Curing and Protection of Compacted Layers
label | 15d8171e-c084-5a8e-913e-33644f43cdde |  | note | Frequency - Each Lot
label | b23f1b97-7a24-5778-8789-9086f29e8be2 |  | note | Acceptance Criteria - The surface of the compacted layer shall be kept continually moist, and free from contamination until the succeeding layer is placed.
label | 69d0e083-6c1c-5cc5-97a9-7775e6bcc969 |  | note | Reference Documents - Cl 290.16
label | 8c3f17fd-166c-51e4-9a12-2907e0478f9f |  | note | Inspection / Test Method - Verify
label | 0c3ef373-3255-59ee-8158-64c4597ce998 |  | note | Record of conformity - This ITP signed
label | cd1cb4bf-6697-5347-93f4-c69334be7564 |  | note | TP
label | bdd074ee-b8b4-50b1-ad25-5e0ca63b45cd |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection - Gradco
label | 58389fca-f92d-5c44-80c8-bba90b3ceec7 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | fb7ec551-ef57-5a06-8f29-f350eb1ef1e5 |  | textbox | Name:
text | 98a2d852-7526-512f-80b5-5a4521bdc139 |  | textbox | Position:
date | c2ace560-5807-5f1c-93ba-793f03c7dbc4 |  | date | Date Completed:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Final Inspection - Fulton Hogan
label | bcb246fc-00dc-5eaa-833f-f33a827b9046 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 5dff8a87-bc82-51f0-930f-152f4f4ef044 |  | textbox | Name:
text | 7d3086c2-f1df-54f1-a57b-8561684cb06e |  | textbox | Position:
date | c4a8b63c-4a20-587d-9648-ab13aa93ea2c |  | date | Date Completed:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | CTN-ITP - Spray Sealing Operation | itp |  |  |  | Yes | CTN-ITP - Spray Sealing Operation | 48a2bf3c-5ce9-4cf4-b685-62f9a846972d
checkpoint-status |  |  | checkpoint | 1.1 - Binder
label | 3d44b88b-2c3e-5f63-853b-e9e0572f9bac |  | note | Frequency - Delivery Docket upon request
label | 9d84e53b-6429-5fab-92d7-b6e0f803c8ce |  | note | Acceptance Criteria - Verify binder being used matches that specified on the job pack
label | 7b2cd62e-46d5-5d22-9e65-9047ec164e27 |  | note | Reference Documents/Clause - 408.08
label | 3af43e61-1aaa-5cdd-9f00-70959ba5abcc |  | note | Inspection / Test Method - Verify
label | 4db459a9-691f-5945-8ec9-785b3d98e595 |  | note | Conformance Record - This ITP signed off & Delivery Docket
label | 3f8067d1-d3fb-5ed6-97f4-19432e5259ca |  | note | IP
label | 6b399cd7-944d-584f-b5f2-86de0e303109 |  | note | Responsibility - Spray Seal Supervisor
text | a7c51a37-963e-56c6-ac27-c7e65cd4fe30 |  | textbox | ITP Opened:
date | 6e6b74f2-3e13-5f19-a785-3fa8f34f4665 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Aggregate Specification
label | 4d3288cf-20e7-511d-9fe0-c5e5aecfad19 |  | note | Frequency - Delivery Docket & Maximum lot size 350t of same class and size
label | e442c038-70b5-595c-a1cd-94d011b3585e |  | note | Acceptance Criteria - VicRoads Standard Specification Sections:
label | 94b2e89e-d6a6-54c3-9a44-ce5ca369a819 |  | note | • 801 - Source Rock;
label | efb5af52-9dde-5147-98ca-325a765b5b8c |  | note | • 831 – Aggregate; and
label | 45307df5-c0f4-5b46-8b91-ea502e964cd9 |  | note | • 832 - Sands
label | 2dbd8c1d-ef24-5418-b911-c156be4e4531 |  | note | Reference Documents/Clause - 408.11 (a)
label | b9e15901-ea99-51e0-8219-0a53d65dfd05 |  | note | Inspection / Test Method - Verify
label | e5e9d8df-094b-570e-9d4a-0944e4e33d25 |  | note | Conformance Record - This ITP signed off & Delivery Docket
label | f62d2dec-50cc-513f-b70d-2b94698cdf9a |  | note | HP/C
label | e050f75c-1023-5521-9c7e-d9a2f85966e8 |  | note | Responsibility - Spray Seal Engineer
date | f43b4283-363a-5e17-ab9c-7c1d10ad7f6d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Aggregate Precoating Materials
label | 82ee5ef9-a517-51b5-aec0-7d1cad4cb411 |  | note | Frequency - All works carried out & Delivery Docket upon request
label | 68702d76-d331-5ed4-ba23-308e9455a54f |  | note | Acceptance Criteria - Distillate based product, cutback bitumen, emulsion based product or proprietary product.
label | f1d815cd-036d-51e8-82b4-3dc6ed02f5ed |  | note | • Supply plant pre-coated aggregate from supplier or field pre-coated aggregate from stack site
label | 80a03414-2b6b-5dc7-9ea8-45481f69729e |  | note | Reference Documents/Clause - 408.09 (b) 408.11 (b)
label | de999048-c8e9-572e-bfbd-5a5ac87a116c |  | note | Inspection / Test Method - Verify
label | 116e5663-b2be-5258-9fec-29b923936e83 |  | note | Conformance Record - This ITP signed off & Delivery Docket
label | 8cdd9180-8137-542e-afb6-3fee2ad67b71 |  | note | IP
label | 840dfa01-a00a-5678-8cfd-f7afd1dfd66b |  | note | Responsibility - Spray Seal Engineer/Supervisor
date | d7169ca3-f645-57f7-b288-65401d53de91 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Rates of Application
label | e498104c-69e4-5660-aaa9-61692abdaba3 |  | note | Frequency - All works carried out
label | 5eb6d305-27c4-5b22-97d0-2153f6840de7 |  | note | Acceptance Criteria - The Contractor shall determine the rates of application in accordance with the procedures set out in the Guide to Pavement Technology: Part 4K.
label | 6416390b-6d9e-5f1a-86c1-7f3c48036a98 |  | note | • Rates shall be expressed in L/m2 and residual binder at 15°C.
label | a53ace55-b420-5d81-a6bf-3075f12fa2c1 |  | note | • At least 1 week prior, rates of application, aggregate and rates for pre-treatment to be reviewed by Superintendent.
label | 31339172-7c21-5adb-ae52-cadf1032a7cc |  | note | Reference Documents/Clause - 408.13 (a)
label | 6662aa8a-978e-529d-821b-b2ea90a2533f |  | note | Inspection / Test Method - Verify
label | 226fa38c-822f-59d2-b719-a6dfa0a37d85 |  | note | Conformance Record - This ITP signed off & Rate of Application for Residual Binder at 15°C
label | 211b88a8-7f02-5f04-92dd-922b61fbcc7b |  | note | HP/S
label | fa0a9cc0-b723-5eaf-ab02-20c5127089ed |  | note | Responsibility - Spray Seal Engineer
date | fe3df5a4-5941-55de-82e3-811260d0f3a4 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Calibration of Bitumen Sprayer
label | 10c06400-e54e-5a0a-8aad-928e71747e4b |  | note | Frequency - Prior to commencing works
label | 23f83bba-c106-5c04-81fb-92b157606124 |  | note | Acceptance Criteria - Calibration Certificate to be provided
label | 4f477b49-76f0-5e10-92ef-05dffad297b4 |  | note | Reference Documents/Clause - 408.07
label | 4aa5b4b0-d5e7-55a6-874d-206fe98c913d |  | note | Inspection / Test Method - Verify
label | c6d56533-51dc-5017-a01c-4ad6428c6d28 |  | note | Conformance Record - This ITP signed off & Compliance Certificate
label | ab418552-2332-50d9-93bb-f8c7f70478e8 |  | note | WP
label | d7c12842-45c5-5924-80c5-c7f1da3f04dc |  | note | Responsibility - Spray Seal Engineer/Supervisor
date | 9f2a4e6d-e9ea-573a-b0a1-35c39f7c7d59 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Commencement of works
label | d2aa28df-de03-58a3-8783-a86e545fd9dc |  | note | Frequency - Prior to commencing works
label | 9d18b2bc-4048-56e4-8f8a-af97be9c403b |  | note | Acceptance Criteria - Prior to the works being carried out, the Contractor shall provide written confirmation of the works that will be undertaken the following day and obtain agreement from the Superintendent to any variation in the rates of application to those provided under Cl. 408.13(a)
label | 2a30f3f4-88b2-5900-ab57-99b95260f231 |  | note | • Works shall not commence until the Contractor & Superintendent have agreed that the road or pavement surface is fit & ready for surfacing no more than 24 hours prior to the works occurring
label | 28c077a6-2e2c-5185-b704-71c449b596e4 |  | note | • DSG Specification Section 310 – Preparation of Granular Pavement for Bituminous Surfacing shall be satisfied for initial seals
label | 25ba4aef-e1c8-58e2-87d5-4f85a30f7ccc |  | note | Reference Documents/Clause - 408.04 (b)
label | ab6abed4-0d52-5d15-a2ba-0ea3a70bb68d |  | note | Inspection / Test Method - Verify
label | 4c5e7da9-ebd0-5b0f-a2a4-37e1f6ae5fd6 |  | note | Conformance Record - This ITP signed off
label | 4a2fedf8-e1cb-5499-a79f-5cf7ddb8704b |  | note | HP/S
label | 094ec53c-e41a-5c7f-b4dd-d4dcd5198e19 |  | note | Responsibility - Spray Seal Engineer/Supervisor
date | dbb530c9-2e07-5b0e-9d57-b6d55c10a947 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Minimum Temperature
label | a59a64a0-b923-5375-8bfe-f3b474a4ed78 |  | note | Frequency - Prior to commencing works
label | 0d9bb798-190a-5e04-afb0-e7ca0b80e691 |  | note | Acceptance Criteria - Minimum Temperature to meet criteria as set out in Table 408.131
label | bd116ae8-e72b-507f-94f3-e9ca8f373852 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 55c5d271-008f-5ae2-a586-3be840e07ebc |  | note | Treatment Type ¦¦ Min. air & pavement Temp. (°C)
label | 6f095a47-39f3-5a34-9e66-d68fc295de54 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | f6d04135-d0c8-5125-aa30-867678d83383 |  | note | Primes ¦¦ 10
label | dff33165-26b5-5596-b2ea-1cd8381f3d00 |  | note | Initial seals (single/single) ¦¦ 15
label | 005df393-0623-5b0d-bea9-aa3136201e9f |  | note | Initial seals (double/double) ¦¦ 10
label | b008413e-d788-5c20-a21d-22fbae961f32 |  | note | C170 and crumb rubber modified PMBs ¦¦ 15
label | c6eb76b2-7d44-552f-9d52-34db4ca434b1 |  | note | Other PMBs ¦¦ 20
label | 9640a3f0-8d32-58b2-9541-6328f8a27d8f |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 874dbb8f-912b-5aaf-875c-923147ec1915 |  | note | Reference Documents/Clause - 408.13 (d)
label | 89ca700e-d6a3-5d8e-b727-36bac5b7bc99 |  | note | Inspection / Test Method - Verify
label | 2d3dcd12-8d54-5611-a2ab-0730fd467af2 |  | note | Conformance Record - This ITP signed off & Temperature Check
label | 7fa98eac-c25f-5bc1-b7aa-b0b6009e82cc |  | note | IP
label | 9f3810bb-a02f-566b-be48-4e18e19411f3 |  | note | Responsibility - Spray Seal Supervisor
date | 2866e035-f850-5ab3-9889-8816c4e4331b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Spraying Binder
label | 13f87ff9-0ec9-5c35-852d-cbf94f2efd8d |  | note | Frequency - Each Run
label | 648acef0-85d5-5063-a2c1-794f75437817 |  | note | Acceptance Criteria - Complete spray sheet
label | 53d35e7c-991d-5da7-86e8-1d8d85078325 |  | note | Inspection / Test Method - Dip sprayer after each run
label | 00bc4a08-3518-542b-917c-d17929edf0a2 |  | note | IP
label | 44b40c43-b3a8-554d-b568-7b85ee50a6ae |  | note | Responsibility - Sprayer Operator
date | 5088dc05-3453-5160-a311-6c2c34591ec8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 - Spreading aggregate
label | 921cbcf3-e53a-5fe2-b904-03c1f7e9dd90 |  | note | Frequency - Each load
label | 372116b6-1706-5381-a738-9c2a27dbcf29 |  | note | Acceptance Criteria - Complete spray sheet
label | 2c2f4d98-a521-56f4-9447-0d242494063d |  | note | Inspection / Test Method - Measure spread of aggregate
label | 65759f49-4d8a-5f20-919c-758ba11fe026 |  | note | IP
label | c9e39f68-643a-5197-a32f-8f97a9c7fa8b |  | note | Responsibility - Supervisor
date | 5c2cc442-a994-564a-8c28-2c869632db46 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 - Removal of loose aggregate
label | 37a720f1-8961-562e-8360-e4115200244d |  | note | Frequency - All works carried out
label | 982e1f45-280b-57f5-a6ea-65dd9bdd0320 |  | note | Acceptance Criteria -
label | b10749be-5aee-56f5-99bc-0f098bfd9cd3 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | a19e1acc-bee1-544e-ba26-6a3ef2a5693f |  | note | (AADT) ¦¦ Max. Time Limit
label | 5912d894-bd17-57e9-940d-d2b209285f14 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | a34d8bae-b9a6-5c6a-8eff-e8008c475cb5 |  | note | >5000 and all Freeways ¦¦ Within 8 hours of sealing
label | 5646cc63-7f3c-510e-82fa-a3d6dd741a28 |  | note | >2000 to 5000 ¦¦ Within 24 hours of sealing
label | c564bf50-88bb-535b-9c2c-1f224dcf84e3 |  | note | >500 to 2000 ¦¦ Within 48 hours of sealing
label | e21a81d1-5668-54de-8c79-b4f9e025302b |  | note | <500 ¦¦ Within 5 days of sealing
label | e95b852a-3a3b-51ca-a652-e73c3984f954 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 4d4c9989-18af-5364-a244-9d0af6287dec |  | note | Reference Documents/Clause - 408.14
label | f1ed3073-70fd-52ca-b630-be15e6631999 |  | note | Inspection / Test Method - Verify
label | cc3dd632-4425-5826-a662-64cec4838ef2 |  | note | Conformance Record - This ITP signed off
label | cf734a3e-368c-5939-987c-4b216d51dbc0 |  | note | IP
label | 61311597-d8dc-5f93-849e-0a195ac4ac56 |  | note | Responsibility - Spray Seal Supervisor
date | 9e0903f6-e99c-5b47-be3e-f9d182950fc4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 - Records
label | 7521ee80-9431-5f6a-9f88-47b4f0e45b9e |  | note | Frequency - Each Lot
label | 5c7d6635-33a7-5ceb-b131-2d76f739a6ff |  | note | Acceptance Criteria - Job completion report (Spray Sheets) to be submitted within seven days of completion of sealing works.
label | ee7bdff6-b7b7-5436-b4b5-c4e91b9560e0 |  | note | Reference Documents/Clause - 408.17
label | 7573f906-7421-5f16-b6f8-7d2914e571f8 |  | note | Inspection / Test Method - Verify
label | 93a6d5dc-fec6-5e41-ba3d-2f91c63cfe45 |  | note | Conformance Record - Spray Sheet Record
label | 0d081adc-8926-5209-b5ed-736be9041496 |  | note | WP
label | 44c14892-e6b1-5ec0-9b6d-72241da81812 |  | note | Responsibility - Spray Seal Engineer
date | bb9da838-6896-5069-bd0b-21eee315ed6c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Acceptance of work- Binder rates
label | 631f2685-d2ce-5ea6-ba86-54662beededc |  | note | Frequency - Each Lot
label | 4e00ac0b-0e0a-5ff4-b756-1777a5233f63 |  | note | Acceptance Criteria - Actual vs design rates. Variation between actual & design assessed by Table 408.131
label | 5b2ab117-41c4-5953-b27d-0c4850c02eb6 |  | note | Reference Documents/Clause - 408.15 (a)
label | 8050e588-8f16-5842-815c-c8fe969b958e |  | note | Inspection / Test Method - Verify
label | e8ecb2b1-a586-52a6-ba89-b9387cb0b6c6 |  | note | Conformance Record - Spray Sheet Record
label | 30b6cc72-d95f-5019-abca-4f3cb5db38c2 |  | note | IP
label | e73beadc-f7ed-5c62-8818-0de44f79008a |  | note | Responsibility - Spray Seal Engineer
date | f68b9a4f-b62e-5818-9efe-07a9e603752a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Acceptance of work - Surface Texture
label | b9b732db-bf1e-55c5-bcd6-aa319cbd62f8 |  | note | Frequency - Each Lot
label | 91eced93-283d-5782-9c2f-ffaa4258d741 |  | note | Acceptance Criteria - Acceptance - visual assessment or (where required) as per Table 408.152
label | 5145f55f-1ccd-554f-b95f-adcd40edf5f5 |  | note | Reference Documents/Clause - 408.15 (b)
label | c72108e8-6744-5253-80ed-ca98da688083 |  | note | Inspection / Test Method - Verify
label | 2c8c2f22-716a-54ec-9f40-1e81bf9ab9e6 |  | note | Conformance Record - This ITP signed off
label | 31fdb46c-271e-5fb2-a8bc-8ec80e45a1e0 |  | note | IP
label | 6caa8b83-fbb9-5ebb-b690-565560abcd08 |  | note | Responsibility - Spray Seal Supervisor
date | 5e5de28d-aeda-5f37-a44b-3d93c34b734f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Acceptance of work - Aggregate retention
label | 663f03b2-8b69-5277-85b1-9443b4ae646a |  | note | Frequency - Each Lot
label | 4a251d94-c4c2-523b-973f-b097c6fe344f |  | note | Acceptance Criteria - Acceptance - visual assessment or (where required) as per Table 408.153
label | f1631f5e-9fb3-5727-9b11-6f1f11bc7939 |  | note | Reference Documents/Clause - 408.15 (c)
label | 12077f8b-1504-5f44-a1b0-abe699a27cdd |  | note | Inspection / Test Method - Verify
label | 608ecf26-f4bc-5f9f-80cb-087188726070 |  | note | Conformance Record - This ITP signed off
label | 2e0a1990-ecb7-513c-9b4a-53b96c0e630b |  | note | IP
label | 34064398-d2c2-502c-833f-65ec48ca237d |  | note | Responsibility - Spray Seal Supervisor
date | 7b2e8515-4d05-5f4f-a96a-4c5a3bdd0962 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Acceptance of work - Visual Uniformity
label | 98caa0f9-b34d-5c2b-a0c3-7a2ee66da308 |  | note | Frequency - Each Lot
label | b793513f-4127-5cc2-90c7-8efed36309fa |  | note | Acceptance Criteria - Provide a surface with uniform colour, texture and consistent appearance
label | 7923a572-254c-5fa4-b7af-20b0a32058f5 |  | note | Reference Documents/Clause - 408.15 (d)
label | a27a9766-93a0-5b6f-a074-f4fbfa4c5bee |  | note | Inspection / Test Method - Verify
label | e4e54615-d903-580e-b237-84dc5e47d8c5 |  | note | Conformance Record - This ITP signed off
label | f014cd53-b2ba-59cd-8462-99e2980716e6 |  | note | IP
label | d6f7ab62-e157-59d1-8866-c875b3fcc299 |  | note | Responsibility - Spray Seal Supervisor
date | 3a53e7bf-d04b-59f9-80b1-f27914214c5f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection - Fulton Hogan
label | 5e86cf6d-503e-5e7b-a0ac-746441c6086e |  | note | This is to verify that the final inspection has been carried out in accordance with the FH’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
text | 001e71e6-f2a4-50a4-b929-d57988551763 |  | textbox | Print Name:
text | 3a9dbeaf-97a6-517e-a4e2-69a5b026f135 |  | textbox | Position:
date | 4ac62454-84aa-5712-9da0-cc0801b344cb |  | date | Work Completed On:
date | 07575be5-2ce7-5fe4-8a02-4f2dc741450b |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-015 - Rejuvenation Treatment of Existing Pavement | itp |  |  |  | Yes | CTN-ITP-015 - Rejuvenation Treatment of Existing Pavement | 58efbf37-bc67-41a4-9829-7570a86cdd4a
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | a96eb6e6-bfc3-5754-bc49-f2be3be33552 |  | note | Frequency - Prior to commencing any activity
label | 37b73659-a640-57f1-bdfd-268ebf5493fd |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | ffea279c-31b1-54e6-a232-9fb19fe6dea4 |  | note | – using the correct and complete set of drawings
label | 2d3ba561-8cc4-51be-9925-932c266b1e64 |  | note | – all drawings are the latest revision
label | 69b6e58d-69ed-5dee-91a5-7a33ec37e39b |  | note | Reference Documents - Drawings and drawing registers
label | 0cd6d8f3-edad-5f84-8152-cac8195cfa7b |  | note | Inspection / Test Method - Visual inspection
label | 0b7b67da-ecaa-54f2-969e-d7bf3c50e6f0 |  | note | Record of conformity - This ITP signed
label | c815807f-78f5-5573-9219-ea23efd2c68e |  | note | HP*
label | 546179fe-7886-54e9-af4a-a9bcaa67b78c |  | note | Responsibility - Site Engineer
text | 8f9a62ff-66f6-5004-9b70-d9484ea9eab3 |  | textbox | ITP Opened:
date | f3e9514b-8918-547c-a40e-9ec740887420 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Preliminary Rejuvenation Trial
label | 40362a5d-121b-5e64-966e-0374c6317938 |  | note | Frequency - Prior to commencing works
label | 2acabdb9-dd8b-5fce-b172-36c9e0e449af |  | note | Acceptance Criteria - Hold Point:
label | b86ac944-23b0-5caf-bcbb-ec39a27c9899 |  | note | The Contractor shall carry out a prelim inary trial of the proposed rejuvenation operation. The trial shall determine the:
label | b8b10041-6154-54c0-b3cc-4459b420ac22 |  | note | (a) effectiveness of the construction plant;
label | d98c7a4b-7aad-5757-91fb-fa1e8251fcf7 |  | note | (b) number of passes of the stabilisation machine necessary to achieve uniform pulverisation and mixing;
label | 2663a31d-24f8-52fe-9c22-bac24b06c858 |  | note | (c) field moisture content required to achieve the specified compaction requirements;
label | e7f15904-b386-5a24-85f6-3406c9559582 |  | note | (d) rolling routine required to meet the specified compaction requirements;
label | 74fa771e-ba36-51a0-8db4-3d546bccf0b2 |  | note | (e) uniformity of mixing six random test holes.
label | 578ce623-0a9e-57af-b353-9d6cea3e6108 |  | note | Reference Documents - Section 160.40C
label | 86548958-78de-5d26-95fb-aa2f6fb05e22 |  | note | Inspection / Test Method - Document Review
label | 13e84b35-50fe-52a4-a0f0-df46dcaf8ca0 |  | note | Record of conformity - This ITP signed
label | 39fee91f-5d74-55af-870d-76783254cc65 |  | note | AP
label | 501a3f83-8e5f-537a-87b9-553432e9da1e |  | note | Responsibility - Site Engineer / QAV
date | accea373-06d5-5f61-9283-dd5bdad28367 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Implementation of all measures and controls
label | 36b0d4dc-7444-5ba9-ab37-bddb73c01bd5 |  | note | Frequency - Prior to commencing works
label | 082f69e8-9ace-5f73-85ab-ce2df7aac2b5 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP`
label | 26e918ae-8286-5e70-a6eb-c90b663f36d0 |  | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | 5d34bb1e-f8db-5afc-be74-4092f3bfca2d |  | note | Inspection / Test Method - Visual Inspection
label | 5d83e47f-0c3e-53a1-8e99-12c65b1072b0 |  | note | Record of conformity - This ITP signed
label | 8f1af65e-9792-52c8-b337-61496d1c96c6 |  | note | HP*
label | 5adccce5-eb8c-5753-b2b4-ebfde87d4cb1 |  | note | Responsibility - Site Engineer
date | be2cba6c-1c50-531d-a32f-e3810a70e139 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Plant and Equipment
label | 3a806ec8-816e-5fb6-a0cf-181a994be310 |  | note | Frequency - Prior to commencing works
label | c2849b90-74a2-573f-a339-6b43f17be449 |  | note | Acceptance Criteria - A purpose built mixing machine designed for in-situ stabilisation of roadworks shall be used to pulverise the existing pavement material and uniformly. Rotary hoes and other types of agricultural machinery shall not be used.
label | 9adf8ef8-1571-5092-961f-4d5f85168595 |  | note | Reference Documents - Section 160.40C
label | 0c6968ee-c09b-5231-bb07-1ef319b962d5 |  | note | Inspection / Test Method - Visual Inspection
label | b1e9d100-8510-5194-b0a7-450557462c71 |  | note | Record of conformity - This ITP signed
label | caae5f89-d7c9-5d9f-b05d-6a2817b2d2d6 |  | note | IP
label | d975d362-8b49-5743-95f7-b679598a402a |  | note | Responsibility - Site Engineer
date | 0bc67c68-04de-5c62-abb2-1b36f1016cfb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Asphalt Removal
label | ba46ca80-81bc-5b1f-8a0b-501032272e97 |  | note | Frequency - Prior to Rejuvenation
label | cb7af551-25f5-5f6a-b772-d455ef6ea89c |  | note | Acceptance Criteria - Prior to base rejuvenation, the existing pavement is to be inspected for existing asphalt patches greater than 1m2, which are to be removed prior to stablisation / blending.
label | 7ab76297-d04d-5434-98e5-5b030fcb24c9 |  | note | • Where asphalt patches are removed, the existing subbase is to be inspected and subject to a test roll in accordance with DSG specification Section 173.03.
label | 961e973c-f306-523d-b557-1ab6cd021ea8 |  | note | • If the exposed subbase comprises of unsuitable material, or fails the test roll, then the subbase is subject to a 200mm deep granular patch using class 3 crushed rock (or better).
label | 7acc5b94-e9fb-5294-8bec-789ee93e5515 |  | note | Reference Documents - Drawings
label | 5ef4864a-1441-58dd-9adf-314ff70a34b1 |  | note | Inspection / Test Method - Verify
label | c364064e-4868-5e9a-9f9b-6a9e9151076a |  | note | Record of conformity - This ITP signed
label | 744b1147-da58-5823-b8df-48744b6a73d5 |  | note | IP
label | f33ff214-d437-58d8-a26d-0e80338c121d |  | note | Responsibility - Site Engineer
date | 42f09df4-8c0b-513d-9e3d-37516ddd1adf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Water Delivery
label | 8f5309f0-430e-572f-986c-401e19cc2da6 |  | note | Frequency - Each lot
label | c0b45606-8aa6-565b-ace7-1645dc75515d |  | note | Acceptance Criteria - Water is to be introduced into the pavement via the attachment on the reclaimer after the first pass. The trial section used 200L/min at a speed of 12m/min to achieve satisfactory moisture content and compaction.
label | 9c2f395a-178c-52bb-b5c3-8c88d6cf1440 |  | note | Reference Documents - Trial
label | 66921bf9-45de-5970-be40-b4ed0705d46b |  | note | Inspection / Test Method - Verify
label | d785e880-f9c4-5d17-a8dc-ebffb7350e60 |  | note | Record of conformity - This ITP signed
label | 66fb5d5f-9ca5-563d-9451-aff12249f211 |  | note | IP
label | 8897a033-aea5-527b-8b50-7e868abcd1c3 |  | note | Responsibility - Site Engineer
date | 75fda3f6-14e6-525d-a8cc-57f41c1594dd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Layer Thickness
label | 22972416-76ce-541a-8fb3-07ef96c25298 |  | note | Frequency - Each layer
label | 117208e8-62b3-5a12-ae3b-4b55bd26c03b |  | note | Acceptance Criteria - Base rejuvenation is to consist of the insitu stabilisation/blending of the top 150mm of existing pavement, including the pulverisation and incorporation of the existing seal.
label | 057fa405-4807-5355-be9b-bf2173b8a2c8 |  | note | • No cementitious binders or additives are to be incorporated.
label | e2f6efab-caa9-5dd2-9e56-403114c5dd6f |  | note | • After stabilisation/ blending has been completed, the material is to be inspected for oversized material (>40mm) or chunks of the existing seal which have not been adequately pulverised.
label | be9956e4-1baf-5679-9c71-94351d398cf5 |  | note | • Oversize material and chunks of unpulverised seal are to be removed or reprocessed as necessary.
label | 4cc8f7a6-6504-587b-b148-16dcd91a7f5d |  | note | Reference Documents - Drawings
label | 64d35ef6-214d-5594-b623-c0593b3e8754 |  | note | Inspection / Test Method - Visual and Measure
label | 217b344a-5c0d-52fa-a737-59aea74271f9 |  | note | Record of conformity - This ITP signed
label | 7e605bdc-313d-536d-8ae0-fb01a5901b0e |  | note | IP
label | 5e219cae-0d0b-5027-9906-c76c2022eaeb |  | note | Responsibility - Site Engineer
date | 973805d8-a5d1-55ea-a7b1-65a470b54f19 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Conformity with Drawing
label | c53eb7ad-4955-57ef-b333-a763e65bcec6 |  | note | Frequency - Each lot
label | 8d1a36bb-4377-5707-b667-bad76cc07a5d |  | note | Acceptance Criteria - All pavement courses shall, after compaction, be finished to smooth and uniform surfaces, free of segregated areas, and conform ing to the limits for level, line, grade, thickness and cross section shown on the drawings or as specified.
label | 78feaa9e-c827-5f29-9d31-708b2f437029 |  | note | Reference Documents - 304.06
label | fd5f31a2-cb34-5557-b08b-695fa6a33fa3 |  | note | Inspection / Test Method - Verify
label | cc47c49a-bb3a-5c48-b3b2-6a3d5802a8a4 |  | note | Record of conformity - This ITP signed
label | 22f74e05-bc32-5041-9b01-2ad532205670 |  | note | IP
label | fe4b72f8-4cee-5d06-b263-70fd1189becb |  | note | Responsibility - Site Engineer
date | 84dd2af5-9acf-5173-b424-2735cb19fb4d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Maintenance of Compacted Layers
label | d5035daa-e9dd-53fe-8efc-8c749933e03d |  | note | Frequency - Each lot
label | 0ad8e941-d5fe-5927-8974-ea7389cb3305 |  | note | Acceptance Criteria - The surface of any compacted pavement layer or prepared subgrade shall be maintained in such a way as to minimise dust, prevent ravelling, erosion, deformation or any other damage to the layer resulting from environmental conditions, traffic or construction activities.
label | 758d73f0-ee93-5211-aff0-b58b1f03632a |  | note | • The layer shall be kept free from contamination until any subsequent pavement work under the Contract is commenced or the Superintendent accepts and takes responsibility for that part of the Works.
label | 35e72369-ac14-5abe-ab45-17b871f4246f |  | note | Reference Documents - 304.09
label | 9790636e-9335-54bc-bd9e-5f6ede7f5a13 |  | note | Inspection / Test Method - Visual Inspection
label | 00406e9b-7b70-50cd-9710-33288c7bf33a |  | note | Record of conformity - This ITP signed
label | e2d8b7ac-e68d-56d5-8bbb-cda498374319 |  | note | IP
label | 7f1899ea-6d4c-5b8c-91e9-23ab4b5ec824 |  | note | Responsibility - Site Engineer
date | 8a3a5f9a-49e0-5c57-bd19-8157a35db575 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | a08ef2ba-9b75-53e0-81be-e02dd608e376 |  | note | Frequency - Prior to Testing
label | 23d4cb29-bb39-5c2e-84e8-7b8a4f8f3317 |  | note | Acceptance Criteria - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
label | 6a0272da-b688-51a7-ba84-865c8480f07b |  | note | Reference Documents - Table 204.161 304.08 (a) 304.11 (b) 304.11 (c)(i) Table 304.111
label | 75376183-a58f-5e17-8f69-b9c9386c61ab |  | note | Inspection / Test Method - Document Review/ Site Inspection
label | 77ef41ac-ed6e-5018-be3b-e432af815f4d |  | note | Record of conformity - This ITP signed
label | ac643b7e-ee1b-5516-bb0f-16fc57dbb668 |  | note | AP
label | 8bf6f72d-4662-5976-b43a-337de3344f51 |  | note | Responsibility - Site Engineer
date | aae762a5-f39d-5854-a619-5ecb8745e7fb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Test Rolling
label | d572232b-7be6-52e2-a0a7-7353f11e6b6b |  | note | Frequency - Each lot
label | 050480fb-5cd0-5689-8c68-fce0c7f53253 |  | note | Acceptance Criteria - Hold Point:
label | 54aaed8b-ce45-5e24-9d21-e5f1743377b4 |  | note | • All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173, prior to acceptance of the layer.
label | d5af97d4-f506-5b4e-bc46-e1c7ae713409 |  | note | Reference Documents - 304.08
label | 25338001-2722-56db-8832-b35e455383ef |  | note | Inspection / Test Method - Test Roll
label | 4882fd63-a8fa-54ad-9a09-f55f01636216 |  | note | Record of conformity - This ITP signed
label | 5fe33e7d-c143-5239-a470-7c3f829262cc |  | note | HP
label | 2e9bb777-d144-51f7-b92d-23ea603fdf12 |  | note | Responsibility - Site Engineer / QAV
date | 7b1ffd6a-c94a-5f73-9cfa-e0ecbb773f48 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Compaction Testing
label | fd18d10c-b4aa-5731-ac52-251aa1cc0c07 |  | note | Frequency - Every Lot, Every second lot (reduced frequency)
label | 17d13f20-3349-5a83-ac90-b8957129801e |  | note | Acceptance Criteria - The calculation of density ratio shall be based on tests performed using Modified compactive effort. The work shall be completed in accordance with Scale A requirements for testing of the upper subbase layer (98% Modified). Minimum testing for compaction is to be completed once every two lots.
label | 8096aea9-1d90-55d6-8fe7-09fc49485260 |  | note | – – – – – – – – – – – – – – – – – – – – – – –
label | d9a08122-e478-597c-8db0-9290c32fa486 |  | note | Characteristic Density Ratio % (six tests)
label | b97e5f74-c9a3-568f-b87c-b3d6185fbd30 |  | note | – – – – – – – – – – – – – – – – – – – – – – –
label | 20b7eadb-0f64-58ac-a631-23425eabce0e |  | note | Compaction Scale ¦¦ Lower Subbase Layers ¦¦ Upper Subbase Layers ¦¦ Base Layers: Layer directly beneath the Bituminous Surfacing ¦¦ Base Layers: Other Layers
label | ba16899e-748f-52ce-bde4-80126ecaf247 |  | note | A ¦¦ Not less than 98.0 ¦¦ Not less than 98.0 ¦¦ Not less than 100.0 ¦¦ Not less than 99.0
label | 64e770cf-0c34-596b-abd9-9f48206ae38d |  | note | B ¦¦ Not less than 97.0 ¦¦ Not less than 97.0 ¦¦ Not less than 98.0 ¦¦ Not less than 98.0
label | 0420f57f-3cb7-5b2b-886e-c277a42c9502 |  | note | – – – – – – – – – – – – – – – – – – – – – – –
label | 5f86ce24-46d0-59f0-98dd-9f29b036a9e3 |  | note | Reference Documents - 304.08 Table 3040.061 304.11 (b) Table 304.111
label | f50131a6-1ca4-5392-937e-8499ad917bf0 |  | note | Inspection / Test Method - Test point
label | ff852421-a03e-555c-a6a5-c337720f8678 |  | note | Record of conformity - This ITP signed
label | 4ffe3d46-1386-5b60-aba8-bb19e9c606a3 |  | note | TP
label | f533b9a1-e1e1-5715-8aea-d7ad82f45188 |  | note | Responsibility - Site Engineer
date | 84d251f1-1e31-55c8-91c3-8053e1737799 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Post Compaction Testing
label | d29368e9-3f28-5b5f-9f18-63193953fbe4 |  | note | Frequency - Refer to table 304.111 for various minimum frequency or testing for Grading and PL
label | 302bc459-089f-5b18-9250-9b50f0269443 |  | note | Acceptance Criteria - If specified in Clause 304.10(c) or Clause 304.10(d), following completion of compaction, material shall be tested for post-compaction grading or Plasticity Index (PI) at the frequency specified in Clause 304.11 for the appropriate Scale of Testing specified in Clause 304.12(a).
label | dabbeded-c845-597f-af33-8aac94e9b982 |  | note | • Pavement Rejuvenation shall have a PI between 0-10, tested once evey 4 lots.
label | 7a44a07e-e979-5984-ab67-6ae15c6b7966 |  | note | Reference Documents - 304.10 Table 304.101 304.102
label | 9cc8b798-99bc-5048-8830-c1e603ebc6f8 |  | note | Inspection / Test Method - Test point
label | 9b0720f7-ecf7-59ee-a8f7-b64113c09489 |  | note | Record of conformity - This ITP signed
label | 0ce73e40-ae77-5970-ae45-4b7986db18ae |  | note | TP
label | ce85a686-7d6c-5db0-808e-1353e761c158 |  | note | Responsibility - Site Engineer
date | 42dfd3e1-13b3-59e2-8c75-ebf1c56b99a3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Shape
label | 61ce94a0-60cb-5f1f-89f2-82af01dbc7b9 |  | note | Frequency - Each lot
label | a00cdc48-17d9-53f2-b85f-6b142f9583bf |  | note | Acceptance Criteria - Layer to be finished to a smooth and uniform surface and after compaction shall have no point deviation > 8mm from 3m straight edge. The subbase shall also not be less than the specified thickness by more than 15mm
label | 47e13c5c-e06d-5556-a5bf-d4b43e83fdaa |  | note | Reference Documents - 304.06(b, d, i) Drawings Table 304.062
label | 0024e18d-858c-575d-8df5-0b7bbb05513d |  | note | Inspection / Test Method - Survey
label | a0ac6bef-29b3-56bb-bef6-29ba6726ea14 |  | note | Record of conformity - This ITP signed
label | b2aeec4a-ca45-5158-ab6e-6df75e9d5937 |  | note | IP
label | bb9df498-8bf1-5ab3-9cd8-f6b44821666b |  | note | Responsibility - Site Engineer
date | 1546020b-70cc-564a-99b4-96ff028c6d7c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 - Completed Surface Level Compliance
label | fdf76ad7-6c86-50eb-bb2a-047c603f3435 |  | note | Frequency - Each lot
label | 34a1d0a5-a6a5-51f5-b6a5-4f620040a5aa |  | note | Acceptance Criteria - The regulation layer is to comprise of Class 1 crushed rock for a minimum thickness of 100mm. Where the base rejuvenation layer is within 100mm of FSL after the mechanical blending / stabilisation has been completed, the rejuvenation layer is to be trimmed to FSL -100 to accomodate the minimum thickness regulation layer.
label | 19add53b-0e13-5b6b-b751-36b3f094389d |  | note | Reference Documents - Drawings
label | 73fd9fbf-68bc-5d29-a1e5-7ace5064c4d5 |  | note | Inspection / Test Method - Survey
label | d8dccbf3-049c-5ff7-88cf-349b5301e0dd |  | note | Record of conformity - This ITP signed
label | 0eea3cdd-a54d-5ab9-a8d6-170c7be29fe3 |  | note | SCP
label | 8f229361-e4bf-56ab-b2c3-ab6cf912e3e8 |  | note | Responsibility - Site Engineer
date | b58be151-a43a-5a9b-a20c-195e99e1dbd4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | ba056b5f-ed5c-585b-9d00-0be627e5d5a8 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | e78b9257-6529-56e3-8557-d91540e46a2a |  | textbox | Print Name:
text | fc8b86eb-ef05-518e-9b7d-83e3dca43b91 |  | textbox | Position:
date | 0d88b5c6-76fd-5c07-a53f-1238a4fb3207 |  | date | Work Completed On:
date | 77161a0f-bc1e-5c6f-9560-24ed3eaae053 |  | date | Date:
checkpoint-status |  |  | checkpoint | Table 304.121 Testing Levels
label | 4cfba669-5797-5b8d-96bb-c7a4c309cb3a |  | note | Roadway ¦¦ Road Chainage / Location ¦¦ Scale of Surface Level Measurement (A, B or C) ¦¦ Scale for Assessment of Compaction (A, B, or C) ¦¦ Scale for Assessment of Post-Compaction Grading and PI (A, B or C)
label | b4caec80-658b-5346-9ce2-c6e8c5192443 |  | note | – – – – – – – – – – – – – – – – – – – – – – –
label | a75530bf-15e6-5d0e-8b51-f19ac1be5b74 |  | note | Midland Highway ¦¦ Within Limits of Works ¦¦ A ¦¦ A ¦¦ A
label | 061086a6-4a85-54ca-b44c-ec0cadba5e4a |  | note | Glen Esk Rd ¦¦ Within Limits of Works ¦¦ B ¦¦ B ¦¦ B
label | 63f7323b-de9d-541d-86d7-ff1def742855 |  | note | Woorak Rd ¦¦ Within Limits of Works ¦¦ B ¦¦ B ¦¦ B
label | a281dea9-e00e-5b99-ba5f-97dd7ae3ece9 |  | note | Access Roads ¦¦ Within Limits of Works ¦¦ C ¦¦ Not applicable ¦¦ C
label | 810f04d9-eba2-5d0c-9b1a-fc6a48d8c29d |  | note | – – – – – – – – – – – – – – – – – – – – – – –
label | 845729f4-b381-5cd8-a94f-c869197f839b |  | note | Where for any location a specific scale has not been nominated, Scale A shall apply.
checklist-flat |  |  | checklist | CTN-ITP-004 - Earthworks - Cut, Fill and Subgrade Preparation(incl. Lime stabilisation) | itp |  |  |  | Yes | CTN-ITP-004 - Earthworks - Cut, Fill and Subgrade Preparation(incl. Lime stabilisation) | 75a3b530-bbb2-4f22-99c9-29747aad7c34
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 0c59f522-91c5-51b0-b886-a04a4336f63d |  | note | Frequency - Prior to commencing any activity
label | 7319b002-2b3f-58ba-bbab-67862bdfc9a0 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are: using Issued for Construction (IFC) drawings
label | a5e4731b-1db9-5a19-9d87-518e3f5ebdb8 |  | note | using the correct and complete set of drawings
label | bec2fcd0-52f6-59dc-8571-9bf42c7836b2 |  | note | all drawings are the latest revision
label | 997a1395-accc-56bc-94ed-cccd2cd0b631 |  | note | Reference Documents - IFC drawings and drawing registers
label | 5b37a279-cf07-5f28-bd0a-d66eeb28db96 |  | note | Inspection / Test Method - Document Review / Visual inspection
label | 21361f71-5a7b-5b78-8871-43268f8685d3 |  | note | Record of conformity - This ITP signed
label | cde1c95f-79ad-55bf-8949-98dc292c1791 |  | note | HP*
label | 3a98e920-1703-587c-a64c-615f3d0a5e1b |  | note | Responsibility - Site Engineer
text | 137ff0a2-c746-59f8-b15a-fee6c192c77a |  | textbox | ITP Opened:
date | 2f1b1563-f82f-527a-9936-bd4a31c48cef |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | e741bbc2-8b73-50e8-ba98-4977f99f3666 |  | note | Frequency - Prior to commencing any activity
label | 8e302765-ecfe-5b24-9020-6d069470bb08 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: OHSMP, EMP, TMP, SWMS & WP. Access and egress inspected and assessed for stability.
label | 87228bd6-8105-5f85-bf07-c0dc5d0c8539 |  | note | Reference Documents - OHSMP, EMP, TMP, SWMS, WP
label | 37cec972-c314-5952-b904-4624c6368793 |  | note | Inspection / Test Method - Visual Inspection
label | e3fc7593-8338-509d-8be1-d703ec699759 |  | note | Record of conformity - This ITP signed
label | cf139787-e7b4-5c6d-9f8e-579f7117e819 |  | note | HP*
label | e5b79824-d7ac-5942-bb1f-2774e999b20e |  | note | Responsibility - Site Engineer
date | 8db9bf3d-c835-5be8-9ba1-2d556bd8056c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Lime Stabilisation mix design
label | b7e99cf7-bfd7-5c35-9532-17a0e41c9a7d |  | note | Frequency - Prior to commencing
label | 1d34dd16-ee09-5f27-a862-8d24be8d3625 |  | note | Acceptance Criteria - Hold Point The Contractor shall not commence work until all mix design details including the stabilising binder spreading rates have been presented to the Superintendent for review.
label | 6e1542f1-75a5-5f0f-bcbe-ac970bbd8408 |  | note | If the Contractor is required to determine the Design Distribution Rate of the stabilised binder(s),
label | d883b05b-b881-5fa9-81b0-a6e19abd031d |  | note | evidence shall be produced to show that the material properties specified in clause 290.07(a) or clause 290.17(a) as appropriate have been met.
label | d05f1459-2efa-50c9-bb82-a516d6effd4f |  | note | Reference Documents - Cl 290.08
label | 58eb3bd2-987e-58dc-afb8-c1a4ea712d9e |  | note | Inspection / Test Method - Verify
label | e12e89ca-b597-58ff-b487-63f92814ef4d |  | note | Record of conformity - This ITP signed
label | 8d832a6c-5a00-5c76-b37b-f3f91b7089fe |  | note | HP
label | 0660d698-aeff-5951-bf10-63634f9236a3 |  | note | Responsibility - Site Engineer/ QAV
date | 61092d36-b0fa-55d8-a189-e984a0eb7f3b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Survey set-out
label | cd82b2fb-2237-535d-853d-b2ee9492087e |  | note | Frequency - Prior to commencing
label | 09dbe77d-aa39-5952-8671-6f40125f1c5e |  | note | Acceptance Criteria - The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity.
label | f29715e9-c20a-5862-a9d6-02b0d2a84f5f |  | note | Survey activities undertaken to ensure and validate that all works meet level and location requirements. Verification of conformity with latest IFC drawings.
label | c4f50e3a-133d-5f61-a4e3-15394d2cb2a9 |  | note | Reference Documents - Section 160, A0113.029
label | 8492f7b2-2594-599a-9842-46ad8bbbc94c |  | note | Inspection / Test Method - Visual Inspection
label | 24c400f3-a8bf-51fa-8cdd-9c4c37e67820 |  | note | Record of conformity - Survey records and pegs on the ground
label | ab15499c-f293-5367-9ee3-7f744bb35d7d |  | note | IP
label | 74d00e9a-75db-566d-837b-6d1d1e87839a |  | note | Responsibility - Site Engineer
date | 8354d4ed-cd57-5b07-87e5-b18cde8248d4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Ground Penetration Permit
label | a2f59e94-c9b1-520b-9edd-c847026e9d14 |  | note | Frequency - Each Lot
label | 334f2c47-fb07-5d2a-8a39-16160f85b507 |  | note | Acceptance Criteria - A ground penetration permit must be issued prior to excavation commencing.
label | 6177f16d-704f-5549-94f4-53efc8ca40a3 |  | note | Plant and equipment must be appropriate for the task.
label | be49dd6e-d40a-5983-affd-7275c28a3c07 |  | note | Excavation operations shall not disturb areas outside the limit of excavation.
label | 83519033-7106-5c0c-bb3b-88d1395e0fbc |  | note | Reference Documents - Ground Penetration Permit
label | 0a442412-bc9b-5604-979b-352f083e0d3b |  | note | Inspection / Test Method - Verify
label | a8b9dda2-662d-5bd4-8971-3bc9fbeaa796 |  | note | Record of conformity - Gradco ITP
label | 535b80d0-3fb7-51b1-9776-a392d08f955b |  | note | IP
label | edc97465-4d0f-5361-b384-92718b6daef8 |  | note | Responsibility - Site Engineer
date | 52123696-74f4-5b14-9b41-88bc2e40b7a0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Lime Stabilisation trial
label | 5f63c2b1-d2ae-56ce-9cf7-ad9c2892b0ae |  | note | Frequency - Once unless further trials required
label | 5c88017f-d4c7-5927-8860-feaeed9c1b66 |  | note | Acceptance Criteria - Hold Point Stabilisation shall not proceed outside the trial sections until the Superintendent has reviewed all aspects of the work.
label | f0be7194-54c2-5f58-9750-61a3e030f5e4 |  | note | If the Specification requirements are not met for the trial, the Superintendent may direct that another trial be undertaken or that the work be re-stabilised and presented for re-assessment.
label | 66597ec7-5bcc-5507-811b-716f91526116 |  | note | Reference Documents - Cl 290.11
label | 7495f859-a603-5a9d-8419-6055d432a7d8 |  | note | Inspection / Test Method - Verify
label | 7e3d7474-0654-5827-a6bc-6e670ac94ebf |  | note | Record of conformity - This ITP signed
label | f5683278-9b72-510c-a919-64169e6754af |  | note | HP
label | 64b43750-a0bc-5dcf-bf81-e7a5d0db1ce1 |  | note | Responsibility - Site Engineer / QAV
date | bcc130c4-a86e-54c2-be78-fb8fb31a9601 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Material Categorisation
label | 7181d47e-f519-5adc-8e25-dd48c0385680 |  | note | Frequency - Each Lot
label | 379fdd61-c359-521c-b449-bfdb544effee |  | note | Acceptance Criteria - Hold Point Prior to commencing excavation in any area and during excavation work, the contractor and Superintendent shall inspect and agree upon the type / category of material encountered
label | f4aca716-4382-5af4-939e-913c94f4e0c8 |  | note | Reference Documents - Cl 204.06c
label | 0e68562b-491f-5bcb-8d72-36b9c78b67d7 |  | note | Inspection / Test Method - Verify
label | 3cac296d-f8a6-512c-96d1-fcef0944beb1 |  | note | Record of conformity - This ITP signed
label | 2c506903-2d7c-50d2-9960-566cb29737fa |  | note | HP
label | 86fa1e53-b65f-56a8-a5ec-a5b1d0b9c36f |  | note | Responsibility - Site Engineer / QAV
date | edd15587-aec4-599f-b1c3-162d95eea53d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Stripping of Topsoil
label | 22d1b5e8-237f-50b5-be06-832baa71fdb7 |  | note | Frequency - Each Lot
label | 370b1cc5-5d27-55fc-87ef-7db29851c8ea |  | note | Acceptance Criteria - Topsoil stripped to full width of the formation and placed in approved stockpile location. Stockpile shaped to shed water and stripped surfaces graded to be self draining.
label | ec3159ed-393e-5002-a526-758c03cc2ec5 |  | note | Topsoil shall not be removed from site unless approved by the superintendent.
label | f95fbb0c-bedb-5bd0-97f3-29248ed7b3ed |  | note | Reference Documents - Cl 204.05
label | 63fdf69b-50e1-5019-8156-0d940b2e5e27 |  | note | Inspection / Test Method - Visual Inspection
label | dacc3c38-9a10-506d-a90a-3861274f0c26 |  | note | Record of conformity - Gradco ITP
label | b01ae3da-66a5-566a-b055-bfe531db25e0 |  | note | IP
label | 544f19a7-eb8a-5cef-9715-725253f39fdf |  | note | Responsibility - Site Engineer
date | 647c0597-30c3-5c28-8e08-178e54807b1c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Unsuitable Material
label | 70d567b5-346d-528b-b55f-22f16d9b1578 |  | note | Frequency - Each Lot containing unsuitable material
label | 614e34fa-2296-5c6b-92f0-59d6a41d5e5f |  | note | Acceptance Criteria - Hold Point For unsuitable material, the proposed in-situ treatment or extent of excavation submitted to the Superintendent for review.
label | 63bfb972-4cce-5121-8086-1e7a1db81bdb |  | note | Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilization to the satisfaction of the Superintendent
label | ba69ff97-b550-5bdc-9664-9907333f2c04 |  | note | Reference Documents - Cl 204.04b, Cl 204.07d
label | a30721ba-1ff3-52bf-8ac8-9bf983a815f9 |  | note | Inspection / Test Method - Verify
label | 074ad294-2cc1-568c-b715-96aafeab1c50 |  | note | Record of conformity - This ITP Signed
label | 6d3bff3e-c4c9-52a8-a55f-d574fd77661f |  | note | HP
label | 981ce51d-ab22-553e-953e-05f9c6492135 |  | note | Responsibility - Site Engineer / QAV
date | c27940ba-fe5a-54f9-9145-5657aadcd6e3 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Subgrade Fill Material
label | 7bf11768-f09b-5aa6-8820-342231bd450d |  | note | Frequency - Each Lot
label | 9cce5190-8fb5-53f5-98ef-8c47c7fe8775 |  | note | Acceptance Criteria - Fill material free of topsoil, deleterious and/or perishable matter. Type A material shall comply with the requirements of Table 204.041
label | 72552f6b-d94a-51c0-ae7f-f2cf6e360ab6 |  | note | Type B material shall have minimum Assigned CBR of 2% and Assigned swell less than 2.5%. Materials with swell greater than 2.5% can only be used as Type B material if approved by the superintendent.
label | ebc04eaa-4604-59c6-93ae-5805e7519713 |  | note | Type C material shall be capable of being spread in layers of not more than 500mm
label | 64ad7a1e-54ff-50f0-ab3a-4cd2bf2bc33d |  | note | Reference Documents - Cl 204.04, Table 204.041
label | bfb35b05-2eb4-5c55-acad-d763a7abe78c |  | note | Inspection / Test Method - Verify
label | b7dd7416-d274-568a-a740-d7cd529a3e25 |  | note | Record of conformity - Gradco ITP, Test Report
label | 240b5b90-e67e-5615-9ad8-6dea7795907c |  | note | TP
label | 65a67118-0402-514e-b3c3-b75c2c6d90a4 |  | note | Responsibility - Site Engineer
date | c68141ed-b087-5d16-a062-44e078c62cb9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Treatment of Rock Subgrade
label | c528b154-5a66-596a-a149-191ec05210ac |  | note | Frequency - Each Lot (prior to construction of regulating layer)
label | 6191c107-35f0-5f06-a28f-63cb91a1f832 |  | note | Acceptance Criteria - Hold Point Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | 848e8902-e0fb-59ef-a55a-dcdb2889a2a7 |  | note | Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | 47f433e4-9b11-5aa5-8f46-df251f0647e7 |  | note | Reference Documents - Cl 204.06f
label | ea28b4f8-9434-50fb-9a10-8e98dd81f040 |  | note | Inspection / Test Method - Visual Inspection
label | 7eda617c-736e-51f1-ae09-ab3ddfe0b435 |  | note | Record of conformity - This ITP signed
label | 9cc9537c-454c-5de7-892c-139b16b233b8 |  | note | HP
label | f10d2678-f71c-5c1c-9e0b-cf647cafe6f2 |  | note | Responsibility - Site Engineer / QAV
date | caa717ee-22f5-5adb-ae09-5089646b065c |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Groundwater
label | eb479987-ce21-5b00-9db7-8e008c735e3b |  | note | Frequency - Each Lot
label | b3412a67-cc0b-5463-889d-e393ad1c491e |  | note | Acceptance Criteria - Hold Point Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | 616d24f7-7140-58aa-b1c4-61cc5f6526d5 |  | note | The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
label | db3efe31-ebbd-5027-a7dc-0bcd395c894e |  | note | Reference Documents - Cl 204.06h EMP
label | 553cf122-5c02-5e6d-ba32-b034f7926202 |  | note | Inspection / Test Method - Verify
label | 26cb3634-6dec-5296-a35a-8165e1bebdff |  | note | Record of conformity - Water Authorities and Superintendent Approval This ITP signed
label | aa0f5504-c5f3-5cbc-a10c-6373404fdbb8 |  | note | HP
label | 816e51f1-8a92-57f8-ad55-3c07d13cf4d4 |  | note | Responsibility - Site Engineer / QAV
date | f982e05b-d6f4-5abf-9771-7facccd39d0b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Surface finish of batters
label | de851f7e-87c6-5a04-8665-7cee934bf160 |  | note | Frequency - Each Lot
label | 0a0946a1-6dc6-525c-b6cb-97dd551d020d |  | note | Acceptance Criteria - Surface of cut and fill batters to be topsoiled and textured by scarifying or horizontal grooving
label | 14a397fb-10b6-5914-91d2-a3eaa354c7de |  | note | Reference Documents - Cl 204.06i
label | 39ba654c-5ae4-5acb-8ccb-7edd18d2706a |  | note | Inspection / Test Method - Visual Inspection
label | 71c48446-4ba2-5529-b3d4-559f239c5721 |  | note | Record of conformity - Gradco ITP
label | 20a2affc-c2c9-5eaa-bc75-4a0167d1f974 |  | note | IP
label | aa048e09-3437-5996-8e36-a78b3edda964 |  | note | Responsibility - Site Engineer
date | efedc1b3-2fa8-54de-995e-987eeabdbd76 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Borrow Excavation
label | f7e8d9b5-1898-5c92-9509-1952c98f63ed |  | note | Frequency - Each Lot
label | 2f3e1064-f884-5980-93fe-d2ed7fbe8274 |  | note | Acceptance Criteria - Hold Point Borrow Excavations within the road reservation are not permitted without prior approval of Superintendent
label | d48934e8-a81a-5aa9-8fef-f245f23772ca |  | note | Reference Documents - Cl 204.09
label | 9ab1c365-4525-599f-8688-1b14cfc70420 |  | note | Inspection / Test Method - Verify
label | b444e18a-7b60-50f1-8ea8-0df0f6cfe3e4 |  | note | Record of conformity - This ITP Signed, Correspondence with superintendent
label | ed0be960-09c9-57ad-9618-6b74f1294ed7 |  | note | HP
label | 85d1b8a2-e918-5bbc-9d6a-aa672ab5ba53 |  | note | Responsibility - Site Engineer / Superintendent
date | 8ec938fd-077c-54d3-b8a4-e2d61ed950b5 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.10 - Areas upon which fills are to be constructed
label | 83008d6a-4dc8-5d04-a4f9-dc2fdff50003 |  | note | Frequency - Each Lot
label | 3b189d7c-662e-5c5e-b1cb-d39943e06792 |  | note | Acceptance Criteria - Hold Point Areas where fill is to be constructed must be reviewed by the superintendent prior to the placement of any fill in the area
label | bc037786-d4df-5069-8bdb-dc284141eb8d |  | note | Reference Documents - Cl 204.10b
label | 76f3e33d-bd8b-5c18-b6b7-eb8feb2d3487 |  | note | Inspection / Test Method - Verify
label | f0011316-aec1-50ba-a3df-0c80f6bac66a |  | note | Record of conformity - This ITP Signed
label | 53e57d7c-9f6e-5fa9-8def-3b80051f17ad |  | note | HP
label | b63ebb08-f123-5fd9-b6e5-0733f1744bf8 |  | note | Responsibility - Site Engineer / QAV
date | b7bdd6a7-84b8-5c9e-bafb-1d9faa15d20c |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Placing of Fill
label | 9a7b9c51-e849-54c3-90ef-4fccb9ece7de |  | note | Frequency - Each Layer
label | 966219ae-d0e0-5dda-af1d-3b8b702a700b |  | note | Acceptance Criteria - Fill placed and spread in uniform layers. Each layer keyed into the next with a textured surface. Any rocky material uniformly distributed throughout the layer.
label | e08e7ace-d7ed-5ede-b50f-23ba647fe877 |  | note | Compacted layers do not exceed specified maximum thicknesses:
label | ad3757f8-e48d-5bb4-a382-635866f32223 |  | note | Type A: Maximum compacted thickness 200mm (can be used in locations specified for Type B material)
label | e388688e-2775-57ab-8bd1-a1752df9323b |  | note | Type B: Maximum compacted thickness 200mm (can be used in locations specified for Type C material). Where > 25% rock by volume,
label | b4b0b59b-dc3f-529d-8b96-2564d9fdebd4 |  | note | loose layer thickness may equal 125% of typical maximum particle dimension up to max 500mm. No rocks > 80% of loose thickness of the layer.
label | e037138b-da47-51ce-971f-cf192476f7c5 |  | note | Type C: Maximum compacted thickness 300mm. Where > 25% rock by volume, loose thickness of each layer may equal the maximum particle dimension of the rock up to max 500mm.
label | 776ed9f5-13a8-51c3-ad02-3141950746aa |  | note | Reference Documents - Cl 204.10d
label | d4217905-013a-5e2d-82af-8fb48b6fe812 |  | note | Inspection / Test Method - Visual Inspection / Measure
label | d9e5c75c-e6be-509c-8757-c0ab12a0c339 |  | note | Record of conformity - Gradco ITP
label | 2ab7fec3-653d-53ab-b720-25534bf7efec |  | note | IP
label | 078e4215-c3c1-5d37-a8d8-32ae268b240f |  | note | Responsibility - Site Engineer
date | c0fdcb54-03fa-535d-9e81-a550b3b0a2e7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Test Rolling
label | 12b5dc64-6ea4-5ffe-a12e-75e1f8cbb103 |  | note | Frequency - Each layer
label | 68463c2f-3491-51df-b176-deb157c62145 |  | note | Acceptance Criteria - Hold Point Areas upon which fills are to be constructed, all layers of fill, material within 150 mm of the cut floor level in cuts,
label | ab82a214-5814-51bb-81a7-053a6f7d202c |  | note | and all stabilised material shall be test rolled in accordance with Section 173.
label | 20d20714-bf1c-516e-9588-8f24f27499b2 |  | note | Reference Documents - Cl 173.03 Cl 204.12
label | 6ddaa841-8f1d-5ccf-aba2-fb3a7f7abfd9 |  | note | Inspection / Test Method - Visual Inspection
label | 10c1039f-a116-5269-a9ad-b919aedb6e89 |  | note | Record of conformity - This ITP signed
label | ac9fec11-33a3-5c7f-91bc-ed80aa24596e |  | note | HP
label | 62caf61b-412c-5c9d-a10a-0a56c9a5bac0 |  | note | Responsibility - Site Engineer / QAV
date | 99bc112c-bd81-5d52-ba3b-fbb769ab3d6f |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Cut and Fill Tolerances
label | 0916cd67-61f2-5ccc-ab2b-eb3d96670931 |  | note | Frequency - In accordance with Table 204.031. Lots < 4,000m²
label | 53769315-5830-55d5-81d3-fff60d6e8545 |  | note | Acceptance Criteria - Formation width and alignment: not less than the widths specified or shown on the drawings
label | afb20c7e-9657-5f3d-96ef-cebef0ad0682 |  | note | Formation level and shape: Verges match FSL at outer edge of shoulder or pavement (± 50mm from design level)
label | b3f4b6ac-9fdf-52cf-9ada-a0dab3cefaac |  | note | Boxing width and alignment: not less than specified or design levels & no deviation > 50mm from designed offset from the centreline or design line.
label | 1bf2e641-b5ca-5c5a-aa06-4ed266960227 |  | note | Type A Material: thickness and width not less than specified at any point.
label | fe82a950-2075-577a-8d51-e4aad62caf90 |  | note | Type B material (immediately below capping / selected material): +15mm -30mm specified level
label | b6c27561-f174-5d37-9761-7f601a7ed534 |  | note | Cut floor level (when capping layer required): +15mm -30mm specified level
label | 3b426262-5556-5a90-afa2-f7b8b933401d |  | note | Cut floor level (no capping layer): same as subgrade tolerance
label | 1388eb7b-42b8-5ed6-bc0d-fd882afbce33 |  | note | Subgrade Scale A & B: random levelling Cl204.03(h). No point > 20mm below a 3m straightedge laid in any direction.
label | f157a650-4c03-5897-add3-462229b94c8c |  | note | Batter and slope: Not steeper than specified at any cross section.
label | bbff2903-5377-5df4-a515-d7f752dd9137 |  | note | Batter line: Batter point < 10% of the batter height outside the calculated batter line.
label | ba66a737-d409-5194-ae99-c973df198879 |  | note | Surface Drains: Invert levels and side slopes ±50mm and free from depressions capable of retaining water.
label | 13624f97-3ae6-5f63-a0d6-6a0dcf06224f |  | note | The contractor shall establish a procedure to verify that compacted layers do not exceed the specified thickness.
label | 8637f813-418e-5d14-b1c6-d1cabfb3d403 |  | note | Verification records must provide evidence of measurements taken every three layers.
label | 13fd0d96-4b47-5c1f-959a-2caf6056e63a |  | note | Reference Documents - Cl 204.03, Table 204.031,
label | 19ca54a8-18d6-5605-acc1-733153afd99d |  | note | Inspection / Test Method - Verify
label | 2e847db9-fae1-5e50-8502-299e93613418 |  | note | Record of conformity - Gradco ITP
label | 0db26df3-91e4-50e0-900c-fffffa90b559 |  | note | SCP
label | 9f925b02-c160-59bc-a1ac-95d81f5d5135 |  | note | Responsibility - Site Engineer
date | ac869453-009f-59dd-bd45-9cce8bbdd165 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Subgrade level conformity
label | c8ba32e5-b19c-5a0e-a96d-061e161c6172 |  | note | Frequency - Each Lot
label | 75f4f81a-5709-5942-9933-1e4eb8f4fdbd |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 2e2acd03-af2a-5513-9dd3-7e1a3571819a |  | note | Level tolerances:
label | 56c76e8b-cb13-5695-838a-4a0842a76fa7 |  | note | Scale A - 80 measurements per lot
label | 4005bbad-bb87-519c-ab21-6b852d75b459 |  | note | Range = +5, -15mm
label | a2ad9f51-f0f6-5785-85aa-15412be58207 |  | note | Max S = 12 mm
label | a3c8e16c-692f-571c-84b8-038b2bd11b6e |  | note | Scale B - 40 measurements per lot
label | 67d1ec25-c995-511d-9fa6-7cb880d0ba39 |  | note | Range x = +5, -25mm
label | 51f23006-6e2b-57be-aec8-1689bfeec16a |  | note | Max S = 15 mm
label | 7f469253-1646-5b3e-a7f3-e4420ffa600b |  | note | Reference Documents - Cl 204.03
label | edc07b48-f5b2-5f73-9ad9-a6d55eca5e8e |  | note | Inspection / Test Method - Verify
label | bfcc27a6-8ad9-5909-8b44-215d2e8424b9 |  | note | Record of conformity - This ITP signed, Survey report
label | 38e1c6c1-97d3-5c84-ad6d-cf8283011758 |  | note | SCP
label | 3292332a-9655-56ad-89ff-6ab6b659a02d |  | note | Responsibility - Site Engineer
date | fbde446e-b3d7-57fc-962e-390ecc363807 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Fill Material Compaction & Moisture Content Requirements
label | eab9f8ab-d4c0-54ef-b74f-ac58052d7038 |  | note | Frequency - Each Lot as defined in Table 204.142. 6 tests per lot. Small area lots (<500m2) as per Cl173.04d. 3 test mean lots. +2% compaction req.
label | 2def4baf-219e-5d3f-bd0d-46abe1ec85bc |  | note | Acceptance Criteria - For Scale A (Midland Hwy):
label | 58ad28eb-cdc2-53a5-a8ec-be7519f01742 |  | note | Min Mean Value of Density Ratio:
label | a0d9af77-7bd6-5550-9565-d3b63e93bca2 |  | note | All type A material: 99%
label | d665e3e8-c56a-5886-b689-dd705ce6bca5 |  | note | Type B material placed within 400mm of top type B material: 99%
label | 8906eebd-4211-51c9-8724-e9bf5b61b9dd |  | note | Ripped and re-compacted material below Cut Floor Level: 99%
label | da846adb-b1b4-5604-9b02-f76ba932ecd3 |  | note | Type B Material placed > 400mm below top of Type B material: 97%
label | 0fee2ecf-4d95-5a25-9946-df1850fe8de8 |  | note | Top 150mm of areas where fill is to be constructed: 97%
label | de0d55e6-0b9f-5b4e-a9b9-bd7fb986d4fe |  | note | Type C Material: 95%
label | 63af61f7-df82-5d74-a4c9-f98d5943351b |  | note | For Scale C (All other roads):
label | ecfa4d1e-62c8-541b-b0d2-9e6353495949 |  | note | Min Mean Value of Density Ratio:
label | 5195f4c1-d063-5604-bd39-423a7deb5a88 |  | note | All type A material: 100%
label | e6db6dc3-8d2c-524b-b489-4a3bfd019fe7 |  | note | Type B material placed within 400mm of top type B material: 100%
label | ee299833-fdbb-5404-b0a7-e60929824eb2 |  | note | Ripped and re-compacted material below Cut Floor Level: 100%
label | 66818a1c-8d0b-59eb-a6bc-3a66376754b7 |  | note | Type B Material placed > 400mm below top of Type B material: 95%
label | 1f454859-a79e-5657-9295-81c7bba7fc86 |  | note | Top 150mm of areas where fill is to be constructed: 95%
label | 467c5958-ba88-52bc-b028-ae99f636d306 |  | note | All fill material and material below the Cut Floor Level shall be compacted at minimum moisture ratio of 80%.
label | f451eab5-77ce-59d2-b017-d036576ad0e0 |  | note | Reference Documents - Cl 204.13 Table 204.131
label | 18664fe3-5ae9-5ecb-9857-dc8c4ee2d039 |  | note | Inspection / Test Method - Verify
label | dd4c52ea-7783-5a7d-941c-c1de12117710 |  | note | Record of conformity - Gradco ITP
label | 03f92cd7-533c-5d25-ba16-f0b27756f7d0 |  | note | TP
label | e19dc431-172e-586f-bf94-0d556d957712 |  | note | Responsibility - Site Engineer
date | 0766ed27-269f-56cf-8371-258c398674e0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Lime Stabilisation testing
label | e5710183-16b0-5195-920f-3a7ea6d59e54 |  | note | Frequency - As specified in Table 290.151
label | 9530bec1-5feb-5d20-b795-c7245fb72849 |  | note | Acceptance Criteria - Testing of the following undertaken at frequency specified in Table 290.151: ALI (require minimum 80%)
label | a8327f53-e289-508c-a5a8-dacd901fa848 |  | note | Uniformity of mixing
label | c026485d-0da1-5168-9acf-063594b9cb6c |  | note | Uniformity of spreading rate
label | f5bdde44-6cfd-5ab7-844e-482e557385dc |  | note | Average spreading rate for stabilising binder
label | 3fece111-f167-570a-b34d-a5a691f20d94 |  | note | Characteristic Density Ratio (require minimum 98%)
label | 6409a6ec-5eb0-5ee5-9160-db97d9355a0b |  | note | CBR of stabilised material
label | 6166cef6-1caa-53c5-b98e-3fabe1403790 |  | note | Reference Documents - Cl 290.15 Table 290.151
label | e59cfdb8-7bc2-5934-8e61-7eecbcd2ecdb |  | note | Inspection / Test Method - Verify
label | fa49b05d-4cd0-5355-ae5b-9c459308fa60 |  | note | Record of conformity - This ITP signed,Test reports
label | c0808754-578d-505f-88e3-5eb48937c49e |  | note | TP
label | 0006cc44-7c4d-5be5-a303-e96fbb5743b0 |  | note | Responsibility - Site Engineer
date | 9cb2b588-45cf-578a-8cd9-8329b74024da |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 - Material Properties Testing (Scale A & B)
label | a3ce821b-3acc-57e5-b4ed-b7fae0f9c79f |  | note | Frequency - Once per lot or per material change, as per Table 204.141
label | e61f1157-0d42-5eb2-a978-97440e717745 |  | note | Acceptance Criteria - The first lot of each material type shall be tested to demonstrate compliance with the material property requirements specified in Clause 204.04.
label | 42c40a79-464d-537d-84de-87783dce4e27 |  | note | Where first lot of each material type satisfies the requirements outlined in Table 204.041, testing can be undertaken at the reduced capacity specified in Table 204.141 depending on agreement from the superintendent
label | b26a01fb-e713-51ab-b8d9-6ebed5056876 |  | note | Reference Documents - Cl 204.14, Table 204.041, Table 204.141
label | e84557dd-fc0e-5c08-8d22-f7b7b452cc1d |  | note | Inspection / Test Method - Verify
label | d1cdfda6-7ed9-5a5c-849f-f9f12f67f824 |  | note | Record of conformity - Gradco ITP
label | fef2c798-a812-503b-bd52-93a0ea278fc5 |  | note | TP
label | e093a49d-6602-59d7-8a42-2cab07b2f705 |  | note | Responsibility - Site Engineer
date | 56e23bb9-64b7-52bd-b6d8-5a8084a29a6d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 - Preparation and Maintenance of Final Earthwork Surface and Subgrade
label | 2f4da9ac-4148-53c3-804d-20fcfce943ed |  | note | Frequency - Each Lot (Final Layer only)
label | 1bdfc0ec-a766-56ad-935b-f275e0392ffc |  | note | Acceptance Criteria - Smooth, hard, tightly bound surface presented. Free from depressions capable of holding water.
label | 67fbac75-5aed-576b-88c2-0fb2309e754e |  | note | Material within 150mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to placement of pavement layer
label | e3752f94-8419-5a75-8146-67897af035e2 |  | note | Reference Documents - Cl 204.15
label | 339d903f-4016-5274-a033-990f8f206b22 |  | note | Inspection / Test Method - Visual Inspection
label | cb02452b-4e6f-5875-a9c7-395a6474a30f |  | note | Record of conformity - Gradco ITP
label | de61b8aa-6a3b-54b4-9fd4-f8a01ad9006b |  | note | IP
label | ac425e03-be69-54e0-bc7a-fa6834f120a0 |  | note | Responsibility - Site Engineer
date | 87738d9e-14b5-569e-9154-94c39793fff4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection - Gradco
label | 35cb99e6-d7ff-5859-ba3a-e5e616473d08 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 8b457941-93fc-545b-aef5-ea0448315565 |  | textbox | Print Name:
text | c3905beb-5819-5163-844e-0802e551673b |  | textbox | Position:
date | d8ba39bc-5dbd-5fc5-9ef4-850b612f97e1 |  | date | Work Completed On:
date | afe0efca-c0aa-5436-a185-7f6b27017e82 |  | date | Date:
checkpoint-status |  |  | checkpoint | Final Inspection - Fulton Hogan
label | 5655679f-db40-52d3-bccb-30f0bc14bbc7 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 229751f6-08f4-5934-bf2f-16585cf3f516 |  | textbox | Print Name:
text | 8cc02bda-b1fd-5e53-94cf-28601f851aad |  | textbox | Position:
date | 2a237759-80fe-5dd0-8bc8-7029503e5627 |  | date | Work Completed On:
date | 3220b6c9-c52e-59aa-b5a1-73ea01f9e060 |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-020 - Rock Fill Construction | itp |  |  |  | Yes | CTN-ITP-020 - Rock Fill Construction | 877b9d18-3302-433b-83aa-46641b55441d
checkpoint-status |  |  | checkpoint | 1.1 - Rock size and strength
label | c85897b4-b802-5e16-99fd-58f165b9bbd8 |  | note | Specification Requirement - CL 205.03
label | 1c274411-b564-5db9-bfa5-dc8cc78c870c |  | note | Acceptance Criteria - 205.03(a) Sound rock fragments with at least 2 x broken or angular faces each Test 10 pieces > 100mm for point Load Strength Is(50) of 2.0MPA or better.
label | d1ea6809-d7b3-514a-8b2a-b63a284df969 |  | note | Inspection Type - TP
label | 5abd5632-97cd-57a5-bf74-acb82f034eff |  | note | Inspection Frequency - Prior to delivery
label | 85a54d23-59bb-538d-8410-775defbb8f76 |  | note | Records to attach - Test Results
date | a0e987a1-e36c-5103-aec2-7c0113c2634f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Post-Compaction Grading
label | b81b01ab-2aa7-5276-8ef4-90982b1841d4 |  | note | Specification Requirement - CL 205.03 – Table 205.031
label | 1e9bf605-ae19-53d1-a555-76c6d4e865fb |  | note | Acceptance Criteria - Post compaction grading complies with the Limits of Grading ion Table 205.031.
label | 9bdddcaf-4ff4-5379-a7b2-53950c997860 |  | note | Inspection Type - HP
label | 92a75596-900b-50eb-a017-a039a2110e36 |  | note | Inspection Frequency - Prior and/or During Works
label | f8394661-8b13-5c69-b4dc-4f6e8bbdbecd |  | note | Records to attach - Grading report
date | b8922a64-495b-585c-b560-5edb911e5d0b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Geotextiles
label | 84a187a7-be59-512b-b828-e19362579236 |  | note | Specification Requirement - CL 205.03(b)
label | 6c749a2e-ba1c-541d-b473-54a42db8464e |  | note | Acceptance Criteria - Geotextiles used in rock fill shall have G robustness rating greater than 3000.
label | 1d427b5a-7bbc-5491-9adf-a99e3ba68e2b |  | note | Inspection Type - Check / inspect
label | aa0d6dfb-fb69-5f44-9ea9-13e13bc49f90 |  | note | Inspection Frequency - Prior to placing initial rock layer
label | 427c60ee-fce1-5ab6-b43e-285e3d71ff2e |  | note | Records to attach - Specification sheet, roll label and manufacturers test report.
date | dac91c2b-7c54-5589-b6e0-7224fcd6ccf7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Fill Construction
label | f45d3572-6db1-58d3-b1fc-4add611b2f1d |  | note | Specification Requirement - CL 205.05 )a), CL 204.10 (b)
label | c997761c-7ead-5256-988b-a5d92de0831c |  | note | Acceptance Criteria - The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
label | cdf2faa9-f7ab-5bb6-ab2f-e6fdb327a847 |  | note | Inspection Type - HP
label | a88eb428-1892-5de9-9cbe-eb7fb7bf8f10 |  | note | Inspection Frequency - Prior to Fill Placement
label | 949732f9-94e7-5cc3-8ac0-99476fa10667 |  | note | Records to attach - HP Release
date | b72d79e6-8866-5e79-9e95-84674f8f1ae8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 - Trial placement and compaction
label | 7481def7-a1db-5723-8096-2da7aebbe4db |  | note | Specification Requirement - CL 205.06
label | 63510f98-5639-5540-b689-e869d1c7f3be |  | note | Acceptance Criteria - For each material type and grading, the first and second layer shall be trialled:
label | 1be504d6-b69b-5100-98a6-68ac85a48db0 |  | note | – An area > 1000m2
label | a9d37987-112d-512b-ac8f-c82af4c23332 |  | note | – Rolled for the greater of - until no further consolidation, or 15 passes.
label | 1585d999-566d-5813-bbb6-035d1d7afc0c |  | note | – Be surveyed after each roller pass, measure minimum of 20 points.
label | c5504a45-1ce5-5cdc-883b-6c266b50481a |  | note | – Engineer / Supervisor / QAV review survey results to determine the number of passes before refusal occurs.
label | 51f710b5-b488-5241-9c4d-42bd17a5af00 |  | note | Inspection Type - HP
label | d06c249d-746b-5689-983d-1c4f47c3de7e |  | note | Inspection Frequency - Prior to Fill Placement
label | 87c69706-2884-58b9-926d-7f006e642195 |  | note | Records to attach - HP Release, consolidation record
date | ac5d1f7a-4f06-5802-9b72-07c879721522 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1 - Placement & Compaction
label | f29aa355-ab68-5739-addb-d772970cd5f5 |  | note | Specification Requirement - CL 205.06
label | 2d768a18-f838-58c7-9c4d-c43accda5891 |  | note | Acceptance Criteria - Proceed with placement and compaction in accordance with the approved procedure. Maintain layer thicknesses and material size in accordance with 2.2, 2.3 and 2.4 above.
label | 88e0362e-16ee-510a-930e-8b7dd1e75a1e |  | note | Inspection Type - HP
label | ee29d4aa-2c78-5f0f-8e09-260192d4a364 |  | note | Inspection Frequency - Every Lot
label | 9056d3e8-bc08-5d65-a880-7bde0d4d8628 |  | note | Records to attach - Placement and compaction record
date | 31a06d46-9f0f-594a-aacb-333b8e59ee50 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Level Control
label | a79cea18-0519-5860-af1e-d4416c19d475 |  | note | Specification Requirement - CL 205.05(d)
label | 1886fc94-114f-58a8-971e-d637f3473739 |  | note | Acceptance Criteria - Survey each layer for conformance with tolerance. +/- 100mm Intermediate layers
label | 0b5f62b5-866e-531a-8404-35361f80cb8f |  | note | Inspection Type - WP
label | b9724469-ee15-5b52-8373-1e3bf0f13406 |  | note | Inspection Frequency - Every layer
date | 2ba0228d-8047-50a0-ae9e-f3175a15aadb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Test Rolling
label | bcdccfaf-63ec-584c-9c8b-d73705009761 |  | note | Specification Requirement - CL 205.07
label | 52c040c3-b494-5297-82e5-50bb89e149b9 |  | note | Acceptance Criteria - Undertake test roll for each layer as per Section 173. Rectify any identified failed areas.
label | 6a2d94c2-d4da-5777-b9f7-339a4f2f2f85 |  | note | Inspection Type - WP
label | 541fca32-ff98-5614-a76d-ef0fcb330667 |  | note | Inspection Frequency - Each layer
date | e4ceb2d7-0642-50aa-8b34-99ab83b7183e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Cover layers
label | 490aa373-1e8d-5dea-bab5-ef470b3b9073 |  | note | Specification Requirement - Table 205.051
label | b3cad17c-c925-5557-a605-ce89c9b9e696 |  | note | Acceptance Criteria - Material size and layer thickness per Table 205.051, Test Roll each layer
label | 19451025-19b7-5ff8-9438-44dd0d29493f |  | note | Inspection Type - WP
label | 9f6be9da-add2-555d-bbbc-971b28263225 |  | note | Inspection Frequency - Each Layer
label | 22e8284c-2439-5141-8492-89c9c6f5b5df |  | note | Records to attach - Test roll record
date | 211c7288-375b-58b6-a5e6-c306ed20f102 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Level Control
label | 8f2685d5-b955-57a5-b3e7-c6c6c611e8b7 |  | note | Specification Requirement - CL 205.05(d)
label | 301dec57-0bff-5add-962b-cb8ba0b0688d |  | note | Acceptance Criteria - Survey final layer for conformance with tolerance. +0mm / - 100mm
label | 8b99b232-4bd3-5e61-8d2d-12d645889867 |  | note | Inspection Type - WP
label | 07c011a3-00fb-5efc-afe4-b9429aeabc8c |  | note | Inspection Frequency - Every layer
date | e48413ae-f780-5340-b15a-5f2c098bdd20 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 - Geotextile separation
label | 2c33580f-58fc-5f9d-b596-8576009c2dcb |  | note | Specification Requirement - CL 205.05 (b)
label | b3dc900a-13e8-5eb8-9adc-ef098172dc63 |  | note | Acceptance Criteria - Geotextiles used in rock fill shall have G robustness rating greater than 3000.
label | 966f2a78-ce59-5602-b5bf-b282b57c8c0a |  | note | Inspection Type - Check / inspect
label | a6758ecc-20ca-587e-a3ab-5ecfcc9d0098 |  | note | Inspection Frequency - Prior to placing initial rock layer
label | 36bcddf0-00bc-5fdb-813d-5bee406e84ea |  | note | Records to attach - Specification sheet, roll label and manufacturers test report.
date | dc8f2c85-e402-5328-9a8a-4b85dd7cd47d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 302a440c-8d14-5e21-a3c5-f9cc0e769655 |  | note | The signature below verifies that this ITP has been completed in accordance with Gradco’s Quality System Procedures and verifies lot compliance with specifications
text | 1f0ff780-bd01-5ffc-85d1-af91606a93de |  | textbox | Print Name:
text | 70125ab9-9bc7-55e1-802a-d4e1b5cda5d3 |  | textbox | Position:
date | 967e10fd-5389-5b4c-a627-9ee72339e4c7 |  | date | Work Completed On:
date | 88b00910-b4a3-545b-a2d4-edb5aa184483 |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-012 - Line Marking | itp |  |  |  | Yes | CTN-ITP-012 - Line Marking | 953a8c32-b137-4ec7-863b-cd21939dd22c
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 1176e791-8bd9-5bda-a1cc-9943e8bff3e0 |  | note | Frequency - Prior to commencing any activity
label | 72c286c5-0b61-567a-9eff-717263db2677 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are: using the correct and complete set of drawings; all drawings are the latest revision
label | 3b19d345-ecc2-5921-b9c3-b753db8df22a |  | note | Reference Documents - Drawings and drawing registers
label | af9c9e9a-d32a-5d70-9526-a2d4211875a1 |  | note | Inspection / Test Method - Document review
label | 210c7718-1b34-5112-9ac3-9cfe52621da4 |  | note | Record of conformity - This ITP signed off
label | 1683b167-12ca-5592-b016-120710b5a221 |  | note | *HP
label | 4275dda2-685f-58fa-83f0-512fbc7ce27b |  | note | Responsibility - Site Engineer / Site Foreman
text | 1fd48bfa-24c0-5ad0-8523-d94d7ffa9ba6 |  | textbox | ITP Opened:
date | f84b248b-d7a3-5333-8bcf-718e1fae8cb7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 8fbf280d-fba2-50f0-bcc5-65802f96845e |  | note | Frequency - Prior to commencing any activity
label | efb2b174-9c88-5f7b-8620-8ea5e6ab84ae |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 5f885c1b-df99-58af-9c38-655db398b57c |  | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | f0435158-e498-542b-ba50-0b89a740eb63 |  | note | Inspection / Test Method - Visual Inspection
label | e5005c9f-7a04-5ea3-b4a5-1097b3464a35 |  | note | Record of conformity - This ITP signed off
label | 548c269b-bfed-5a05-9bb3-4efe62de3eb0 |  | note | *HP
label | 56c10a95-669c-5cf3-a7d1-7b530948df03 |  | note | Responsibility - Site Engineer / Site Foreman
date | 187aaa8b-4cdf-54ea-b7de-fd83e42e4a34 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Set out of line markings; dimensions and spacings
label | 00a316ad-4dce-5075-8c65-19b25dd82dd5 |  | note | Frequency - Prior to commencing line marking works
label | 95ad7259-07b7-5411-aa9b-a482444a19f3 |  | note | Acceptance Criteria - Hold Point: Painting/application of material shall not commence until the Superintendent has inspected the setout and given consent to proceed, unless a written exemption has been granted by the Superintendent
label | d818699c-9a47-557f-b815-0bcad402d57c |  | note | Reference Documents - Cl.721.B05
label | dfd727b8-1cb4-5c06-af77-fc6e067788f5 |  | note | Inspection / Test Method - Document review & Site inspection
label | 36f38844-548a-5a76-bc72-cd8cf0fb0c3a |  | note | Record of conformity - Consent to proceed by Superintendent OR written exemption granted. This ITP signed
label | c31ac3c5-ad65-5124-8a1e-55f76f94624f |  | note | HP
label | 8edf4d8d-7a5d-5f5e-9705-4c0aa477dea0 |  | note | Responsibility - Site Engineer / QAV
date | bdb7a9ce-d617-5717-bca2-b566aac97cd6 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Verification of line marking material
label | 762762f9-6d55-54ae-97d8-ecb23b996593 |  | note | Frequency - Prior to commencing line marking works
label | 301ebf99-dd41-535f-9ac4-fb5eba752d58 |  | note | Acceptance Criteria - Line marking material is to comply with minimum requirements as specified in Spec Tables 721.D021 and 721.E021
label | 6a361980-57e0-5ea9-996a-9b432e065abf |  | note | Reference Documents - Cl.721.D02 Cl.721.E02
label | 19095ab5-75c7-522d-8c8a-4b48c712a77d |  | note | Inspection / Test Method - Document review
label | cb5f0b50-a1be-5c83-91f0-4b1cf7fa73fa |  | note | Record of conformity - Material compliance. This ITP signed
label | 2c1a98a2-8295-5f98-b0c2-4d97026bb006 |  | note | IP
label | 16aec596-1d58-5ca1-9f13-a1cf27cfa2d5 |  | note | Responsibility - Site Engineer
date | 5b934b33-9178-5abe-84c1-2624fdc9d766 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Materials
label | b12da231-963f-52af-a9b6-d7d0fd6cea38 |  | note | Frequency - Each lot
label | eafaf835-9566-5a5a-bdcc-e42c0149dbae |  | note | Acceptance Criteria - Markers shall comply with the relevant requirements of AS 1906, Part 3. Epoxy adhesive shall be Standard Set or Rapid Set adhesive complying with the relevant requirements of AS 3554
label | f6ece83d-c877-5d19-9711-34f6b77cdb57 |  | note | Reference Documents - Cl 710.03
label | b7872d4a-1e43-55bc-8d49-345344385f43 |  | note | Inspection / Test Method - Visual Inspection
label | 83d7da78-07d4-583e-b832-c99d5f543ebd |  | note | Record of conformity - This ITP signed off
label | d88e650c-d43e-52b9-85b5-a7beb5ce7184 |  | note | IP
label | daa40829-7dd2-5280-bc6e-a6c98492769d |  | note | Responsibility - Site Engineer
date | 544dc6ff-bd17-5ecb-9892-d88ad316984b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Preparing Adhesive
label | b125deed-8f10-5b11-9dc3-e37869511dab |  | note | Frequency - Each lot
label | 3e11a750-bcce-5b5e-aa3c-8ac9f73e4197 |  | note | Acceptance Criteria - Adhesive components shall be batched so that the mixed adhesive contains not less than 45% nor more than 55% by volume of either component. Before starting work each day, or when changing to a different batch of adhesive, a hand-mixed colour standard shall be prepared for reference during the day. When hand-mixing is used not more than 500 g of each component shall be mixed at any time. The components shall be mixed on a flat surface and the mixed adhesive shall be used within 10 minutes of the time the two components are brought together. Hot melt bitumen adhesive shall not be used on days of total fire ban without the written approval of the Tasmanian Fire Service
label | 05991ec7-d8f9-5bcb-813d-afafc301aea1 |  | note | Reference Documents - Cl 710.04, Cl 710.05
label | 20afd2ca-e4a7-5454-bcbb-b57fab0440e5 |  | note | Inspection / Test Method - Visual Inspection
label | d3ab3b07-1ac3-54ff-b7b2-4cd456070ddb |  | note | Record of conformity - This ITP signed off
label | 3a064061-ca06-5550-a52c-bcacbba5502f |  | note | IP
label | abfa6d24-b40c-5461-adac-313af5066d52 |  | note | Responsibility - Site Engineer
date | cca41a7a-7bee-5e03-b2a2-2a473b052f0e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Pavement preparation
label | 6847139a-81f1-5d20-a702-f27aa6c1a1d1 |  | note | Frequency - Each lot
label | e94a0258-44af-5ddd-b668-6795d5f44491 |  | note | Acceptance Criteria - The Contractor shall sweep or air blast each marker site as necessary to remove loose material before placing markers. Markers shall only be placed at locations where the pavement is free from dirt, oil, grease, paint, or any other material
label | f0452da6-0ace-5057-8423-b8c71cfba539 |  | note | Reference Documents - Cl 710.06
label | e55ffe59-14b0-59ed-b051-e07b1e340e1d |  | note | Inspection / Test Method - Visual Inspection
label | dba40b86-175d-5b9c-a902-e4a48f7b55d5 |  | note | Record of conformity - This ITP signed off
label | acd02567-8d66-5ae1-811a-068160d101fa |  | note | IP
label | 19499dfc-c826-5746-9ac4-508ae9186f01 |  | note | Responsibility - Site Engineer
date | 0de67cdf-5213-5452-9dba-aa7729e56426 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Placing markers
label | df2176b6-edf0-55e9-a8ae-c13d99c3e98f |  | note | Frequency - Each lot
label | 5599792e-e3c8-53a3-8f97-ad3e462cd154 |  | note | Acceptance Criteria - Markers shall not be placed in any of the following circumstances: when the pavement is wet; when the relative humidity is greater than 80%; when the ambient temperature or the temperature of the road surface is less than 15deg for standard set adhesive or 0deg for rapid set or hot melt adhesive. Where a marker is not positioned correctly within 10 seconds for hot melt bitumen adhesive, 2 minutes for rapid set machine mix adhesive, 4 minutes for standard set machine mix, or 10 minutes for standard set hand mix from the time mixing commences, it shall be discarded and a new marker placed.
label | 98b29e63-a31f-5276-967b-fd62cd29f5a1 |  | note | Reference Documents - Cl 710.07
label | 526cc9a3-0957-58a9-ac98-60e3cb3041d0 |  | note | Inspection / Test Method - Visual Inspection
label | 8e176c7f-6dcb-51f1-a910-c91335940234 |  | note | Record of conformity - This ITP signed off
label | 3e1d820f-8ece-5d78-9c0f-77d649640119 |  | note | IP
label | 8f919f7e-06b6-5e01-b6c6-8a93d99f5244 |  | note | Responsibility - Site Engineer
date | d7754b4e-e357-568e-ba4d-e5a69478a291 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Tolerances
label | 86577256-30da-5146-982c-4d0bf6262f80 |  | note | Frequency - Each lot
label | 053964e4-5e69-557d-bf6a-b3780cc40a3e |  | note | Acceptance Criteria - (a) Markers in Line with Broken Line Segments Transverse position within 25 mm of the centreline of the segments. Longitudinal position within 0.5 m of the specified position.
label | fc64045b-2581-5757-ad82-e16356412cd6 |  | note | (b) Markers in a Longitudinal Group: Transverse position of the centre of each marker within 25 mm of the specified position and within 10 mm of a line joining the centres of the end markers of the group.
label | 926ee1da-8e32-5df9-8cd4-a78066043458 |  | note | (c) Markers Adjacent to Unbroken Line: Clearance to edge of line within 5 mm of that specified. Longitudinal mismatch between markers in transverse pairs at barrier line not more than 25 mm.
label | 844b73c8-4f6c-5b2a-b8e0-83c5dfa2f873 |  | note | (d) Orientation of Reflective Markers: Lower edge of the reflective face at 85deg to 95deg to the centreline of the roadway or any adjacent line.
label | db0f7dbd-b2b0-5364-93a3-299b594b38ac |  | note | Reference Documents - Cl 710.02
label | 5dbebecd-1302-5d71-9865-6066de2d81a5 |  | note | Inspection / Test Method - Visual Inspection
label | 8869c61b-7bea-5bc6-b83c-382b67836f14 |  | note | Record of conformity - This ITP signed off
label | 25b01c18-7e82-5cc6-b49c-aaa2c040bf49 |  | note | IP
label | 4b47e977-3e51-5d38-b011-e69597ba4cb3 |  | note | Responsibility - Site Engineer
date | 52f9743d-16ce-5695-925e-74a45f49b509 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 - Line Marking Tolerances
label | a65e8b48-9845-53ed-a10f-28696745e81b |  | note | Frequency - After completion of works
label | d45db907-1652-58d8-b325-24a127d014e4 |  | note | Acceptance Criteria - Line marking shall comply with the tolerances shown in Table 721.A101.
label | d07edb34-d9e9-5c14-b07d-08727299e3e7 |  | note | Reference Documents - . Table 721.A131, Project Spec. Table 721.A101
label | 3dbadd4b-3f15-5846-aecf-e6d56db594f3 |  | note | Inspection / Test Method - Document review & Site inspection
label | bd251e58-63bf-5b47-98a3-6dd4884d9b24 |  | note | Record of conformity - This ITP signed
label | 5c2a6afa-c4aa-57ed-a7d6-ac9147855cc9 |  | note | IP
label | e120ad1d-6575-5f26-b66a-964dcd1e572e |  | note | Responsibility - Site Engineer
date | 75b26398-11ee-5f58-a84b-829a0a8dc671 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Removal of Non-compliant marking
label | b86d781b-0a2f-5641-b983-38ce97197881 |  | note | Frequency - After completion of works
label | 5ae4dcf4-f6f4-5a05-a99a-4c53735286da |  | note | Acceptance Criteria - Hold Point: Where the removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence
label | 1aabeaea-18d9-5d86-9580-c92e9092de45 |  | note | Reference Documents - Project Spec. Cl.721.A12
label | d416c93c-b664-552b-9cab-bf1dfa484d54 |  | note | Inspection / Test Method - Document review
label | f78fa274-ed98-5bc1-b374-f4ecdb8bc08c |  | note | Record of conformity - Approval from Superintendent, This ITP signed
label | bd78d2b2-90e9-504a-8e58-7df2478eb88c |  | note | HP
label | 0280e25c-cfe7-5228-8530-fe2890716f6a |  | note | Responsibility - Site Engineer / Superintendent
date | f0f943f1-67ce-531d-b877-af720625025d |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Final Inspection - Fulton Hogan
label | 346d526e-d467-53c3-a527-c808b6fbe445 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 7f5dffe8-7b8f-58bf-b527-e83ea2043702 |  | textbox | Print Name:
text | f5c7e58b-e692-5b2c-8640-3cb3a7f8943d |  | textbox | Position:
date | fbaaecd6-1904-5fef-a8b3-ad687c26c745 |  | date | Work Completed On:
date | 461d5940-914c-5124-b829-9e03cdf014d8 |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-011 - Wire Rope Safety Barrier Installation | itp |  |  |  | Yes | CTN-ITP-011 - Wire Rope Safety Barrier Installation | 9d770073-9cf7-4b4a-87d8-5c4f54c69518
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 2a3dbf67-d8e3-531d-94b2-44877f0c3b5b |  | note | Frequency - Prior to commencing any activity
label | 7c83af1e-2ffd-55d8-97cd-beccaf811d4c |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are: using the correct and complete set of drawings; all drawings are the latest revision; conflicting documents will be referenced to the heirarcy of documents listed in Section 175.03
label | 96049d35-981c-5c17-bd9a-258d7bad6484 |  | note | Reference Documents - Drawings and drawing registers; 175.03
label | 1a3ae80b-2c78-5dbc-ac4f-00b4d2db44c6 |  | note | Inspection / Test Method - Visual inspection
label | f8fe6e71-ab2e-561b-8236-5131416773f9 |  | note | Record of conformity - This ITP signed
label | 56d59150-87f3-55f0-a0a9-855ec5df9b26 |  | note | HP*
label | 0a7f817e-00ab-5abd-aeea-d6899ec7d0f8 |  | note | Responsibility - Site Engineer
text | d5bf3331-3ce1-5104-8895-fc96f8d6adca |  | textbox | ITP Opened:
date | 3cb0b431-2f79-59bf-91bf-91cd0c99f7ee |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 9aa7c475-2bc0-56b2-a999-283ac87ed82e |  | note | Frequency - Prior to commencing any activity
label | 1f43f7cb-d654-543f-af73-6f4f5077bff0 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 59c02a21-066b-5bea-9bc5-19b80734bd12 |  | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | 9b757bdb-50bc-5f1c-8d53-34854830e5bd |  | note | Inspection / Test Method - Visual Inspection
label | ef720af6-9fdc-52e9-9d79-bfecd12816ce |  | note | Record of conformity - This ITP signed
label | f7ef051b-0d13-556a-be4f-2160422208d1 |  | note | HP*
label | 87272960-30b5-5993-866f-ccdcaab4335d |  | note | Responsibility - Site Engineer
date | f48bc33e-e012-5ca5-9b49-c25e2e8432a4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Materials used comply with the relevant standards
label | e9daf5b9-e7d6-589c-8552-c6b44a5df980 |  | note | Frequency - Not less than 14 days
label | 53d87434-d817-5ca7-96e9-9f14ec620ec2 |  | note | Acceptance Criteria - Hold Point: Material are in accordance with Australian Standards and VicRoads specification (section 711.02) Superintendent to sign statement and certificates of compliance. The installation of the WRSB shall not proceed until the signed statement and certificates of compliance have been accepted by the Superintendent.
label | cc8cf4ce-12e5-54b4-8ab9-994a4e50fc82 |  | note | Reference Documents - Cl. 711.05
label | ab990dca-fff7-5953-a7c7-235aed489e49 |  | note | Inspection / Test Method - Verify
label | b75c90a8-3794-5214-85e9-a84134e9f41d |  | note | Record of conformity - This ITP signed
label | 2d9dc36a-0ff9-5351-8433-a64b552718cf |  | note | HP
label | 0e79a67a-fb6b-5518-8f54-98f4b490c8a4 |  | note | Responsibility - Site Engineer / QAV
date | ae03f7a1-0b3d-53c1-94c5-29adb7256cce |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4 - Check design and manufacturer's acceptance
label | 546687b4-5397-57e5-b0f1-1ebd18a5dd8b |  | note | Frequency - Prior to Commencing
label | 1d3b042c-df79-52e0-a1b4-c5af52046143 |  | note | Acceptance Criteria - Hold Point: Anchor blocks and post foundations shall not be constructed until the Design and manufacturers acceptance has been reviewed by the Superintendent
label | a1eb9feb-ebb6-5205-b814-1e82f070347f |  | note | Reference Documents - Cl.711.07 (b)(ii-2)
label | c6c15812-d7bf-57d6-9754-b27d111646e5 |  | note | Inspection / Test Method - Document Review
label | 63c0b95a-5f58-599d-bcc3-aee36979c8e6 |  | note | Record of conformity - This ITP signed
label | 2eab1fde-8deb-52b4-894d-4391b0ffef9d |  | note | HP
label | a24ab21c-e383-5fbc-90fb-f01595c197e6 |  | note | Responsibility - Site Engineer / QAV
date | 556dcb2c-ef1a-5848-90c6-11bab62bd429 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.5 - Setout
label | 8e295076-a1fa-5f21-b14f-829d3508278c |  | note | Frequency - Prior to Commencing
label | f9d55a78-fdb2-5f22-8dc2-ab87b76c8fb2 |  | note | Acceptance Criteria - Hold Point: WRSB not installed until the set out alignment of the posts has been reviewed nad accepted by the superintendent. Allow at least one working day for Superintendent to inspect the pegged alignment and minimum 5 working days to provide its acceptance, including any changes.
label | ccde499e-19f0-5d93-a6c0-015f3f6404df |  | note | Reference Documents - Cl.711.07 (c)
label | c188f28b-b2bd-55ca-a210-41b4f99410a0 |  | note | Inspection / Test Method - Verify
label | 43af5e80-3874-517a-a1e4-5c2e9ff3dfce |  | note | Record of conformity - This ITP signed
label | aeba1ca5-6bdc-53f7-b49a-c9a0c5a0d6b0 |  | note | HP
label | 9c636eb6-4cba-50a0-b3eb-2cab0e21c197 |  | note | Responsibility - Site Engineer / QAV
date | 069a88ee-62da-5448-9072-ba03ce3882ab |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.1 - Auger Post Holes to correct depth and alignment
label | e2b56e1c-f0f6-50c2-a3c2-32885024ef12 |  | note | Frequency - Each lot
label | 893c6da4-9ae0-588b-80b0-133a150ce2b1 |  | note | Acceptance Criteria - Post holes depth and diameter as per Austroads Safety Barrier Technical Conditions for Use
label | 3d4996bd-4acb-5a3d-a3b3-b0aa8645045e |  | note | Reference Documents - Austroads Technical Conditions for Use sheet
label | 2b849fe5-8005-507d-88ba-8928ab4bb4a1 |  | note | Inspection / Test Method - Verify
label | 4d75f23a-79c0-536b-982a-9a72dec07e10 |  | note | Record of conformity - This ITP signed
label | d530b4eb-e673-5882-af96-00a6cccd3f31 |  | note | IP
label | e42613db-be28-5ec2-a059-32b7968cf050 |  | note | Responsibility - Site Engineer
date | 4d358464-adcf-5b42-93bd-e5b23726400d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Tolerances for WRSB
label | 6f3faf7b-8c94-5b62-8c38-fd82637316ec |  | note | Frequency - Each lot
label | 01881858-cec6-5521-844a-6b4e947a0167 |  | note | Acceptance Criteria - Vertical & longitudinal tolerance: -/+ 20mm from the design line. Post spacing tolerance: -/+ 25mm. These tolerances are to be checked against survey set-out. Any adjustment shall be as per the manufacturers specification and obtained written statement of advice, which shall be submitted by the Contractor for review by the Superintendent.
label | 88c67535-ee8d-5f52-a21c-732907a67403 |  | note | Reference Documents - Cl.711.08
label | dc538d4a-55f0-5251-88e9-8720f8137be5 |  | note | Inspection / Test Method - Measure
label | d395103c-557b-5591-a281-f7efa28eb6f2 |  | note | Record of conformity - This ITP signed
label | 052fc671-a706-588a-9a1f-232ecc099a2a |  | note | IP
label | ad989dfa-1c34-5883-acfb-0d15da53de1d |  | note | Responsibility - Site Engineer
date | 8cc52de3-d64b-5c58-976c-386d458668e7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Excavate for Anchors and Post Foundations
label | 76b8c18c-cb74-5eab-aa10-a3db6eb35d69 |  | note | Frequency - Each lot
label | 76402e4b-ad33-5702-864d-6bb2242c4698 |  | note | Acceptance Criteria - Anchor block and post foundations excavated to size as specified in manufacturers installation manual. Holes free of loose material and water prior to placement of concrete
label | a86ae264-f5db-5929-b22e-cc52cba7a89b |  | note | Reference Documents - Cl.711.07(b)(iii)
label | 7a9001bc-06b8-55a6-8c80-aa8683b5c83d |  | note | Inspection / Test Method - Measure / Visual Inspection
label | 370c0959-edf0-52a5-81f5-79c7301f9cd5 |  | note | Record of conformity - This ITP signed
label | 2f47b0d0-b7dc-57b7-a927-96880508ec71 |  | note | IP
label | 7e8867b0-bd8d-512f-ae7e-ff6eaee7bb2b |  | note | Responsibility - Site Engineer
date | 2eaeeebc-ca2e-5eca-adaa-4fced81039ef |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Install Anchors and Post Foundations
label | c3092805-65e4-5a79-bf96-1626ec635c2b |  | note | Frequency - Each lot
label | 2cf24a42-7296-5d4c-8b16-a9eeec86c699 |  | note | Acceptance Criteria - Hold Point: Anchor blocks and post foundation shall not be cast until inspected by the Superintendent. N32 concrete to be used for terminal anchors and N25 for post footings
label | 865e6234-3995-5240-bd46-28512a1e9503 |  | note | Reference Documents - Cl.711.07(b)(iii)
label | 41d35899-a153-5b9b-90ce-54c5c9c7c21c |  | note | Inspection / Test Method - Verify
label | 5bf4d916-4924-5464-b21d-c0b1c6f04280 |  | note | Record of conformity - This ITP signed
label | 271bef86-51f6-5ed1-aae9-7b2fdc97d184 |  | note | HP
label | c23e7568-d477-5133-8823-379a4d4be561 |  | note | Responsibility - Site Engineer / QAV
date | 35c910a9-3188-57e1-bb3a-a544504eb663 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.5 - Loading Test of Post Foundations
label | 250a8875-2d56-5ff4-acc4-2cee31d8fe6b |  | note | Frequency - Prior to installation of wire rope
label | 89dbb48f-23d1-5d5b-a80d-8cba4fd52522 |  | note | Acceptance Criteria - Witness Point: Side loading undertaken at locations nominated by the superintendent. Side load testing of posts shall be carried out by applying a force of 10 kN (approximately 1 tonne) to the post 600 mm above ground level at an angle of 45 degrees to the WRSB. The top of the footing shall not move more than 3 mm. If the footing withstands the force with a movement of less than 3 mm at ground level then the footing shall be considered acceptable.
label | b5aa0853-4aea-53a3-8893-c2bc913cf3dc |  | note | Reference Documents - Cl.711.07(f)
label | 272120e7-c6e6-543b-89a7-60ff39dd6513 |  | note | Inspection / Test Method - Verify
label | da26baa9-7791-5dff-ad77-7ab57fcf657e |  | note | Record of conformity - Test Records
label | 6b3f4086-0f7f-5d38-affd-dafe25ab08f6 |  | note | WP
label | 4cb70d8b-ce3f-5c8a-8a9f-88848da9a90e |  | note | Responsibility - Site Engineer / QAV
date | c6e66ccf-3c0b-55e7-a149-cc5bb649cf0e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Install wire rope and tension
label | 10326b93-2fdd-5ecf-9d8c-bdd00e5a8da5 |  | note | Frequency - Each lot
label | 1e8429c6-4984-5088-9d04-9e2e43b68e79 |  | note | Acceptance Criteria - Wire rope tensioned as per Manufacturers Spec. Tension to be measurted by tension meter with current calibration certificate. The Contractor shall prepare and submit a tensioning report for review by the Superintendent within seven days of the tensioning works being carried out
label | ad137df0-2957-5c64-b1aa-0d66d81b16d2 |  | note | Reference Documents - Cl.711.07( e)
label | 0a70ae24-2f84-5eeb-8deb-bcbc3a63fa22 |  | note | Inspection / Test Method - Verify
label | c4f387a4-aed8-5128-b2b4-8d28274282cd |  | note | Record of conformity - This ITP signed
label | 931eded3-65ec-5358-99ac-d9158397e545 |  | note | IP
label | 910d8e9d-832b-59fc-b083-e408ca3092a3 |  | note | Responsibility - Site Engineer
date | 40f5df57-c62c-5a07-98a1-8e9fdf671505 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Install Delineators
label | 7d1ec864-13cf-5af1-b2be-de355df03120 |  | note | Frequency - Each lot
label | 509147ea-1596-54de-a34d-479969fb9c6b |  | note | Acceptance Criteria - retro reflective post caps fitted to post above wire ropes as a spacing of 12.5m to 15m. Delineators relative to drivers should be red on left side and white on the right side
label | 33bfbb82-fc38-597b-a6e1-8d80511536ba |  | note | Reference Documents - Cl 711.10
label | 5bce4772-733c-5596-b0f2-be6af170074d |  | note | Inspection / Test Method - Visual inspection
label | b12c8aab-04e2-5114-bd6e-c0ed3a6e27c3 |  | note | Record of conformity - This ITP signed
label | 25da9f16-0742-5651-a2d4-de9e65d55d42 |  | note | IP
label | d728ef9f-e4e6-57fb-bfee-1887de2b2e36 |  | note | Responsibility - Site Engineer
date | 84caaf76-e446-5f44-b2b4-de08245994d5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Stray currents
label | 7a2fad57-375a-538b-a55f-fa50660c7220 |  | note | Frequency - Each lot
label | 5f9e6fe3-dabc-53c5-b57c-abd25e33da50 |  | note | Acceptance Criteria - Tests shall be undertaken at each location where two sections of WRSB overlap at anchorage points. Where an induced current or voltage is recorded, or high voltage powerlines are within 50 m of the barrier, WRSB system shall be earthed to remove current or voltage running through the wires. If required, earthing procedure and spacing to be carried out in accordance to the specifications and reviewed by the Superintendent.
label | b9da0c27-47f5-5b91-823e-bdc78f12cd1f |  | note | Reference Documents - Cl.711.11
label | d41c953b-5bb7-5bac-a4ec-2de631f08f78 |  | note | Inspection / Test Method - Site inspection
label | 3175cb1d-b48b-5639-8823-2c8e0502ecb7 |  | note | Record of conformity - Copy of electrician test readings and Signed ITP
label | 177f07a2-23f3-5b71-be4f-15dad1826e1a |  | note | IP
label | 31d7a09c-79a5-578b-a016-f2e366faec7a |  | note | Responsibility - Site Engineer
date | 0ecd19e4-ce38-5aa5-8cc6-d3bb1cfe2176 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Compliance Audit of Barrier System Installation
label | 8c02e983-0c77-5610-84bf-a8b7c8f23fb1 |  | note | Frequency - Prior the issue of the Certificate of Practical Completion
label | 9f0c1ad3-7ab6-5ee2-9c6e-75a32fd750fd |  | note | Acceptance Criteria - Hold Point: Arrange for a safety barrier compliance audit on all WRSB installations constructed under the Contract. A Certificate of Compliance shall be provided for each end treatment and length of WRSB installed. A signed copy of the manufacturers Installation Checklist / Inspection and Test Plan as per the manufacturers Product and Installation Manual shall be completed and submitted to the Superintendent.
label | b707871b-e733-57b7-a74f-275bd7724b16 |  | note | Reference Documents - Cl.711.09
label | 718d43a3-87df-5ae4-ab99-b8d625b3abad |  | note | Inspection / Test Method - Safety Audit
label | cfa8a88c-4cbb-51fb-b2cd-9e2432e5eb28 |  | note | Record of conformity - Completed copy of the manufacturers Installation Checklist / Inspection and Test Plan as per the manufacturers Product and Installation Manual submitted to Superintendent & Safety barrier audit report
label | d533ff32-e792-5e23-9758-dbd5ef1da18b |  | note | HP
label | 17f84913-935d-5641-a384-35e0fdd27055 |  | note | Responsibility - Site Engineer / QAV
date | 2ea49844-66f3-55f6-986d-a3a31ad92718 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Final Inspection - Fulton Hogan
label | 06edec1d-9c5c-596e-84b2-aa911ecbc402 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 3e63a76c-6721-5809-9817-2ff9245f3238 |  | textbox | Print Name:
text | a9d6fd71-356c-5077-9d6d-3e48d2830cc9 |  | textbox | Position:
date | cec24f99-4c39-5259-84d3-4807aaf10d22 |  | date | Work Completed On:
date | e6d39c75-c376-5be7-affa-622372b48df4 |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-006 - Asphalt Placement | itp |  |  |  | Yes | CTN-ITP-006 - Asphalt Placement | 9ec97c74-5a77-45d7-af35-a4278b135851
checkpoint-status |  |  | checkpoint | 1.1 - Submission of Mix Design
label | 0b7d095a-de75-5358-8918-08159b90aa0d |  | note | Frequency - Prior to commencing paving
label | de90ea08-9784-5815-860f-75eb58e9b2f4 |  | note | Acceptance Criteria - No Asphalt shall be supplied until the mix has been registered and the superintendant approves the mix for use. Only use mixes that are registered by State Growth as 'General Mixes'
label | 78b3892a-e4d7-56cf-a6b8-e7ca48fc190f |  | note | Reference Documents - Cl 407.06
label | 8349b89f-9270-5794-b39d-a79f8c7c849f |  | note | Inspection / Test Method - Verify
label | 570c77e1-5854-5c71-8dc3-9a086ce5af7c |  | note | Record of conformity - Mix registration & correspondence
label | 27a040ce-9042-5de4-af73-1e9026d5dc41 |  | note | HP
label | ff9e8ea4-6031-5fda-866e-e7c69a20f19d |  | note | Responsibility - FH Engineer/ Asphalt Supervisor / QAV
text | cc07b01a-836b-5f7e-8769-ba0864100161 |  | textbox | ITP Opened:
date | c602b284-840c-53bc-94e9-c3d7c1910df7 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 3ab8101a-32e8-59c6-9c02-fe9e2d53c09f |  | note | Frequency - Prior to commencing any activity
label | 8e377d3c-2eda-5286-a4a8-6c0a8b42b80a |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 27f5b08d-f136-58ed-a7d6-3fcbe2e1caa8 |  | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | c9992684-0280-563b-973c-d4f369465c25 |  | note | Inspection / Test Method - Visual Inspection
label | caa643a7-3cc3-593d-b01e-341846ec749d |  | note | Record of conformity - This ITP signed off
label | 550e3159-6e5b-58ca-86a5-6042632e47b5 |  | note | HP*
label | 95282532-cf05-5c32-a71e-876c387cec6f |  | note | Responsibility - FH Engineer
date | d79a4b2c-4cdd-5968-a8c5-69e26c2753b5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Site Inspection and Base Condition
label | 4d6fa075-bea9-5526-8ce9-bebe42f2c367 |  | note | Frequency - Prior to commencing paving
label | 492b7c85-ac4a-5554-a563-b5817680af26 |  | note | Acceptance Criteria - Surface on which asphalt is to be placed is essentially dry and free from surface water, defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | b5fa2b6e-c905-5df3-80a3-1cb4b6f6af8e |  | note | Reference Documents - Cl 407.13, Cl 407.15, AS2150 10.1, AS2150 10.3
label | ef3bb8ff-270d-5cf8-aa57-ff4a279372c2 |  | note | Inspection / Test Method - Visual Inspection
label | 8a35f413-bcc3-5c84-94f3-8d6bccfe3cc1 |  | note | Record of conformity - This ITP signed off
label | 679c4ff7-a6f9-506e-a70c-c66fbed36b9b |  | note | IP
label | 0747fa88-12d8-59fb-9164-acbf524ae4cc |  | note | Responsibility - FH Engineer / Asphalt Supervisor
date | 5adbf571-44d4-508f-a36a-101e82980ac2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Ambient Conditions for Placing
label | 04d76112-46eb-5285-9b51-22b922f0c683 |  | note | Frequency - Prior to commencing paving
label | 39ffc2c5-f49e-5d59-b6be-1b0892b8ca26 |  | note | Acceptance Criteria - The majority of the surface area to be paved has a temperature greater than or equal to the following: Base & Intermediate Courses: 5°C for conventional binders or 10°C for asphalt mixes with PMB and Class 600 binder. Wearing Course: 10°C or 15°C for mixes with polymer modified binder
label | dcf35701-e09a-5a01-82ec-07e64c7dbfae |  | note | Reference Documents - Cl 407.13
label | 829749bd-46ff-5a3f-add0-9748e676d9ce |  | note | Inspection / Test Method - Verify
label | 34e7a55a-c703-534d-98a1-18f0f9779ce6 |  | note | Record of conformity - This ITP Signed off
label | 1d265aaa-a54b-5e57-bdc4-348a4b6d243b |  | note | IP
label | a42c3df3-b43f-5140-8275-967edfd7d25d |  | note | Responsibility - FH Engineer / Asphalt Supervisor
date | 11017ec3-52ab-5d2d-85c1-4d342e9f174b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Tack Coat
label | 716b6de5-ec8c-5d49-a287-236d4316019e |  | note | Frequency - Prior to commencing paving
label | 72e10bd9-eb75-53d9-8ea4-d5d8f6b9a937 |  | note | Acceptance Criteria - Tack coat shall be sprayed in a uniform film over the entire road surface. Tack coat must be allowed to change colour from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client or if the unsealed surface has been primed
label | b803c61c-0276-5536-bf90-d181e5bcb355 |  | note | Reference Documents - Cl 407.15 AS2150 11
label | 13a467d9-82d0-5d31-90d0-06cf9818efd5 |  | note | Inspection / Test Method - Visual Inspection
label | bd7f181a-f4fb-5316-8a26-683e3ec26841 |  | note | Record of conformity - This ITP Signed off
label | af18ab19-b300-5017-96e1-8dd990976d38 |  | note | WP
label | 248f3681-2444-5868-9d63-72c3e13c3e5e |  | note | Responsibility - FH Engineer/ Asphalt Supervisor
date | bea3d723-89d1-534d-b7a8-e8b6a36ef1d5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Commencement of Placing
label | 68b15c7a-3794-50f5-b7b2-bf8570736e9b |  | note | Frequency - Prior to commencing Paving
label | bd65dd5f-3c08-581a-9b24-094a7e073984 |  | note | Acceptance Criteria - The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Superintendent
label | 95e5bb6c-0649-59ba-9f58-5bfd64489143 |  | note | Reference Documents - Cl 407.18
label | 086fb7c5-d27b-5206-bb60-0be000b4f22e |  | note | Inspection / Test Method - Visual Inspection
label | f5d3fb64-1c31-566b-b3c9-95417fde7282 |  | note | Record of conformity - Hold Point Release
label | 5f2cb84d-9019-598f-82e5-7ae161a03fdf |  | note | HP
label | 976ba80d-aa30-5f7d-b8a2-ae78cd376592 |  | note | Responsibility - FH Engineer / QAV
date | aa3b417f-8f27-5973-9c6a-7f7a95427ef7 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3 - Delivery of Mix
label | d651c8b2-b8e2-5b2c-b92f-8803f0b81f74 |  | note | Frequency - Each load
label | 908ceda2-4b6a-5988-a329-1d4009f8fa27 |  | note | Acceptance Criteria - Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | 2194711e-c69a-5eba-a763-a88d3e65ad4b |  | note | Reference Documents - Cl 407.08 Table 407.081
label | b7305c5d-4acc-5157-ab2c-4dde63bbfbcc |  | note | Inspection / Test Method - Visual Inspection
label | ccb93379-c3ed-5aeb-ae87-336d77f88969 |  | note | Record of conformity - Delivery Docket /Asphalt Traceability Sheet
label | 8150ffc9-9ad7-5483-8df9-23b469aaa2f0 |  | note | IP
label | 08fb566d-5b69-53f0-a8f3-7178878a4c3e |  | note | Responsibility - FH Foreman / Asphalt Supervisor
date | f501e9a0-b6cc-5fef-9be1-46112843f78c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Layer Thickness and Level Control
label | c86d8594-6bab-5434-a624-eb9a7c2ca11f |  | note | Frequency - Regularly during paving
label | fa912e27-c045-5e92-97b7-6393ca693f54 |  | note | Acceptance Criteria - Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | 01ead0cd-828b-5b5a-b87f-82663fac2978 |  | note | Reference Documents - Cl 407.20 Drawings
label | 54c105b6-eb9d-582c-bccf-97fdd4591390 |  | note | Inspection / Test Method - Verify
label | a3585c24-c700-5678-a946-542df3b8057b |  | note | Record of conformity - Dips using ruler or dip stick
label | da132b17-5662-5ac5-b214-179ccf3b7fdc |  | note | IP
label | 45bd8090-7525-5ee0-8a16-5d87dd381285 |  | note | Responsibility - FH Foreman / Asphalt Supervisor
date | ab9190a3-8763-54ea-9618-80832f3fad72 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Paver Stoppages
label | 9467fa94-f0cb-5062-9246-d44ce8261204 |  | note | Frequency - If paver stops
label | cd4cce85-c064-55ab-80dd-9d71e35018f0 |  | note | Acceptance Criteria - A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
label | d67c88cd-7e3f-53b7-99e5-c88a706ae005 |  | note | Reference Documents - Cl 407.20 (c)
label | 47853ffb-fd50-5551-b3bd-6e71a2465007 |  | note | Inspection / Test Method - Verify
label | ac82d2ca-f181-522a-98df-eb068d04bab6 |  | note | Record of conformity - Thermometer
label | 6b4e23a8-06b7-5778-86e9-7b3192f1fb7d |  | note | IP
label | efaf63df-4f9a-5304-829c-0b6a78303094 |  | note | Responsibility - FH Foreman / Asphalt Supervisor
date | c171efec-314a-5d41-a6c3-3f8fddf7bd4e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Surface Finish of Wearing Course
label | 4715fac0-817a-5f89-a02d-fc80fc376c2c |  | note | Frequency - During paving and after final roll
label | 26d071c8-91fc-529d-8bb0-85ffa20e1337 |  | note | Acceptance Criteria - The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | 29cc645c-cd64-5008-957f-ccadeb017364 |  | note | Reference Documents - Cl 407.23 (a)(i)
label | 6e350885-efd2-5381-ad52-64b056450c11 |  | note | Inspection / Test Method - Visual Inspection
label | 37ffc919-bd88-52ae-af4b-5d2dfbdb1ada |  | note | Record of conformity - This ITP signed off
label | 1ca8b012-a524-5e52-9a2f-ca4c48d98027 |  | note | IP
label | faaedd88-25eb-53d3-a46d-da183ad3a623 |  | note | Responsibility - FH Foreman / Asphalt Supervisor
date | de4cdd21-da45-589a-9d80-57dc3a98dd83 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Kerb and Channel
label | 275daa34-53e5-579f-ae33-70e90d40aa6a |  | note | Frequency - During paving and after final roll
label | a80a0eb3-fa55-5fdb-b280-094d31988f71 |  | note | Acceptance Criteria - Where asphalt is placed against kerb and channel, The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel
label | 5fd09980-33d6-5494-9bca-e18d580992e4 |  | note | Reference Documents - Cl 407.23 (a)(ii)
label | 26d1ad91-c14c-58ed-bb3b-9d1ec4f34683 |  | note | Inspection / Test Method - Visual Inspection
label | 447c7db4-3115-588c-bd70-e894e2f259b5 |  | note | Record of conformity - This ITP signed off
label | cb42f519-d628-5d31-89df-d81a87d4c365 |  | note | IP
label | f048e372-fdc4-51e6-a713-68e50558b849 |  | note | Responsibility - FH Foreman / Asphalt Supervisor
date | 20c4dfd3-15d9-56d2-879b-21a312645feb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Alignment of layers not placed against concrete edge
label | ecf0d04e-6fdf-59f9-9284-bf408f551695 |  | note | Frequency - During paving and at completion of work
label | cb50e14a-988d-5335-af52-d87d2750eca8 |  | note | Acceptance Criteria - The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | 2bf9dd22-8329-56e1-9c42-f6c430fd88fd |  | note | Reference Documents - Cl 407.23 (a)(iv) Drawings
label | 75800dc4-33cf-56e3-85a4-f6b807593781 |  | note | Inspection / Test Method - Visual Inspection
label | 371437d4-3eaa-56a6-a347-f52cf4aefd29 |  | note | Record of conformity - This ITP signed off
label | 57cbb2fe-5965-5fde-a5b4-541bd7112b2e |  | note | IP
label | 2db91f99-4f39-5807-b30e-dafa5e76b780 |  | note | Responsibility - FH Foreman / Asphalt Supervisor
date | 9b9e2e74-89fd-53ac-b17f-4d4fe2cad609 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Width of layers not placed against concrete edge
label | 56c087a2-28cf-5866-b4f9-ba3237d6aa81 |  | note | Frequency - During paving and at completion of work
label | c7670e72-6998-50d2-9adc-1c198207163e |  | note | Acceptance Criteria - The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm. The average width over any 300m shall not be less than the design or specified width
label | b1cd1935-4517-527c-872a-bb1cb5b79c0b |  | note | Reference Documents - Cl 407.23 (a)(v)
label | ec109d32-6a84-5d2c-af9b-b911b0a2ec64 |  | note | Inspection / Test Method - Visual Inspection
label | 5d1ac340-7142-5023-9fe6-6929175cd5da |  | note | Record of conformity - This ITP signed off
label | 0a19023f-b852-5134-adb5-0c8a306b5668 |  | note | IP
label | 9f9530fa-9feb-53c2-b168-43069a34b2db |  | note | Responsibility - FH Foreman / Asphalt Supervisor
date | 74aaf4ff-949c-53d0-ba53-fbe4377613d0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Compaction
label | d00ccd59-99d6-53f3-8da6-08f29d5fa413 |  | note | Frequency - Per Lot
label | 4b4549b5-3610-57f6-868b-7afcfd0073e5 |  | note | Acceptance Criteria - For layers >= 50mm, if characteristic density ratio is: 96.0% or greater Accept lot; 91.0% to 95.9% Lot may be accepted at reduced rate
label | 71fad022-68f0-517b-8e49-4369d68a1306 |  | note | Reference Documents - Cl 407.22, Table 407.221, Cl 173.04
label | 45f9b073-952d-5a9e-89dd-645454bee292 |  | note | Inspection / Test Method - Verify
label | 5abe632a-bdfd-5f0e-a285-967ee8906f6c |  | note | Record of conformity - Test Report
label | 232e5698-cba8-5f19-9429-a5f43ef7fb75 |  | note | TP
label | 37ef590c-f34c-5434-9aad-59d56381151f |  | note | Responsibility - FH Engineer/ Lab Technician
date | 88dae0fa-a7fe-5925-a692-7e3e131220c4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Level Conformance
label | 24fb9d2c-abb6-5c9c-b972-ad24af7c54f3 |  | note | Frequency - Per 4,000m2 at completion of work
label | 0937b055-480e-5696-99a8-04cfa033f78b |  | note | Acceptance Criteria - Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
label | 253e1dfb-b2ca-5091-b6ee-d6088e697a3b |  | note | Reference Documents - Cl 407.23 Table 407.232
label | c271d9be-1e19-50ba-a39e-91198296d318 |  | note | Inspection / Test Method - Verify
label | 7c6e96fc-7f22-56bc-a1bd-a6c59cbdb3d5 |  | note | Record of conformity - Visual match existing / This ITP signed off
label | 0e4ab4c9-72f7-5f3b-89ad-bc4ae70e9317 |  | note | SCP
label | cb7c5aa8-4e09-506b-8b41-8592589c965f |  | note | Responsibility - FH Engineer/ Surveyor
date | 5124a44a-ebbb-5273-9aee-5feaddc351c7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection - Fulton Hogan
label | d53fe1ba-2b48-558d-9e2e-6d59549b57cd |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | a535a490-d2f1-583f-b521-696202a1108c |  | textbox | Print Name:
text | b8ff4566-18a3-5870-b97b-ed9416b3b89c |  | textbox | Position:
date | d2028358-ac46-555e-bfdc-fce0640f115b |  | date | Work Completed On:
date | 365bb068-1c01-5b45-9e97-3fc7825a9282 |  | date | Date:
checklist-sectioned |  |  | checklist | ITP - 017 - Rock Beaching | itp |  |  |  | Yes | CTN-ITP-017 - Rock Beaching | bd5533c3-bd34-4cba-a197-e70bf34ffbc1
checkpoint-group |  |  | section | 1. Preliminary Works
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 8a1e8ccf-89a9-51e9-8fab-bb2d46103a1e |  | note | Frequency - Prior to commencing any activity
label | 906975b3-2c68-5890-9ceb-b0d99eb3fc11 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | c4f8c3ca-7767-5155-b8f5-8d3a7605a322 |  | note | Reference Documents - PSP, EMP, TGS, SWMS, WP
label | 282c5b2d-15d1-526f-88f3-282e95271689 |  | note | Inspection / Test Method - Visual Inspection
label | 9d88a483-4273-50ee-bcd0-e10a83c78f43 |  | note | Record of conformity - This ITP signed
label | de08cb08-886a-5445-a969-b333b770aabf |  | note | HP*
label | c721ca64-af77-533a-98b1-fb84c9c1abac |  | note | Responsibility - Site Engineer
checkpoint-group |  |  | section | 2. Material Classification
checkpoint-status |  |  | checkpoint | 2.1 - Material Source
label | 5bcaca6c-7d32-541e-a625-cb09e4d386b2 |  | note | Frequency - Each lot
label | 4b1faa3c-bbdb-5021-acd1-9f138e5d0437 |  | note | Acceptance Criteria - Witness Point Prior to the commencement of work, the Contractor shall nominate the source of the proposed materials, supply specified test results and provide a representative sample for approval by the Superintendent.
label | ed896f46-5d01-5f09-9453-c90308c8433b |  | note | Reference Documents - Cl 713.03
label | 4d54b3cf-4a9e-51d2-9666-d3d04e2caf7d |  | note | Inspection / Test Method - Verify
label | 8d8ef0e2-f910-57e8-96c2-c81cfaff8fe4 |  | note | Record of conformity - This ITP Signed
label | 52f7e146-06cb-57bd-8a53-b91f688d57de |  | note | WP
label | d459b1da-3701-567a-99ca-bef94f329001 |  | note | Responsibility - Site Engineer/ QAV
checkpoint-status |  |  | checkpoint | 2.2 - Beaching Material
label | eb63878d-93dd-5767-af6f-4e2911da2f83 |  | note | Frequency - Each lot
label | 18cd9fa7-b822-5776-93ee-44f477224aa6 |  | note | Acceptance Criteria - For Type 1 - Un-grouted rock beaching: Rock for Type 1 beaching shall consist of field or quarry rock All rocks shall have a mass of between 20 and 70 kg and at least 60% by number shall be over 40 kg. Rocks shall be of such size that the layer of beaching is not less than 225 mm thick.
label | f477e4b9-c2d3-5e58-8654-3c9644cb5ad8 |  | note | Reference Documents - Cl 713.03 (a) (i)
label | 5be0dee5-2ebd-5786-92e1-795b5031f675 |  | note | Inspection / Test Method - Visual Inspection
label | 1bb85577-a724-54c0-bfba-9e1baefb2cef |  | note | Record of conformity - This ITP signed
label | 74b53a7b-2b69-5ccf-a203-9fccbd5215c0 |  | note | WP
label | d58ad87c-1ffd-531c-aba8-24ab8b69cfbc |  | note | Responsibility - Site Engineer
checkpoint-group |  |  | section | 3. Placement
checkpoint-status |  |  | checkpoint | 3.1 - Underlying surface prep
label | 29052d72-52b1-599e-a02f-b20322a9d847 |  | note | Frequency - Each Lot
label | 4f3c1eef-aac9-52fd-81da-5a5497f1ad80 |  | note | Acceptance Criteria - Areas on which beaching is to be placed are compacted and trimmed, with very robust needle-punched non-woven geotextile laid over the trimmed and compacted surface
label | 04f5ce0a-d47c-55a0-a2c9-a2b162fb3411 |  | note | Reference Documents - Cl 713.03 (b)
label | 34e8b46b-3c03-54e2-9f00-a6ef43d4dba7 |  | note | Inspection / Test Method - Visual Inspection
label | 832b4c52-a641-5840-b833-36d6bdd8e7e6 |  | note | Record of conformity - This ITP signed
label | 5b60d1d0-9f56-54f7-88ce-7cfbb9cd00bc |  | note | IP
label | f9822585-9800-5a64-98a9-e49179de6caf |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3.2 - Beaching Placement SWMS
label | c4ff1413-fb99-53dc-b3bf-f0ebab6bad14 |  | note | Frequency - Prior to Placement
label | ba3eb769-208b-5a8e-8b6b-f67a3e60e574 |  | note | Acceptance Criteria - Witness Point The completed job safety assessment and the Safe Work Method Statement shall be submitted to the Superintendent for review.
label | 7a8c6870-1e23-54b7-a414-3453ce6a0bb0 |  | note | Reference Documents - Cl 713.05 (a)
label | 1ed8cdf8-c532-535f-8bd0-aeed27adc87c |  | note | Inspection / Test Method - Verify
label | 95c667f1-47d6-588d-b7b4-203b19320633 |  | note | Record of conformity - This ITP signed
label | c31a9399-bac4-54ed-9e45-20c596680ee4 |  | note | WP
label | 6d390dc8-2a93-5741-8db5-09e4daf8da23 |  | note | Responsibility - Site Engineer/ QAV
checkpoint-status |  |  | checkpoint | 3.3 - Finished Beaching Surface
label | 9baf54f6-03c2-5f73-8d08-f23c79296292 |  | note | Frequency - Each Lot
label | a1d61b49-ddaa-5d54-8fc8-0bdd1e704e82 |  | note | Acceptance Criteria - The general surface of the finished beaching shall not vary from a 3 metre straight edge laid across the surface of the beaching by more than: 100 mm for Type 1 Beaching. Type 1 Beaching: Gaps between rocks shall be as narrow as practicable and not exceed 60 mm on average. Voids shall be filled to at least mid-height of the rocks with topsoil. The level of the topsoil shall be increased where planting is required within Type 1 rock beaching. The topsoil depth shall be increased to finish flush with the general rock surface and adjacent ground level.
label | 59c58997-1c83-517e-80af-d65022dff86a |  | note | Reference Documents - Cl 713.05 (b)
label | d79efa04-9265-53c0-8933-4f1d07f0edcf |  | note | Inspection / Test Method - VIsual inspection
label | f4ef62ad-0f26-5963-bc44-4556cd3d180d |  | note | Record of conformity - This ITP signed
label | c4d7ed8e-a8b4-5f82-8c89-10c9059c55d5 |  | note | WP
label | dfec4e0b-aec7-538d-84bc-61e5cacdf1e1 |  | note | Responsibility - Site Engineer
checkpoint-group |  |  | section | 4. Cleaning
checkpoint-status |  |  | checkpoint | 4.1 - Cleaning
label | 8de4ac63-ff51-5570-a842-916507a180bb |  | note | Frequency - At completion of stage
label | 496b357b-138e-5f1f-85f9-ca601162c749 |  | note | Acceptance Criteria - On completion of the work, the beaching shall be cleaned to remove all foreign materials and discolouration from the beaching surface. Any joint mortar adhering to the surrounding rock surfaces shall be removed
label | b900c26e-c9df-5b26-8d11-de9fea418c9c |  | note | Reference Documents - Cl 713.09
label | e66674a7-23d2-5f23-957e-30067f6698b3 |  | note | Inspection / Test Method - Site inspection
label | 3e24c59a-bafe-5d8d-a11e-9203a11a2f1c |  | note | Record of conformity - This ITP signed
label | d6a90e46-bf49-5b90-8a05-c3b007cfc3b7 |  | note | iP
label | 7c462f02-7de2-505c-bb9c-2391d24ec47a |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | d37df891-860f-59c6-bbd2-f3a28adc9b30 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | ef49b4f4-0495-5a69-8e2d-0c0ec18bef54 |  | textbox | Name:
text | 6360c2e8-c6eb-5518-898d-63135b51c6f2 |  | textbox | Position:
text | 0f93453a-04d7-5326-a1d8-eb2058d6acde |  | textbox | Signature:
holdpoint |  |  | signoff | Date:
checklist-flat |  |  | checklist | CTN-ITP-019 - Tree Planting | itp |  |  |  | Yes | CTN-ITP-019 - Tree Planting | c6f24558-35f8-49ae-8abf-26e0106924b2
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 9083c6de-ac3b-55f3-859c-e07ab30e6540 |  | note | Frequency - Prior to commencing any activity
label | 52d2f826-864e-51d0-b2b5-8bda775cc093 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | e2157e6b-f1c4-5945-9fc5-9b17efa89f77 |  | note | – using the correct and complete set of drawings
label | 92984244-9d9f-5a81-9adf-e2529067151e |  | note | – all drawings are the latest revision
label | 3728ec91-8ebf-5755-ad16-affd25787bda |  | note | – Conflicting documents will be referenced to the hierarchy of documents listed in Section 175.03
label | 2cb39a30-6a1c-56fd-9300-3b7718c883a5 |  | note | Reference Documents - Drawings and drawing registers Section 720
label | 3db83d17-1f16-5860-a4d2-ad46025f2951 |  | note | Inspection / Test Method - Visual inspection
label | 4e1efb66-da3a-59f9-a36e-f6e7fe25fef8 |  | note | Record of conformity - This ITP Signed
label | b03c3e35-56e8-5693-87b6-14787e1f07b7 |  | note | HP*
label | 8fd6feb2-9523-5207-bbe9-7577b9479c88 |  | note | Responsibility - Site Engineer
date | 67b952fa-7722-5e69-9c09-d463a76f8541 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | c0850f78-66c0-57e9-abb1-1c20df2834c7 |  | note | Frequency - Prior to commencing any activity
label | 12d2b1aa-d589-5dec-82d4-9c629b255a18 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 5f97510e-4721-54ab-8cbc-559cd3372d1c |  | note | Reference Documents - OHSMP, EMP, TMS, SWMS, WP
label | e3e4ffe8-20e8-5502-9847-b46ec2075395 |  | note | Inspection / Test Method - Visual Inspection
label | e76a6be5-febc-563d-8cbd-fc12731104e2 |  | note | Record of conformity - This ITP Signed
label | 712c6bab-3075-589e-9511-3e9b4f458388 |  | note | HP*
label | 59799e6e-cdb6-5f12-a65c-30e85cbb5aa3 |  | note | Responsibility - Site Engineer
date | 75b988c1-7875-5f45-a11f-a08e8f4d63c7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Provide records
label | 7cca4317-548e-540b-8163-21e848939404 |  | note | Frequency - As required, Prior to commencement of relevant work
label | 519f1883-7d4d-5ae2-92fd-22b7b620add9 |  | note | Acceptance Criteria - Evidence of origin of indigenous provenance plant material
label | 8545edac-e436-58b8-9ed4-44b3640a6757 |  | note | – details of suppliers
label | b8eb5d22-3761-5667-b788-07d5e117edcb |  | note | – soil tests on topsoil
label | 38c854f6-aea6-59d7-a0dd-d03a4bc99184 |  | note | – copies of fertiliser labels
label | fb455fd6-edf4-5df7-8e01-72ff65ec73a6 |  | note | Reference Documents - 719.02
label | a242afea-bb1c-51bf-96ed-70f41eae6c87 |  | note | Inspection / Test Method - Verify
label | fa224e2f-18c5-570f-81d7-e1d0a1e54e31 |  | note | Record of conformity - Records, This ITP signed
label | af229367-0eef-5ae6-8f18-93e842b5505f |  | note | WP
label | a59b51b1-73fa-5f55-8bf2-e6be897bfe74 |  | note | Responsibility - Site Engineer/ QAV
date | 66ae587e-981a-5ba8-bfcf-306b7759c62e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Topsoil, Fertiliser and Mulch
label | 82aba32d-059c-570f-914b-dc018edde613 |  | note | Frequency - Prior to any planting for each lot
label | 99cddd8d-6767-53a5-8429-b601ece52eb5 |  | note | Acceptance Criteria - Utilise locally stripped topsoils only, Fertilisers shall be suitable for the establishment of plant types, sizes and species specified in the plant schedule and Site created Mulch shall be used where possible - imported mulch must meet requirements of Table 719.071
label | 708a0ebb-b3cc-52f2-986f-7e37b2e3a4e6 |  | note | Reference Documents - 719.05, 719.07, Table 719.071
label | 319f514e-f88e-59e8-a784-dada8ad051e4 |  | note | Inspection / Test Method - Verify
label | 8be226bd-b9ae-529a-8261-486fdd99e38d |  | note | Record of conformity - This ITP Signed
label | 91e6e256-7a25-5f15-b48f-709768078efc |  | note | IP
label | 450de1ee-56f9-5255-bb40-030bda32da23 |  | note | Responsibility - Site Engineer
date | c23f8a53-b1eb-52cc-bd86-f969d1db2b2a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Plants
label | f0949cde-98b2-5a3e-b7d2-87c0be5428a0 |  | note | Frequency - Prior to any planting for each lot
label | 94e35733-79bb-5b58-9167-5d83fc8980fc |  | note | Acceptance Criteria - Plants to be as per planting schedule (drawing 4795): PMA replacement trees to be 45L white peppermint (Eucalyptus Pulchella)
label | 0e1c2a49-bf48-562c-9e54-c8448d3ef471 |  | note | Reference Documents - Planting Schedule
label | 6252f4dc-87d5-5b74-b0fd-3338543a7ae8 |  | note | Inspection / Test Method - Verify
label | c77f7f9a-8581-5c0d-8a7c-be389c339a14 |  | note | Record of conformity - This ITP Signed
label | 8d3d7bd5-cbc0-5977-8d09-4614ab92ab89 |  | note | IP
label | 93fabe98-f159-5708-aa8b-67c25eac5a0a |  | note | Responsibility - Site Engineer
date | 36673509-020f-5f56-a45b-32db77580c95 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Soil Ripping
label | 0fbeed50-05e4-58ee-8eb0-d4a886f6fa13 |  | note | Frequency - Each Lot
label | 34dfa790-cc0b-59fb-9da8-0b6170576bfb |  | note | Acceptance Criteria - Soil ripped as per Table720.061;
label | aa38e080-0f1b-57f1-b91d-ed68a3258ec9 |  | note | 1. 25m2 of min 400mm deep at 500mm max spacing
label | 0e257943-2c78-5443-9e4b-6214d7f42f2f |  | note | 2. In disturbed areas; place 150mm topsoil (leave uncompacted)
label | 22911a42-41c2-5af5-9292-ffa03b17a79f |  | note | 3. cross rip min 300mm deep at 500mm max spacing
label | 2e63813f-a79b-553c-a907-9ef0c640e369 |  | note | Reference Documents - 719.06, Table 719.061
label | 3cb6465f-7221-5a87-a4e4-d1c4ff214d02 |  | note | Inspection / Test Method - Visual inspection
label | d59690c4-d8a4-523c-b421-992687282c11 |  | note | Record of conformity - This ITP Signed
label | 0779b556-e9f4-55eb-9c2d-4a9b260e9e45 |  | note | HP*
label | 8a7e37a1-111d-57ee-9bbd-7695781aefcb |  | note | Responsibility - Site Engineer
date | f780e241-2dfe-544c-9f6b-d2ecf97d7c43 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Fertilising, Planting and Mulching
label | 71c90477-d5a2-598b-8254-9ac452e20e0a |  | note | Frequency - Each Lot
label | 36ddad67-8953-5b65-bf31-d33120b87c5f |  | note | Acceptance Criteria - Holes to be dug to correct size for root ball, Holes in heavy soils prepared to ensure adequate drainage, Holes not left smooth sided in Basalt or Plastic soils
label | 895743e6-fc2a-5e1f-acb8-7c78a14823f1 |  | note | – Planting holes shall be backfilled with friable topsoil, free of debris, rocks and clods greater than 50mm in diameter
label | 7cd7d238-8daf-5097-80fd-80e8032dea4b |  | note | – Fertiliser is to be applied to all disturbed surfaces and the contractor shall fertilise advanced trees
label | be863636-83ff-58c4-a93e-234d36ba6306 |  | note | – Mulch, no less than 1.5 diameter and 150mm depth, will be applied around all planted trees
label | 52020091-7f39-5732-a71f-4c8e60198139 |  | note | Reference Documents - 719.07
label | bdf0561b-021e-55c2-be52-f7e128326458 |  | note | Inspection / Test Method - Verify
label | 79232dce-303a-5d44-af75-22f5ca3eb286 |  | note | Record of conformity - This ITP Signed
label | 0656c858-d2bc-5c3f-a24f-935ff1cc738b |  | note | HP*
label | 15b9c884-d6cd-599b-b283-a7239e91283f |  | note | Responsibility - Site Engineer
date | dc51161a-6ddc-5661-bf9d-bfb4d8cbdd3e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Initial Watering
label | f33dd394-31d5-5c87-9b31-5dc806283db9 |  | note | Frequency - Each Lot
label | 445ce704-9a23-5433-9b33-9da4d8f20802 |  | note | Acceptance Criteria - The Contractor shall saturate each plant within 8 hours after planting. Cells and tubes shall be irrigated with a minimum 3 litres of water per plant. Other container sizes shall be irrigated with a volume of water greater than the container size.
label | e09954e8-8daf-591b-94fb-1cf0ed398ea6 |  | note | Reference Documents - 719.07
label | 3c1ec953-3ae0-5ef5-b32b-d698ed6becf5 |  | note | Inspection / Test Method - Visual inspection
label | 11872ae3-f4f2-5e71-bae8-1c320f333bba |  | note | Record of conformity - This ITP Signed
label | 2a92e488-97e2-5caf-80a5-0f74c52daefb |  | note | HP*
label | 6fe00b97-c0a5-5c34-b942-cdf051d6414a |  | note | Responsibility - Site Engineer
date | 1b38079a-30b6-5489-b3c9-f55643733764 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 - Performance requirements
label | 0a7d2b9d-936e-54ff-a1ab-55a471bd24a6 |  | note | Frequency - Each Lot
label | 2222b194-60a2-5c34-9480-c19ddda4e924 |  | note | Acceptance Criteria - Where tree planting areas do not achieve the performance requirements detailed in Table 719.092 (below) they shall be replaced annually to achieve 100% of the original specified planting numbers.
label | 13f752e1-efd3-5d13-976a-7441cdf72d0c |  | note | PREVIOUS 12 MONTHS RAINFALL - ADVANCED TREES MIN GROW RATE
label | bef61e40-f921-55d6-8fdd-47fa4fbb9455 |  | note | ○ more than 750mm - 300mm per annum
label | 1720dfba-c03d-5083-b0b8-cf40f4bd7ed3 |  | note | ○ 500 - 700mm - 200mm per annum
label | 7338df48-ba05-58d0-8c12-9b6b2531e1d8 |  | note | ○ Less than 500mm - 100mm per annum
label | 0e2e13af-fc3a-5649-b9cf-48ee011f88ac |  | note | Reference Documents - 719.09, Table 719.092
label | f3c04175-fd28-574e-b788-d88a9b8331bd |  | note | Inspection / Test Method - Verify
label | 47549cd1-d9c8-5382-929e-a56f90eb4415 |  | note | Record of conformity - Lot Map
label | fb6cc330-d953-5779-9b08-c87896d9e8c0 |  | note | HP*
label | 943743b1-e587-542e-9fc0-a4477303b45c |  | note | Responsibility - Site Engineer
date | 802f0d6e-53c0-5244-93e9-1947d14ecec6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Watering and Re-Mulching
label | f302279a-d4a7-593a-a64e-77408bd4ec3c |  | note | Frequency - Each Lot
label | aa759dda-cc70-5403-bdc8-221206cd4b6b |  | note | Acceptance Criteria - The Contractor shall water all plants, including seeded areas, as necessary to ensure continued healthy and vigorous growth from time of planting or seeding. Maintenance of areas mulched shall begin from the first planting
label | 01b06d2d-18e1-5e82-a564-1449333ba334 |  | note | Reference Documents - 719.09, Table 719.092
label | e0713e58-f238-5529-be0b-2f59c6a31cc5 |  | note | Inspection / Test Method - Verify
label | d032c69f-7efa-54df-8c32-46157880a3db |  | note | Record of conformity - Lot Map
label | dff50bd7-bd4a-5f13-9392-2b05d45b4e18 |  | note | HP*
label | 52aa5e11-cdab-575d-ae16-9f428cd47adf |  | note | Responsibility - Site Engineer
date | 5ed62741-f4f2-554d-8551-81e7371c2cd5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 05bf8742-8ab0-538c-9970-48e71689245a |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 3cee0bb2-2311-5251-b90c-6448e7fdc9dd |  | textbox | Print Name:
text | 61827e46-0dc9-59ad-99dc-109992a59c92 |  | textbox | Position:
date | f8c5c0ee-4f83-5722-95a7-d948a9d1809f |  | date | Work Completed On:
date | 19783a1b-92de-544b-b8fd-4ffbc7994614 |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-009 - Stormwater Drainage | itp |  |  |  | Yes | CTN-ITP-009 - Stormwater Drainage | e97b3000-fdce-47d4-916b-1f0f16de332e
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 49d3ff57-a750-5854-9bf3-928424b7b1aa |  | note | Frequency - Prior to commencing any activity
label | dceffc41-91f0-52d9-9c13-671cd966e015 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are: using the correct and complete set of drawings; all drawings are the latest revision; Conflicting documents will be referenced to the hierarchy of documents listed in Section 175.03
label | 8c17f6f8-d9e5-5e04-bb45-ce7aa605745d |  | note | Reference Documents - Drawings and drawing registers;175.03
label | e0a48739-d1e7-55a8-8189-864378794eef |  | note | Inspection / Test Method - Visual inspection
label | 8f377091-afb5-572c-8bbe-1b5d86a1de51 |  | note | Record of conformity - This ITP Signed
label | 979b44f6-2da1-508a-80c6-93bf8f40f70c |  | note | HP*
label | 7958add5-950e-5105-8060-44918e70c16b |  | note | Responsibility - Site Engineer
text | 0f0b7e0c-d48a-5f55-8239-8ea2e205bdfb |  | textbox | ITP Opened:
date | 7328a74d-f711-5296-9aed-bb7a6da16d5d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | e5180fdb-fa20-5559-88ab-f2e20fd9b249 |  | note | Frequency - Prior to commencing any activity
label | bdd7a16f-4ea3-5597-9e7a-7175c3ac8ccd |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 5e9966e3-5d63-53bf-8f8f-1fea27a1f389 |  | note | Reference Documents - OHSMP, EMP, TMS, SWMS, WP
label | 9dc43c51-6270-5816-bcee-5911968fa063 |  | note | Inspection / Test Method - Visual Inspection
label | 3d364d0e-5647-50c2-a222-b7e1b37e5d7c |  | note | Record of conformity - This ITP Signed
label | 034e6e0e-76d3-5a12-8e44-f41d1f06972e |  | note | HP*
label | 6e93d0c3-1cd3-5bb9-a05d-598209447450 |  | note | Responsibility - Site Engineer
date | eaaf634f-828d-5a56-be5e-9e446f6e6307 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Precast Reinforced Concrete Pipe Supply
label | 2062ab53-5a69-577d-9727-a05d592e1056 |  | note | Frequency - Prior to works commencing
label | d6615e02-dbb0-5ef0-a20f-2fc390c1d0b3 |  | note | Acceptance Criteria - Pipe class and size and endwall type as per drainage schedule
label | c051c5f3-e933-5f39-a479-01f52236b78c |  | note | Reference Documents - Cl 701.05 Drawings
label | ee0d2c4f-d463-5a65-8967-89c1b0741ba8 |  | note | Inspection / Test Method - Verify
label | 9844e98c-2c53-5979-87f5-72c7cdafac39 |  | note | Record of conformity - This ITP Signed Order acceptance certificate
label | 120fe87c-4ca4-5200-b0ee-eb10c63cf413 |  | note | HP*
label | 47cc6d44-26fa-5881-af1f-83f86a009df1 |  | note | Responsibility - Site Engineer
date | 17cbdf1f-e48f-5740-b451-fd89c67ae0fa |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Precast Reinforced Concrete Inlet and Outlet Structures supply
label | 4fcb5840-4498-5b8e-b51f-94f65d5d473f |  | note | Frequency - Prior to works commencing
label | 58e7f126-eed1-5fae-b14a-2a7a7eca5e1c |  | note | Acceptance Criteria - The supply of precast inlet and outlet structures shall conform with D.S.G standard drawings. Concrete supply shall conform with Section 610 and reinforcement supply shall comply with Section 611.
label | ca2dd696-8e30-5971-9295-cb3c09ff8350 |  | note | Reference Documents - 610, 611, DSG 3402 standard drawings
label | ea5f830a-145e-54ad-acf7-9710ad0e0ac3 |  | note | Inspection / Test Method - Verify
label | cee1222d-a4d9-5dc1-956e-c2bfefca8c43 |  | note | Record of conformity - This ITP Signed, Recievable Inspection Checklist
label | d42419a0-5638-5481-be93-7bbc470e5fd3 |  | note | HP*
label | a4ca5ae6-9e5e-54da-837d-633d2a771d52 |  | note | Responsibility - Site Engineer
date | 4e782742-5508-532e-94b1-c9a5d157a97f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Bedding and Backfill Material Specification
label | e317f6a4-3902-5e2b-8d18-a03eb9a98b73 |  | note | Frequency - Grading 1 test per 1,000t
label | caf5b512-3761-55b8-9af7-3062f8b7012f |  | note | Acceptance Criteria - Bedding and Backfill materials free from perishable matter and lumps and has max PI value of 20. Bedding and Backfill conforms to sieve requirements of Table 701.091 in the specification
label | 2546f7ef-a413-5ca9-9779-5679c452f9c8 |  | note | Reference Documents - 701.09(d), T701.091, T701.092
label | 7c0eab18-553a-51d6-ae00-a3a9ca0cebc2 |  | note | Inspection / Test Method - Verify
label | 457b7562-708b-5198-b520-826ff74b375f |  | note | Record of conformity - This ITP Signed, Quarry test report
label | aa589e10-e9ca-52d3-8cfe-51cc341b51da |  | note | TP
label | 8f58463a-b571-5b81-a73b-4090bd3905f6 |  | note | Responsibility - Site Engineer
date | 08261fd4-f3cd-5955-adb5-3b198168060a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Setout of Works
label | 2b57a4a8-7c77-5a1e-a7ea-244e87db8d8a |  | note | Frequency - Prior to works commencing
label | 3cde2ac2-4668-56b6-9b70-7aaafd6248fe |  | note | Acceptance Criteria - Hold Point: Position of culverts confirmed with the superintendent prior to commencement of excavation
label | 8c9a676c-bb68-53a5-a7a8-53d8540ae7e0 |  | note | Reference Documents - Cl 701.10
label | a4433328-d66a-5e1d-a9f3-903b61704030 |  | note | Inspection / Test Method - Visual inspection
label | cff5384a-1ab1-53c7-93a2-ef8d0e1fc8eb |  | note | Record of conformity - Survey records, pegs on ground & this ITP Signed
label | 10d96632-5f5b-5763-9a08-0ba3b240f8cd |  | note | HP
label | 6612d014-7861-515d-974b-66827d7c2873 |  | note | Responsibility - Site Engineer / QAV
date | d73a9863-babe-5979-be6d-cff418db0b29 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.1 - Excavation for pipe
label | 2b053200-834b-5edd-870f-a4b8173ff268 |  | note | Frequency - Each Lot
label | 74c3b508-7374-5321-b72a-bcf4fe311426 |  | note | Acceptance Criteria - Excavation for the installation of pipes shall allow for the clearance from the outside of the pipe to the wall of the trench between 300mm and 600mm
label | 30a1f139-1fb2-53b3-8dc0-a9e6f4688d7a |  | note | Reference Documents - 701.15 Table 701.151
label | 257246fa-8174-5d40-8e79-d49b884e53f7 |  | note | Inspection / Test Method - Visual Inspection
label | 49f5e252-db7e-5e40-99b7-e99604cdf77d |  | note | Record of conformity - This ITP Signed
label | 428cd8de-e96c-5e3c-b84f-72d8a57ee4af |  | note | IP
label | 2a6ca864-bc1d-5a8e-af4f-55551cbb9345 |  | note | Responsibility - Site Engineer
date | b94892d5-f415-5be5-968d-89b5ad2a3ebc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Trench Base Preparation / Bedding
label | 80a01ed3-222b-518c-8fb9-a7433b397d42 |  | note | Frequency - Each Lot
label | 3cd22cef-5884-53f5-8541-9017064c8207 |  | note | Acceptance Criteria - Bedding material placed in full width of trench and compacted to at least 100mm thick. Treat or replace all soft, wet or unstable material below the level required to provide the minimum specified thickness of culvert bedding
label | 76d1053d-df5f-54a6-a792-3bc031731dfb |  | note | Reference Documents - 701.15, 701.16
label | ff214957-0c8f-53a7-a44d-36da35b191b4 |  | note | Inspection / Test Method - Visual inspection / Measure
label | b6a29009-4a9c-5095-9cd8-a2c5f04a59a2 |  | note | Record of conformity - This ITP Signed
label | 30c87f59-1045-5649-917a-e710336d9e28 |  | note | IP
label | c99b072b-abf3-5c42-be6d-1a281d6dd975 |  | note | Responsibility - Site Engineer
date | abcb54aa-234f-5daa-949a-37d50135670c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Haunching
label | 1428fb48-7708-5efd-9818-c17d1f77bbee |  | note | Frequency - Each Lot
label | 36d82616-f519-5d86-8c81-c1629c08919d |  | note | Acceptance Criteria - Huanching layer to be placed reaching a height equal to 30% of nominal pipe diameter or culvert height
label | 991c5b36-3b9e-5041-ad68-cdc1d1ed52e7 |  | note | Reference Documents - 701.16
label | 3c8428f2-42e7-52f6-9b7b-fed64b2078c7 |  | note | Inspection / Test Method - Visual Inspection
label | a6a4661b-7d17-57a4-98ce-80cf83d5e01a |  | note | Record of conformity - This ITP Signed
label | 1e3917b5-0ccb-57f2-9b0a-4f56509e513d |  | note | IP
label | 920ac7c6-586d-509a-9948-bc7cfdac52e1 |  | note | Responsibility - Site Engineer
date | 853f604d-51a7-59e8-82b6-79ff825d9863 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Laying of pipes
label | 3f673e47-e213-590d-95aa-7daa39cdfb1c |  | note | Frequency - Each Lot
label | 094b31a8-4011-5d60-9f70-0c1436bf36ad |  | note | Acceptance Criteria - Laying of pipes to commence from the downstream end. Pipes to be laid with rebate or socket end facing upstream. design grade tolerance of +- 10mm in 10m.
label | f9487e20-1d52-593b-acd6-a73c7144490f |  | note | Reference Documents - 701.10d 701.17
label | f4221c78-1247-5621-84ad-b2f7aff8389b |  | note | Inspection / Test Method - Visual Inspection
label | 08e6286a-a3cf-5713-8c3e-29a6870a5abb |  | note | Record of conformity - This ITP Signed
label | c15152ee-d141-558f-9336-b072f20d0d75 |  | note | IP
label | 1a72987f-adc2-5f91-bf52-bec492762989 |  | note | Responsibility - Site Engineer
date | 9d19449b-1399-5d2b-9def-fa0d737039da |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Jointing
label | f175fee4-b7ec-59e0-9132-3a5e281ca07d |  | note | Frequency - Each Lot
label | c11bf470-7078-5d61-9bb3-81a197d38e59 |  | note | Acceptance Criteria - RC Pipes shall be jointed with rubber rings. Rubber rings shall be kept undisturbed, clean and free from dirt and other foreign materials. Rubber rings are to be in place and inspected after each connection and before proceeding to next section.
label | 1bd80a5f-8c79-59ee-ae14-685d2e663a7b |  | note | Reference Documents - 701.18
label | 1ba4a48d-9817-577c-a62c-6ec4c540be7f |  | note | Inspection / Test Method - Visual Inspection
label | 8158edb2-dba8-57fa-8f26-b5beaaff14e9 |  | note | Record of conformity - This ITP Signed
label | e3f1578a-920e-559b-a849-1eb538ffb344 |  | note | IP
label | b8ae18f7-26a0-5e6a-9882-aaac52c3a13b |  | note | Responsibility - Site Engineer
date | 42e4eb29-db25-5e05-bd7c-1129e90b9817 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 - Tolerance
label | 37031ba3-3c82-52a6-adf3-f711f8b31886 |  | note | Frequency - Each Lot
label | 2920dd78-267f-53f6-af1f-7a5657ff1928 |  | note | Acceptance Criteria - Location of each culvert run verified by survey prior to backfilling and recorded in as-constructed drawings. Tolerance: Invert level of pipes at pits ± 50mm. Departure from design grade of pipe runs ± 10mm in 10m provided min grade > 1:250
label | 96692e4f-9457-5791-876e-d5ea8c5d7b5d |  | note | Reference Documents - 701.10
label | edf867ec-6295-56bf-9ba3-65b3f944454f |  | note | Inspection / Test Method - Verify
label | ec53a67a-daf0-5e1a-9acb-fcefef2cfb5d |  | note | Record of conformity - This ITP Signed
label | c5aeb19b-c669-54dc-adfb-832f7b11eb4a |  | note | SCP
label | e80df788-b5a1-5227-926e-901779e306fa |  | note | Responsibility - Surveyor, Site Engineer
date | 3e3fc9ac-8421-5aad-8c82-d1a80e26f2c4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 - Filling
label | cd8571c4-9dd1-5b52-a305-fb096d4818af |  | note | Frequency - Each Lot
label | d773589e-3c12-5f02-a323-42fb8dfcbf4e |  | note | Acceptance Criteria - (i) Culvert Under Area to be Paved. The trench shall be backfilled to subgrade with selected material. Above subgrade level, materials as per pavement design. (ii) Culvert Under Area not to be Paved. The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level
label | 960286d0-a5b6-55c0-8021-06a2bb9ef6cd |  | note | Reference Documents - 701.19
label | 9c3d3cfb-59e5-5cfe-b57d-9242a4c0e658 |  | note | Inspection / Test Method - Visual Inspection
label | d65577f4-fcd3-5d50-bf9a-321f7628cfb8 |  | note | Record of conformity - This ITP Signed
label | 3050460b-8240-5f52-a2cd-c0ae025c815d |  | note | IP
label | 0fe4507f-7ec1-5f96-af87-6ad6139ff261 |  | note | Responsibility - Site Engineer
date | ceb83efc-1395-57f1-b3ed-915b042eb809 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Testing and Acceptance of Fill Materials
label | daa055db-d30b-5ccd-aa51-0e589a5a5157 |  | note | Frequency - 3 Tests per Lot tested with 20% of all Lots tested
label | 54be8aba-a528-51ee-ae8c-503fc180e1cc |  | note | Acceptance Criteria - Bedding and backfill materials shall be placed and compacted in layers not exceeding 150mm loose thickness and shall be assessed for compaction and moisture content.
label | dd76c8f0-f755-59a9-ae87-9ef0737cb413 |  | note | Bedding shall be compacted to refusal using hand held mechanical equipment.
label | 363b5622-7e25-523c-afde-38abe4d1c097 |  | note | Backfill material with nominal size < 40mm after compaction shall be compacted to a mean density ratio of not less than 97% CDR.
label | 141b01d5-0af2-5f4f-80f1-f88ad4dc5feb |  | note | Backfill material with a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | 88006100-5885-5b9d-ba2d-ca59773d9da8 |  | note | Reference Documents - 701.20
label | 4ac11869-e54d-5a2c-a394-7851ec58cb75 |  | note | Inspection / Test Method - Verify
label | 4263a0c2-5b68-5caf-8a27-15b8fdc8b1e2 |  | note | Record of conformity - Compaction Test Result OR This ITP Signed
label | 89f73c0e-296d-5089-892f-3bcd730fcea8 |  | note | TP
label | 4720aed0-2a8c-5f2b-ab83-e91deb469088 |  | note | Responsibility - Site Engineer
date | b53d3b9a-aa71-529b-80b0-0849945c9ecc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Installation of Inlet or Outlet Structure
label | 62234a59-98a5-5b48-9e60-a7f656ef75fb |  | note | Frequency - Each Lot
label | 7d756fb8-371b-5350-bb2c-3d705bd0dbba |  | note | Acceptance Criteria - Inlet and outlet structures shall be installed to a tolerance of +-20mm where matching kerbs or barriers or +-100mm in all other areas.
label | be3fcd0e-2f85-587f-aa4a-21ed10bff659 |  | note | Reference Documents - 701.10 701.25
label | b734fb86-5fc6-50f5-9298-ca0ea04acbc3 |  | note | Inspection / Test Method - Verify
label | 968d7190-3943-5e01-ade9-178ecbd0071d |  | note | Record of conformity - This ITP Signed
label | b7804b7b-2155-517d-9c66-567766c4cc6d |  | note | IP
label | 3f21bd1c-8e59-550b-bad4-5c5f8781cc5e |  | note | Responsibility - Site Engineer
date | 33334dba-16d9-51fa-b401-b4ffcb29b380 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Culvert Coverage
label | 19924410-d565-530a-a93c-f55f6e1a1793 |  | note | Frequency - Each Lot
label | 20eb3416-acd0-5ab4-b750-fdd60640370e |  | note | Acceptance Criteria - Until the minimum compacted thickness of cover in Table 701.141 for axle or track loading has been provided, construction traffic shall not be permitted to travel over the culvert
label | 32aee7a9-358c-5478-99a4-5ada8b2e7ac3 |  | note | Reference Documents - 701.14 T701.141
label | 4dbe07e4-bd2e-5714-b02b-0ebe74721a8d |  | note | Inspection / Test Method - Visual inspection
label | adab6980-bb4c-56dd-9e85-69d6c5611da4 |  | note | Record of conformity - This ITP Signed
label | 2dfae391-5d94-5753-a9f8-1d71732218ef |  | note | IP
label | 0df783b5-67f4-569c-a567-78634f69998a |  | note | Responsibility - Site Engineer
date | ff13e105-f0bc-5d2e-b26e-562c5f5dc4e6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 - Finishing and Rendering Pipes
label | e2bcb2c7-e316-50eb-a558-af061e9a6b3a |  | note | Frequency - Each Lot
label | fb86142c-1652-5562-8099-f8a894ee51fa |  | note | Acceptance Criteria - All stormwater inlet and outlet connections shall be cut trimmed neat and finished with cementitious mortar.
label | b3fc50c3-c0d1-564e-816e-56057728a9a4 |  | note | Reference Documents - Work Procedure
label | 1d73837b-5983-5ceb-9782-e86257fcde22 |  | note | Inspection / Test Method - Verify
label | 5f3b7d08-558e-51ba-8162-2f3486cc6d70 |  | note | Record of conformity - This ITP Signed
label | 6ad2e17d-95e9-50c5-967a-039bb1a0dac3 |  | note | IP
label | 74c82f2e-1692-5df6-a480-6073b8777d05 |  | note | Responsibility - Site Engineer
date | cd3db774-4ff7-548f-a48f-98c582ff9743 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Repair of Damaged Pipes
label | f2b29d39-717e-5906-9763-d4c40211620c |  | note | Frequency - Each Lot
label | 7c2c833b-3d30-5c45-90dd-140c0f65873f |  | note | Acceptance Criteria - Damaged pipes shall be repaired in accordance with 701.31 of the Specification, no repairs shall be undertaken without the Superintendent's approval of the repair materials and procedures.
label | 3445849d-48d1-5a79-bcae-c5a1deea6cf0 |  | note | Reference Documents - 701.31
label | a78d7b2a-4e06-5d8c-9f3e-8190f3c6d301 |  | note | Inspection / Test Method - Verify
label | 7441d97d-3ed7-54a7-a745-ce496644240b |  | note | Record of conformity - This ITP Signed
label | ac15c812-aeeb-5c40-b0ce-bb6c732fc899 |  | note | HP
label | b22ce4c2-da50-5cb2-af0c-28e233812a63 |  | note | Responsibility - Site Engineer / Superintendent
date | b6d2232f-b758-5303-9372-24dc28a4afa7 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.3 - CCTV
label | 48e7097f-3112-5ac6-9b1e-cd2e6b33cbf7 |  | note | Frequency - Each Lot
label | 387bd4c4-0198-5ba9-965d-c38435c905ab |  | note | Acceptance Criteria - Hold Point: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | 652ae4e6-d038-5c30-811a-dea8317b9255 |  | note | Reference Documents - 701.30, WSA 05-2013
label | 73dab149-3bb0-5f2a-9249-3e8c7240ca1d |  | note | Inspection / Test Method - Verify
label | 89fe5152-69d4-58d4-8c12-1ac140eabe14 |  | note | Record of conformity - This ITP Signed
label | 29d96de2-deaf-5db4-bb38-255735775099 |  | note | HP
label | feed5880-ada6-5561-af1f-da60791435fc |  | note | Responsibility - Site Engineer / QAV
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Final Inspection - Fulton Hogan
label | 12e02d2f-5b6e-5e04-9723-192f698b61e1 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | fdb8593a-5783-50f7-876a-e9978bfe23c1 |  | textbox | Print Name:
text | 51473d7b-7422-52c3-a5a9-7ea8a20feafe |  | textbox | Position:
date | 68b2a984-b7e2-581e-af6f-e783d32d1056 |  | date | Work Completed On:
date | 7a2585fe-13cb-5b3d-bd5f-7329d432dbee |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-018 - Hydroseed | itp |  |  |  | Yes | CTN-ITP-018 - Hydroseed | ed7b47fb-cce2-4f71-baba-11af7b342e19
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | aab46e21-202e-5013-85d3-053ca3a2580c |  | note | Frequency - Prior to commencing any activity
label | 7ea44e4d-6fa9-5d36-aadc-4eb4266febba |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | c5fe3b49-d078-5c28-889a-9658b05b47c6 |  | note | – using the correct and complete set of drawings
label | 6337b644-6068-5583-a889-ce8f5c8855b6 |  | note | – all drawings are the latest revision
label | 5158e6c1-7543-57b0-8a4e-04998bd97ac5 |  | note | – Conflicting documents will be referenced to the hierarchy of documents listed in Section 175.03
label | a6785c68-d86a-5ee6-b764-3996e8566a99 |  | note | Reference Documents - Drawings and drawing registers Section 720
label | fe326484-a7d2-5ff7-afa9-9e0291c45fa0 |  | note | Inspection / Test Method - Visual inspection
label | 2b9fcb76-6448-5c3e-b866-43cb853a8389 |  | note | Record of conformity - This ITP Signed
label | 5cbb1e67-641c-5fae-b60a-a3a42219c72e |  | note | HP*
label | 68a64ab5-0a7e-50b8-80b9-cb3aabf4e8ee |  | note | Responsibility - Site Engineer
date | f8d26388-6456-5163-9078-63954d2fc0f2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 22042d5d-49b0-59e6-b5a7-e97d12ee5ce7 |  | note | Frequency - Prior to commencing any activity
label | be2dd07f-4d68-5584-86de-7153b70be2ff |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 586c7092-263b-5a67-a477-762ba9792c2f |  | note | Reference Documents - OHSMP, EMP, TMS, SWMS, WP
label | 28c5b5da-51c6-5d1e-a920-5458a61d1631 |  | note | Inspection / Test Method - Visual Inspection
label | f60d6d2a-ffb9-554c-9b8d-2256ef0513f6 |  | note | Record of conformity - This ITP Signed
label | d2594b5e-2aeb-50e7-8a92-420fc378780a |  | note | HP*
label | d603ef6f-5c41-5366-9849-f428f6d36a22 |  | note | Responsibility - Site Engineer
date | d7688638-24c5-5fbb-b962-dbc4d35d9a6e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Hydroseed Mix
label | 5a00c2be-19e2-5d7b-9ff2-cf68049b33de |  | note | Frequency - Each Lot
label | 4d361a96-70da-5415-a4c6-9b197086d0b3 |  | note | Acceptance Criteria - Conformance of hydroseed mix with grass seed properties table 720.045
label | 961279d9-f0cd-5c38-a94b-1a229fe6aadd |  | note | Reference Documents - 720.045
label | faabcfd3-ca66-5d39-935b-b1f03cb468b3 |  | note | Inspection / Test Method - Verify
label | 763601d0-b464-55c7-82d0-44bb61a2ca70 |  | note | Record of conformity - This ITP Signed, Data sheet
label | b0dbd9c1-2784-5054-a787-ad96f1f82f40 |  | note | HP*
label | 17bbdb67-a53a-5f8b-a2a8-334137e608f7 |  | note | Responsibility - Site Engineer
date | 6540e348-e968-5ed0-a4d2-5c8c1516c5e5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Hydroseed application
label | 2eba073a-7165-5b29-a09a-dc7b4d5f52dc |  | note | Frequency - Each Lot
label | 7d6ef60c-14e1-5718-845f-7dee320e0464 |  | note | Acceptance Criteria - Grass seed shall be sown at minimum 100 kg/Ha (if drilled) or 200 kg/Ha (if broadcast)
label | a9e3697e-39d5-5cd6-b822-1241743d6c6d |  | note | Reference Documents - 720.08
label | 02f6ee19-83d3-5394-81f2-0cedf8c89daf |  | note | Inspection / Test Method - Verify
label | f37da0cd-69fb-583f-92ae-d8a8e43283ce |  | note | Record of conformity - This ITP Signed, Recievable Inspection Checklist
label | c19be8df-1fdd-59f0-a39f-f421d91105a5 |  | note | HP*
label | 0c941753-2bfa-51df-9cc4-9551465ebc07 |  | note | Responsibility - Site Engineer
date | 57cda38e-83e8-587a-83de-ba79a957767f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Germination
label | 454dc0bc-6e02-5db3-ac5c-ed6b0a8eb4b3 |  | note | Frequency - Each Lot
label | 9286c128-e0af-55a7-986f-d8ebd0fbd081 |  | note | Acceptance Criteria - Germination rate shall be minimum 80% cover within 8 weeks and 95% cover within 3 months of sowing.
label | 84b563ae-9ede-5e2a-b7d8-f4400ac83bb5 |  | note | Reference Documents - 720.08
label | 003de7ec-cdd5-5ff8-a709-17f1dfc0c3f6 |  | note | Inspection / Test Method - Verify
label | ae26b166-5fa1-59fd-8542-2ff0b0690b48 |  | note | Record of conformity - This ITP Signed
label | 2f4afebf-ed1e-5585-a9d3-3f42c1ba2ef3 |  | note | HP*
label | f23c0cee-8e69-5067-b937-fa7371ad3055 |  | note | Responsibility - Site Engineer
date | f3b5db79-7749-5a26-a2ef-ecfcf5fea0fc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Reseeding
label | 7f70eb24-fcab-5aa1-932c-897fbf03cda5 |  | note | Frequency - Each Lot
label | a49d4114-1b02-5f33-bf22-1e95a313b63c |  | note | Acceptance Criteria - If germination has not been achieved in any grassed area within 8 weeks, then the area(s) shall be reseeded with the specified grass seed mix
label | 48bfa9fb-12cb-5485-ac31-d12c06b0b7ef |  | note | Reference Documents - 720.08
label | c341b830-aeab-540b-9b6e-0d1cf74c922e |  | note | Inspection / Test Method - Verify
label | 10dbf8f9-1126-5c41-a13b-83da6e33d968 |  | note | Record of conformity - This ITP Signed
label | 70b6224a-8f3b-5097-b967-e58d575f1bad |  | note | HP*
label | 2b02522e-27d0-59ae-ac46-e00ef151a45e |  | note | Responsibility - Site Engineer
date | 9cae753d-9b30-58c4-bec2-c2e6b61469c4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 - As Built Documentation
label | 43f112b1-eff5-5985-b60b-3c3b94da6536 |  | note | Frequency - Each Lot
label | 1dae52a7-9129-5c52-bf53-c2eea1649e61 |  | note | Acceptance Criteria - Lot map showing location and area of hydroseed
label | 047a03cb-7c20-59a1-a70b-bbb909cab2e8 |  | note | Reference Documents - Drawings and drawing registers Section 720
label | 7f618bb8-1d03-54a7-b691-3d47768ded1c |  | note | Inspection / Test Method - Verify
label | d2c7d5a5-26e3-5ac8-a1d0-a3b6ce7ce05e |  | note | Record of conformity - Lot Map
label | 75d0885f-3678-547f-8335-035d59588b48 |  | note | HP*
label | d1f07e63-acde-53d9-8f6f-96c27eea6c4c |  | note | Responsibility - Site Engineer
date | b9c8b9fd-73cb-5e91-b6d1-7e5926a727c8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 78d510be-db72-52c6-bace-a5ef07018638 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 5fe0cb6b-bb37-5b9f-87a7-7aa85a2d4a66 |  | textbox | Print Name:
text | 2d02d593-0b47-51ad-9e6e-271e61c10b1e |  | textbox | Position:
date | 46f38670-e95d-5439-b90e-5f706bee6a4f |  | date | Work Completed On:
date | f3f42739-af62-5bf6-8e18-cd1efd666be9 |  | date | Date:
checklist-flat |  |  | checklist | CTN-ITP-003 - Watermain Installation | itp |  |  |  | Yes | CTN-ITP-003 - Watermain Installation | f61a61d1-e1d6-4542-8c26-34e90775ba09
checkpoint-status |  |  | checkpoint | 1.1 - Check that current revision drawings are being used
label | a033c417-d8e6-57e6-9f89-119149468c5f |  | note | Frequency - Prior to Commencing Work
label | ceeb2dd9-0fae-5b58-be39-ea18a1f24a3c |  | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
label | 20434b3e-a8c4-5e36-8c6b-6ad881bf9f98 |  | note | Reference Documents - IFC Project Drawings/ Drawing Register
label | 46a9506f-5e2a-5cd0-afe7-6f267fbf3cb9 |  | note | Inspection / Test Method - Document review
label | 72af98e4-02d5-5623-930d-89d080c4a8c4 |  | note | Record of conformity - Latest revision IFC drawings
label | d2381e37-b837-5990-a430-01a47daefff1 |  | note | *FH
label | a7ee27dd-ae55-549a-aba3-7409adf2dc6d |  | note | Responsibility - Site Engineer
text | 870a4e4f-5092-5ff3-93fc-f0b46e6dc7d4 |  | textbox | ITP Opened:
date | c2b027bb-9774-5227-9a61-b2cc1c4f813c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | d38facce-6ea9-5ec0-9244-dea602a2d4fc |  | note | Frequency - Prior to Commencing
label | bafc57d3-517b-5f43-9762-47821f236e01 |  | note | Acceptance Criteria - All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | db189e46-b71e-5736-a500-70da1680f137 |  | note | Reference Documents - EMP, Site induction,
label | 71627433-a2ec-5a53-afdd-d168680d12d1 |  | note | Inspection / Test Method - Document review & Site inspection
label | f5a8c788-bfcd-51b9-b537-42affc62a4f1 |  | note | Record of conformity - This ITP signed
label | da3bbb3d-0825-5fd1-a0aa-e2d880215b14 |  | note | *FH
label | 497b0562-c3b3-5db4-9d43-44a7c2a4f897 |  | note | Responsibility - Site Engineer
date | ed65d663-80c7-5259-a7bc-211f5b1aefa7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Survey set out works
label | 25d73c1c-e2db-5b8f-a1c2-dc747322452d |  | note | Frequency - Prior to Commencing Work
label | c5d72e2d-1016-57e5-b152-77f6b2c15deb |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all works meet level and location requirements.
label | e1bc6613-992b-5738-ae69-6b42d4e2d652 |  | note | The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. IFC and latest available revision used.
label | ba6962dd-1f67-5dc6-895a-5c569c846d91 |  | note | Reference Documents - Drawings
label | 66cd23de-7707-5089-b789-ff38d00ae588 |  | note | Inspection / Test Method - Site inspection
label | 8d7fc9cc-341c-5c2e-88ed-0651bc3b55bd |  | note | Record of conformity - Survey records & pegs in the ground. This ITP Signed
label | d27803b4-f37a-5862-892f-2157aa749a14 |  | note | SCP
label | 02b7e0a7-7970-57a9-a28d-6796b335ef41 |  | note | Responsibility - Site Engineer
date | 924a17ea-d568-5549-8823-fadc5e5c7cc8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Water Pipes and fittings
label | bbeb6ff6-9b0d-5253-bc26-c69c6396d3d5 |  | note | Frequency - Every batch of new material
label | f4769d0a-57d8-5f89-90c3-c503cbe4079f |  | note | Acceptance Criteria - Pipes and fittings to be free from defects.
label | 99827594-29d7-5bcb-ac17-3cf4bfb2a7bd |  | note | Pipes as per the following: PE100 HDPE DN90 PN16 Pipe DN25 PVC-U
label | 1acb75c0-7c20-509f-a344-265509a9e515 |  | note | Reference Documents - Drawings: 8001 - 8207
label | 60c3036a-76e7-5c76-9d8a-29295c5e1941 |  | note | Inspection / Test Method - Verify
label | 9a1d0dc0-cb32-57c8-a81c-d8b0158b13c1 |  | note | Record of conformity - Paneltec ITP
label | b65c1233-ddad-5166-94bf-576f0792b482 |  | note | IP
label | ccdcdb0b-5f2b-5018-9011-b050fab277a0 |  | note | Responsibility - Site Engineer
date | d067ad5f-685f-533b-8a3d-9db203538d1b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 - Ground Penetration Permit
label | 44b227c8-05e7-5b34-a5a3-c43647c4b87d |  | note | Frequency - Each Lot
label | 87a38670-e1bc-53f5-8d46-0767f45fddcb |  | note | Acceptance Criteria - Ground Penetration Permit must be in place prior to commencement of any ground penetration
label | 80c7190e-dc9d-5b28-8388-29e31036f0b2 |  | note | Reference Documents - Ground penetration Permit
label | da10d763-6554-5ebb-ac58-55f3e769dde8 |  | note | Inspection / Test Method - Verify
label | 20ddecb6-6b25-5a86-8130-035fbf473776 |  | note | Record of conformity - This ITP signed
label | 234e7279-e890-5d1b-9a6f-fd3281989a57 |  | note | IP
label | f7d1b0fc-231f-5b66-8e84-6fc77ca12172 |  | note | Responsibility - Site Engineer
date | 64322c16-602f-5f1c-b792-194237cf48dc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Pipe Joints
label | 21de0f7c-6edc-58b4-991c-f46a374481fa |  | note | Frequency - Each Lot
label | 7868e86c-80b0-5c1d-9564-87e138b6e876 |  | note | Acceptance Criteria - Ensure pipe joint deflection is acceptable, as per drawings and product specifications. Bell end facing upstream and rubber rings installed.
label | 93828633-fb82-515f-84b6-15d8d01e4a29 |  | note | Reference Documents - Drawings
label | 358112a5-800d-50a9-9280-e304c56d42f4 |  | note | Inspection / Test Method - Visual Inspection
label | 0674c806-5a8a-5b03-b919-7d6cc0f6434f |  | note | Record of conformity - Paneltec ITP
label | 742fa128-157d-5b9a-9bbb-a12c72ba3cbd |  | note | IP
label | d908acf0-f8e5-57f4-ae7d-a30823742b09 |  | note | Responsibility - Site Engineer
date | 7325858f-cd03-5e57-9e1f-120f93532857 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Pipe connections
label | 1b6f38fe-092b-5884-a060-e052fb7ce0de |  | note | Frequency - Each Lot
label | 0d0ba6ae-1a85-5261-a22d-f6f9e74961ff |  | note | Acceptance Criteria - Pipe connections installed as per drawing 8031
label | fd7f291f-1f56-5bc7-9553-0bbf8ad43f81 |  | note | Reference Documents - Drawing 8031
label | 62565ceb-bb09-5996-abcd-fe06397d2148 |  | note | Inspection / Test Method - Visual Inspection
label | 6f8f378e-9b17-5ac4-9ffb-9ca70a926fd6 |  | note | Record of conformity - Paneltec ITP
label | 49ed8482-c14e-5744-b557-9ee05a51a078 |  | note | IP
label | aa5ff391-990f-5828-b010-344190e50e2d |  | note | Responsibility - Site Engineer
date | b5546843-571e-534d-9172-55522374e5ca |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Clearance from services
label | f14ff1e3-2fb2-5d23-86d7-de7e9ece09a6 |  | note | Frequency - Each lot
label | c1daa40a-6f09-5593-8a82-820bb4e2ad09 |  | note | Acceptance Criteria - Clearances from existing or proposed services as per tables in drawing 8031
label | 0ff4d817-a44e-56ee-8acb-12736479fac7 |  | note | Reference Documents - Drawing 8031
label | 1400ac9d-7b82-5938-89d0-b0703e5d5f8c |  | note | Inspection / Test Method - Verify
label | fdb3715f-af5a-5a49-a7de-db74d7fb1961 |  | note | Record of conformity - Paneltec ITP
label | 3bd52551-9785-5508-a85f-3e7b22e126f9 |  | note | IP
label | 9a25ac6f-f707-5fb1-b673-e7fcf87695be |  | note | Responsibility - Site Engineer
date | b04d3f19-3171-5e41-867a-54514c899010 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Valves
label | c3f1f95b-3d54-5eb1-99df-be0086fd2713 |  | note | Frequency - Each Lot
label | 0774ec1d-f295-55df-8366-a6f4c5de959a |  | note | Acceptance Criteria - Install valves in the vertical position and provide surface fittings and valve markings in accordance with Drawings"
label | 6c06a6f4-b8fa-5c74-9dca-bc51cc2aca63 |  | note | Inspect the valve for damage. Repair any damage to the external coating in accordance with the manufacturers instructions
label | 892ee12b-fc8a-5b72-8b7b-42f8ea473d5f |  | note | Check the valve and off-take clamp flanges to ensure the sleeves fit in the bolt holes.
label | 81b09836-9fb4-57aa-9395-88474ded7fce |  | note | Trim insulation sleeves such that they join inside one flange, and not at the flange joint.
label | ac525f32-9398-5927-8ba2-345ff824fbd5 |  | note | Lid on valve to be centrally placed
label | c8b07026-4d42-55a3-a3cb-52e25bb7bb87 |  | note | Reference Documents - WSA 03-2011 3.1, MRWA-W-300, MRWA-W-301 and MRWA-W-302, TasWater Permit to construct
label | 6c51033f-198d-5b00-b858-ede2a1b7dcec |  | note | Inspection / Test Method - Verify
label | c35546f7-de04-5489-923d-bcabe51e93dc |  | note | Record of conformity - This ITP signed
label | 7726c5fe-b815-5ee0-8139-4cf8a0818323 |  | note | HP
label | 99955f06-99f7-57b5-ace4-5356dcf609e7 |  | note | Responsibility - Site Engineer/ TasWater
date | 1f7beba2-6a9b-58b0-9031-778a03460431 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Thrust blocks
label | d555877a-80c3-543a-b377-45ce922ecfc8 |  | note | Frequency - Where required
label | a722ff7b-06d7-56d6-a80c-d65f3faca5c4 |  | note | Acceptance Criteria - Thrust blocks are not be used in soft clay | loose sand or uncompacted fill"
label | 3b155085-fc2b-5d45-81a5-34ce4aceb674 |  | note | In line thrust blocks must have a minimum of 2m of solid undisturbed ground around both sides of the block
label | 026eb38d-e6e8-5739-8e13-9c4c411e2ebc |  | note | Finish thrust blocks approx 100mm above the top of fitting or bearing pad
label | 9a127272-6bbd-5ad7-a6cc-514cc0f77137 |  | note | Polyethylene to be placed around fittings and joints when pouring concrete
label | c611e992-d6f9-5614-9a41-4aa4c2f113e6 |  | note | Concrete blocks to be kept clear of other services
label | 04db0ed5-a4be-566d-9948-d89c1d7a55cf |  | note | Reference Documents - MRWA-W-205a, TasWater Permit to Construct
label | 91e70de6-dbe7-5759-95cc-02d3a0d94922 |  | note | Inspection / Test Method - Verify
label | 36ecddaa-bd22-5d41-955f-2532b86465df |  | note | Record of conformity - This ITP signed
label | ca64ebcc-21d5-5e1a-b1e7-367914e73027 |  | note | HP
label | 8523dff0-a32b-5631-91aa-0310ef48a078 |  | note | Responsibility - Site Engineer/ TasWater
date | a341bd8c-ee09-5f2f-85ab-2e5f160ad4e8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Marker posts and plates
label | 174270c7-c192-56e4-8891-ce4a023484f1 |  | note | Frequency - Each Lot
label | f0f9ab52-3bc8-567a-8fdc-a557d7cf681d |  | note | Acceptance Criteria - Marker posts installed at all sluice valves, scour valves, air valves and horizontal changes in pipeline alignment.
label | 232a48fe-f756-5c7e-9f2a-992600ba89a1 |  | note | Marker posts installed at right angles to the main with marker facing towards the valve, posts extended 1.5m above FSL in grassed areas
label | af4348fa-a527-56e2-a2da-15524da3e0d1 |  | note | Reference Documents - Drawings, MRWA-W-301
label | 5cc1803d-d415-556f-b2e7-f1687687d716 |  | note | Inspection / Test Method - Visual Inspection
label | 35b4ee04-92cd-507c-9214-8f080ee83c3a |  | note | Record of conformity - Paneltec ITP
label | 48542ecb-3ade-5763-baa5-7e091ac1ae4e |  | note | IP
label | 93f573f8-1e96-59da-9816-dcdc71fa2e26 |  | note | Responsibility - Site Engineer
date | a5542c36-2897-522b-abef-909e578e9240 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 - Compaction Testing (when applicable)
label | e9f3817b-53ca-5d38-ad97-7e366434dc18 |  | note | Frequency - Completion of pipe installation & fittings.
label | 8ecbaf80-6a55-503c-b5c1-9740574a044b |  | note | Acceptance Criteria - Undertake field density testing of trench fill for areas where method of installation is open trenching
label | 5a588a8d-057a-58e3-87a4-8c714889bfb9 |  | note | Reference Documents - Taswater permit to construct
label | f36653dc-2e6f-5657-a848-f0919ffb6c9e |  | note | Inspection / Test Method - Compaction Testing
label | 5055bcf3-cc70-52e2-873e-db301b1cd7a7 |  | note | Record of conformity - This ITP signed
label | a6726435-48f2-59f8-8c89-3f2b947c2091 |  | note | WP
label | 68080a94-2df2-5707-a5b8-af92c6ff0727 |  | note | Responsibility - Site Engineer / QAV / TasWater
date | aaa2edd5-7578-5268-999a-fbe2700da980 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Pipeline Pressure Testing
label | 4b89b875-c5c3-5348-b74c-a022e01ab31a |  | note | Frequency - Completion of pipe installation & fittings.
label | 09129ef7-ba85-5d1e-86ef-21ef33352d48 |  | note | Acceptance Criteria - Undertake pressure testing of pipelines in accordance with the methods specified in WSA 02 - 2014-3.1 & WSA 03 - 2011-3.1.
label | 60c54eb1-9857-5320-af90-9e65cc6869cb |  | note | Reference Documents - Taswater permit to construct
label | cfb69160-3e31-53df-9965-a027cd75ffb2 |  | note | Inspection / Test Method - Pressure Testing
label | 2be7deb7-c5d0-5eb5-8870-4e1d189f5525 |  | note | Record of conformity - Pressure testing record Paneltec ITP
label | bfe9d521-a524-5ccd-86a1-e0b023e4fcac |  | note | HP
label | 13fd14f7-9dd0-5539-ac68-dc2f8c1fa839 |  | note | Responsibility - Site Engineer / QAV / TasWater
date | 930ffe49-8807-5044-b03a-f00b19495005 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.1 - As constructed drawings
label | c2821593-751f-5505-98de-bb571b581fe9 |  | note | Frequency - Each Lot
label | 68dc64c8-1dec-5ac0-bc54-f47685f6ee93 |  | note | Acceptance Criteria - Ensure all deviations are captured on redline drawings for updating the IFC Drawings, and providing as built data for TasWater
label | 622c98ff-c148-5bff-a969-cb73ec938945 |  | note | Reference Documents - Taswater permit to construct
label | c4823de0-571b-59c1-b39f-4ec676b158bc |  | note | Inspection / Test Method - Verify
label | 508f3765-0f24-5fb2-ba5e-f3ee5645cabe |  | note | Record of conformity - ITP signed
label | 1bbe2a2e-bd68-5f56-acc9-344e5cb9ffb0 |  | note | IP
label | a96d523c-550b-515e-bd7f-c378898553b8 |  | note | Responsibility - Site Engineer
date | 5a1ef273-2a42-5cf0-9b23-8e0d14d55e88 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Tolerances (Horizontal)
label | 92c109d7-6653-59df-a8a8-a948f58fadb2 |  | note | Frequency - Each Lot
label | d7486a2f-e1d6-5066-97fa-850861683b07 |  | note | Acceptance Criteria - Do not exceed the following positional tolerances: (a) Water mains +/-100 mm lateral displacement from the design water main alignment.
label | ca574f6f-eb73-51b7-a4b9-228d2bd4ef17 |  | note | (b) Appurtenances and structures lateral displacement as for the water main, and +/-200 mm displacement (from the design position) along the water main axis.
label | 6ba85e33-e5aa-5223-a414-81c7a74bcf86 |  | note | (c) Property services +/-100 mm displacement along water main axis from the position as specified.
label | 69b6a49f-4a95-5468-9189-9247fe3a2841 |  | note | (d) Water meters +/-100 mm displacement from the position as specified
label | 78166349-1834-522f-a778-46c2acedfd71 |  | note | Reference Documents - WSA 03-2011 3.1
label | f45e7f7f-1bdd-5ad6-9b60-ffb16c7e2f4a |  | note | Inspection / Test Method - Verify
label | c0a1e1ea-c9c3-5269-bbde-ce22e1626ef6 |  | note | Record of conformity - Survey records
label | dc956540-6748-5eb4-b6e1-55fa9b016061 |  | note | IP
label | 10c66fda-1db5-53be-a715-749686a4574b |  | note | Responsibility - Site Engineer
date | 319405db-ba46-5736-9553-6cc806db442a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Tolerances (Vertical)
label | 0c326fbd-dd1d-5e41-ad0b-717daa23ad75 |  | note | Frequency - Each Lot
label | a93f0676-71ce-5171-ac3b-d7dc7c2c0b87 |  | note | Acceptance Criteria - For hydrant risers, access chambers, shrouds and aqueduct piers, apply a tolerance at any point on the pipe or structure as follows:
label | 82517e33-db8e-5ebf-bec3-8f5c0357740d |  | note | (a) 30 mm deviation (from vertical) per metre rise in any direction; and
label | 46c00639-9bb6-5f24-8147-3b5ecb7f5da3 |  | note | (b) limited to a maximum 50 mm cumulative deviation (from vertical) in any one particular direction for structures higher than 5 m.
label | 1a2d9f17-93ce-5c3e-a4e6-b5226248bcda |  | note | For structures and fittings designed flush with the ground / pavement surface or proud of the surface, apply a vertical tolerance on the finished surface levels as follows:
label | 4b62817f-ce4a-5288-8b28-3ec796d8b6ad |  | note | (a) +/-5 mm in road reserves, including sealed pavements, road verges, driveways, footways, and pedestrian thoroughfares.
label | f9e01c59-4a68-5cdb-b180-9bba2c268940 |  | note | (b) +/-5 mm in sealed and trafficable areas within private properties (pedestrian and/or vehicular traffic).
label | b03780c4-67eb-5501-8a0e-fa616af10d5e |  | note | (c) +50 mm,-20 mm in private property including garden areas, unsealed areas, non-trafficable areas and areas of occasional traffic (pedestrian and/or vehicular traffic).
label | 232a5c35-9d95-513b-8901-c5e4dda6f363 |  | note | Reference Documents - WSA 03-2011 3.1
label | f2818410-d44c-5c08-bf99-e91035d0dd18 |  | note | Inspection / Test Method - Verify
label | d1435ef6-bf1f-5d9a-8f6a-8c247f7ea2b5 |  | note | Record of conformity - Survey records
label | 4441c0ed-11c6-5d24-92a2-788cd67a555a |  | note | HP*
label | 1632e3aa-f32e-5722-a10a-a587552bce5a |  | note | Responsibility - Site Engineer
date | b56ba11e-75eb-5307-b51c-08a0848b9abf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0d9eef78-a577-5910-9f17-9fcc960bed58 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 968b6375-1553-56c9-a4b2-b0a9b0e4dbe0 |  | textbox | Print Name:
text | 4aa25615-3070-5020-a247-94d50664734c |  | textbox | Position:
date | 7ba94b23-23ad-5314-bdb8-51f137ea4a43 |  | date | Work Completed On:
date | ad469193-c122-5744-abe1-4bb057a44f3f |  | date | Date: